## Summary
MHHS Programme M8 Code Change Control
Owner | MHHS Code Workstream
Purpose | A central deposit and change control for all Programme related Code change post M6 (August '24)
Input Owners | MHHS Code, Balancing Settlement Code, Retail Energy Code, Distribution and Connection Use of System Agreement
and DIP Manager
Governance Control | MHHS Cross Code Advisory Group (CCAG) and L5 Cross Code Change Control Subgroup (CCCCSG)
Publication | MHHS Code Governance Collaboration Base Page

## Control Log
M8 Change Control Log - seeking CCAG feedback on template - NOT OPERATIONAL!
Last update: 16/12/2024 |  |  | Updated from row: M8-001
Change Ref | Input Category | Source Ref | Source Title | Subject | Description | Code Artefact | Code owner | Status | Delivery solution
M8-001 | Programme CR | CR54 | CR054 Change to Non-Functional Requirements for LDSOs | LDSO Non Functional design/code changes | Amend LDSO Non functional requirements for system processing volumes | DIP Rules | DIP | Design and Code update required
M8-002 |  | ? | 8.2 and 8.3 | Code Correction | DI338, 339, 363, 403 and 404 format amended to include '-' at the start | EMDS | BSC | Code update required | CP
M8-003 |  | ? | 8.2 and 8.3 | Code Correction | DI411 and 412 amended format to include '+/-' at the start | EMDS | BSC | Code update required | CP
M8-004 | DIN log | DIN-1119? | 8.2 and 8.3 | Code Correction | Amended hierarchy for group 900-03 and 04 | EMDS | DCUSA | Code update required | CP
M8-005 | DIN log | DIN-1077 | 8.2 and 8.3 | Code Correction | Adding II enumeration to Settlement Code Data Item | EMDS | BSC | Code update required | CP
M8-006 | DIN log | DIN-1120 | 8.3 | Code Correction | DI-533 change to MHHS data type as per DIN | EMDS | DCUSA | Code update required | CP
M8-007 | DIN log | DIN-1120 | 8.3 | Code Correction | DI-600 change to MHHS data type as per DIN | EMDS | DCUSA | Code update required | CP
M8-008 | DIN log | DIN-1114 | 8.3 | Code Correction | DI-567, DI-486, DI-357, DI-030 Boolean update | EMDS | Mixed | Code update required | CP
M8-009 |  | ? | 8.3 | Code Correction | Amended hierarchy for group R011 | EMDS | BSC | Code update required | CP
M8-010 |  | ? | 8.3 | Code Correction | Removal of DI-30 (DPI) from R003 group in DIP Common tab | EMDS | BSC | Code update required | CP
M8-011 | DIN log | DIN-1072 | 8.2 | Code Correction | Reflecting Load Shape DPI is nullable | EMDS | BSC | Code update required | CP
M8-012 | DIN log | DIN-1077 | 8.2 | Code Correction | Adding II enumeration to Settlement Code Data Item | EMDS | BSC | Code update required | CP
M8-013 |  | ? | 8.2 and 8.3 | Code Correction | Addition of words 'where available in Registration' against the MAP block B075 | EMDS | BSC | Code update required | CP
M8-014 |  | ? | 8.2 and 8.3 | Code Correction | change to validation response REG1032 to reference local time | EMDS | BSC | Code update required | CP
M8-015 | DIN log | CR | 8.3 | Code Correction | Changes to volume requirements - possible duplicate of M8-001 | EMDS | DIP | Code update required | CP
M8-016 | DIN log | DIN-1115 | 8.3 | Code Correction | DI 988 amended to no nulls / mandatory | EMDS | BSC | Code update required | CP
M8-017 | DIN log | DIN-1114 | 8.3 | Code Correction | Boolean update | EMDS | Mixed | Code update required | CP
M8-018 |  | ? | 8.3 | Code Correction | Removal of examples against certain data items DI023, 25, 26, 27, 28, 29 | EMDS |  | Code update required | CP
M8-019 | DIN log | DIN1123 | 8.3 | Code Correction | Removed obsfuscation reference against DI800 in IF035 | EMDS | BSC | Code update required | CP
M8-020 | DIN log | DIN1117 | 8.3 | Code Correction | Removing routing to MDS to save duplication | EMDS | BSC | Code update required | CP
M8-021 |  |  | 8.4 | Code Correction | IF001 (BSC) – redlining showing Boolean enumerations true / false. I think this is an earlier IR, plus we take the enumerations from the data catalogue page not individual flows. | EMDS | BSC | Code update required | CP
M8-022 | DIN log | DIN1128 | 8.4 | Code Correction | IF008 (REC – DIN1128) Adding an exclusion against correlation id and in the notes box to clarify the correlation id is not required where the SMRS auto de-energises | EMDS | BSC, REC | Code update required | CP
M8-023 | DIN log | DIN1135 | 8.4 | Code Correction | IF035 (BSC – DIN1135) as per the IF008 - Adding an exclusion against correlation id and in the notes box to clarify the correlation id is not required for Linked / Related MPANs | EMDS | BSC | Code update required | CP
M8-024 | DIN log | DIN1112 | 8.4 | Code Correction | IF036 (BSC – DIN1112) additional value of ‘inherited’ for correlation id with additional interface notes to support Linked / Relate MPANs | EMDS | BSC | Code update required | CP
M8-025 |  |  | 8.5 | Code Correction | IF001 (BSC) – same redlining as IR8.4 – believe left from earlier IR | EMDS | BSC | Code update required | CP
M8-026 | DIN log | DIN1136 | 8.5 | Code Correction | IF002 (BSC – DIN1136) – removal of the caveat which made B075 group optional in IR8.3. Should mean no change to EMDS from existing M6 version. | EMDS | BSC | Code update required | CP
M8-027 | DIN log | DIN1136 | 8.5 | Code Correction | IF006 (REC – DIN1136) – as per IF002 | EMDS | BSC | Code update required | CP
M8-028 | DIN log | DIN1136 | 8.5 | Code Correction | IF020 (BSC – DIN1136) – as per IF002 | EMDS | BSC | Code update required | CP
M8-029 | DIN log | DIN1136 | 8.5 | Code Correction | IF033 (BSC – DIN1136) – as per IF002 | EMDS | BSC | Code update required | CP
M8-030 | DIN log | DIN1142 | 8.5 | Code Correction | IF034 (BSC – DIN1142) removal of statement in flow notes regarding validation against DCC service flag | EMDS | BSC | Code update required | CP
M8-031 |  |  | 8.5 | Code Correction | IF035 – no change to interface however, there is redlining in the routing table carried over from IR8.4 | EMDS | BSC | Code update required | CP
M8-032 | DIN log | DIN1136 | 8.5 | Code Correction | IF036 (BSC – DIN1136) – as per IF002 | EMDS | BSC | Code update required | CP
M8-033 | Code only |  | MHHS internal report definitions | Code Correction | Internal reports in BSCP703 are not defined, because EMDS only holds external / DIP delivered reports. These need to be either changed to 'internal interface' or defined elsewhere in the BSC | BSCP703 | BSC | Code update required | CP
M8-034 | Code only |  | Agent response code enumerations | Code Correction | Agent response codes (DI-0143) to be added for agent response codes in IF-034, and possibly referenced in BSCP706. | EMDS | BSC | Code update required | Mod
M8-035 | Code only |  | Additional redlining to BSC Section K | Code Correction | Clarifications in respect of Shared SVA Metering Systems where these are explicitly defined as Half Hourly Metering Equipment. | Section K | BSC | Code update required | Mod
M8-036 | Code only |  | Additional redlining to BSC Section S | Code Correction | Clarifications in respect of the SVA Metering Systems Register (S10) to allow MHHS Metering Systems to participate in the BM. | Section S | BSC | Code update required | Mod
M8-037 | Code only |  | MHHS update to SVA Data Catalogue | Supporting Change | Adding business context for IF/PUB, REP and D-flows to the SVA Data Catalogue Volume 1, Appendix A | SVA DC Vol 1 | BSC | Code update required | CP
M8-038 | Code only | CR055 | Updates to Annex S-4 to account for later M8 implementation | Code Correction | Annex S-4 has a number of hardcoded dates for activities at known points in the calendar year. These were drafted on the basis of the original M8 implementation date, and some dates will have passed when the P478 code goes live. Review needed. | Annex S-4 | BSC | Code update required | CP
M8-039 | Code only |  | BSCP 65 alignment with BSCP707 Appendix for BSC Party Name | Code Correction | In BSCP707 Appendix 1 and 2, the allowed character limit for the company name is 160, while in BSCP65, it remains at 30. | BSCP65 | BSC | Code update required | CP
M8-040 | Code only | CR059 | Replacement of REP-020 with D0357 | Code Correction | Update code to reflect the use of D0357 instead of the REP-020 | BSCP703 | BSC | Code update required | CP
M8-041 | Code only | Code review | Ownership of new/amended message/data items | code ommision at M6 | the code needs to incorporate new and amended messages/data items introduced by the Programme on similar lines to how the BSC intridcued them at M6 | EMDS | DCUSA | reference made in the change proposal
M8-042 | Code only | DCP445 voting response | Implementation of Market-wide Half Hourly Settlement (MHHS) Arrangements | Code Correction to error in DCP445 | In re Schedule 16, paragraph 128 there is a reference to “REP-002” which should be to “REP-002B” to align with the definition of “Supercustomer DUoS Report”. | Schedule 16, paragraph 128 | DCUSA | Code update required
M8-043 | Code only | DCP433 | Limitation for backdating of rebates/charges under Schedule 32 | additional MHHS text required | DCP433 introduces a term that has an equivent term introduced by DCP445. | Schedule 32, paragraphs 6.10 and 6.11 | DCUSA | Code update required
M8-044 | Programme CR | CR-056 & DIN 1138 | 8.5 | Code alignment | 7.3B The ERDA shall provide Supplier Agent and SMDR Appointment data in a single CSS00200 Market Message per Metering Point by 23:00 hours on the day the agent appointment is issued by the equivalent SMRA. | ERDS Service Definition | REC | Code update required | CP
M8-045 | Code only | EES API - 1 | EES API - 1 | Code Correction | Removal of capitalisation from the return detail tables (API returns will always be lower case) | EES API Technical Specification | REC | Code update required | CP
M8-046 | Code only | EES API - 2 | EES API - 2 | Code Correction | Removal of the MHHS Indicator from the SearchAddress and SearchRELAddress Methods | EES API Technical Specification | REC | Code update required | CP
M8-047
M8-048
M8-049
M8-050
M8-051
M8-052
M8-053
M8-054
M8-055
M8-056
M8-057
M8-058
M8-059
M8-060
M8-061

## Field values (hidden)
Matrix Field Values - To be agreed
Ref | Input Category | Ref | Title | Subject | Description | Additional Commentary | Code Artefact | Code | Status | Delivery owner | Delivery solution | Mechanism | PCR status | Implementation Date | Agreed imp date | Milestone | MHHSP impact | Core Code | Priority | Status
| Programme CR | [6 empty] | BSC | Design and Code update required | BSC | Mod | SCR | PCR required |  |  | M8 | Yes | BSCP700 series | 1 | Open
| DIN log | [6 empty] | REC | Code update required | REC | CP | BAU | PCR not required |  |  | Post-M8,M10 | No | REC Interfaces | 2 | Closed
| Code only | [6 empty] | DCUSA | Code correct, Design update required | DCUSA |  |  | PCR raised |  |  | Post M11 |  | BSC Section Appendix | 3
[8 empty] | BSC, REC |  | MHHS Programme | [7 empty] | N/A | 4
[8 empty] | BSC, DCUSA |  | BSC, REC | [8 empty] | 5
[8 empty] | REC, DCUSA |  | BSC, REC, DCUSA
[8 empty] | BSC, REC, DCUSA |  | DIP Manager
DIP
BSC, DIP,
Notes | [7 empty] | REC, DIP
BSC, REC, DIP
Unique ref | Change trigger | EG DIN/CR ref | Change title | Change subject | Change Description | Additional Commentary | Code Artefact | RACI | What is impacted | Change owner/lead | Change approach | Change mechanism | Programme CR required | Proposed Deliver Date | Deliver Date | Milestone | MHHSP impact | Core Code | Priority

## Process (hidden)
M8 Workoff process - to be agreed
| Step | Activity
| 1 | Code change identified
| 2 | Code change added to Post - M6 Work off matrix
| 3 | Code triage committee convenes
| 4 | Code triage committee assesses change and updates control
| 5 | Code changes batched into change vehicles
| 6 | Target delivery date proposed
| 7 | Target delivery date agreed
| 8 | Publish/update the control
| 9 | *Progress to agreed change mechanisum
| * | Pre-M8 Code changes delivery via SCR/BAU Modification CP. Post-M10 change process to be defined