## Summary
MHHS Programme M8 Code Change Control
Owner | MHHS Code Workstream
Purpose | A central deposit and change control for all Programme related Code change post M6 (August '24)
Input Owners | MHHS Code, Balancing Settlement Code, Retail Energy Code, Distribution and Connection Use of System Agreement
and DIP Manager
Governance Control | MHHS Cross Code Advisory Group (CCAG) and L5 Cross Code Change Control Subgroup (CCCCSG)
Publication | MHHS Code Governance Collaboration Base Page

## Control Log
M8 Change Control Log
Ref | Input Category | Ref | Title | Subject | Description | Additional commentary | Code Artefact | Code owner | Status | Change Raiser | Delivery solution | Mechanism | PCR status | Milestone | MHHSP impact | Core Code | Priority | Status
M8-001 | Programme CR | CR54 | CR054 Change to Non-Functional Requirements for LDSOs | LDSO Non Functional design/code changes | Amend LDSO Non functional requirements for system processing volumes |  | DIP Rules | DIP | Design and Code update required | DIP Manager |  |  | PCR raised | M8 | Yes | N/A |  | Open
M8-002 |  | ? | 8.2 and 8.3 | Code Correction | DI338, 339, 363, 403 and 404 amended format to include '-' at the start | No DIN identified for this change. Swagger defines the Data Type DT-024 N as positive decimal not sure why the format is negative. Swagger also defines as 10,6 whereas the reporting catalogue is 16,6 Further issue identified in swagger where DT-024 is defined as 10,6 but with an example that aligns to that format. The example against DT-024N is not consistent with the definition. Both are inconsistent with the ECS Reporting Catalogue which has added the '-' in IR8.3 14/10 Programme reviewing the data definition in Swagger. | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-003 |  | ? | 8.2 and 8.3 | Code Correction | DI411 and 412 amended format to include '+/-' at the start | Same issues as above | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-004 | DIN log | DIN-1119? | 8.2 and 8.3 | Code Correction | Amended hierarchy for group 900-03 and 04 | ER1011B not called out in DIN log as impacted - this was in 8.1 | EMDS | DCUSA | Code update required |  | CP | BAU | PCR not required | M8
M8-005 | DIN log | DIN-1077 | 8.2 and 8.3 | Code Correction | Adding II enumeration to Settlement Code Data Item | Change aso applied to DES138 which will mean it is picked up in EMDS | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-006 | DIN log | DIN-1120 | 8.3 | Code Correction | DI-533 change to MHHS data type as per DIN |  | EMDS | DCUSA | Code update required |  | CP | BAU | PCR not required | M8
M8-007 | DIN log | DIN-1120 | 8.3 | Code Correction | DI-600 change to MHHS data type as per DIN |  | EMDS | DCUSA | Code update required |  | CP | BAU | PCR not required | M8
M8-008 | DIN log | DIN-1114 | 8.3 | Code Correction | DI-567, DI-486, DI-357, DI-030 Boolean update |  | EMDS | Mixed | Code update required |  | CP | BAU | PCR not required | M8
M8-009 |  | ? | 8.3 | Code Correction | Amended hierarchy for group R011 | No DIN identified for this change - this was in 8.1 | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-010 |  | ? | 8.3 | Code Correction | Removal of DI-30 (DPI) from R003 group in DIP Common tab | No DIN identified for this change. Removal of DI-30 (DPI) from R003 group is redlined. This group is in REP-006 which does not have DPI in the structure. Looks like EMDS is correct so just a carry over of redlining in the DIP Common tab | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-011 | DIN log | DIN-1072 | 8.2 | Code Correction | Reflecting Load Shape DPI is nullable |  | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-012 | DIN log | DIN-1077 | 8.2 | Code Correction | Adding II enumeration to Settlement Code Data Item |  | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-013 |  | ? | 8.2 and 8.3 | Code Correction | Addition of words 'where available in Registration' against the MAP block B075 | No DIN identified for this change - looks like quite a material change. Programme recognised this was an error - DIN1136 raised to correct. 14/10 RECCo pushing for the new DIN to be captured in IR8.4 | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-014 |  | ? | 8.2 and 8.3 | Code Correction | change to validation response REG1032 to reference local time | This is redlined but was already in 8.1 so suspect it will link to an IR8.1 DIN. No change to code drafting as these details are not codified. | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-015 | DIN log | CR | 8.3 | Code Correction | Changes to volume requirements |  | EMDS | DIP | Code update required |  | CP | BAU | PCR not required | M8
M8-016 | DIN log | DIN-1115 | 8.3 | Code Correction | DI 988 amended to no nulls / mandatory |  | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-017 | DIN log | DIN-1114 | 8.3 | Code Correction | Boolean update |  | EMDS | Mixed | Code update required |  | CP | BAU | PCR not required | M8
M8-018 |  | ? | 8.3 | Code Correction | Removal of examples against certain data items DI023, 25, 26, 27, 28, 29 | No DIN identified - it looks like this could be a copy and paste formating error and has led to these examples being removed. Programme correcting. 14/10 correction to be applied to a re-published IR8.3 version | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-019 | DIN log | DIN1123 | 8.3 | Code Correction | Removed obsfuscation reference against DI800 in IF035 |  | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-020 | DIN log | DIN1117 | 8.3 | Code Correction | Removing routing to MDS to save duplication |  | EMDS | BSC | Code update required |  | CP | BAU | PCR not required | M8
M8-021 |  |  | 8.4 | Code Correction | IF001 (BSC) – redlining showing Boolean enumerations true / false. I think this is an earlier IR, plus we take the enumerations from the data catalogue page not individual flows. |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-022 | DIN log | DIN1128 | 8.4 | Code Correction | IF008 (REC – DIN1128) Adding an exclusion against correlation id and in the notes box to clarify the correlation id is not required where the SMRS auto de-energises |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-023 | DIN log | DIN1135 | 8.4 | Code Correction | IF035 (BSC – DIN1135) as per the IF008 - Adding an exclusion against correlation id and in the notes box to clarify the correlation id is not required for Linked / Related MPANs |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-024 | DIN log | DIN1112 | 8.4 | Code Correction | IF036 (BSC – DIN1112) additional value of ‘inherited’ for correlation id with additional interface notes to support Linked / Relate MPANs |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-025 |  |  | 8.5 | Code Correction | IF001 (BSC) – same redlining as IR8.4 – believe left from earlier IR |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-026 | DIN log | DIN1136 | 8.5 | Code Correction | IF002 (BSC – DIN1136) – removal of the caveat which made B075 group optional in IR8.3. Should mean no change to EMDS from existing M6 version. |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-027 | DIN log | DIN1136 | 8.5 | Code Correction | IF006 (REC – DIN1136) – as per IF002 |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-028 | DIN log | DIN1136 | 8.5 | Code Correction | IF020 (BSC – DIN1136) – as per IF002 |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-029 | DIN log | DIN1136 | 8.5 | Code Correction | IF033 (BSC – DIN1136) – as per IF002 |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-030 | DIN log | DIN1142 | 8.5 | Code Correction | IF034 (BSC – DIN1142) removal of statement in flow notes regarding validation against DCC service flag |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-031 |  |  | 8.5 | Code Correction | IF035 – no change to interface however, there is redlining in the routing table carried over from IR8.4 |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-032 | DIN log | DIN1136 | 8.5 | Code Correction | IF036 (BSC – DIN1136) – as per IF002 |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-033 | Code only |  | MHHS internal report definitions | Code Correction | Internal reports in BSCP703 are not defined, because EMDS only holds external / DIP delivered reports. These need to be either changed to 'internal interface' or defined elsewhere in the BSC |  | BSCP703 |  | Code update required |  | CP | BAU | PCR not required | M8
M8-034 | Code only |  | Agent response code enumerations | Code Correction | Agent response codes (DI-0143) to be added for agent response codes in IF-034, and possibly referenced in BSCP706. |  | EMDS |  | Code update required |  | CP | BAU | PCR not required | M8
M8-035 | Code only |  | Additional redlining to BSC Section K | Code Correction | Clarifications in respect of Shared SVA Metering Systems where these are explicitly defined as Half Hourly Metering Equipment. |  | Section K |  | Code update required |  | CP | BAU | PCR not required | M8
M8-036 | Code only |  | Additional redlining to BSC Section S | Code Correction | Clarifications in respect of the SVA Metering Systems Register (S10) to allow MHHS Metering Systems to participate in the BM. |  | Section S |  | Code update required |  | CP | BAU | PCR not required | M8
M8-037
M8-038
M8-039
M8-040
M8-041
M8-042
M8-043
M8-044
M8-045
M8-046
M8-047
M8-048
M8-049
M8-050
M8-051
M8-052
M8-053
M8-054
M8-055
M8-056
M8-057
M8-058
M8-059
M8-060
M8-061

## Field values (hidden)
Matrix Field Values - To be agreed
Ref | Input Category | Ref | Title | Subject | Description | Additional Commentary | Code Artefact | Code | Status | Delivery owner | Delivery solution | Mechanism | PCR status | Implementation Date | Agreed imp date | Milestone | MHHSP impact | Core Code | Priority | Status
| Programme CR | [6 empty] | BSC | Design and Code update required | BSC | Mod | SCR | PCR required |  |  | M8 | Yes | BSCP700 series | 1 | Open
| DIN log | [6 empty] | REC | Code update required | REC | CP | BAU | PCR not required |  |  | Post-M8,M10 | No | REC Interfaces | 2 | Closed
| Code only | [6 empty] | DCUSA | Code correct, Design update required | DCUSA |  |  | PCR raised |  |  | Post M11 |  | BSC Section Appendix | 3
[8 empty] | BSC, REC |  | MHHS Programme | [7 empty] | N/A | 4
[8 empty] | BSC, DCUSA |  | BSC, REC | [8 empty] | 5
[8 empty] | REC, DCUSA |  | BSC, REC, DCUSA
[8 empty] | BSC, REC, DCUSA |  | DIP Manager
DIP
BSC, DIP,
Notes | [7 empty] | REC, DIP
BSC, REC, DIP
Unique ref | Change trigger | EG DIN/CR ref | Change title | Change subject | Change Description | Additional Commentary | Code Artefact | RACI | What is impacted | Change owner/lead | Change approach | Change mechanism | Programme CR required | Proposed Deliver Date | Deliver Date | Milestone | MHHSP impact | Core Code | Priority

## Process (hidden)
M8 Workoff process - to be agreed
| Step | Activity
| 1 | Code change identified
| 2 | Code change added to Post - M6 Work off matrix
| 3 | Code triage committee convenes
| 4 | Code triage committee assesses change and updates control
| 5 | Code changes batched into change vehicles
| 6 | Target delivery date proposed
| 7 | Target delivery date agreed
| 8 | Publish/update the control
| 9 | *Progress to agreed change mechanisum
| * | Pre-M8 Code changes delivery via SCR/BAU Modification CP. Post-M10 change process to be defined