## Settlement Date Cutover
MHHS Proposal for revised Settlement Timetable cut-over - Based of 2 July 2027 cut-over
Settlement Run Date
|  | New Partial Timetable published to end of September |  | M16 Checkpoint 1 (25th) | Confirm Date (23rd) | Readiness Assessment 20th) | Decision 1 | New Partial Timetable Implemented up to M16 |  |  |  |  | Decision 2 | M16 Checkpoint 2 (2nd) and Readiness Assessment (19th) | Decision 3 - Full Migration complete (7th) (M15) and confirmation of M16 date & ISD Calendar(30th) |  | M16 (02/07/2027) | [8 empty] | 2028/29 Settlement Timetable Implemented | [7 empty] | Key
|  | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | SF | SF
| 2026-04-01 | 2026-04-01: SF; 2026-05-01: R1; 2026-07-01: R2; 2026-10-01: R3; 2027-05-01: RF
| 2026-05-01 | 2026-05-01: SF; 2026-06-01: R1; 2026-08-01: R2; 2026-11-01: R3; 2027-06-01: RF
| 2026-06-01 | 2026-06-01: SF; 2026-07-01: R1; 2026-09-01: R2; 2026-12-01: R3; 2027-07-01: RF | R1 | R1
| 2026-07-01 | 2026-07-01: SF; 2026-08-01: R1; 2026-10-01: R2; 2027-01-01: R3; 2027-08-01: RF | R2 | R2
| 2026-08-01 | 2026-08-01: SF; 2026-09-01: R1; 2026-11-01: R2; 2027-02-01: R3; 2027-09-01: RF | R3 | R3
| 2026-09-01 | 2026-09-01: SF; 2026-10-01: R1; 2026-12-01: R2; 2027-03-01: R3; 2027-10-01: RF | RF | RF
| 2026-10-01 | 2026-10-01: SF; 2026-11-01: R1; 2027-01-01: R2; 2027-04-01: RF (Replaces R3) | SF 7 WD | SF
| 2026-11-01 | 2026-11-01: SF; 2026-12-01: R1; 2027-02-01: R2; 2027-05-01: RF | R1 29 WD | R1
| 2026-12-01 | 2026-12-01: SF; 2027-01-01: R1; 2027-03-01: R2; 2027-06-01: RF
| 2027-01-01 | 2027-01-01: SF; 2027-02-01: R1; 2027-04-01: R2; 2027-07-01: RF
| 2027-02-01 | 2027-02-01: SF; 2027-03-01: R1; 2027-05-01: R2; 2027-08-01: RF
Settlement Date | 2027-03-01 | 2027-03-01: SF; 2027-04-01: R1; 2027-09-01: RF
| 2027-04-01 | 2027-04-01: SF; 2027-05-01: R1; 2027-07-01: RF (Replaces R2)
| 2027-05-01 | 2027-05-01: SF; 2027-06-01: R1; 2027-08-01: RF
| 2027-06-01 | 2027-06-01: SF; 2027-07-01: R1; 2027-09-01: RF
| 2027-07-01 | 2026-08-01: 02/07/2027 cut-over of VAS SF Run to 7 WD; 2027-07-01: SF; 2027-08-01: R1; 2027-10-01: RF
| 2027-08-01 | 2027-08-01: SF; 2027-09-01: R1; 2027-11-01: RF
| 2027-09-01 | 2027-09-01: SF; 2027-10-01: R1; 2027-12-01: RF
| 2027-10-01 | 2027-10-01: SF; 2027-11-01: R1; 2028-01-01: RF
| 2027-11-01 | 2027-11-01: SF; 2027-12-01: R1; 2028-02-01: RF
| 2027-12-01 | 2027-12-01: SF; 2028-01-01: R1; 2028-03-01: RF
| 2028-01-01 | 2028-01-01: SF; 2028-02-01: R1; 2028-04-01: RF
| 2028-02-01 | 2028-02-01: SF; 2028-03-01: R1; 2028-05-01: RF
| 2028-03-01 | 2028-03-01: SF; 2028-04-01: R1; 2028-06-01: RF
| 2028-04-01 | 2026-04-01: New Settlement Timetable for 2028/29; 2028-04-01: SF; 2028-05-01: R1; 2028-07-01: RF
| 2028-05-01 | 2028-05-01: SF; 2028-06-01: R1; 2028-08-01: RF
| 2028-06-01 | 2028-06-01: SF; 2028-07-01: R1; 2028-09-01: RF
| 2028-07-01 | 2028-07-01: SF; 2028-08-01: R1; 2028-10-01: RF
M16 cut over Settlement Date
RF Runs moved to 7 Months
RF Runs moved to 4 Months
SF Runs moved to 7 WD from 15 WD and R1 moved from 38 WD to 29 WD
Review of Monitoring Data
Decision point on reduction to the RF Runs or revision of the M16 Milestone
Decision 3 on reduction to the SF Run from 15 WD to 7 WD or revision of the M16 Milestone. ISD and Settlement Calendar updates for dates from 02/07/2027
Review of Monitoring Data
Decision 2 Moving RF to 4 Months
Review of Monitoring Data