## Introduction
MHHS-DEL1165 MHHS Participant Checklist
The Programme has created this Participant Checklist to provide participants with information on Programme requests for review and engagement. The checklist includes information on: · Consultations · Assurance activities · Programme Participant Information Requests (PPIR) · Artefact releases · Key deadlines and dates
This checklist is frequently reviewed to provide the latest view of Programme requests, although there will be some occasions where an item is added at short notice.
All items in this checklist will be communicated in our weekly Programme newsletter (The Clock) and in the majority of cases, via email to the Programme Principal Contacts and/or relevant participant groups (e.g., Advisory or Working Groups).
If you have any questions about this document, please get in touch with the PMO team by emailing PMO@mhhsprogramme.co.uk

## Participant Checklist
Workstream | Document / Artefacts | Version | Target Audience | Working Group | Approval Forum | Estimated Consultation Start Date | Consultation Timeline | Due Date | Status | Location: MHHS Website | Location: Collaboration Base | Note
Transition | Full MPAN Refresh Data Cleanse activity | 1 | C&C and LDSOs | DCWG | MCAG | n/a | n/a | October and November 24 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> Non-SIT Supplier and Agent Post-QT Sandbox PPIR | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> Non-SIT Supplier and Agent Post-QT Sandbox PPIR
Governance - Change Request | CR031: Amending Transition Design Milestone Description and Delivery Date | n/a | All PPs | n/a | DAG | n/a | n/a | n/a | Closed | Planning --> Facilitating Engagement between Suppliers and Agents | Planning --> Facilitating Engagement between Suppliers and Agents
Transition | Milestone 10 (M10)/M11 Cutover status report | n/a | M10/M11-ready Programme participants | n/a | n/a | n/a | n/a | 15:00 each Wednesday | Closed | Qualification --> Qualification Overview --> Retail Energy Code (REC), Balancing & Settlement Code (BSC) and Data Integration Platform (DIP) Qualification Assessment Criteria for MHHS Qualification | Qualification --> REC, BSC & DIP Qualification Assessment Criteria for MHHS Qualification
Qualification | Non-SIT Supplier and Agent Post-QT Sandbox PPIR | n/a | Non-SIT Suppliers & Agents | QWG | QAG | 2025-10-30 | 15 Working Days | 2025-11-21 | Closed | Transition --> M10/M11 Cutover Plan | Transition --> M10/M11 Cutover Plan
Migration | Request for Consent: Publication of Migration Contact Details PPIR | n/a | Migration Principal Contact | TORWG | MCAG | 2025-11-07 | 10 Working Days | 2025-11-21 | Closed | Transition --> M10/M11 Cutover Plan | Transition --> M10/M11 Cutover Plan
Qualification | BSC Assessment Criteria Consultation | 5.1 | QWG attendees | QWG | QAG | 2025-10-13 | 10 Working Days | 2025-10-28 | Closed | Transition --> Data Cleanse Plan | Transition --> Data Cleanse Plan
Transition | Data Cleanse activity: Final report once 100% of the portfolio has been populated. | n/a | LDSOs | TORWG | n/a | n/a | n/a | 2025-09-24 | Closed | Transition --> Data Cleanse Plan | Transition --> Data Cleanse Plan
Transition | Self-declarations | n/a | LDSOs, Elexon, ElectraLink, EES, DCC and DIP Manager | TORWG | n/a | n/a | n/a | 2025-09-22 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> Request for Urgent Response to M10 Contingency Scenarios and Plans Impact Assessment PPIR | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> Request for Urgent Response to M10 Contingency Scenarios and Plans Impact Assessment PPIR
Transition | Data Cleanse activity: Self-declaration confirming that Market Segment has been populated for 100% of LDSO portfolios | n/a | LDSOs | TORWG | n/a | n/a | n/a | 2025-09-22 | Closed | If you have any questions on self-declarations, please email the Operational Readiness team at Opreadiness@mhhsprogramme.co.uk | If you have any questions on self-declarations, please email the Operational Readiness team at Opreadiness@mhhsprogramme.co.uk
PPIR | Request for Urgent Response to M10 Contingency Scenarios and Plans Impact Assessment | n/a | All PPs | n/a | n/a | 2025-09-05 | 5 Working Days | 2025-09-11 | Closed | DIP --> DIP Guidance Documents | DIP --> DIP Guidance Documents
Transition | M10/M11 Cutover Plan - Deployment to Production Self-Declaration | n/a | LDSOs | n/a | n/a | n/a | n/a | 2025-09-01 | Closed | SIT --> SIT Overarching Exit Reports | SIT --> SIT Overarching Exit Reports
DIP | Data Integration Platform (DIP) Onboarding: Promotion to Production | n/a | LDSOs | n/a | n/a | n/a | n/a | 2025-08-22 | Closed | If you have any questions, please email dcusa@electralink.co.uk | If you have any questions, please email dcusa@electralink.co.uk
Testing | SIT Operational SI Overarching Exit Report | 0.1 | SIT PPs | SITWG | SITAG | 2025-08-05 | 8 Working Days | 2025-08-12 | Closed | SIT --> SIT Overarching Exit Reports | SIT --> SIT Overarching Exit Reports
DCUSA | Distribution Connection Use of System Agreement (DCUSA) DCP456 Consultation | n/a | All PPs | n/a | n/a | 2025-06-18 | 38 Working Days | 2025-08-08 | Closed | Transition --> Service Management | Transition --> Elexon Helix Service Operating Manual & Transition --> Service Management
Testing | SIT Non-Functional SI Overarching Exit Report | 0.1 | SIT PPs | SITWG | SITAG | 2025-07-18 | 10 Working Days | 2025-08-01 | Closed | Qualification --> Non-SIT Supplier & Agent Qualification --> Non-SIT Supplier & Agent Qualification Testing Test Scenarios & Test Cases | Qualification --> Non-SIT Supplier & Agent Qualification --> Non-SIT Supplier & Agent Qualification Testing Test Scenarios & Test Cases
Transition | Helix Service Operating Manual and Low-Level Service Design (LLSD) Consultation | 1.6 & 1.4 | All PPs | TORWG | MCAG | 2025-07-16 | 10 Working Days | 2025-07-30 | Closed | Programme Information --> Programme Change Control --> Change Control Documents --> CR063 | Programme Information --> Programme Change Control --> Change Control Documents --> CR063
PMO | Issue Resolution Group (IRG) nomination | n/a | All PPs | n/a | n/a | 2025-07-11 | 10 Working Days | 2025-07-25 | Closed | Transition --> Transition Governance --> Issue Resolution Group (IRG) | Transition --> Transition Governance --> Issue Resolution Group (IRG)
Qualification | Non-Systems Integration Testing (SIT) Supplier & Agent Qualification Testing Test Case: Batch 3 Housekeeping Consultation | 2.1 | All PPs | QWG | QAG | 2025-07-09 | 10 Working Days | 2025-07-23 | Closed | Transition --> Data Cleanse Plan | Transition --> Data Cleanse Plan
Planning | Change Request CR063 | n/a | All PPs | n/a | n/a | 2025-07-09 | 10 Working Days | 2025-07-23 | Closed | SIT --> SIT Overarching Exit Reports | SIT --> SIT Overarching Exit Reports
Transition | Data Cleanse Plan: Supplier Exception Resolution Self-declaration | n/a | Suppliers | n/a | n/a | n/a | n/a | 2025-07-21 | Closed | Transition --> M10/M11 Cutover Plan | Transition --> M10/M11 Cutover Plan
Testing | SIT Functional and Migration SI Overarching Exit Report | 1 | SIT PPs | SITWG | SITAG | 2025-07-03 | 10 Working Days | 2025-07-17 | Closed | Transition --> M10/M11 Cutover Plan --> Participant Cutover Plans | Transition --> M10/M11 Cutover Plan --> Participant Cutover Plans
Transition | M10/M11 Programme Cutover Plan Consultation | 1.2 | All PPs | TORWG | MCAG | 2025-06-27 | 10 Working Days | 2025-07-11 | Closed | https://www.mhhsprogramme.co.uk/planning-home/facilitating-engagement-between-suppliers-and-agents | https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Facilitating-Engagement-between-Suppliers-and-Agents.aspx
Transition | M10/M11 Participant Cutover Plans | 2 | LDSOs and SIT Suppliers & Agents | TORWG | MCAG | 2025-06-27 | 10 Working Days | 2025-07-11 | Closed | Migration --> Migration Supplier Envelope & Plan Submission Round 2 | Migration --> Migration Supplier Envelope & Plan Submission Round 2
Qualification | Facilitating Engagement between Suppliers & Agents | n/a | All PPs | n/a | n/a | n/a | n/a | 2025-07-09 | Closed | If you have any questions on DCR0003, please email DIPManager@elexon.co.uk | If you have any questions on DCR0003, please email DIPManager@elexon.co.uk
Migration | Migration Supplier Submission 2 Supplier Self-Certification | n/a | Suppliers | n/a | n/a | n/a | n/a | 2025-07-08 | Closed | If you have any questions, please email the Testing team at Testing@mhhsprogramme.co.uk | If you have any questions, please email the Testing team at Testing@mhhsprogramme.co.uk
Testing | Systems Integration Testing (SIT) Non-Functional Exit Reports | n/a | SIT PPs | n/a | n/a | 2025-06-27 | 5 Working Days | 2025-07-04 | Closed | If you have any questions, please email enquiries@recmanager.co.uk | If you have any questions, please email enquiries@recmanager.co.uk
Elexon DIP | Data Integration Platform (DIP) Change Consultation: DCR0003 | n/a | DIP Users | n/a | n/a | 2025-06-10 | 18 Working Days | 2025-07-03 | Closed | Transition --> M10/M11 Cutover Plan --> Participant Cutover Plans | Transition --> M10/M11 Cutover Plan --> Participant Cutover Plans
Elexon REC | Retail Energy Code (REC) R0241 Consultation | n/a | All PPs | n/a | n/a | 2025-06-17 | 10 Working Days | 2025-07-01 | Closed | Please visit the Elexon website: https://www.elexon.co.uk/bsc/mod-proposal/p489/ If you have any questions, please email bsc.change@elexon.co.uk | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> MHHS Central Parties PPIR
Transition | MHHS M10/M11 Cutover Plan Request: LDSOs, SIT Suppliers, and SIT Agents updated plan and template following the publication of the consolidated Programme M10/M11 Cutover Plan | 1 | LDSOs, SIT Suppliers and Agents | n/a | n/a | n/a | n/a | 2025-06-27 | Closed | Programme Information --> Programme Change Control --> Change Control Documents --> CR062 | Programme Information --> Programme Change Control --> Change Control Documents --> CR062
Elexon BSC | Balancing & Settlement Code (BSC) P489 Consultation | n/a | All PPs | n/a | n/a | 2025-06-16 | 9 Working Days | 2025-06-27 | Closed | If you have any questions, please email the Testing team at Testing@mhhsprogramme.co.uk | If you have any questions, please email the Testing team at Testing@mhhsprogramme.co.uk
Planning | Change Request CR062 | n/a | All PPs | n/a | PSG | 2025-06-12 | 10 Working Days | 2025-06-26 | Closed | Migration --> Migration Supplier Envelope & Plan Submission Round 2 | Migration --> Migration Supplier Envelope & Plan Submission Round 2
Testing | Systems Integration Testing (SIT) Functional and Migration Exit Reports - participants to sign proformas | n/a | SIT PPs | n/a | n/a | 2025-06-10 | 5 Working Days | 2025-06-25 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> MHHS Central Parties PPIR | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> MHHS Central Parties PPIR
Migration | Migration Supplier Submission Round 2 | n/a | All PPs | n/a | n/a | n/a | n/a | 2025-06-20 | Closed | Design --> Baselined Design Artefacts --> Design Interim Release 8.0 - 8.11 | Design --> Baselined Design Artefacts --> Design Interim Release 8.0 - 8.11
Migration | MHHS Central Parties PPIR | n/a | Central Parties | n/a | n/a | 2025-06-05 | 10 Working Days | 2025-06-19 | Closed | Please email the Operational Readiness team at opreadiness@mhhsprogramme.co.uk. | Please email the Operational Readiness team at opreadiness@mhhsprogramme.co.uk.
Design | Design Interim Release 8.11 Artefacts | IR8.11 | All PPs | n/a | n/a | n/a | n/a | 2025-06-11 | Closed | Transition --> Service Activation --> Elexon Helix Supplier of Last Resort (SoLR) Consultation | Transition --> Service Activation --> Elexon Helix Supplier of Last Resort (SoLR) Consultation
Transition | Data Cleanse activity: Self-declaration Suppliers | n/a | Suppliers | n/a | n/a | 2025-05-12 | 20 Working Days | 2025-06-09 | Closed | Qualification --> End-to-End Sandbox | Qualification --> End-to-End Sandbox
Transition | Elexon Helix Supplier of Last Resort (SoLR) Consultation | 1 | All PPs | n/a | n/a | 2025-05-27 | 10 Working Days | 2025-06-09 | Closed | Please email the Operational Readiness team at opreadiness@mhhsprogramme.co.uk. | Please email the Operational Readiness team at opreadiness@mhhsprogramme.co.uk.
Qualification | End-to-End Sandbox Test Data Approach and Plan | TBC | All PPs | QWG | QAG | 2025-05-27 | 9 Working Days | 2025-06-06 | Closed | If you have any queries about the management letter, please email MHHSPAF@elexon.co.uk | If you have any queries about the management letter, please email MHHSPAF@elexon.co.uk
Transition | Data Cleanse activity: Self-declaration LDSOs | n/a | LDSO | n/a | n/a | 2025-05-12 | 15 Working Days | 2025-06-02 | Closed | Qualification --> Non-SIT Supplier and Agent Qualification --> Non-SIT Supplier and Agent Qualification Testing Test Scenarios and Test Cases | Qualification --> Non-SIT Supplier and Agent Qualification --> Non-SIT Supplier and Agent Qualification Testing Test Scenarios and Test Cases
Qualification | Legacy Settlement Arrangements Management Letters | n/a | Member of a Compliance or Assurance Team within a Programme participant. | n/a | Elexon | n/a | n/a | 2025-05-31 | Closed | Qualification --> Qualification Approach & Plan | Qualification --> Qualification Approach & Plan
Qualification | Non-Systems Integration Testing (SIT) Supplier & Agent Qualification Testing (QT) Test Scenarios and Test Cases, Functional Batches 1, 2 and 3 | 1 | All PPs | QWG | QAG | 2025-05-19 | 9 Working Days | 2025-05-30 | Closed | Transition --> M10/M11 Cutover Plan --> Participant Cutover Plans | Transition --> M10/M11 Cutover Plan --> Participant Cutover Plans
Qualification | Qualification Approach and Plan & Annex 2 Industry Consultation | 4.1 | All PPs | QWG | QAG | 2025-05-19 | 9 Working Days | 2025-05-30 | Closed | Programme Information --> Programme Change Control --> Change Control Documents --> CR061 | Programme Information --> Programme Change Control --> Change Control Documents --> CR061
Transition | MHHS M10/M11 Cutover Plan Request: LDSOs, SIT Suppliers, and SIT Agents | 1 | LDSOs, SIT Suppliers and Agents | n/a | n/a | n/a | n/a | 2025-05-30 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: Further Questions regarding the Use of the Meter Data Retrieval (MDR) function | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: Further Questions regarding the Use of the Meter Data Retrieval (MDR) function
Qualification | Non-SIT Supplier and Agent Qualification Test Case (QTC) Rationalisation | n/a | Non-SIT Suppliers & Agents | QWG | QAG | 2025-05-19 | 8 Working Days | 2025-05-29 | Closed | Planning --> Readiness Assessment 5/6 | Planning --> Readiness Assessment 5/6
Migration | MHHS Migration Supplier Agent and Software Provider PPIR | n/a | Supplier Agent & Software Providers | n/a | n/a | 2025-05-14 | 11 Working Days | 2025-05-29 | Closed | Transition --> M10/M11 Cutover Plan --> Participant Cutover Plans | Transition --> M10/M11 Cutover Plan --> Participant Cutover Plans
Planning | Change Request CR061 | n/a | All PPs | n/a | PSG | 2025-05-07 | 11 Working Days | 2025-05-22 | Closed | Transition --> Service Management --> Elexon Helix Service Management Consultation | Transition --> Service Management --> Elexon Helix Service Management Consultation
PPIR | PPIR: Further Questions regarding the Use of the Meter Data Retrieval (MDR) function | n/a | Supplier or Smart Data Service (SDS) participant. | n/a | Elexon | 2025-05-07 | 10 Working Days | 2025-05-21 | Closed | Participants are asked to please confirm by email to Testing@mhhsprogramme.co.uk | Participants are asked to please confirm by email to Testing@mhhsprogramme.co.uk
Planning | Readiness Assessment Five / Six (RA5/6) | n/a | All PPs | n/a | PSG | 2025-04-28 | 15 Working Days | 2025-05-16 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> MHHS Migration Licensed Distribution System Operator (LDSO) Information | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> MHHS Migration Licensed Distribution System Operator (LDSO) Information
Transition | MHHS M10/M11 Cutover Plan Request: Central Parties | 1 | Central Parties | n/a | n/a | n/a | n/a | 2025-05-16 | Closed | Collaboration Base only | Transition --> Data Cleanse Plan --> Exceptions Count - Smart Meter Types Installed on CT Connection Types
Transition | Operational Readiness Testing Scripts consultation | 1 | All PPs | n/a | n/a | 2025-05-09 | 5 Working Days | 2025-05-16 | Closed | Transition --> Service Management --> Elexon Helix Service Management Consultation | Transition --> Service Management --> Elexon Helix Service Management Consultation
Testing | Systems Integration Testing (SIT) Regression Settlement Data Load | n/a | Suppliers and LDSOs | n/a | n/a | 2025-05-06 | 7 Working Days | 2025-05-14 | Closed | Qualification --> Non-SIT Supplier and Agent Qualification --> Non-SIT Supplier and Agent Qualification Testing Test Scenarios and Test Cases | Qualification --> Non-SIT Supplier and Agent Qualification --> Non-SIT Supplier and Agent Qualification Testing Test Scenarios and Test Cases
Migration | PPIR: MHHS Migration Licensed Distribution System Operator (LDSO) Information | n/a | LDSOs | n/a | n/a | 2025-04-22 | 14 Working Days | 2025-05-12 | Closed | Qualification --> Non-SIT Supplier and Agent Qualification --> Non-SIT Supplier & Agent Test Data | Qualification --> Non-SIT Supplier and Agent Qualification --> Non-SIT Supplier & Agent Test Data
Transition | MHHS Data Cleanse Plan - Connection Type and Meter Type Misalignments Template | 1 | LDSOs | n/a | n/a | n/a | n/a | 2025-04-30 | Closed | Ofgem website: https://www.ofgem.gov.uk/consultation/amendments-market-wide-half-hourly-settlement-governance-framework | Ofgem website: https://www.ofgem.gov.uk/consultation/amendments-market-wide-half-hourly-settlement-governance-framework
Transition | Helix Service Management Consultation | TBC | All PPs | TORWG | MCAG | 2025-04-07 | 15 Working Days | 2025-04-28 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: Proposal to Descope the Qualification Testing Framework (QTF) CSS Stub | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: Proposal to Descope the Qualification Testing Framework (QTF) CSS Stub
Qualification | Non-SIT Supplier and Agent Qualification Testing Scenarios and Cases Consultation | 1.1 | Non-SIT Suppliers & Agents | QWG | QAG | 2025-04-07 | 13 Working Days | 2025-04-23 | Closed | Testing --> SIT Regression --> SIT Regression Framework and Regression Pack Consultation | Testing --> SIT Regression --> SIT Regression Framework and Regression Pack Consultation
Qualification | Non-SIT Supplier and Agent Qualification Test Data Approach and Plan Consultation | 1.1 | Non-SIT Suppliers & Agents | QWG | QAG | 2025-04-07 | 13 Working Days | 2025-04-23 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> Sandbox Testing PPIR | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> Sandbox Testing PPIR
Ofgem | Ofgem Amendments to Market-Wide Half-Hourly Settlement Governance Framework​ Consultation | n/a | All PPs | n/a | n/a | 2025-04-07 | 10 Working Days | 2025-04-21 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: Migration and Qualification Supplier Organisation Information | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: Migration and Qualification Supplier Organisation Information
Qualification | PPIR: Proposal to Descope the Qualification Testing Framework (QTF) CSS Stub | 1 | Non-SIT Suppliers | n/a | n/a | 2025-04-03 | 10 Working Days | 2025-04-17 | Closed | Testing --> SIT Regression --> SIT Regression Framework and Regression Pack Consultation | Testing --> SIT Regression --> SIT Regression Framework and Regression Pack Consultation
Testing | SIT Regression Framework and Regression Pack Consultation | 1 | SIT PPs | SITWG | SITAG | 2025-04-03 | 5 Working Days | 2025-04-09 | Closed | Migration --> MHHS Migration Framework | Migration --> MHHS Migration Framework
Testing | PPIR: Proposed use & value provided from the defined Sandbox using the UIT and SIT-A environments | 1 | All PPs | n/a | n/a | 2025-03-24 | 9 Working Days | 2025-04-03 | Closed | Design --> Baselined Design Artefacts --> Design Interim Release 8.0 - 8.10 | Design --> Baselined Design Artefacts --> Design Interim Release 8.0 - 8.10
Migration | PPIR: Migration and Qualification Supplier Organisation Information | 1 | Suppliers | n/a | n/a | 2025-03-18 | 11 Working Days | 2025-03-31 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: Use of MDR Function - Supporting Assumptions for DCC Capacity Planning | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: Use of MDR Function - Supporting Assumptions for DCC Capacity Planning
Testing | SIT Regression Framework and Regression Pack Consultation | 1 | SIT PPs | SITWG | SITAG | 2025-03-17 | 10 Working Days | 2025-03-28 | Closed | Transition --> Early Life Support Model | Transition --> Early Life Support Model
Migration | Migration Framework Consultation 4 | 0.1 | All PPs, particularly SIT PPs | MWG | MCAG | 2025-03-14 |  | 2025-03-28 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: M10 Checkpoint — Feasibility of bringing M14 forwards | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: M10 Checkpoint — Feasibility of bringing M14 forwards
Design | Design Interim Release 8.10 Artefacts | IR8.10 | All PPs | n/a | n/a | n/a | n/a | 2025-03-26 | Closed | SIT --> SIT Scope Traceability | SIT --> SIT Scope Traceability
PPIR | Use of MDR Function - Supporting Assumptions for DCC Capacity Planning | n/a | All PPs | n/a | DCC | 2025-03-03 | 11 Working Days | 2025-03-17 | Closed | SIT Operational --> SIT Operational Theme 3 | SIT Operational --> SIT Operational Test Scenarios & Test Cases --> SIT Operational Theme 3 (Batch 2) Supplementary Test Cases
Transition | Early Life Support Model Industry Review | 0.1 | All PPs | TORWG | TORWG | 2025-02-21 | 10 Working Days | 2025-03-07 | Closed | Qualification --> Qualification Assessment Document | Qualification --> Qualification Assessment Document
PPIR | M10 Checkpoint — Feasibility of bringing M14 forwards | n/a | All PPs | n/a | n/a | 2025-02-21 | 10 Working Days | 2025-03-07 | Closed | SIT Principal Contacts have emailed from the PPC with information on this. | SIT Principal Contacts have emailed from the PPC with information on this.
Testing | SIT Scope Traceability Document Industry Review | TBC | SIT PPs | NFTWG and SITWG | SITAG | 2025-02-20 | 10 Working Days | 2025-03-06 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: New Connections between M10-M14 | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: New Connections between M10-M14
Testing | SIT Operational Theme 3 Batch 2 Supplementary Test Cases Industry Review | TBC | SIT PPs | NFTWG and SITWG | SITAG | 2025-02-19 | 10 Working Days | 2025-03-04 | Closed | Design --> Baselined Design Artefacts --> Design Interim Release 8.1, 8.2, 8.3, 8.4, 8.5, 8.6, 8.7 and 8.8 | Design --> Baselined Design Artefacts --> Design Interim Release 8.1, 8.2, 8.3, 8.4, 8.5, 8.6, 8.7 and 8.8
Qualification | Qualification Assessment Document Consultation - Smart Meter Exemption | n/a | Suppliers | QWG | QAG | 2025-02-12 | 10 Working Days | 2025-02-26 | Closed | Migration --> MHHS Migration Framework | Migration --> MHHS Migration Framework
Testing | Request for SIT Suppliers to provide information regarding contractual arrangements with Agents | n/a | SIT PPs | n/a | n/a | n/a | n/a | 2025-02-24 | Closed | Please send information to to opreadiness@mhhsprogramme.co.uk | Please send information to to opreadiness@mhhsprogramme.co.uk
Design | PPIR: New Connections Between M10 – M14 | n/a | All PPs | n/a | n/a | 2025-02-07 | 10 Working Days | 2025-02-20 | Closed | SIT Operational --> SIT Regression Testing Approach and Plan | SIT Operational --> SIT Regression Testing Approach and Plan
Migration | MHHS Migration Framework Consultation 3: Post Consultation Updated Artefacts for Assurance Review | 1 | All PPs | MWG | MCAG | 2025-01-31 | 10 Working Days | 2025-02-13 | Closed | Qualification --> Qualification Approach & Plan | Qualification --> Qualification Approach & Plan
Design | Design Interim Release 8.8 Artefacts | IR8.8 | All PPs | n/a | n/a | n/a | n/a | 2025-02-12 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: Defect 43971 – Distribution Use of System (DUoS) Tariff ID | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> PPIR: Defect 43971 – Distribution Use of System (DUoS) Tariff ID
Transition | Self-declaration for Meter Location and Number of Displayed Register Digits | n/a | Suppliers | n/a | n/a | n/a | n/a | 2025-02-07 | Closed | Qualification --> Qualification Pre-Integration Testing (PIT) | Qualification --> Qualification Pre-Integration Testing (PIT)
Testing | SIT Regression Testing Test Approach & Plan | TBC | SIT PPs | SITWG | SITAG | 2025-01-27 | 10 Working Days | 2025-02-07 | Closed | Testing --> Pre-Integration Testing (PIT) | Testing --> Pre-Integration Testing (PIT)
Qualification | Qualification Approach & Plan Annex 3 Consultation | TBC | All PPs | QWG | QAG | 2025-01-23 | 10 Working Days | 2025-02-06 | Closed | Ofgem website: https://www.ofgem.gov.uk/consultation/direction-elexon-market-wide-half-hourly-settlement-mhhs-implementation-manager | Ofgem website: https://www.ofgem.gov.uk/consultation/direction-elexon-market-wide-half-hourly-settlement-mhhs-implementation-manager
Design | PPIR: Defect 43971 – Distribution Use of System (DUoS) Tariff ID | n/a | All PPs | n/a | n/a | 2025-01-21 | 10 Working Days | 2025-02-03 | Closed | Planning --> Facilitating Engagement between Suppliers and Agents | Planning --> Facilitating Engagement between Suppliers and Agents
Qualification | Final PIT Approach & Plan | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-01-31 | Closed | Not yet available | Not yet available
Qualification | Non-Functional and Operational PIT Test Completion Report | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2025-01-31 | Closed | Please send information to to opreadiness@mhhsprogramme.co.uk | Please send information to to opreadiness@mhhsprogramme.co.uk
Ofgem | Ofgem Proposed Directions to Elexon about reporting on MHHS Implementation and about managing MHHS Testing cohorts consultation | n/a | All PPs | n/a | n/a | 2025-01-16 | 10 Working Days | 2025-01-30 | Closed | Migration --> MHHS Migration Framework | Migration --> MHHS Migration Framework
Qualification | Facilitating engagement between Suppliers & Agents opt in and consent | n/a | All PPs | QWG | QAG | n/a | n/a | 2025-01-24 | Closed | Qualification --> Non-SIT Supplier and Agent Qualification --> Non-SIT Supplier and Agent Qualification Testing Test Scenarios and Test Cases | Qualification --> Non-SIT Supplier and Agent Qualification --> Non-SIT Supplier and Agent Qualification Testing Test Scenarios and Test Cases
Design | Design Interim Release 8.7 Artefacts | IR8.7 | All PPs | n/a | n/a | n/a | n/a | 2025-01-22 | Closed | Transition --> Data Cleanse Plan | Transition --> Data Cleanse Plan
Transition | Request for Suppliers to report volume of S2 Meters | n/a | Suppliers | n/a | n/a | n/a | n/a | 2025-01-17 | Closed | Qualification --> Qualification Approach & Plan | Qualification --> Qualification Approach & Plan
Migration | Migration Framework Consultation 3 | 0.1 | All PPs, particularly SIT PPs | MWG | MCAG | 2024-12-20 | 17 Working Days | 2025-01-17 | Closed | Qualification --> Non-SIT LDSO Qualification | Qualification --> Non-SIT LDSO Qualification
Qualification | Batch 3 Qualification Testing Test Scenarios Consultation | 1 | Non-SIT Suppliers & Agents | QWG | QAG | 2024-12-18 | 17 Working Days | 2025-01-15 | Closed | Qualification --> Qualification Assessment Document | Qualification --> Qualification Assessment Document
Transition | Supplier Exception Resolution Activity – ESME ID | n/a | Suppliers | n/a | n/a | n/a | n/a | 2024-12-20 | Closed | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> Smart Data Communications Company (DCC) MHHS Meter Data Retrievers (MDR) Onboarding PPIR | Programme Information --> Programme Change Control --> PPIRs --> Current PPIRs --> Smart Data Communications Company (DCC) MHHS Meter Data Retrievers (MDR) Onboarding PPIR
Qualification | Qualification Approach and Plan Annex 1 & 2 Consultation | n/a | All PPs | QWG | QAG | 2024-12-06 | n/a | 2024-12-20 | Closed | Transition --> Service Management --> Helix --> Service Operating Manual | Transition --> Service Management --> Helix --> Service Operating Manual
Non-SIT LDSO | Non-SIT LDSO Qualification Testing Readiness Report Template | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-12-13 | Closed | Design --> Baselined Design Artefacts --> Design Interim Release 8.1, 8.2, 8.3, 8.4, 8.5 and 8.6 | Design --> Baselined Design Artefacts --> Design Interim Release 8.1, 8.2, 8.3, 8.4, 8.5 and 8.6
Qualification | Qualification Assessment Document (QAD) Consultation Update | 3.3 | All PPs | QWG | QAG | 2024-12-09 | 5 Working Days | 2024-12-13 | Closed | Testing --> SIT --> SIT Operational --> SIT Operational Test Scenarios and Test Cases --> SIT Operational Theme 3 (Batch 2): DIP Onboarding, Certificate/Domain renewal and BCDR | Testing --> SIT --> SIT Operational --> SIT Operational Test Scenarios and Test Cases --> SIT Operational Theme 3 (Batch 2): DIP Onboarding, Certificate/Domain renewal and BCDR
PPIR | Smart DCC MHHS Meter Data Retrievers (MDR) Onboarding PPIR | n/a | SIT Suppliers | n/a | n/a | 2024-11-28 | n/a | 2024-12-12 | Closed | You can access more information, and download the consultation and response form, from the DCR0003 Consultation folder on Elexon's Public DIP SharePoint. If you have any questions on DCR0003, please email DIPManager@elexon.co.uk | You can access more information, and download the consultation and response form, from the DCR0003 Consultation folder on Elexon's Public DIP SharePoint. If you have any questions on DCR0003, please email DIPManager@elexon.co.uk
Transition | Service Operating Manual Consultation | 0.1 | All PPs | TORWG | MCAG | 2024-11-28 | n/a | 2024-12-11 | Closed | If you have any questions about this upcoming consultation, please email dcusa@electralink.co.uk | If you have any questions about this upcoming consultation, please email dcusa@electralink.co.uk
Design | Design Interim Release 8.6 Artefacts | IR8.6 | All PPs | n/a | n/a | n/a | n/a | 2024-11-25 | Closed | Transition > Service Management > Helix - Service Operating Manual | Transition > Service Management > Helix - Service Operating Manual
Testing | SIT Operational Theme 3 Test Scenarios and Test Cases (Batch 2): Service Management Industry Consultation | 0.1 | SIT PPs | NFTWG and SITWG | SITAG | 2024-11-11 | n/a | 2024-11-22 | Closed | Qualification --> Qualification Assessment Document | Qualification --> Qualification Assessment Document
Transition | Industry Review of the Draft Elexon Helix Service Operating Manual | 0.1 | All PPs | TORWG | MCAG | 2024-11-13 | n/a | 2024-11-22 | Closed | Programme Information --> Programme Change Control Doccuments --> Qualification Wave Reallocation PPIR | Programme Information --> Programme Change Control Doccuments --> Qualification Wave Reallocation PPIR
Qualification | Qualification Assessment Document (QAD) Consultation | 1 | All PPs | QWG | QAG | 2024-11-06 | n/a | 2024-11-20 | Closed | Testing --> SIT --> SIT Operational --> SIT Operational Test Scenarios and Test Cases --> SIT Operational Theme 3 (Batch 1): Service Management | Testing --> SIT --> SIT Operational --> SIT Operational Test Scenarios and Test Cases --> SIT Operational Theme 3 (Batch 1): Service Management
Qualification | Qualification Wave Reallocation PPIR | 1 | Non-SIT Suppliers & Agents | QWG | QAG | 2024-10-30 | n/a | 2024-11-14 | Closed | Transition --> Data Cleanse Plan | Transition --> Data Cleanse Plan
Testing | SIT Operational Test Scenarios and Test Cases Theme 3 (Batch 1): Service Management Industry Consultation | 0.1 | SIT PPs | NFTWG and SITWG | SITAG | 2024-10-28 | n/a | 2024-11-11 | Closed | Design --> Baselined Design Artefacts --> Design Interim Release 8.1, 8.2, 8.3, 8.4 and 8.5 | Design --> Baselined Design Artefacts --> Design Interim Release 8.1, 8.2, 8.3, 8.4 and 8.5
Design | Design Interim Release 8.5 Artefacts | IR8.5 | All PPs | n/a | n/a | n/a | n/a | 2024-11-06 | Closed | SIT --> SIT Functional --> SIT Functional Test Scenarios and Test Cases | SIT --> SIT Functional --> SIT Functional Test Scenarios and Test Cases
Testing | SIT Functional Cycle 3 Test Scenarios and Test Cases – Uplifted | n/a | All PPs | SITWG | SITAG | n/a | n/a | 2024-10-17 | Closed | Design --> Baselined Design Artefacts --> Design Interim Release 8.1, 8.2, 8.3 and 8.4 | Design --> Baselined Design Artefacts --> Design Interim Release 8.1, 8.2, 8.3 and 8.4
Design | Design Interim Release 8.4 Artefacts | IR8.4 | All PPs | n/a | n/a | n/a | n/a | 2024-10-16 | Closed | Qualification --> Non-SIT LDSO Qualification --> Non-SIT LDSO Qualification Testing Industry Standing Data (ISD) Files | Qualification --> Non-SIT LDSO Qualification --> Non-SIT LDSO Qualification Testing Industry Standing Data (ISD) Files
Non-SIT LDSO | Non-SIT LDSO Qualification Testing Industry Standing Data (ISD) Files | n/a | Non-SIT LDSOs | QWG | QAG | 2024-09-18 | n/a | 2024-10-11 | Closed | Qualification --> Qualification Assessment Document --> Self-Qualification Assessment Document | Qualification --> Qualification Assessment Document --> Self-Qualification Assessment Document
Qualification | Self-Qualification Assessment Document (SQAD) Consultation | 0.2 | New Entrant Data Services | QWG | QAG | 2024-09-16 | n/a | 2024-09-27 | Closed | Transition --> Service Management --> Elexon – MHHS Service Definition Document and Low-Level Service Definition Document | Transition --> Service Management --> Elexon – MHHS Service Definition Document and Low-Level Service Definition Document
Transition | Service Definition Document (SDD) and Low-Level Service Definition Document (LLSD) | 0.1 | All PPs | TORWG | TORWG | 2024-09-04 | n/a | 2024-09-19 | Closed | Testing --> SIT --> SIT Operational --> SIT Operational Test Scenarios and Test Cases --> SIT Operational Theme 3 (Batch 1): Service Management | Testing --> SIT --> SIT Operational --> SIT Operational Test Scenarios and Test Cases --> SIT Operational Theme 3 (Batch 1): Service Management
Testing | SIT Operational Test Scenario and Test Case Delivery Theme 3 Industry Review | 0.1 | SIT PPs | NFTWG and SITWG | SITAG | 2024-09-04 | n/a | 2024-09-19 | Closed | Design --> Baselined Design Artefacts --> Design Interim Release 8.1, 8.2 and 8.3 | Design --> Baselined Design Artefacts --> Design Interim Release 8.1, 8.2 and 8.3
Design | Design Interim Release 8.3 Artefacts | IR8.3 | All PPs | n/a | n/a | n/a | n/a | 2024-09-18 | Closed | Design --> Baselined Design Artefacts --> Design Interim Release 8.1 and 8.2 | Design --> Baselined Design Artefacts --> Design Interim Release 8.1 and 8.2
Design | Design Interim Release 8.2 Artefacts | IR8.2 | All PPs | n/a | n/a | n/a | n/a | 2024-08-21 | Closed | Testing --> SIT --> SIT Functional Test Scenarios and Test Cases --> SIT Functional Test Scenarios Cycle 2 | Testing --> SIT --> SIT Functional Test Scenarios and Test Cases --> SIT Functional Test Scenarios Cycle 2
Testing | SIT Functional Cycle 2 Test Scenarios and Cases – Uplifted | n/a | SIT PPs | SITWG | SITAG | n/a | n/a | 2024-08-20 | Closed | SIT --> SIT Non-Functional --> SIT Non-Functional Test Scenarios and Test Cases --> SIT Non-Functional Theme 3: Targeted Interfaces | SIT --> SIT Non-Functional --> SIT Non-Functional Test Scenarios and Test Cases --> SIT Non-Functional Theme 3: Targeted Interfaces
Testing | SIT Non-Functional Test Scenarios and Cases Theme 3: Targeted Interfaces uplifted | n/a | SIT PPs | NFTWG | SITAG | n/a | n/a | 2024-08-16 | Closed | Non-SIT LDSO Qualification Test Scenarios and Test Cases > Non-SIT LDSO Non-Functional Test Scenarios and Test Cases | Non-SIT LDSO Qualification Test Scenarios and Test Cases > Non-SIT LDSO Non-Functional Test Scenarios and Test Cases
Non-SIT LDSO | Non-SIT LDSO Non-Functional Test Scenarios and Test Cases Consultation | TBC | Non-SIT LDSOs | QWG | QAG | 2024-07-24 | n/a | 2024-08-02 | Closed | Code --> Code Artefacts --> Code Artefacts Consistency Check | Code --> Code Artefacts --> Code Artefacts Consistency Check
Code | Code Consistency Check Assurance Review | n/a | All PPs | CDWG | CCAG | 2024-07-26 | n/a | 2024-08-02 | Closed | Qualification --> Non-SIT LDSO Qualification | Qualification --> Non-SIT LDSO Qualification
Qualification | Non-SIT LDSO Qualification Testing Readiness Report Template | 1 | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-07-26 | Closed | Programme Information --> Programme Change Control Doccuments --> PPIR in relation to 'Validation of Service Provider CoS Appointment' prior to formal Change Request | N/A
Design | PPIR in relation to 'Validation of Service Provider CoS Appointment' prior to formal Change Request | n/a | All PPs | DRG | Change Board | 2024-07-08 | n/a | 2024-07-22 | Closed | Qualification Overview --> Qualification Request for Participant Contact Details | Qualification --> Qualification Request for Participant Contact Details
Qualification | Qualification Request for Participant Contact Details | n/a | All PPs | QWG | QAG | 2024-07-05 | n/a | 2024-07-19 | Closed | Qualification --> Non-SIT LDSO Qualification --> Non-SIT LDSO Qualification Testing Test Scenarios and Test Cases | Qualification --> Non-SIT LDSO Qualification --> Non-SIT LDSO Qualification Testing Test Scenarios and Test Cases
Non-SIT LDSO | Non-SIT LDSO Operational Test Scenarios & Test Cases Consultation | 1 | Non-SIT LDSOs | QWG | QAG | 2024-07-09 | n/a | 2024-07-19 | Closed | Non-Systems Integration Testing (SIT) Licensed Distribution System Operators (LDSO) Qualification --> Non-SIT LDSO Test Data Approach & Plan | Non-Systems Integration Testing (SIT) Licensed Distribution System Operators (LDSO) Qualification --> Non-SIT LDSO Test Data Approach & Plan
Non-SIT LDSO | Non-SIT LDSO Test Data Approach & Plan Consultation | TBC | Non-SIT LDSOs | QWG | QAG | 2024-07-08 | n/a | 2024-07-19 | Closed | Qualification --> Qualification Approach and Plan | Qualification --> Qualification Approach and Plan
Qualification | Qualfication Approach & Plan: Annex 2 Non-SIT Supplier & Agents Consultation | TBC | Non-SIT Suppliers & Agents | QWG | QAG | 2024-07-08 | n/a | 2024-07-19 | Closed | Qualification --> Qualification Approach and Plan | Qualification --> Qualification Approach and Plan
Qualification | Qualfication Approach & Plan: Annex 1 Non-SIT LDSOs Consultation | TBC | Non-SIT LDSOs | QWG | QAG | 2024-07-08 | n/a | 2024-07-19 | Closed | Qualification --> Qualification Approach & Plan | Qualification --> Qualification Approach & Plan
Qualification | Qualification Approach & Plan Consultation | v3.0 | All PPs | QWG | QAG | 2024-07-08 | n/a | 2024-07-19 | Closed | Qualification --> Qualification Assessment Document | Qualification --> Qualification Approach & Plan
Qualification | Self Qualification Assessment Document | TBC | New Entrant Data Services | QWG | QAG | 2024-07-08 | n/a | 2024-07-19 | Closed | Qualification --> Qualification Assessment Document | Qualification --> Qualification Assessment Document
Qualification | Qualification Assessment Document (QAD) Consultation | 1.2 | All PPs | QWG | QAG | 2024-07-03 | n/a | 2024-07-19 | Closed | MHHS Migration Contact Nomination Form | MHHS Migration Contact Nomination Form
Migration | Migration Contact Nominations Request | n/a | Suppliers | MWG | MCAG | 2024-06-21 | n/a | 2024-07-19 | Closed | Migration --> MHHS Migration Framework | Migration --> MHHS Migration Framework
Migration | Migration Framework Consultation 2 Assurance Review | 0.1 | All PPs | MWG | MCAG | 2024-07-11 | n/a | 2024-07-18 | Closed | N/A | N/A
Migration | Test Population Activity: Population of ESME ID | n/a | DCC and LDSOs | MWG | MCAG | n/a | n/a | 2024-07-18 | Closed | N/A | N/A
Migration | Test Population Activity: Population of Meter Location and Number of Displayed Register Digits | n/a | DCC, MEMs and LDSOs | MWG | MCAG | n/a | n/a | 2024-07-18 | Closed | DIP --> Interface Code of Connection and PKI Certificate Policy | Not yet available
DIP | Code of Connection Consultation | TBC | All PPs | SDWG | DAG | 2024-07-01 | n/a | 2024-07-12 | Closed | Code --> Code Artefacts --> Code Artefacts Consistency Check | Code --> Code Artefacts --> Code Artefacts Consistency Check
Code | Consistency Check Consultation (All Codes) | n/a | All PPs | CDWG | CCAG | 2024-06-24 | n/a | 2024-07-12 | Closed | Transition --> Elexon Programme Participant Information Request: DTN File Numbering during Transition | Transition --> Elexon Programme Participant Information Request: DTN File Numbering during Transition
Transition: Elexon PPIR | Elexon PPIR: DTN File Numbering during Transition | n/a | All PPs | TORWG | n/a | 2024-06-13 | n/a | 2024-07-11 | Closed | Transition --> Data Cleanse Plan | Transition --> Data Cleanse Plan
Transition | Test Population Activity: Population of Meter Location and Number of Displayed Register Digits | n/a | MEMs | DCWG | MCAG | 2024-06-21 | n/a | 2024-07-05 | Closed | Planning --> Ofgem PPIR | Planning --> Ofgem PPIR
Ofgem PPIR | Ofgem PPIR: MHHS Cost Analysis | n/a | All PPs | n/a | n/a | 2024-05-24 | n/a | 2024-07-05 | Closed | Qualification --> End-to-End Sandbox Guidance | Qualification --> End-to-End Sandbox Guidance
Qualification | End-to-End Sandbox Guidance | 1 | All PPs | QWG | QAG | 2024-06-21 | n/a | 2024-07-05 | Closed
Testing | SIT Operational Test Scenarios and Test Cases for Theme 1 uplifted to v0.2 | 0.2 | SIT PPs | NFTWG and SITWG | SITAG | 2024-07-03 | n/a | 2024-07-03 | Closed
Testing | Systems Integration Testing (SIT) Non-Functional Test Scenarios and Test Cases for Themes 2 & 3 uplifted to v0.2 | 0.2 | SIT PPs | NFTWG and SITWG | SITAG | 2024-07-03 | n/a | 2024-07-03 | Closed | PIT | PIT
Non-SIT LDSO | Non-SIT LDSO Non-Functional and Operational Pre-Integration Testing (PIT) Approach and Plan | n/a | Non-SIT LDSOs | QWG | QAG | 2024-06-14 | n/a | 2024-07-01 | Closed | Migration --> MHHS Migration Framework | Migration --> MHHS Migration Framework
Qualification | Non-SIT LDSO Qualification Testing Approach and Plan Template completion | n/a | Non-SIT LDSOs | QWG | QAG | 2024-05-24 | n/a | 2024-06-28 | Closed | Programme Change Control --> PPIR | Programme Change Control --> PPIR
Qualification | Non-SIT Supplier Meter Point Administration Number (MPAN) Data Request for Qualification Testing | n/a | Non-SIT Suppliers | QWG | QAG | 2024-06-19 | n/a | 2024-06-28 | Closed | Qualification | Qualification
DIP | Data Integration Platform (DIP) Simulator updates for Interim Releases 8 & 8.1 | 8 & 8.1 | All PPs | SDWG | DAG | 2024-06-28 | n/a | 2024-06-28 | Closed | Qualification --> MPAN Data Request | Qualification --> MPAN Data Request
Qualification | Wave Allocation | n/a | All PPs | QWG | QAG | 2024-06-28 | n/a | 2024-06-28 | Closed | Not yet available | Not yet available
Migration | Migration Framework Consultation 2 | 0.1 | All PPs, particularly SIT PPs | MWG | MCAG | 2024-06-13 | n/a | 2024-06-27 | Closed | Not yet available | Not yet available
CR45 PPIR | CR45 PPIR | n/a | All PPs | n/a | CB | 2024-06-11 | n/a | 2024-06-24 | Closed | Qualification --> Non-SIT Suppliers & Agents Qualification Test Data and Approach | Qualification --> Non-SIT Suppliers & Agents Qualification Test Data and Approach
Testing | Non-SIT Supplier and Agent Qualification Test Data Approach and Plan | 0.5 | Non-SIT Suppliers & Agents | QWG | QAG | 2024-06-06 | n/a | 2024-06-21 | Closed | Qualification --> Non-SIT Suppliers & Agents Qualification Test Data Approach | Qualification --> Non-SIT Suppliers & Agents Qualification Test Data Approach
Qualification | Non-SIT Supplier & Agent Qualification Testing Test Data Approach | TBC | Non-SIT Suppliers & Agents | QWG / SAQTSG | QAG | 2024-06-10 | n/a | 2024-06-17 | Closed | Testing --> SIT --> SIT Non-Functional | Testing --> SIT --> SIT Non-Functional
Testing | SIT Non-Functional Test Scenario and Test Cases Delivery Theme 3 | n/a | SIT PPs | NFTWG | SITAG | 2024-06-10 | n/a | 2024-06-17 | Closed | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios
Qualification | Non-SIT Supplier & Agent Qualification Testing Migration Test Scenarios and Test Cases | v0.1 | Non-SIT Suppliers & Agents | QWG / SAQTSG | QAG | 2024-06-03 | n/a | 2024-06-14 | Closed | Design --> Baselined Design Artefacts --> Baselined Design Artefacts Interim Release 8.1 | Design --> Baselined Design Artefacts --> Baselined Design Artefacts Interim Release 8.1
Design | Design Interim Release 8.1 Artefacts | IR8.1 | All PPs | n/a | n/a | 2024-06-12 | n/a | 2024-06-12 | Closed | Testing --> SIT Functional --> SIT Functional Test Scenarios and Test Cases ---> SIT Functional Test Scenarios Cycle 2 | Testing --> SIT Functional --> SIT Functional Test Scenarios and Test Cases ---> SIT Functional Test Scenarios Cycle 2
Testing | SIT Operational Test Scenario and Test Cases Theme 2 Industry Review | n/a | SIT PPs | NFTWG and SITWG | SITAG | 2024-06-04 | n/a | 2024-06-11 | Closed | Testing --> SIT --> SIT Operational | Testing --> SIT --> SIT Operational
Testing | SIT Functional Cycle 2 Test Scenarios and Cases – Alignment with Interim Release 7 (IR7) | n/a | SIT PPs | NFTWG and SITWG | SITAG | 2024-05-20 | n/a | 2024-06-10 | Closed | Testing --> Environment Approach & Plan | Testing Overview --> Environment Approach & Plan
Testing | Environments Approach & Plan assurance review | v2.15 | All PPs | EWG | SITAG | 2024-05-28 | n/a | 2024-06-07 | Closed | SIT --> Operational | SIT --> Operational
Testing | SIT Operational Test Scenario and Test Cases Theme 1 Industry Review | n/a | SIT PPs | NFTWG and SITWG | SITAG | 2024-05-28 | n/a | 2024-06-04 | Closed | Testing --> SIT --> SIT Non-Functional --> Test Scenarios and Test Cases | Testing --> SIT --> SIT Non-Functional --> Test Scenarios and Test Cases
Testing | SIT Non-Functional Test Scenarios and Test Cases Theme 2 Industry Review | n/a | SIT PPs | NFTWG | SITAG | 2024-05-20 | n/a | 2024-05-29 | Closed | Testing --> SIT --> SIT Non-Functional --> Test Scenarios and Test Cases | Testing --> SIT --> SIT Non-Functional --> Test Scenarios and Test Cases
Testing | SIT Non-Functional Test Tooling Queries - Theme 2 | n/a | SIT PPs | NFTWG and SITWG | SITAG | 2024-05-22 | n/a | 2024-05-24 | Closed | Change Control Documents | Change Control Documents
CR44 PPIR | CR44 PPIR | n/a | All PPS | n/a | CB | 2024-05-17 | n/a | 2024-05-24 | Closed | Qualification --> Qualification Assessment Document | Qualification --> Qualification Assessment Document
Qualification | Qualification Assessment Document Guidance Informal Consultation | v1.1 | All PPs | QWG | QAG | 2024-05-07 | n/a | 2024-05-21 | Closed | SIT --> SIT Migration --> SIT Migration Participant Readiness Reporting | SIT --> SIT Migration --> SIT Migration Participant Readiness Reporting
Testing | SIT Migration Participant Readiness Reporting | n/a | SIT PPs | SITWG | SITAG | 2024-05-07 | n/a | 2024-05-15 | Closed | Testing --> SIT --> SIT Functional test scenarios and test cases --> SIT Non-Functional theme 1 | Testing --> SIT Non-Functional -- > SIT Non-Functional test scenarios and test cases --> SIT Non-Functional Theme 1 - DIP and Helix
Testing | SIT Non-Functional Test Scenario and Test Cases Delivery Theme 1 | n/a | SIT PPs | NFTWG | SITAG | 2024-05-02 | n/a | 2024-05-10 | Closed | Transition --> M10 / M11 Cutover Plan | Transition --> M10 / M11 Cutover Plan
Transition | M10 M11 Cutover Plan Consultation | v0.1 | All PPs | TORWG | MCAG | 2024-04-23 | n/a | 2024-05-07 | Closed | Qualification --> Qualification Approach & Plan | Qualification --> Qualification Approach & Plan
Qualification | Qualification Approach & Plan: Annex 1 Non-Functional and Operational Testing Updates Consultation | v1.1 | Non-SIT LDSOs | QWG | QAG | 2024-04-23 | n/a | 2024-05-03 | Closed | Qualification --> Non-SIT LDSO Test Cases and Test Scenarios | Qualification --> Non-SIT LDSO Test Cases and Test Scenarios
Qualification | Non-Systems Integration Testing (SIT) Licensed Distribution System Operators (LDSOs) Migration Test Scenarios & Test Cases Consultation | n/a | Non-SIT LDSOs | QWG | QAG | 2024-04-22 | n/a | 2024-05-03 | Closed | N/A | N/A
Data Cleanse Activities | LDSOs issue a self-declaration to the Programme that they have completed population activities set out within section “6.2.1.4 Population of Connection Type for Traditional and Advanced Meters within Measurement Class ‘A’” | n/a | LDSOs | n/a | n/a | 2024-04-08 | n/a | 2024-04-29 | Closed | N/A | N/A
Data | 6.2.1.4 Population of Connection Type for Traditional and Advanced Meters within Measurement Class ‘A’” | n/a | LDSOs | DWG | SITAG | 2024-04-08 | n/a | 2024-04-29 | Closed | Qualification --> Pre-Qualification Submission | Qualification --> Pre-Qualification Submission
Migration | Migration Framework Assurance Meeting | n/a | All PPs | MWG | MCAG | 2024-04-19 | n/a | 2024-04-26 | Closed | Transition --> Data Cleanse Plan | Transition --> Data Cleanse Plan
Qualification | Pre-Qualification Submission | n/a | Non-SIT Suppliers & Agents | QWG | QAG | 2024-02-05 | n/a | 2024-04-26 | Closed | Code --> Code artefacts --> Mop Up 2 | Code --> Code Artefacts --> Mop Up 2
Code | Topic Area Mop-up 2 (All Codes) Assurance Review | n/a | All PPs | CDWG | CCAG | 2024-04-10 | n/a | 2024-04-22 | Closed | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios
Qualification | Qualification Non-SIT Suppliers & Agents Test Cases & Test Scenarios Batch 2 | v0.2 | Non-SIT Suppliers & Agents | QWG | QAG | 2024-04-05 | n/a | 2024-04-19 | Closed | Testing --> SIT --> SIT Operational | Not yet available
Testing | SIT Operational Test Approach & Plan Assurance Review | TBC | SIT PPs | SITWG, NFWG | SITAG | 2024-04-15 | n/a | 2024-04-19 | Closed | Testing --> SIT --> SIT Operational | Not yet available
Testing | SIT Operational Test Data Approach & Plan Assurance Review | TBC | SIT PPs | SITWG, NFWG | SITAG | 2024-04-15 | n/a | 2024-04-19 | Closed | Testing --> SIT --> SIT Non-Functional --> Test Data A&P | Testing --> SIT --> SIT Non-Functional --> Test Data A&P
Testing | SIT Non-Functional Test Data Approach and Plan Assurance Review | TBC | SIT PPs | SITWG, NFWG | SITAG | 2024-04-11 | n/a | 2024-04-17 | Closed
Testing | SIT Non-Functional Test Approach and Plan Industry Assurance Review | TBC | SIT PPs | SITWG, NFWG | SITAG | 2024-04-11 | n/a | 2024-04-17 | Closed | Qualification --> Non-SIT LDSO Approach & Plan | Qualification --> Non-SIT LDSO Approach & Plan
Testing | Non-SIT LDSO Test Data Approach and Plan Consultation | v0.8 | Non-SIT LDSOs | QWG | QAG | 2024-03-28 | n/a | 2024-04-15 | Closed | Not yet available | Not yet available
Testing | SIT Operational Test Approach & Plan Industry Consultation | TBC | SIT PPs | SITWG | SITAG | 2024-03-27 | n/a | 2024-04-09 | Closed | Not yet available | Not yet available
Testing | SIT Operational Test Data Approach & Plan Industry Consultation | TBC | SIT PPs | SITWG | SITAG | 2024-03-27 | n/a | 2024-04-09 | Closed | Migration & Transition --> MHHS Migration Framework | Migration & Transition --> MHHS Migration Framework
Migration | Migration Framework Consultation 1 | TBC | All PPs, particularly SIT PPs | MWG | MCAG | 2024-03-18 | n/a | 2024-04-08 | Closed | Not yet available | Not yet available
Testing | SIT Non-Functional Test Data Approach and Plan Industry Consultation | 0.2 | SIT PPs | SITWG, NFWG | SITAG | 2024-03-26 | n/a | 2024-04-05 | Closed | Qualification --> Qualification Approach & Plan | Qualification --> Qualification Approach & Plan
Qualification | Annex 2: Qualification Approach & Plan: Non-SIT Supplier & Agent MHHS Qualification Testing Approach Consultation | v0.5 | Non-SIT Suppliers & Agents | QWG | QAG | 2024-03-18 | n/a | 2024-04-05 | Closed | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios
Qualification | Non-SIT Supplier & Agent Qualification Testing Test Scenarios Batch 1 | v0.2 | Non-SIT Suppliers & Agents | QWG | QAG | 2024-03-18 | n/a | 2024-04-05 | Closed | Not yet available | Not yet available
Design | Design Interim Release 8 published | IR8 | All PPs | n/a | n/a | n/a | n/a | 2024-04-03 | Closed | Timeline adjusted as agreed at SITAG on 21-Feb-24 | Not yet available
Testing | SIT Non-Functional Test Approach and Plan Industry Consultation | TBC | SIT PPs | SITWG, NFWG | SITAG | 2024-03-18 | n/a | 2024-04-02 | Closed | Testing --> Environment Approach & Plan | Testing --> Environment Approach & Plan
Testing | Environment Approach & Plan Industry Consultation | 2.12 | All PPs | EWG | SITAG | 2024-03-14 | n/a | 2024-03-21 | Closed | Testing --> SIT | Testing --> SIT --> SIT Migration Test Scenarios & Test Cases --> SIT Migration Theme 3
Testing | SIT Migration Theme 3 - Import/Export MPANs & Exception Handling | TBC | SIT PPs | SITWG | SITAG | 2024-03-13 | n/a | 2024-03-20 | Closed | Not on the website | Not on the Collaboration Base
N/A | MHHS PPIR: Use of MDR Function - Supporting Assumptions for DCC Capacity Planning | N/A | All Suppliers | n/a | n/a | 2024-03-06 | n/a | 2024-03-19 | Closed | Code --> MHHS Supply, Distribution and Transmission Licence Review | Code Homepage --> MHHS Supply, Distribution and Transmission Licence Review
N/A | MHHS Licence Review Consultation | n/a | All PPs | N/A | CCAG | 2024-01-31 | n/a | 2024-03-13 | Closed | Code --> Code artefacts --> Mop Up 2 | Code --> Code artefacts --> Mop Up 2
Code | Topic Area Mop-up 2 (All Codes) Consultation | n/a | All PPs | CDWG | CCAG | 2024-02-19 | n/a | 2024-03-11 | Closed | Not on the website | Qualification --> Non-SIT LDSO Qualification
Qualification | Non-SIT LDSO Test Scenarios & Test Cases Review | Multiple | Non-SIT LDSOs | QWG | QAG | 2024-02-26 | n/a | 2024-03-08 | Closed | Testing --> Qualification | Testing --> Qualification --> Qualification Assessment Document
Qualification | Qualification Assessment Document Consultation | TBC | All PPs | QWG | QAG | 2024-02-16 | n/a | 2024-03-01 | Closed | n/a | n/a
Testing | SIT Functional Defect Management Approach and Plan released to participants | n/a | SIT PPs | SITWG | SITAG | 2024-02-29 | n/a | 2024-02-29 | Closed | Testing --> SIT--> SIT Migration | Testing --> SIT --> SIT Migration Test Scenarios & Test Cases --> SIT Migration Theme 1
Testing | SIT Migration Theme 1 Test Scenarios and Cases – Further Uplifts | TBC | SIT PPs | SITWG | SITAG | 2024-02-13 | n/a | 2024-02-28 | Closed | Testing --> SIT | Testing --> SIT--> SIT Functional Participant Readiness Report
Testing | SIT Functional Readiness Report Template | n/a | SIT PPs | SITWG | SITAG | 2024-02-05 | n/a | 2024-02-14 | Closed | Qualification --> Qualification Approach & Plan | Qualification --> Qualification Approach & Plan
Qualification | Qualification Approach & Plan | v1.1 | All PPs | QWG | QAG | 2024-01-31 | n/a | 2024-02-14 | Closed | Not yet available | Not yet available
Testing | CIT Test Completion Report Template - for completion | n/a | SIT PPs | SITWG | SITAG | 2024-02-06 | n/a | 2024-02-13 | Closed | Not yet available | Not yet available
Testing | SIT Migration Theme 1 Test Scenarios and Cases - Industry Review | n/a | SIT PPs | SITWG | SITAG | 2024-02-05 | n/a | 2024-02-12 | Closed | Migration --> Data Cleanse Plan | Migration --> Data Cleanse Plan
Testing | SIT Functional Test Scheduling / Prioritisation released to participants | n/a | SIT PPs | SITWG | SITAG | 2024-02-09 | n/a | 2024-02-09 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 5.4 (Red-lined versions) | Design --> Red-lined Design Artefacts --> Interim Release 5.4 (Red-lined versions)
Migration | Data Cleanse Plan Consultation | v1.1 | All PPs | DCWG | MCAG | 2024-01-29 | n/a | 2024-02-09 | Closed | Not yet available | Not yet available
Design | Design Interim Release 5.4 published | n/a | All PPs | n/a | n/a | 2024-02-07 | n/a | 2024-02-07 | Closed | Not yet available | Not yet available
Testing | SIT Functional Readiness Report Template - released to participants | v1.0 | SIT PPs | SITWG | SITAG | 2024-02-05 | n/a | 2024-02-05 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 7 (Red-lined versions) | Design --> Red-lined Design Artefacts --> Interim Release 7 (Red-lined versions) OR Design --> Baselined Design Artefacts (Clean versions)
Design | Design Interim Release 7 published | n/a | All PPs | n/a | n/a | 2024-01-31 | n/a | 2024-01-31 | Closed | Code --> Code Artefacts | Code --> Code Artefacts
Code | Topic Area Mop-up 1 (All Codes) Assurance Review | n/a | All PPs | CDWG | CCAG | 2024-01-17 | n/a | 2024-01-31 | Closed | Migration --> Migration Overview --> MHHS Service Management Strategy Consultation --> MHHS Service Management Strategy / MHHS Service Management Strategy Comments Log | Migration --> Service Management Strategy --> MHHS Service Management Strategy v0.1 / MHHS Service Management Strategy Comments Log
Transition and Operational Readiness | MHHS Service Management Strategy Consultation | v0.1 | All PPs | TORWG | TMAG | 2024-01-15 | n/a | 2024-01-26 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG for Impact Assessment
Governance - Change Request | CR040: Change to NFR E2E1009 for DNO and iDNO roles | n/a | All PPs | n/a | DAG | 2024-01-10 | n/a | 2024-01-24 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG for Impact Assessment
Governance - Change Request | CR041: Change the format of Market Participant Code from Char(1) to Char(2) | n/a | All PPs | n/a | DAG | 2024-01-10 | n/a | 2024-01-24 | Closed | Qualification | Qualification
Code | Topic Area Mop-up (All Codes) | n/a | All PPs | CDWG | CCAG | 2023-11-30 | n/a | 2024-01-02 | Closed | Design --> Baselined Design Artefacts --> MHHS Impacts to DTN Flows | Design --> Baselined Design Artefacts --> MHHS Impacts to DTN Flows
Code | Transition Text (REC & BSC) and Interfaces / Data Spec (REC & BSC) Assurance Review | Multiple | All PPs | CDWG | CCAG | 2023-11-22 | n/a | 2023-12-13 | Closed | Code --> Code artefacts --> Mop Up 1 | Code --> Code artefacts --> Mop Up 1
Migration | M15 Acceptance Criteria | 0.1 | All PPs | MWG | TMAG | 2023-11-22 | n/a | 2023-12-06 | Closed | Code --> Code artefacts --> Tranche 4 | Code --> Code artefacts --> Tranche 4
Testing | CIT Test Cases, Batch 3 (Interval 5 & 6) Assurance Review | TBC | SIT PPs | SITWG | TMAG | 2023-11-27 | n/a | 2023-12-01 | Closed | Migration | Migration
Testing | SIT Migration Test and Test Data Approach & Plan Assurance Review | TBC | SIT PPs | SITWG | TMAG | 2023-11-21 | n/a | 2023-11-27 | Closed | Testing --> SIT | Testing --> SIT
Testing | CIT Test Cases, Batch 3 (Interval 5 & 6) Consultation | n/a | SIT PPs | SITWG | TMAG | 2023-11-09 | n/a | 2023-11-21 | Closed | Testing --> SIT--> SIT Migration | Testing --> SIT--> SIT Migration
Testing | SIT Migration Test and Test Data Approach & Plan Industry Consultation | v0.2 | SIT PPs | SITWG | TMAG | 2023-11-02 | n/a | 2023-11-15 | Closed | Testing --> SIT | Testing --> SIT
Design | Interim Release 6 Release | IR6 | All PPs | n/a | n/a | n/a | n/a | 2023-11-01 | Closed | Testing --> SIT | Testing --> SIT
Code | Interfaces / Data Spec (REC & BSC) Consultation | n/a | All PPs | CDWG | CCAG | 2023-10-11 | n/a | 2023-11-01 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 6 (Red-lined versions) | Design --> Red-lined Design Artefacts --> Interim Release 6 (Red-lined versions)
Code | Transition Text (REC & BSC) Consultation | n/a | All PPs | CDWG | CCAG | 2023-10-11 | n/a | 2023-11-01 | Closed | Code --> Code artefacts --> Tranche 4 | Code --> Code artefacts --> Tranche 4
Governance - Change Request | CR032: Change to interface MHHS-IF-165 P0210 TUoS reporting | n/a | All PPs | n/a | DAG | 2023-10-13 | n/a | 2023-10-30 | Closed | Code --> Code artefacts --> Tranche 4 | Code --> Code artefacts --> Tranche 4
Design | Programme Participant Information Request: UTC vs Clock | n/a | All PPs | DRG | DAG | 2023-10-16 | n/a | 2023-10-30 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG for Impact Assessment
Testing | CIT Test Cases, Batch 2 (Interval 3 & 4) Assurance Review | n/a | SIT PPs | SITWG | TMAG | 2023-10-23 | n/a | 2023-10-27 | Closed | Testing --> SIT | Testing --> SIT
Transition Design | Settlement Timetable Transition Solution Consultation | TBC | All PPs | MTDSG | DAG | 2023-10-11 | n/a | 2023-10-25 | Closed | N/A | N/A
Code | REC & BSC Qualification / Governance and Migration Code Artefacts Assurance Review | n/a | All PPs | CDWG | CCAG | 2023-09-29 | n/a | 2023-10-20 | Closed | Design --> Transition Design | Design --> Transition Design
Testing | Environment Approach & Plan Assurance Review | v2.7 | All PPs | EWG | TMAG | 2023-10-16 | n/a | 2023-10-20 | Closed | Code --> Code artefacts --> Tranche 3 | Code --> Code artefacts --> Tranche 3
Design | Interim Release 6 Objection Cut-off | IR6 | All PPs | n/a | n/a | n/a | n/a | 2023-10-18 | Closed | Testing Overview --> Environment Approach & Plan | Testing Overview --> Environment Approach & Plan
Migration | Migration Thresholds | v0.1 | All PPs | MWG | TMAG | 2023-09-27 | n/a | 2023-10-11 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG on 13-Sep-23. Approved without IA due to low impact T2 milestone. Please view the Master Change Request dashboard tab for more information.
Design | Interim Release 5 Release | IR5 | All PPs | n/a | n/a | n/a | n/a | 2023-10-04 | Closed | n/a | n/a
Planning | Readiness Assessment Three (RA3) | N/a | All PPs | n/a | PSG | 2023-09-05 | n/a | 2023-09-25 | Closed | Migration --> Migration Thresholds | Migration --> Migration Thresholds
Testing | CIT Test Cases, Batch 1 (Interval 1 & 2) Assurance Review |  | SIT PPs | SITWG | TMAG | 2023-09-18 | n/a | 2023-09-22 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 5 (Red-lined versions) OR Design --> Baselined Design Artefacts (Clean versions) | Design --> Red-lined Design Artefacts --> Interim Release 5 (Red-lined versions) OR Design --> Baselined Design Artefacts (Clean versions)
Design | Interim Release 5 Objection Cut-off | IR5 | All PPs | n/a | n/a | 2023-08-30 | n/a | 2023-09-20 | Closed | Planning --> RA3 | Planning --> RA3
Code | Migration (REC & BSC) and Qualification Governance (REC & BSC) | n/a | All PPs | CDWG | CCAG | 2023-08-18 | n/a | 2023-09-08 | Closed | n/a | n/a
Testing | SIT Functional Test Scenarios Assurance Review | v5.2.1 | SIT PPs | SITWG | TMAG | 2023-08-21 | n/a | 2023-09-05 | Closed | Shared via email | Shared via email
Testing | Test Data SFTP Guide | v1.0 | FTIG PPs | FTIG | FTIG | 2023-08-29 | n/a | 2023-09-05 | Closed | Code --> Code artefacts --> Tranche 3 | Code --> Code artefacts --> Tranche 3
Design | Interim Release 4 Release | IR4 | All PPs | n/a | n/a |  | n/a | 2023-08-30 | Closed | Testing --> SIT | Testing --> SIT
Design | MHHS Impacts to BSC Owned Data Flows | v0.5 | All PPs | n/a | DAG | 2023-08-14 | n/a | 2023-08-29 | Closed | n/a | n/a
Code | Balancing and Settlement Code (BSC) Central Services Assurance Review | n/a | All PPs | CDWG | CCAG | n/a | n/a | 2023-08-25 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 4 (Red-lined versions) | Design --> Red-lined Design Artefacts --> Interim Release 4 (Red-lined versions)
Testing | Bilateral Data Sharing Agreement: Review and Signing (FTIG PPs) | v2.3 | FTIG PPs | n/a | n/a | n/a | n/a | 2023-08-25 | Closed | Design --> Design Overview | Design
Testing | SIT CIT Test Scenarios Assurance Review | v5.2.2 | SITWG & TMAG Attendees | SITWG | TMAG | n/a | n/a | 2023-08-25 | Closed | Code --> Code Artefacts --> Tranche 2 | Code --> Code Artefacts --> Tranche 2
Governance - Change Request | CR030: Introduction of Compressed Payloads into DIP Messages | n/a | All PPs | n/a | DAG | 2023-08-11 | n/a | 2023-08-25 | Closed | Testing --> Data | Testing --> Data
Governance - Change Request | CR029: DIP LDSO Interface Processing | n/a | All PPs | n/a | DAG | 2023-08-10 | n/a | 2023-08-24 | Closed | Testing --> SIT | Testing --> SIT
Governance - Change Request | CR028: Change to interface MHHS-IF-165 P0210 TUoS reporting | n/a | All PPs | n/a | DAG | 2023-08-10 | n/a | 2023-08-24 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG on 13-Sep-25. Please view the Master Change Request dashboard tab for more information.
Design | Interim Release 4 Objection Cut-off | IR4 | All PPs | n/a | n/a | n/a | n/a | 2023-08-16 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG on 13-Sep-24. Please view the Master Change Request dashboard tab for more information.
Testing | SIT Functional Test Approach & Plan (Assurance) | v0.3 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-07-28 | n/a | 2023-08-04 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG on 13-Sep-23. Please view the Master Change Request dashboard tab for more information.
Testing | SIT Functional Test Data Approach & Plan (Assurance) | v0.3 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-07-28 | n/a | 2023-08-04 | Closed | n/a | n/a
Design | Interim Release 3 Release | IR3 | All PPs | n/a | n/a | n/a | n/a | 2023-08-02 | Closed | Testing --> SIT | Testing --> SIT
Testing | SIT Component Integration Testing (CIT) Test Scenarios (Assurance) | v5.2 | All PPs, particularly SIT PPs | n/a | n/a | 2023-07-21 | n/a | 2023-07-28 | Closed | Testing --> SIT | Testing --> SIT
Governance - Change Request | CR027: DUoS E-Billing DIP message for MHHS issued for Impact Assessment | n/a | All PPs | n/a | DAG | 2023-07-13 | n/a | 2023-07-27 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 3 (Red-lined versions). Design --> Baselined Design Artefacts (Clean versions) | Design --> Red-lined Design Artefacts --> Interim Release 3 (Red-lined versions). Design --> Baselined Design Artefacts (Clean versions)
Governance - Change Request | CR023: Standardisation of Interfaces within the Smart and Advanced Data Services Roles issued for Impact Assessment | n/a | All PPs | n/a | DAG | 2023-07-06 | n/a | 2023-07-21 | Closed | Testing --> SIT | Testing --> SIT
Testing | SIT Functional Test Approach & Plan | v0.2 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-07-07 | n/a | 2023-07-21 | closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents
Testing | SIT Functional Test Data Approach & Plan | v0.2 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-07-07 | n/a | 2023-07-21 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents
Governance - Change Request | CR024: Data Item Names and Descriptions - Re-Issued for IA | n/a | All PPs | n/a | DAG | 2023-07-13 | n/a | 2023-07-20 | Closed | Testing --> SIT | Testing --> SIT
Testing | Environment Approach and Plan - CIT environments | v2.4 | All PPs, particularly SIT PPs | EWG | TMAG | 2023-07-07 | n/a | 2023-07-13 | Closed | Testing --> SIT | Testing --> SIT
Design | Interim Release 3 Objection Cut-off | IR3 | All PPs | n/a | n/a | n/a | n/a | 2023-07-12 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents
Code | Balancing and Settlement Code (BSC) Central Services Consultation | n/a | All PPs | CDWG | CCAG | 2023-06-21 | n/a | 2023-07-12 | Closed | Testing Overview --> Environment Approach & Plan | Testing Overview --> Environment Approach & Plan
Testing | SIT Component Integration Testing (CIT) Test Approach & Plan (Assurance) | v0.5 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-06-30 | n/a | 2023-07-06 | Closed | n/a | n/a
Testing | SIT Component Integration Testing (CIT) Test Data Approach & Plan (Assurance) | v0.5 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-06-30 | n/a | 2023-07-06 | Closed | Code --> Code Artefacts --> Tranche 2 | Code --> Code Artefacts --> Tranche 2
Design | Interim Release 2 Release | IR2 | All PPs | n/a | n/a | n/a | n/a | 2023-07-05 | Closed | Testing --> SIT | Testing --> SIT
FTIG | Delivery Assurance Cohort Two Questionnaire Issued | n/a | All SIT volunteers with an MHHS role under the TOM who were not part of Cohort 1 | FTIG | N/A | 2023-06-16 | n/a | 2023-06-30 | Closed | Testing --> SIT | Testing --> SIT
DIP | Interface Code of Connection & PKI Policy (Assurance) | v0.7 | All PPs | SDWG | DAG | 2023-06-22 | n/a | 2023-06-28 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 2 (Red-lined versions) OR Design --> Baselined Design Artefacts (Clean versions) | Design --> Red-lined Design Artefacts --> Interim Release 2 (Red-lined versions) OR Design --> Baselined Design Artefacts (Clean versions)
Migration | Data Cleanse Plan (Review 2) | v0.1 | All PPs | MWG | TMAG | 2023-06-09 | n/a | 2023-06-23 | Closed | Shared via email. Questions can be found Programme Information --> Delivery Assurance | Shared via email. Questions can be found Programme Information --> Delivery Assurance
Testing | Overarching Test Data Approach & Plan | v0.6 | All PPs | DWG | TMAG | 2023-06-19 | n/a | 2023-06-23 | Closed | Programme Information --> Data Integration Platform (DIP) | Programme Information --> Data Integration Platform (DIP)
Design | Interim Release 2 Objection Cut-off | IR2 | All PPs | n/a | n/a | n/a | n/a | 2023-06-23 | Closed | Migration --> Data Cleanse Plan | Migration --> Data Cleanse Plan
Testing | SIT Component Integration Testing (CIT) Test Approach & Plan | v0.4 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-06-09 | n/a | 2023-06-22 | Closed | Testing --> Data | Testing --> Data
Testing | SIT Component Integration Testing (CIT) Test Data Approach & Plan | v0.4 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-06-09 | n/a | 2023-06-22 | Closed | n/a | n/a
Code | Registration (REC & BSC) | n/a | All PPs | CDWG | CCAG | 2023-05-31 | n/a | 2023-06-21 | Closed | Testing --> SIT | Testing --> SIT
FTIG | Delivery Assurance Cohort One Questionnaire Issued | n/a | Central Parties and Core Capability Providers, and SIT volunteers who are not dependent on the Placing Reliance Policy | FTIG | N/A | 2023-05-31 | n/a | 2023-06-16 | Closed | Testing --> SIT | Testing --> SIT
Testing | SIT Functional Test Scenarios | v0.3 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-05-15 | n/a | 2023-05-30 | Closed | Code --> Code Artefacts --> Tranche 2 | Code --> Code Artefacts --> Tranche 2
DIP | Code of Connection & PKI Policy Formal Review | v0.6 | All PPs | n/a | DAG | 2023-05-12 | n/a | 2023-05-25 | Closed | Shared via email. Questions can be found: Programme Information --> Delivery Assurance | Shared via email. Questions can be found: Programme Information --> Delivery Assurance
Testing | Overarching Test Data Approach & Plan | v0.5 | All PPs | DWG | TMAG | 2023-05-05 | n/a | 2023-05-22 | Closed | Testing --> SIT | Testing --> SIT
Migration | Data Cleanse Plan (Review 1) | n/a | All PPs | MWG | TMAG | 2023-05-04 | n/a | 2023-05-19 | Closed | Programme Information --> Data Integration Platform (DIP) | Programme Information --> Data Integration Platform (DIP)
Migration | Migration, Data Strategy and Cutover | v0.2 | All PPs | MWG | TMAG | 2023-05-04 | n/a | 2023-05-19 | Closed | Testing --> Data | Testing --> Data
DIP | Interface Code of Connection Informal Review | n/a | All PPs | n/a | DAG | 2023-05-03 | n/a | 2023-05-11 | Closed | Migration --> Data Cleanse Plan | Migration --> Data Cleanse Plan
DIP | PKI Policy | n/a | All PPs | n/a | DAG | 2023-05-05 | n/a | 2023-05-11 | Closed | Migration --> Migration, Data Strategy and Cutover | Migration --> Migration, Data Strategy and Cutover
Design | Amended Design Documents | n/a | All PPs | n/a | DAG | 2023-04-14 | n/a | 2023-05-09 | Closed | Programme Information --> Data Integration Platform (DIP) | Programme Information --> Data Integration Platform (DIP)
Testing | SIT Component Integration Testing (CIT) Test Scenarios | v0.3 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-04-17 | n/a | 2023-05-02 | Closed | Programme Information --> Data Integration Platform (DIP) | Programme Information --> Data Integration Platform (DIP)
Design | Transition Design | Multiple | All PPs | MTDSG | DAG | 2023-04-14 | n/a | 2023-04-28 | Closed | n/a | n/a
Planning | CR022 Impact Assessment | n/a | All PPs | n/a | Change Board | 2023-04-06 | n/a | 2023-04-26 | Closed | Testing --> SIT | Testing --> SIT
Testing | Qualification Approach & Plan | v0.1 | All PPs | QWG | TMAG | 2023-03-28 | n/a | 2023-04-11 | Closed | Design --> Transition Design | Design --> Transition Design
Testing | Placing Reliance Policy Part 2 | v0.5 | All PPs | SITWG | TMAG | 2023-03-31 | n/a | 2023-04-11 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents
Testing | Placing Reliance Policy Part 1 | v0.4 | All PPs | SITWG | TMAG | 2023-03-09 | n/a | 2023-03-14 | Closed | Testing --> Qualification | Testing --> Qualification
Code | Data Services (BSC) and Metering Services (REC) | n/a | All PPs | CDWG | CCAG | 2023-02-14 | n/a | 2023-03-13 | Closed | Testing --> Testing Overview | Testing landing page
Design | Migration Design | Multiple | All PPs | MTDSG | DAG | 2023-02-14 | n/a | 2023-02-24 | Closed | Testing --> Testing Overview | Testing landing page
Qualification | Placing Reliance Form Submission | n/a | Non-SIT LDSOs | QWG | TMAG | n/a | n/a | 2023-01-05 | Closed | Code --> Code Artefacts --> Tranche 1 | Code --> Code Artefacts --> Tranche 1
Design | MHHS Impacts to Data Transfer Network (DTN) flows Consultation | Multiple | All PPs | n/a | DAG | 2023-12-13 | n/a | 2023-01-05 | Closed | Design --> Migration Design | Design --> Migration Design

## Qualification Deliverables
Workstream | Document / Artefacts | Target Audience | Baseline Due Date | Status
Non-SIT Suppliers & Agents | Smart Market Segment (SMS) Exemption | Non-SIT Suppliers & Agents | 2025-04-02 | Closed
Non-SIT LDSO QT | MHHSP LDSO QT Team Review of PIT submission complete (Functional and Migration) | Non-SIT LDSOs | 2025-01-30 | Closed
Non-SIT LDSO QT | Submission of MHHS-DEL1052 PIT Test Completion Report, supporting test evidence and MHHS-DEL1050 PIT Requirements to Test Traceability Matrix (Non-Functional, Operational and Functional PIT of MPRS) | Non-SIT LDSOs | 2025-01-30 | Closed
SIT Qualification | Initial QAD Submission Window | SIT participants | 06-Jan-25 to 14-Feb-25 | Closed
Non-SIT LDSO QT | Initial QAD Submission Window | Non-SIT LDSOs | 06-Jan-25 to 14-Feb-25 | Closed
Non-SIT LDSO QT | Final PIT Test Readiness Report and Evidence Submission | Non-SIT LDSOs | 2024-11-29 | Closed
Non-SIT LDSO QT | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Readiness Confirmed (Final Test Readiness Review for LDSOs) | Non-SIT LDSOs | 2024-12-20 | Closed
Non-SIT LDSO QT | Submission draft QT Test Completion Report | Non-SIT LDSOs | 2025-04-14 | Closed
Non-SIT LDSO QT | Submission of final QT Test Completion Report | Non-SIT LDSOs | 2025-05-15 | Closed
Wave 1 Qualification | Initial QAD Submission Window | Non-SIT Suppliers and Agents | 05-May-25 to 14-July-25 | Closed
Wave 1 Qualification | Final PIT Approach and Plan covering Functional, Migration, Non-Functional and Operational | Non-SIT Suppliers & Agents | 2024-10-25 | Closed
Wave 1 Qualification | PIT RTTM (Including list of PIT Test Scenarios) | Non-SIT Suppliers & Agents | 2025-04-14 | Closed
Wave 2 Qualification | Initial QAD Submission Window | Non-SIT Suppliers and Agents | 09-June-25 to 12-Sep-25 | Closed
Wave 1 Qualification | QT Test Plan | Non-SIT Suppliers & Agents | 2025-06-13 | Closed
Wave 1 Qualification | QT Test Catalogue | Non-SIT Suppliers & Agents | 2025-06-16 | Closed
Wave 1 Qualification | QT RTTM | Non-SIT Suppliers & Agents | 2025-06-16 | Closed
Wave 1 Qualification | QT Interim Readiness Report (incl. PIT Progress) | Non-SIT Suppliers & Agents | 2025-06-16 | Closed
Wave 1 Qualification | PIT Completion Report (Incl. Final PIT RTTM and all PIT evidence uploaded) | Non-SIT Suppliers & Agents | 2025-07-14 | Closed
Wave 1 Qualification | QT Final Readiness Report | Non-SIT Suppliers & Agents | 2025-07-14 | Closed
Wave 1 Qualification | QT Completion Report (including QT RTTM) | Non-SIT Suppliers & Agents | At test exit | Closed
Wave 2 Qualification | Final PIT Approach and Plan covering Functional, Migration, Non-Functional and Operational | Non-SIT Suppliers & Agents | 2024-11-29 | Closed
Wave 2 Qualification | PIT RTTM (Including list of PIT Test Scenarios) | Non-SIT Suppliers & Agents | 2025-06-16 | Closed
Wave 3 Qualification | Initial QAD Submission Window | Non-SIT Suppliers and Agents | 11-Aug-25 to 7-Nov-25 | Closed
Wave 2 Qualification | QT Test Plan | Non-SIT Suppliers & Agents | 2025-08-18 | Closed
Wave 2 Qualification | QT Test Catalogue | Non-SIT Suppliers & Agents | 2025-08-18 | Closed
Wave 2 Qualification | QT RTTM | Non-SIT Suppliers & Agents | 2025-08-18 | Closed
Wave 2 Qualification | QT Interim Readiness Report (incl. PIT Progress) | Non-SIT Suppliers & Agents | 2025-08-18 | Closed
Wave 1 Qualification | Final QAD Submission Window | Non-SIT Suppliers and Agents | 25-Aug-25 to 16-Jan-26 | Open
Wave 2 Qualification | PIT Completion Report (Incl. Final PIT RTTM and all PIT evidence uploaded) | Non-SIT Suppliers & Agents | 2025-09-08 | Closed
Wave 2 Qualification | QT Final Readiness Report | Non-SIT Suppliers & Agents | 2025-09-08 | Closed
Wave 2 Qualification | QT Completion Report (including QT RTTM) | Non-SIT Suppliers & Agents | At test exit | Closed
Wave 3 Qualification | Final PIT Approach and Plan covering Functional, Migration, Non-Functional and Operational | Non-SIT Suppliers & Agents | 2025-01-31 | Closed
Wave 3 Qualification | PIT RTTM (Including list of PIT Test Scenarios) | Non-SIT Suppliers & Agents | 2025-08-11 | Closed
Wave 4 Qualification | Initial QAD Submission Window | Non-SIT Suppliers and Agents | 20-Oct-25 to 16-Jan-26 | Closed
Wave 3 Qualification |  | Non-SIT Suppliers & Agents | 2025-10-20 | Closed
Wave 3 Qualification | QT Test Plan | Non-SIT Suppliers & Agents | 2025-10-20 | Closed
Wave 3 Qualification | QT RTTM | Non-SIT Suppliers & Agents | 2025-10-20 | Closed
Wave 3 Qualification | QT Interim Readiness Report (incl. PIT Progress) | Non-SIT Suppliers & Agents | 2025-10-20 | Closed
Wave 2 Qualification | Final QAD Submission Window | Non-SIT Suppliers and Agents | 20-Oct-25 to 6-Mar-26 | Open
Wave 3 Qualification | PIT Completion Report (Incl. Final PIT RTTM and all PIT evidence uploaded) | Non-SIT Suppliers & Agents | 2025-11-10 | Closed
Wave 3 Qualification | QT Final Readiness Report | Non-SIT Suppliers & Agents | 2025-11-10 | Closed
Wave 3 Qualification | QT Completion Report (including QT RTTM) | Non-SIT Suppliers & Agents | At test exit | Closed
Wave 4 Qualification | Final PIT Approach and Plan covering Functional, Migration, Non-Functional and Operational | Non-SIT Suppliers & Agents | 2025-03-28 | Closed
Wave 4 Qualification | PIT RTTM (Including list of PIT Test Scenarios) | Non-SIT Suppliers & Agents | 2025-10-06 | Closed
Wave 4 Qualification | QT Test Plan | Non-SIT Suppliers & Agents | 2026-12-08 | Closed
Wave 4 Qualification | QT Test Catalogue | Non-SIT Suppliers & Agents | 2025-12-08 | Closed
Wave 4 Qualification | QT RTTM | Non-SIT Suppliers & Agents | 2025-12-08 | Closed
Wave 4 Qualification | QT Interim Readiness Report (incl. PIT Progress) | Non-SIT Suppliers & Agents | 2025-12-08 | Closed
Wave 3 Qualification | Final QAD Submission Window | Non-SIT Suppliers and Agents | 12-Jan-26 to 22-May-26 | Upcoming
Wave 4 Qualification | PIT Completion Report (Incl. Final PIT RTTM and all PIT evidence uploaded) | Non-SIT Suppliers & Agents | 2026-01-09 | Upcoming
Wave 4 Qualification | QT Final Readiness Report | Non-SIT Suppliers & Agents | 2025-12-26 | Upcoming
Wave 4 Qualification | Final QAD Submission Window | Non-SIT Suppliers and Agents | 09-Mar-26 to 24-July-26 | Upcoming
Wave 4 Qualification | QT Completion Report (including QT RTTM) | Non-SIT Suppliers & Agents | At test exit | Upcoming

## SIT Deliverables
Workstream | Document / Artefacts | Target Audience | Due Date | Status | Note
Testing | PIT Test Readiness Report | PIT for SIT Non-Functional Testing | 2024-05-24 | Closed | To be submitted every two weeks on a Friday after issuing PIT Approach and Plan, until the start of PIT test execution.
Testing | PIT Test Execution Progress Report | PIT for SIT Non-Functional Testing | 2024-06-21 | Closed | To be submitted every month start of PIT test execution and on a weekly basis in the last 4 weeks before completion of testing.
Testing | PIT Test Readiness Report | PIT for SIT Operational Testing | 2024-06-28 | Closed | To be submitted every two weeks on a Friday after issuing PIT Approach and Plan, until the start of PIT test execution.
Testing | SIT Regression Testing Test Approach & Plan | SIT PPs | 2025-02-07 | Closed | SIT Operational --> SIT Regression Testing Approach and Plan
Testing | Final PIT Completion Report | PIT for SIT Operational Testing | 2024-09-06 | Closed
Testing | PIT Test Execution Progress Report | PIT for SIT Operational Testing | 2024-08-30 | Closed | To be submitted every month start of PIT test execution and on a weekly basis in the last 4 weeks before completion of testing.
Testing | Placing Reliance Arrangements for SIT Operational | SIT Operational Testing | 2024-08-19 | Closed | To complete Forms to inform any changes to placing reliance arrangements for SIT Operational Testing, which is due to commence in October. Here is a link to the Forms: https://forms.office.com/Pages/ResponsePage.aspx?id=iy6OqhkmDk2tWIr96QqlSu0GgdNiGapNtWTKZ4Yv3tZUMkYxT1NNUjAxTTlZWTJJM0QwSlBQRE41TC4u
Testing | Draft PIT Completion Report | PIT for SIT Operational Testing | 2024-08-16 | Closed
Testing | SIT Non-Functional Participant Readiness Report Template | SIT Non-Functional Testing | 2024-08-09 | Closed | To access this on the Collaboration Base and Website please go to: Testing --> SIT Non-Functional --> SIT Non-Functional Participant Readiness Reporting
Testing | Final PIT Completion Report | PIT for SIT Non-Functional Testing | 2024-08-02 | Closed
Testing | Draft PIT Completion Report | PIT for SIT Non-Functional Testing | 2024-07-12 | Closed
Testing | PIT RTTM | PIT for SIT Non-Functional Testing | 2024-05-30 | Closed | **If you have not yet submitted this deliverable to the Programme, it is overdue - please complete this as a priority.**
Testing | PIT Test Scenarios | PIT for SIT Non-Functional Testing | 2024-05-30 | Closed | **If you have not yet submitted this deliverable to the Programme, it is overdue - please complete this as a priority.**
Testing | PIT Test Approach and Plan | PIT for SIT Non-Functional Testing | 2024-05-10 | Closed | **If you have not yet submitted this deliverable to the Programme, it is overdue - please complete this as a priority.**
Testing | PIT RTTM | PIT for SIT Operational Testing | 2024-07-04 | Closed
Testing | PIT Test Approach and Plan | PIT for SIT Operational Testing | 2024-06-14 | Closed | **If you have not yet submitted this deliverable to the Programme, it is overdue - please complete this as a priority.**
Testing | PIT Test Scenarios | PIT for SIT Operational Testing | 2024-07-04 | Closed | **If you have not yet submitted this deliverable to the Programme, it is overdue - please complete this as a priority.**
For further information, Programme Participants are encouraged to refer to the latest version of the MHHS-DEL852 Pre-Integration Testing Guidance.

## IPA Activities
For further information, please see Slide 24 of the 6 November 2024 Programme Steering Group Meeting

## Master Change Request Dashboard
Date Raised | Change Request | CR Name | Advisory Group | Status | IA Issue Date | IA Deadline Date | Advisory Group Approval Decision | Target Implementation Date | Open/Closed | Comments
2025-08-01 | CR064 | Updating the MHHS Programme Governance Framework for post-M10 | PSG | Approved | N/A - Housekeeping | N/A - Housekeeping |  |  | Closed | Housekeeping Change recommended for approval at PSG
2025-07-01 | CR063 | Extend the provision of the SIT A environment for Production, covering the ELS phase of the MHHS Programme. | PSG | Rejected | 2025-07-09 | 2025-07-24 | Rejected at PSG 06/08 |  | Closed | Rejected at PSG as out of Programme Scope, CR raiser now going through DIP BaU process
2025-06-01 | CR062 | Issue Resolution Group (IRG) – MHHS Programme Governance Framework Update | PSG | Approved | 2025-06-12 | 2025-06-26 | Approved at PSG on 02-Jul-25 |  | Closed
2025-05-01 | CR061 | Alignment of M10 (go live) delivery date to 22.09.25 for clarification | PSG | Approved | 2025-05-08 | 2025-05-22 | Approved at PSG on 04-Jun-25 | Jun-25 PSG | Closed | Approved at PSG, implemented into Programme Plan
2025-03-01 | CR060 | Amendment of M8 (Code Changes Delivered) delivery date to 22.09.25 | N/A - Housekeeping | Approved | N/A - Housekeeping | N/A - Housekeeping | N/A |  | Closed | Approved at CCAG 26/3 and implemented into Programme Plan.
2024-10-24 | CR059 | ELEX-REP-020 implementation | PSG | Approved | 2024-10-30 | 2024-11-13 | Approved by PSG on 04-Dec-24 |  | Closed | ELEX-REP-020 included in IR8.7, published 22/01
2024-10-24 | CR058 | Adding the DIP Manager as an Industry Representative to Advisory Groups | PSG | Approved | 2024-10-30 | 2024-11-13 | Approved by PSG on 04-Dec-25 |  | Closed
2024-09-05 | CR057 | Remove requirement to respond to DIP with a JSON body for synchronous requests where all validation is asynchronous (Level 4) | PSG | Rejected | N/A | N/A | Rejected by PSG on 06-Nov-24 |  | Closed | Rejection due to not meeting Change Freeze criteria
2024-09-05 | CR056 | Batching of ERDS to CSS Agent Appointment Files | PSG | Approved | 2024-09-26 | 2024-10-10 | Approved by PSG on 18-Oct-24 |  | Closed | Changes implemented 20/01
2024-09-05 | CR055 | Amendments to M10 and corresponding milestones | PSG | Approved | 2024-09-20 | 2024-10-04 | Approved for Ofgem recommendation by PSG on 18-Oct-24 |  | Closed | Approved by Ofgem on 29/11, plan re-baselined
2024-07-01 | CR054 | Change to Non-Functional Requirements for LDSOs | PSG | Approved | 2024-08-08 | 2024-08-22 | Approved by PSG on 04-Sep-24 | IR8.3 (Sep-24). | Closed | Design updates published in IR8.3
2024-06-01 | CR053 | ISD Publication Frequency Change | PSG | Approved | 2024-07-12 | 2024-07-26 | Approved by PSG on 07-Aug-24 | M6 (Aug-24). | Closed
2024-06-01 | CR052 | Amending the 'M7 SCR powers enabled' Milestone | PSG | Approved | 2024-07-11 | 2024-07-25 | Approved by PSG on 07-Aug-24 | Aug-24. | Closed
2024-06-01 | CR051 | Deferral of MHHSP-037 | PSG | Approved | 2024-06-27 | 2024-07-11 | Approved by PSG on 07-Aug-24 | M6 (Aug-24). | Closed
2024-04-01 | CR050 | Amendments to the MHHS Change Control Approach and Form | PSG | Approved | 2024-05-14 | 2024-05-29 | Approved by PSG on 05-Jun-24 | Jun-24. | Closed | SRO approval upheld by Ofgem at PSG.
2024-04-01 | CR049 | Swagger Open API 3.0 to 3.1 Upgrade | PSG | Retracted | N/A | N/A |  |  | Closed | Change request retracted by the Change Raiser.
2024-03-01 | CR048 | Amending Qualification Milestones for Non-SIT Supplier and Agent QT | PSG | Approved | 2024-04-02 | 2024-04-16 | Approved by PSG on 01-May-24 | May-24. | Closed
2024-03-01 | CR047 | Amending Qualification Milestones for non-SIT LDSO QT | PSG | Approved | 2024-04-02 | 2024-04-16 | Approved by PSG on 01-May-24 | May-24. | Closed
2024-03-01 | CR046 | Enabling Metering Point Energy Flow to be changed more than once | DAG | Approved | 2024-03-14 | 2024-03-28 | Approved by DAG on 10-Apr-24 | IR8.1 (Jun-24). | Closed
2024-03-01 | CR045 | Supply Start Date (SSD) Correction Tool | DAG | Rejected | 2024-03-14 | 2024-03-28 | Rejected by PSG on 03-Jul-24 |  | Closed | Programme to hand over solution to Code Bodies for post-M10 implementation.
2024-03-01 | CR044 | Implementation of 'Data Refresh' Message IF-051 | DAG | Rejected | 2024-03-14 | 2024-03-28 | Rejected by PSG on 05-Jun-24 |  | Closed | Programme to hand over solution to Code Bodies for post-M10 implementation.
2024-02-01 | CR043 | Supplier Registration of ABMU and MPAN Mapping | DAG | Approved | 2024-02-15 | 2024-02-29 | Approved by DAG on 13-Mar-24 | IR8 (Apr-24). | Closed
2024-01-01 | CR042 | Amending the ‘M16 Methodology Approved’ Milestone | PSG | Approved | N/A | N/A | Approved by PSG on 07-Feb-24 | Feb-24. | Closed | Approved without IA due to low impact T2 milestone.
2024-01-01 | CR041 | Change the format of Market Participant Code from Char(1) to Char(2) | DAG | Rejected | 2024-01-10 | 2024-01-24 | Rejected by DAG on 14-Feb-24 |  | Closed | Rejected on the grounds that it does not meet the requirements of the Change Freeze.
2024-01-01 | CR040 | Change to NFR E2E1009 for DNO and iDNO roles | DAG | Approved | 2024-01-10 | 2024-01-24 | Approved by DAG on 14-Feb-24 | IR8 (Apr-24). | Closed
2024-01-01 | CR039 | Registration Service IF-40 Change | DAG | Approved | 2024-01-17 | 2024-01-31 | Approved by DAG on 14-Feb-24 | IR8 (Apr-24). | Closed
2023-12-01 | CR038 | Amendments to the MHHS Change Board Terms of Reference | N/A - Housekeeping | Approved | N/A | N/A | N/A | Dec-23. | Closed
2023-12-01 | CR037 | Migration Message Processing Choreography Update | TMAG | Approved | 2023-12-20 | 2024-01-11 | Approved by TMAG on 17-Jan-24 | IR8 (Apr-24). | Closed
2023-11-01 | CR036 | Use of Clock Midnight for Appointments and Reads | DAG | Approved | 2023-11-24 | 2023-12-01 | Approved by DAG on 13-Dec-23 | IR7 (Jan-24). | Closed | Decision appeal received from LSC.
2023-11-01 | CR035 | Programme proposal to restructure TMAG in the MHHS Governance Framework and other housekeeping updates | PSG | Approved | 2023-11-14 | 2023-11-28 | Approved by PSG on 06-Dec-23 | Jan-24. | Closed
2023-10-01 | CR034 | Delay to Elexon Level 4 validation response - NFR (1009) | DAG | Approved | 2023-11-09 | 2023-11-23 | Approved by DAG on 13-Dec-23 | IR7 (Jan-24). | Closed
2023-10-01 | CR033 | Remove ELEX REP-005 and include LLF details as part of ISD catalogues | N/A | Issued to DIN log |  |  |  |  | Closed
2023-09-01 | CR032 | Change to interface MHHS-IF-165 P0210 TUoS reporting | DAG | Approved | 2023-11-28 | 2023-12-05 | Approved by DAG on 13-Dec-23 | IR7 (Jan-24). | Closed
2023-08-01 | CR031 | Amending Transition Design Milestone Description and Delivery Date | DAG | Approved | N/A | N/A | Approved by DAG on 13-Sep-23 |  | Closed | Approved without IA due to low impact T2 milestone.
2023-08-01 | CR030 | Introduction of Compressed Payloads into DIP Messages | DAG | Approved | 2023-08-11 | 2023-08-25 | Approved by DAG on 13-Sep-23 | IR5 (Oct-23). | Closed
2023-08-01 | CR029 | DIP LDSO Interface Processing | DAG | Approved | 2023-08-10 | 2023-08-24 | Approved by DAG on 13-Sep-23 | IR5 (Oct-23). | Closed
2023-08-01 | CR028 | EES and SDEP Requirements | DAG | Approved | 2023-08-10 | 2023-08-24 | Approved by DAG on 13-Sep-23 | IR5 (Oct-23). | Closed
2023-07-01 | CR027 | DUoS E-Billing DIP message for MHHS | DAG | Approved | 2023-07-13 | 2023-07-27 | Approved by DAG on 13-Sep-23 | IR5 (Oct-23). | Closed
2023-06-01 | CR026 | Enhancements to the Change Control Approach | N/A - Housekeeping | Approved | N/A | N/A | N/A |  | Closed
2023-06-01 | CR025 | DIP Interface Name Changes | DAG | Approved | 2023-06-14 | 2023-06-28 | Approved by DAG on 12-Jul-23 | Postponed until post-M10. | Closed
2023-06-01 | CR024 | Data Item Names and Descriptions | DAG | Approved | 2023-07-13 | 2023-07-20 | Approved by DAG on 09-Aug-23 | Postponed until post-M10. | Closed
2023-05-01 | CR023 | Standardisation of Interfaces within the Smart and Advanced Data Services Roles | DAG | Approved | 2023-07-06 | 2023-07-28 | Approved by DAG on 13-Sep-23 | IR7 (Jan-24). | Closed
2023-04-01 | CR022 | MHHS Programme Re-plan | PSG | Approved | 2023-04-05 | 2023-04-26 | Approved by Ofgem on 8-Jun-23 |  | Closed
2023-03-01 | CR021 | Update TMAG Terms of Reference to Reflect Option of Meeting Co-Representation | N/A - Housekeeping | Approved | N/A | N/A | Approved by Change Board on 29-Mar-23 |  | Closed
2023-03-01 | CR020 | Update Interim Plan to Reflect 1 Month Deferment to Replan Times | N/A - Housekeeping | Approved by Change Board | N/A | N/A | Approved by Change Board on 24-Apr-23 |  | Closed
2023-03-01 | CR019 | Replacement of D0242 D0315 for MHHS | DAG | Approved | 2023-03-15 | 2023-03-30 | Scheduled for Design Release 5 |  | Closed
2023-02-01 | CR018 | Registration Service Operating Hours | DAG | Approved | 2023-06-07 | 2023-06-14 | Approved by DAG Chair on 12-Jul-23 |  | Closed | Approval upheld by SRO following LSC objection.
2023-01-01 | CR017 | DSO Registration Service DIP Messages Processing Times | DAG | Rejected | 2023-03-02 | 2023-03-23 | Rejected by DAG Chair on 12-Jul-23 |  | Closed | Rejected as CR018 is mutually exclusive to CR017.
2023-01-01 | CR016 | Changes to the Change Control Approach to Incorporate Design Change Process | N/A - Housekeeping | Approved | N/A | N/A | N/A |  | Closed
2023-01-01 | CR015 | Differential Settlement for E7E10 Meters for Smart Opt-out Customers | PSG | Approved | 2023-02-02 | 2023-02-16 | Approved by PSG on 1-Mar-23 |  | Closed
2023-01-01 | CR014 | Changes to the Baselined LSS Design | N/A - Housekeeping | Retracted | N/A | N/A | N/A |  | Closed
2022-11-01 | CR013 | Examination of Settlement Impacts resulting from MHHS Programme | PSG | Approved | 2022-12-07 | 2023-01-09 | Approved by PSG on 1-Feb-23 | 2023-10-01 | Closed | Report approved at October PSG.
2022-10-01 | CR012 | Increase in Scope of CCAG ToR and Code Drafting Activities to Include Consequential Change | PSG | Approved | 2022-11-02 | 2022-11-16 | Approved by PGS on 7-Dec-22 |  | Closed
2022-09-01 | CR011 | Update to the Programme Interim Poap to Reflect Decisions made at September 2022 PSG | N/A - Housekeeping | Approved | N/A | N/A | N/A |  | Closed
2022-07-01 | CR010 | Proposal to Include the Full Plan Review 'PM2' Activity within Programme Governance | PSG | Approved | N/A | N/A | N/A |  | Closed
2022-07-01 | CR009 | M5 and M3 Milestone Date Changes | PSG | Approved | 2022-07-15 | 2022-07-29 | Approved by Ofgem on 1-Sep-22 |  | Closed
2022-05-01 | CR008 | Inclusion of RECCo Membership of Level 2 and 3 Governance Groups | PSG | Approved | 2022-05-11 | 2022-05-25 | Approved by PSG on 8-Jun-22 |  | Closed
2022-05-01 | CR007 | Proposal to Change M3 | PSG | Retracted | N/A | N/A | N/A |  | Closed
2022-04-01 | CR006 | Programme Proposal to Update DAG ToR | N/A - Housekeeping | Approved | N/A | N/A | N/A |  | Closed
2022-03-01 | CR005 | Adding Cooperation to Governance Framework | PSG | Approved | 2022-03-29 | 2022-04-12 | Approved by CCAG on 4-May-22 |  | Closed
2022-03-01 | CR004 | Programme Proposal to Change TMAG ToR | N/A - Housekeeping | Approved | N/A | N/A | N/A |  | Closed
2022-03-01 | CR003 | CCAG Proposals for M6 and M7 | CCAG | Approved | 2022-03-29 | 2022-04-12 | Approved by Ofgem on 21-Apr-22 |  | Closed
2022-03-01 | CR002 | Supplier Proposal to Delay M5 by 7+ Months | PSG & DAG | Rejected | 2022-03-11 | 2022-03-25 | Rejected by Ofgem on 21-Apr-22 |  | Closed
2022-03-01 | CR001 | Extend the Delivery of Design from the Current 30th April 2022 Baseline to 29th July 2022 | DAG | Approved | 2022-03-11 | 2022-03-25 | Approved by Ofgem on 21-Apr-22 |  | Closed

## On Hold Change Requests
Date Raised | Change Request | CR Name | Raised by | Been through MHHS Change Process | MHHS CR No. | Target Implementation Date | Reason for postponement | Status
2024-11-24 | OHCR007 | Remove requirement to respond to DIP with a JSON body for synchronous requests where all validation is asynchronous (Level 4) | Helix | No - did not meet Change Freeze criteria | CR057 | Post M10, date TBC | Rejected by PSG due to not meeting the pre-M10 Change Freeze criteria, with the alternative solution currently undergoing implementation. | Change Board decision to close of On-Hold Change request. Alternate solution for CR057 undergoing testing. Recommendation for change raiser to go through BAU process if the proposed solution from OHCR007 is required post-M10.
2024-07-01 | OHCR006 | Advanced Register Read and Meter Configuration Inclusion | LSC | No - did not meet Change Freeze criteria | N/A | Post M10, date TBC | CR not eligible for pre-M10 Change Control process as implementation not required until after M10, as stated by Change Raiser. | Change Board decision to close of On-Hold Change request. Recommendation for change raiser to go through BAU process.
2024-07-01 | OHCR005 | Validation of Service Provider CoS Appointments | British Gas | No - did not meet Change Freeze criteria | N/A | Post M10, date TBC | CR raised to Programme in July 2024. PPIR issued to all Participants, responses confirmed pre-M10 implementation is not feasible. CR not eligible for pre-M10 Change Control process as post-M10 implementation does not meet the Change Freeze criteria. | Change Board decision to close of On-Hold Change request. Recommendation for change raiser to go through BAU process.
2024-02-01 | OHCR004 | Supply Start Date (SSD) Correction Tool | MHHSP & SCS | Yes - rejected | CR045 | Post M10, date TBC | PPIR issued to gather views on whether solution is implementable pre-M10. Rejected at PSG on 03-Jul-24 based on PPIR responses. Recommended for post-M10 implementation. | Change Board decision to close of On-Hold Change request. Going through BAU process as R0201, IA response submitted by Programme. Implementation target date of February 2026 (or after Early Life Support).
2024-02-01 | OHCR003 | Implementation of 'Data Refresh' Message IF-051 | MHHSP | Yes - rejected | CR044 | Post M10, date TBC | PPIR issued to gather views on whether solution is implementable pre-M10. Rejected at PSG on 05-Jun-24 based on PPIR responses. Recommended for post-M10 implementation. | Change Board decision to close of On-Hold Change request. Recommendation for change raiser to go through BAU process, with Programme support to facilitate.
2023-06-01 | OHCR002 | DIP Interface Name Changes | RECCo | Yes - partially approved | CR025 | Post M10, date TBC | Raised to Programme in June 2023 and issued to Impact Assessment. Deferred to a post-M10 implementation at DAG 13-Mar-24. Please note that RECCo has implemented these changes into the M6 Code baseline. | Change Board decision to close of On-Hold Change request. Recommendation for DIP Change request to be raised, with Programme support to facilitate.
2023-06-01 | OHCR001 | Data Item Names and Descriptions | RECCo | Yes - partially approved | CR024 | Post M10, date TBC | Raised to Programme in June 2023 and issued to Impact Assessment. Deferred to a post-M10 implementation at DAG 13-Mar-24. Please note that RECCo has implemented these changes into the M6 Code baseline. | Change Board decision to close of On-Hold Change request. Recommendation for DIP Change request to be raised, with Programme support to facilitate.

## Sheet1 (hidden)
List
Live
Closed
Upcoming