## QA&P Comments
MHHS-DEL3317 - QA&P, Annex 1 and Annex 2 Consultation Consolidated Comments Log
Please use this tab to populate comments relating to the QA&P
*Organisation: | Consolidated feedback log |  |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency: | N/A
*Date: | 14/01/2025
Comment ID | Organisation | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | Decision | Theme | Action | Code Bodies Response
20_12_01_01 | Utilita Energy | Qualification A&P - Section 9.1.3 | Are the POAPs for SIT (on page 30) out of date? It appears these do not align with the re-baselined dates from CR055 | Update POAP | Incorrect POAP contained within the document | Acknowledge | CR055 Date updates | N/A | Thanks for reviewing, however it looks like the POAP does align with CR055 dates which can be found in the document linked.
20_12_02_01 | Npower Business Solutions | 5.3 Other Qualification Documentation | The link provided at the bottom of page 13 does not link to an existing page (Page not found error): Programme Participants should also keep up to date on other useful documents cited on the Qualification page of the MHHS Collaboration Base. | Link to be corrected | Participants may not be accessing the latest documents | Action | Housekeeping | Update Document | Thanks for reviewing, the link has been updated in the newest version.
20_12_02_02 | Npower Business Solutions | 5.4.2 QAD | The QAD will now also be approved by the DIP manager. Will there be enough resouce available across all parties to review and respond to the agreed timelines? | n/a | Delay in participants receiving responses | Acknowledge | DIP Manager | Response | Thanks for reviewing, the DIP Manager role is not an individual role and within the team we will be reviewing the response rate for documentation and this is not seen as a risk to Qualification timelines.
20_12_02_03 | Npower Business Solutions | 5.4.2 QAD | QAD version 1.1 is mentioned in this section. Latest version is QAD v3.3 (currently out for consultaion) so will need to be amended in line with approvals | Amend version number | Participants may not be accessing the latest documents | Action | Housekeeping | Update Document | Thanks for reviewing, some clarification has been added next to the mention of the final version of the QAD which includes the newest version number (v4.0).
20_12_02_04 | Npower Business Solutions | 5.4.3 QT Test Scenarios | Link missing from the following sentence | Link to be corrected | Participants may not be accessing the latest documents | Action | Housekeeping | Update Document | Thanks for reviewing, the document has been updated to include the correct information which is 'As set out in Annex 2'.
As set out in Error! Reference source not found., the first set of Test Scenarios and Test Cases delivered for QT will
cover functional requirements.
20_12_02_05 | Npower Business Solutions | 7.2 Requirements included in Scope of MHHS Qualification | Requirements now include the DIP Manager Assessment Criteria but this will not be made available until 'Early 2025'. What impact will this have on being able to submit initial versions of the QAD if this is not yet available? | Planned dates for publication and associated activites to be made available | Potential impact on initial QAD responses. Unplanned activity to review & responsd (if aplicable) | Acknowledge | DIP Manager | Response | The DIP Manager is confident the requirements are not new requirements based on agreed MHHS Design. The delay in sharing the DIP Manager Assessment Criteria was associated to providing details on measures/evidence for each criteria rather than adding new items to be assessed.
Will a consultatoin be required when this is published?
20_12_02_06 | Npower Business Solutions | Figure 11 Non-SIT Supplier, Agent and new entrant LDSO Qualification Waves POAP | Old and new versions of the PoaP in the document | Remove old versions | Reduces clarity as to the dates we are working to | Acknowledgee | Housekeeping | N/A | Thanks for reviewing, we can see in the redline version both the old and new version of the POAP have been included but this is correct in the clean version which can be found in the link attached to this cell. We will ensure that only this one is included in the newest version.
20_12_02_07 | Npower Business Solutions | General | Alignment of sub headings throughout the document needs correcting | n/a | n/a | Action | Housekeeping | Update Document | Thanks for reviewing, the subheadings are now aligned throughout the document
20_12_02_08 | Npower Business Solutions | 15 Appendix C | Eaxample - For SIT : The code bodies and DIP manager review of the initial QAD will be complete within 6 weeks of Initial QAD submission or 04/04/25 | Include an expectation of when participants should expect to see feedback, as will be a required input to the final QAD version | Participants may not be able to incorporate feedback into final submission and /or cause a delay to submission | Acknolwedge | Timelines | Response | The DIP Manager is supporting Code Bodies to complete review within 6 weeks of Initial QAD submission, with complete review being inclusive of a response of the review. For the Final QAD, the timescales are 4 weeks. We will endevour to complete the review earlier where possible.
(whichever is earlier).
What is the SLA for actually providing feedback to participants? This is particularly important for SIT as short gap between inital and final submissions
20_12_03_01 | Electricity North West | QA&P V3.1 Redlined - Page 19 Section 7 Table 2. "DIP Rules" are listed under the heading of 'Code body'. | "DIP Rules" are not a 'Code body'. | Amend the column header to "Approval Body" and amend "DIP Rules" as "DIP Manager" | Minor | Action | Housekeeping | Update Document | Thanks for reviewing, we have changed the column header to 'Relevant Code' and as a result have kept 'DIP Rules'
20_12_04_01 | National Grid Electricity Distribution | Page 5 | SIT Functional Test Data Approach & Plan no longer has a version reference | Add version reference | to not have a version may lead to confusion | Action | Housekeeping | Update Document | Thanks for reviewing, the version reference has now been included and it is v1.0
20_12_04_02 | National Grid Electricity Distribution | 9.4 DIP Onboarding | Typo - requireents | Amend to requirements | No impact | Action | Housekeeping | Update Document | Thanks for reviewing, the typo has been amended in the newest version of the document

## Annex 1 Comments
MHHS-DEL3317 - QA&P, Annex 1 and Annex 2 Consultation Comments Log
Please use this tab to populate comments relating to Annex 1
*Organisation: | Consolidated feedback log |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency: | N/A
*Date: | 14/01/2025
Comment ID | Organisation | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | Decision | Theme | Action | Code Bodies Response
A1_20_12_01_01 | SPEN | Section 9.5 | It is also expected that non-SIT LDSO participants will uplift to IR8.5 during test execution | or complete the IR8.5 regression testing in between end of qualification and before M10 | Qualification schedules may not allow time to deploy the releases from suppliers to allow testing to take place within schedules | Action | Release Management | Update document | Document has been updated. 'or complete the IR8.5 regression testing in between end of qualification testing and before M10 if agreed with Code Bodies and MHHSP' added to section 9.6.
A1_20_12_01_02 | SPEN | Section 9.6 | The approach to any further IR releases will be agreed in conjunction with Code Bodies, DIP Managers, Non-SIT LDSO participants and MHHSP. | This is an open ended comment and does not support the Non SIT LDSO's if the program release further DIP Releases we need to know the rules up front based on the timelines that we have to complete Qualification. This is an issue that should be logged, we have a dependency on our supplier in completing any impact assessment based on the DIP Releases creating code and test and then we obtain the patch to deploy this takes time which has not been built into the existing scheduled | Non SIT LDSO's don’t meet Qualification timelines based on an open ended decision that will come when the DIP releases IR's. | Action | Release Management | Update document | Document has been updated to include the following 'The approach to any further IR releases will be agreed in conjunction with Code Bodies, DIP Managers, Non-SIT LDSO participants and MHHSP. The agreed approach would depend on the criticality of the contents of the IR but it is likely to be that LDSOs would be expected to uplift between the end of Qualification Testing window M10 and complete any regression testing.
A1_20_12_01_03 | SPEN | Page 30 Footnote 9 | ‘The current requirement is that non-SIT LDSOs will complete PIT on IR8, as this is the IR the UIT environment will be aligned to when QT starts later. However, some non-SIT LDSOs have raised that this is a challenge due to the delivery timelines of service providers and have asked whether completing PIT against IR7 would be acceptable. In the above scenario, the expectation is that non-SIT LDSOs complete PIT on IR7 instead based on this being the only available release. They will then be expected to assess the changes required to meet IR8.X baseline and provide evidence that sufficient regression testing has been performed on this IR prior to the QT start date, or, with agreement, during QT execution. The approach and timescales should be documented in LDSOs’ PIT and/or QT test plan. ‘ | Is the above text now outdated? It was a long time ago that the LDSO asked to complete on IR7. Given that in the rest of the document there is clear reference to IR8.3/8.4 is this footnote required? | May cause confusion | Action | Release Management | Update document | Document has been updated and footnote removed.
20_12_02_01 | UKPN | N/A | UK Power Networks has reviewed the updates to the Qualification Approach & Plan (QA&P), Annex 1: Non-SIT LDSO MHHS Qualification Testing Approach to ensure the artefacts reflect updated delivery timelines in CR055: Amendments to M10 and Corresponding Milestones. We do not have any comments. | N/A | N/A | Acknowledge |  | No action required | Many thanks for taking the time to review the document.
A1_20_12_03_01 | ENWL | Page 13 Section 4.1 "Non-SIT LDSO QT will begin on Interim Release (IR)IR8.3" and Page 42 Section 9.6 | It has been agreed that Non-SIT LDSO QT particpants may choose to commence on IR8.4 if they are ready to do so. Confirmed in the Non-SIT LDSO Qualification Testing Sub-Group (LQTSG) 27/11 | Non-SIT LDSO QT will begin on Interim Release (IR)IR8.3 or higher | Forces LDSO to commence tetsing against an earlier version when 8.4 has already been made available to them | Action | Release Management | Update document | Section has been updated to refer that LDSO may commence on IR8.4 if they choose to do so.

## Annex 2 Comments
MHHS-DEL3317 - QA&P, Annex 1 and Annex 2 Consultation Comments Log
Please use this tab to populate comments relating to Annex 2
*Organisation: | Consolidated feedback log |  |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency: | N/A
*Date: | 14/01/2025
Comment ID | Organisation | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | Constituency | *Comment Owner | *Comment Owner to be anonymised | Decision | Theme | Action | Code Bodies Response
A2_20_12_01_01 | Npower Business Solutions | 1.3 References | Final versions of the QT RTTM template and QT Test Catalogue Template will not be available until February 2025. | The relevant dates should be added to the table to highlight final versions are not yet available | May be working to the wrong version | I&C | Sarah Lewis | No | Action | Housekeeping | Updated Document | Thanks for reviewing, we have added in that the final version will not be available until February 2025, within the additional information column.
A2_20_12_01_02 | Npower Business Solutions | Figure 1 Document Hierarchy | The diagram does not include the DIP Manager Assessment Criteria | Update the diagram | Not a complete picture of documents to be considered | I&C | Sarah Lewis | No | Action | Housekeeping | Updated Document | Thanks for reviewing, the diagram has now been updated to include the DIP Manager Assessment Criteria
A2_20_12_01_03 | Npower Business Solutions | 3.1 Document Purpose | Requirements now include the DIP Manager Assessment Criteria but this will not be made available until 'Early 2025', which is ambigous and does not allow for the planning of Qualification activities | Planned dates for publication and associated activites to be made available | Potential impact on initial QAD responses. Unplanned activity to review & responsd (if aplicable) | I&C | Sarah Lewis | No | Acknowledge | DIP Manager | Response | Thanks for reviewing, It is correct to state Early 2025 is vague. This will be within January. The DIP Manager does not consider this impacting participants planning the work needed to qualify. The delay in sharing the DIP Manager Assessment Criteria was associated to providing details on measures/evidence for each criteria rather than adding new items to be assessed.

## Control (hidden)
Constituency | Artefacts
Central Party | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments
Large Supplier | MHHS-DES242-Transitional BMU Aggreated Data
Medium Supplier | MHHS-DES241 - Transitional Scaling Weights
Small Supplier
I&C Supplier
Supplier Agent
Independent Supplier Agent
DNO
IDNO
Software Provider
Other- MHHS Participant

## Design Artefacts (hidden)
Published Documents |  | Lists
Design Artefact | Version Number | Version Number | Status
METH001 - ADV Validation and Estimation | 1 | v1.1 | Accepted
Rejected
Requires Further Clarification
Action
Submitted