# Requirements for the Transition to the new MHHS Settlement Timetable – MHHS Programme proposal

| Document owner | Document number | Version |
| --- | --- | --- |
| MHHS Programme | MHHS-DEL1557 | 1.2 |
| Status: | Date | Classification |
| Public | 25 August 2023 | Public |

| Document owner | Document number | Date |
| --- | --- | --- |

# Contents

1	Contents	1

1.1	Change Record	2

1.2	Reviewers	2

1.3	References	2

2	Executive Summary	3

3	Introduction	3

3.1	Background	3

3.2	The Settlement Timetable and the Operational Choreography	4

3.3	Key Milestones relating to the Settlement Timetable	4

3.4	Other Consideration	5

4	Proposed Approach for cut-over to New Settlement Timetable	5

4.1	Summary Diagram	5

4.2	Detailed Steps	6

5	Validating the Transition Approach against the DWG Approach	8

6	Proposal Recommendation	9

7	Appendix	10

7.1	Transition Design Plan	10

## Change Record

| Date | Author | Version | Change Detail |
| --- | --- | --- | --- |
| 10/8/2023 | Kevin Spencer | 0.1 | Initial Draft |
| 16/08/2023 | Andrew Margan | 0.2 | Initial Draft |
| 16/08/2023 | Kevin Spencer | 0.3 | Initial Draft |
| 21/08/2023 | Kevin Spencer | 0.4 | Initial Draft |
| 26/08/2023 | Kevin Spencer | 1.0 | For MTDSG |
| 13/09/2023 | Kevin Spencer | 1.1 | Following MTDSG |
| 27/09/2023 | Kevin Spencer | 1.2 | Following MTDSG |

## Reviewers

| Reviewer | Role |
| --- | --- |
| Andrew Margan | Transition Design Workstream Lead |
| Jason Brogden | LDP SME Assurance Lead |
| Chris Welby | SRO SME Assurance Lead |

## References

| Document/Link | Publisher | Published | Additional Information |
| --- | --- | --- | --- |
| Master_Settlement_Timetable_Examplev1.0 |  |  |  |
| Replacement_RF_Settlement_Timetable_RF_Illustrationv1.0 |  |  |  |
| Master_Settlement_Timetable_Example_replacementv01.0 |  |  |  |

# Executive Summary

This paper sets out the proposal to transition from the legacy 14 month Settlement Timetable to a new 4 month Settlement Timetable, known as the Settlement Timetable Transition (M16), which is the planned cutover date of 07 December 2026.  This proposal aims to enable the completion of all Settlement Runs for pre-M16 Settlement Dates by the 31 March 2027. The plan is to achieve this in two stages:

- Firstly to reduce the RF Runs for pre-M16 Settlement Days so the complete by the 31 March 2027 moving them to replace either the R3 Run or the R2 Run as required;

- Secondly, to move the SF VAR Runs from 15 working days to 7 working days and the R1 VAR Runs from 38 working days to 29 working days at the M16 cut-over date.

The high-level solution to achieve this requires four transition timetables to be produced –

- A Settlement Timetable for M11 ‘Start of 18-month migration for UMS / Advanced’ until 31 March 2026;

- A Settlement Timetable, covers 1 April 2026 until the day before the M16 cutover date of 07 December 2026;

- A timetable that aligns with the revised operational Choreography covering the period from the 7 December 2026 until the 31 March 2027; and

- A rolling ‘fall back’ Settlement timetable, which covers the period up until the next financial year 01 April 2027.

Migration activity finishes 2 months earlier than M16 in October 2026.  Completion of Migration should be known before October, i.e. if the 07 December cutover is at risk.  Providing Migration is on track, the table in step 3 above will be used to transition to the new Settlement Timetable as set out in the Operational Choreography.  If there is a risk of Migration delaying the cutover date, the risk will be managed by deferring the cutover date and deferring the publishing the Settlement Timetable Transition defined in step 4.

We believe the solution approach aligns with the original Design Working Group (DWG) recommendations and high-level principles as set out in the document below.

We welcome Transition Design Subgroup feedback on the proposal, before we request a Design Advisory Group (DAG) industry consultation and subsequent DAG approval.

# Introduction

## Background

The new Market-wide Half Hourly Settlement (MHHS) Target Operating Model (TOM) developed by the Design Working Group (DWG) and refined by the Code Change and Development Group (CCDG) set out the requirements for the Settlement Timetable under MHHS. The DWG agreed the following:

Agreed that the simplest approach to implementing the revised Settlement timetable is to wait until all MPANs are being settled under the TOM;

Agreed that the TOM needs to be in place (i.e. all NHH MPANs moved to the MHHS) before reducing the timing of the Initial Settlement (SF) Run, as this is reliant on the Load Shaping Service;

Discussed the potential to reduce the timings of different Settlement Runs at different times – for example, reducing the RF Run timing before the SF Run timing;

Discussed the potential to ‘cut off’ different segments at the current Second Reconciliation (R2) Run at different times, with Settlement no longer processing data for the given segment after R2;

Agreed that the DF Run timing cannot be shortened until all Meter data is being received by the BSC Central Settlement Services, due to the impact on Data Aggregators;

Discussed an approach of gradually reducing the gaps between Settlement Runs and thought this was not appropriate;

Discussed the potential to reduce the Settlement timetable gradually, though did not identify any benefits of changing it more than once;

After discussing all of the complexities above, that transition to the reduced Settlement timetable would ideally occur after changes to the BSC Central Settlement Services have gone live; and

Agreed that the decision on how and when to reduce the Settlement timetable could be taken nearer the time, based on market monitoring against trigger points.

The DWG also recommended that the timing of the Post Final Settlement should be reduced from 28 Months to 20 Months.

The MHHS Programme notes that decisions relating the reduction of the Post Final Settlement timelines (Trading Disputes) relates to Participant assurance and is outside of Programme scope.

## The Settlement Timetable and the Operational Choreography

- The requirements for the timings of Settlement Runs is set out in the artefact MHHSP_OPC001_Operational_Choreography. This set out the to be Settlement schedule as follows:

|  | Activity | Transition Gate Closure | Post Transition Gate Closure |
| --- | --- | --- | --- |
| OPC_900 | Load Shaping Run Consumption Gate Closure | 00:00 CAL +4 | 00:00 CAL +4 |
| OPC_910 | Load Shape Publication | 12:00 CAL +4 | 12:00 CAL+4 |
| OPC_920 | MDS & Settlement Run (II) | 17:00 WD +4 | 17:00 WD +4 |
| OPC_930 | Best Estimate Provision (SF) | 00:00 WD +14 | 00:00 WD +6 |
| OPC_940 | MDS Run (SF) | 17:00 WD +14 | 17:00 WD +6 |
| OPC_950 | Settlement Run (SF) | 17:00 WD +15 | 17:00 WD +7 |
| OPC_960 | Best Estimate Provision (R1) | 00:00 WD +38 | 00:00 WD +29 |
| OPC_970 | MDS Run (R1) | 17:00 WD +38 | 17:00 WD +29 |
| OPC_980 | Settlement Run (R1) | 17:00 WD +39 | 17:00 WD +30 |
| OPC_990 | Best Estimate Provision (RF) | 00:00 WD +291 | 00:00 WD + 83 |
| OPC_1000 | MDS Run (RF) | 17:00 WD +291 | 17:00 WD + 83 |
| OPC_1010 | Settlement Run (RF) | 17:00 WD +292 | 17:00 WD + 84 |

## Key Milestones relating to the Settlement Timetable

- The following are the Tier 1 Milestones relating to the Settlement Timetable:

| Tier | Milestone | Date | Comment |
| --- | --- | --- | --- |
| Tier 1 | Central systems ready for migrating MPANs (M10) | 07/03/2025 17:00 | The Master Settlement Timetable will need to be published in ISD From the 1st April 2025 |
| Tier 1 | Load Shaping Service switched on (M13) | 07/03/2025 17:00 |  |
| Tier 1 | Start of 18-month migration for UMS / Advanced (M11) | 04/04/2025 17:00 | The Master Settlement Timetable will need have the runs for MHHS Services scheduled from this date. |
| Tier 1 | Start of 18-month migration for Smart / Non-smart (M12) | 04/04/2025 17:00 | The Master Settlement Timetable will need have the runs for MHHS Services scheduled from this date. |
| Tier 1 | All suppliers must be able to access MPANs under the new TOM (M14) | 16/03/2026 17:00 |  |
| Tier 1 | Full transition complete (M15) | 05/10/2026 17:00 | Following this date all MPANs will be Settling under the MHHS arrangements. |
| Tier 1 | Cut over to new settlement timetable (M16) | 07/12/2026 17:00 | A revised Master Settlement Timetable will need to be published prior to this date with revised Settlement Run from this date. |

- There are also some specific Milestones for assessing the move at the M16 Milestone:

T2-MR-0400 M16 Checkpoint (15/09/2026),

T2-RA-0800 Readiness assessment 9 – readiness for new settlement timetable – completed (30/09/2026)

T2-EL-0100 Confirm M16 date (13/10/2026)

T1-CP-4000 Control Point 5 – cut over to the new settlement timetable (07/12/2026) (M16)

- This proposal is suggesting some additional Milestones as follows:

      - T2-MR-0aaa M16 Checkpoint (07/12/2025) – A year ahead of the M16 Milestone

T2-EL-0bbb Confirm M16 date (05/01/2026)  - Start of Settlement Calendar Production for 2026

T2-RA-0ccc Readiness assessment ‘X’ – readiness for new settlement timetable – completed (02/02/2026) – ahead of Panel (SVG) decision in March on new Settlement Calendars.

## Other Consideration

- There are a number of other considerations that need to be factored into when revising the Settlement Timetable:

The Master Settlement Table will be published in ISD and is therefore subject to the timing of the ISD Timetable;

Every Settlement Date requires an RF Run: Certain charges are levied off the back of the RF Run e.g. BSUoS;

It has been suggested that once populated in Market Participant Systems make retrospective changes e.g. making the R3 Run the Final Reconciliation Run (RF) once the R3 Run has completed; Ofgem aim was to reduce settlement timetable to 4 months as part of SCR. The rational is to reduce the timescale of any Supplier (and counter parties) financial exposure.  It also reconciles Use of System charges faster providing certainty for all participants;

There is no desire to keep legacy “systems” supported longer than necessary. There is a cost for participants to maintain legacy systems operational, staffed, backed up, archived, audited, BSC audited, etc.  So there will be a strong desire to shut these down as soon as possible.  These systems are already stated as operating on unsupported software, so by 2027 this will be a significantly greater risk.  The “systems” cover – all the qualified roles – MEM, MA, DC, DA, ElectraLink (all the legacy DTN flows), central systems and code documentation;

Data Aggregators cannot surrender until last MPAN has reached RF. The BSC currently does not allow a DA to surrender their qualification until their last MPAN has completed RF.  This could be changed, but the underlying rational reflects the need to be available and able to provide updated data for RF.  If the DAs shut down in advance of RF, then the value of RF is negated because there will not be any revised data to process at RF.

# Proposed Approach for cut-over to New Settlement Timetable

Taking into account of Section 3, the following is the MHHS Programmes proposal for moving to the revised Settlement Timetable by the M16 Milestone:

## Summary Diagram

| Solution a) | Dec/Jan | Apr | Oct | Dec - Mar | April |
| --- | --- | --- | --- | --- | --- |
| a) As planned (07/12) cutover solution | M16 Decision Checkpoint 1 – confirm on track for cutover date – confirm planned calendar | Publish an adjusted Settlement Timetable up to December | Go decision | Follow Published Settlement Timetable a) as planned | Publish 2027 timetable (BAU) process |
| Solution b) | Dec/Jan | Apr | Oct | Dec - Mar | April |
| b) Rolling ‘fall back’ solution | M16 Decision Checkpoint – confirm on track cutover date – confirm revised M16 Milestone | Publish an adjusted Settlement Timetable up to December | No-go decision | Published Settlement Timetable b) up until revised M16 Milestone | Publish 2027 timetable (BAU) process (dependent on revised M16 date) |

## Detailed Steps

| Step | When | What needs to happen? | Comment |
| --- | --- | --- | --- |
| 1 | By 1st April 2025 | The Settlement Calendars shall need to be produced for the Settlement Year 2025/26. ISD need to have the Master Settlement Timetable aligned with the existing Settlement Calendars (SVAA and SAA) with Settlement Runs for new MHHS Services (LSS, MDS and VAS) scheduled from the M11 Milestone (04/04/2025). | Note if the M11 milestone moves the scheduled runs for the new Services will not be undertaken until the revised Migration Start date. See worked example based on the 2023/24 Settlement Calendars: Master_Settlement_Timetable_Examplev1.0 |
| 2 | From M11 (04/04/2025) | Elexon shall initiate Monitoring of Migrated MPANs commences (evaluation criteria to be defined at a future date) | Monitoring will be undertaken by Elexon from M11 at the start of Migration. Monitoring will include but not limited to: • The number of MPANs, not consenting to provision of HH data in each GSP Group; • The percentage of consumption being settled with Actual Data in each GSP Group; and • The percentage of MPANs being settled with Actual Data in each GSP Group. |
| 3 | M16 Checkpoint 1(07/12/2025) | Review the monitoring data from Step 2 to understand the volume of actual data at each Settlement Run. | Approximately 8 Months of monitoring data should be available by the M16 Checkpoint 1. |
| 4 | Confirm M16 date (05/01/2026) | Confirm if the M16 date will be retained as 07/12/2026. | If confirmed move to Step 5 else set new M16 checkpoint and develop a calendar to be used until the revised M16 date is confirmed as defined in Step 6 below. |
| 5 | Readiness for new Settlement Timetable – completed (02/02/2026) | Readiness assesses Participant’s preparedness to transition to the new Settlement Timetable. | Readiness assessment will inform Panel (SVG decision in March 2026 on whether the Settlement Calendars defined in Step 6 are published or the revised Calendars defined in Step 4 are published. |
| 6 | By 1st April 2026 | The Settlement Calendars shall need to be produced and published for the Settlement Year 2026 for Settlement Dates up until the day before the M16 cut-over (06/12/2026). When setting this calendar any RF Run where the VAS Run Date would have been greater than the 31/03/2027 will be reduced to 7 months and replace the R3 Runs. Likewise, any R3 Run where the VAS Run Date would have been greater than the 31/03/2027 will be reduced to 4 months and replace the R2 Run with a RF Run. | This would mean that from mid-February 2026 the Settlement Timetable is reduced to 7 months and from the end of August 2026 the Settlement Timetable is reduced to four month. It should be noted that this means the timing of the RF run will be reduced before all Metering Systems have been migrated. The SF, R1 are retained at their pre-cut over timings and DF is still at 28 Months. See example based on the 2023/24 calendar: Master_Settlement_Timetable_Example_replacementv1.0 and the illustration: Replacement_RF_Settlement_Timetable_RF_Illustrationv1.0 If the M16 date is not confirmed in Step 4 as the 7/12/2026 then a calendar shall be produced that moves the RF adjustments in relation to the revised M16 date. E.G. If the milestone move 3 months then the RF Runs would only be reduced where they were greater than 31 July 2027. |
| 7 | Following Step 6 | In case the cut-over date is missed two versions of the Settlement Timetable shall be produced for Settlement Dates from M16 (07/12/2026) until the 31/03/2027: - A Settlement Timetable that aligns with the Operational Choreography SF 7 WD and R1 at 29 WD with the DF Run reduced to 20 Months. - A Settlement Timetable that retains the existing timings for the SF Run and the DF Run retained at 28 Months. | Examples of Settlement Calendars a) and b) can be found in: Master_Settlement_Timetable_Example_replacementv1.1 These calendars can be developed at the same time as those for Step 5 and provided to Market Participants for information. |
| 8 | M16 Checkpoint 2 (15/09/2026) | Review the latest monitoring data from Step 2 to understand the volume of actual data at each Settlement Run. |  |
| 9 | Readiness for new Settlement Timetable – completed (30/09/2026) | Readiness assesses Participant’s preparedness to transition to the new Settlement Timetable. | The date of this Milestone will need to be revised from the current 04/12/2026. |
| 10 | Confirm M16 date (13/10/2026) | Confirm if the M16 date will be retained as 07/12/2026. |  |
| 11 | Following Step 10 | Raise Fast Track Change to ISD (November publish): If go ahead is given for M16 on the 07/12/2026 publish the Settlement Timetable set out in a) of Step 7. Otherwise, publish all or some of the Settlement Timetable set out in b) of Step 7. | If M16 date is moved the Settlement Timetable cut-over date will need to be after the 31 March 2027 unless only a proportion of the Settlement Timetable in b) of Step 7 is published (e.g. only another 2 months).The SAA and SVAA Calendars will need to be aligned with the revised Master Settlement Timetable . The EMR Settlement Calendar will also need to be cut-over at the same time. It should be noted that the timings may require changes to some regulations which ‘hard codes’ the timings of CFD and Capacity Runs to the current Settlement Timetable. |
| 12 | 07/12/2026 – M16 Milestone | Settlement Runs proceed in accordance with Settlement Calendars published in Step 10. |  |
| 13 | January 2027 if M16 has been met on the 07/12/2026 | Start production of the Master Settlement Timetable for the Settlement Year 2027/2028 or repeat this process from Step 7 with revised M16 date. |  |

The above approach would allow all pre-cutover Settlement Runs to be completed by the 31 March 2027 (unless M16 Milestone date is deferred). The Post Final Settlement Runs will be brought into 20 Months at the M16 Cut-over date. It should be noted that once the RF dates are completed, for pre M16 Settlement Dates, revised data will not be available for non-migrated MPANs. Hence, the data for these MPANs will be crystallised at RF. Migrated MPANs can have revised data submitted for Pre-M16 Settlement Dates for Post Final Settlement Runs up to 28 Months.

Participant systems shall maintain an archive of all transactional data for 40 months where the settlement date is prior to M16 and for 24 months for Settlement dates greater than or equal to the M16 date.. Currently the 40 month retention period is derived from a period twice the current settlement window plus a further 12 months. Noting the reduction in the Settlement Timetable post transition the retention period for Settlement Data will be 24 months.

# Validating the Transition Approach against the DWG Approach

In proposing the above approach for Settlement Timetable Transition, the analysis compares the proposed solution to the original DWG Agreements and Discussions:

| DWG Agreed Approach | Transition Meets Approach | Comment |
| --- | --- | --- |
| Agreed that the TOM needs to be in place (i.e. all NHH MPANs moved to the TOM) before reducing the timing of the Initial Settlement (SF) Run, as this is reliant on the Load Shaping Service. | Yes | All NHH MPAN moved at M15 so M16 will fall after that Milestone. If M15 not met then approach is flexible to allow a later reduction of the SF Run. |
| Discussed the potential to reduce the timings of different Settlement Runs at different times – for example, reducing the RF Run timing before the SF Run timing. | Yes | This approach reduces the timings of the RF and R3 Runs before moving the timing of SF. |
| Discussed the potential to ‘cut off’ different segments at the current Second Reconciliation (R2) Run at different times, with Settlement no longer processing data for the given segment after R2. | Partial | This approach does reduce the overall timing of the RF Run to R2 but does it for all Market Segments. It is not clear how this was envisaged to work without having separate Settlement Timetables for each Market Segment. |
| Agreed that the DF Run timing cannot be shortened until all Meter data is being received by the BSC Central Settlement Services, due to the impact on Data Aggregators. | Yes | The reduction of the DF Run only occurs when the M16 Milestone is achieved. |
| Discussed an approach of gradually reducing the gaps between Settlement Runs and thought this was not appropriate. | Yes | This approach does not seek to reduce the gaps between Settlement Runs e.g. Moving RF to 10 Months. |
| Discussed the potential to reduce the Settlement timetable gradually, though did not identify any benefits of changing it more than once. | Partial | It does reduce the timetable in two stages firstly reducing the RF to R3 and then R2. |
| After discussing all of the complexities above, that transition to the reduced Settlement timetable would ideally occur after changes to the BSC Central Settlement Services have gone live. | Yes | BSC Central Services will have ‘Gone-Live’ at M10. |
| Agreed that the decision on how and when to reduce the Settlement timetable could be taken nearer the time, based on market monitoring against trigger points. | Yes | This approach introduces Market Monitoring and trigger point Milestones. |
| The DWG also agreed that the timing of the Post Final Settlement should be reduces from 28 Months to 20 Months. | Yes | The DF Runs is reduced to 20 Months at the M16 Milestone. |

# Proposal Recommendation

The MHHS Programme recommendation is that Participants accept this proposal for 07 December 2026, with a fall back Settlement Timetable up to 31 March 2027 for Settlement Timetable Transition, because it aligns with the Principles of -

- A single solution which is hard cut over;

- The cut over date is as soon as practicably possible linked to M16;

- The transition timescale are linked to the new 4 month MHHS TOM;

- RF for all settlement periods are enabled for billing and settlement close out; and

- It provides for some flexibility in case the cutover date is not achievable.

Which this is the Programme’s recommendation, we welcome Transition Design Workgroup engagement and feedback, where the solution can be improved, made easier to understand and/or where additional detail is required.

# Appendix

## Transition Design Plan

Note: this will be a change to the Readiness Assessments under the MHHS Programme.