## Settlement Date Cutover
MHHS Proposal for revised Settlement Runs to RF Timetable cut-over - Based of 7 December 2026 cut-over
Settlement Run Date
|  | M16 Checkpoint 1 (7th) | Confirm Date (5th) | Readiness Assessment 2th) |  | New Timetable Implemented |  |  |  |  | M16 Checkpoint 2 (15th) and Readiness Assessment (30th) | Full Migration complete (5th) (M15) and confirmation of M16 date (13th) | ISD Updated | M16 (07/12/2026) | [16 empty] | Key
|  | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | SF | SF
| 2025-12-01 | 2025-12-01: SF; 2026-01-01: R1; 2026-03-01: R2; 2026-06-01: R3; 2027-01-01: RF | R1 | R1
| 2026-01-01 | 2026-01-01: SF; 2026-02-01: R1; 2026-04-01: R2; 2026-07-01: R3; 2027-02-01: RF | R2 | R2
| 2026-02-01 | 2026-02-01: SF; 2026-03-01: R1; 2026-05-01: R2; 2026-08-01: R3; 2027-03-01: RF | R3 | R3
| 2026-03-01 | 2026-03-01: SF; 2026-04-01: R1; 2026-06-01: R2; 2026-09-01: RF (Replaces R3) | RF | RF
| 2026-04-01 | 2026-04-01: SF; 2026-05-01: R1; 2026-07-01: R2; 2026-10-01: RF | SF 7 WD | SF
| 2026-05-01 | 2026-05-01: SF; 2026-06-01: R1; 2026-08-01: R2; 2026-11-01: RF | R1 29 WD | R1
| 2026-06-01 | 2026-06-01: SF; 2026-07-01: R1; 2026-09-01: R2; 2026-12-01: RF
| 2026-07-01 | 2026-07-01: SF; 2026-08-01: R1; 2026-10-01: R2; 2027-01-01: RF
| 2026-08-01 | 2026-08-01: SF; 2026-09-01: R1; 2026-11-01: R2; 2027-02-01: RF
Settlement Date | 2026-09-01 | 2026-09-01: SF; 2026-10-01: R1; 2026-12-01: RF (Replaces R2)
| 2026-10-01 | 2026-10-01: SF; 2026-11-01: R1; 2027-01-01: RF
| 2026-11-01 | 2026-11-01: SF; 2026-12-01: R1; 2027-02-01: RF
| 2026-12-07 | 2026-02-01: 07/12/2026 cut-over of VAS SF Run to 7 WD; 2026-12-01: SF; 2027-01-01: R1; 2027-03-01: RF
| 2027-01-01 | 2027-01-01: SF; 2027-02-01: R1; 2027-04-01: RF
| 2027-02-01 | 2027-02-01: SF; 2027-03-01: R1; 2027-05-01: RF
| 2027-03-01 | 2027-03-01: SF; 2027-04-01: R1; 2027-06-01: RF
| 2027-04-01 | 2026-02-01: New Settlement Calendar Introduced; 2027-04-01: SF; 2027-05-01: R1; 2027-07-01: RF
| 2027-05-01 | 2027-05-01: SF; 2027-06-01: R1; 2027-08-01: RF
| 2027-06-01 | 2027-06-01: SF; 2027-07-01: R1; 2027-09-01: RF
| 2027-07-01 | 2027-07-01: SF; 2027-08-01: R1; 2027-10-01: RF
| 2027-08-01 | 2027-08-01: SF; 2027-09-01: R1; 2027-11-01: RF
| 2027-09-01 | 2027-09-01: SF; 2027-10-01: R1; 2027-12-01: RF
| 2027-10-01 | 2027-10-01: SF; 2027-11-01: R1; 2028-01-01: RF
| 2027-11-01 | 2027-11-01: SF; 2027-12-01: R1; 2028-02-01: RF
| 2027-12-01 | 2027-12-01: SF; 2028-01-01: R1; 2028-03-01: RF
M16 cut over Settlement Date
RF Runs moved to 7 Months
RF Runs moved to 4 Months
SF Runs moved to 7 WD from 15 WD and R1 moved from 38 WD to 29 WD
ISD and Settlement Calendar updates for dates from 7/12/2026
Review of Monitoring Data
Decision point on reduction to the RF Runs or revision of the M16 Milestone
Decision point on reduction to the SF Run from 15 WD to 7 WD or revision of the M16 Milestaone
Review of Monitoring Data