## Pro Forma
Non-SIT S&A Qualification Testing Configuration
VERSION: | 1.3
AS OF: | 2025-10-02
CHANGE SUMMARY: | v1.3 - Added missing Role Reqs/QTC Scale for Prerequisite Tests, corrected SUP QTC run count for Supplier Linked QTCs v1.2 - Updates following Wave 1 activities (Effective Time, Prerequesite Test To Be Run updates). Including QTC Timeline Explanation tabs v1.1 - Effective Time and T-Shirt Sizing added to Test Lists following requests from Participants v1.0 - Guidance tab provided; run counts and pre-requesite tests now indicated in catalogue; exclusion column moved left for convenience; 500 and 800/900 series tests seperated to new tabs; please see guidance tab for details of changes v0.5 - QTC Master List updated, column for Scope theme added (column 'C') v0.4 - QTC Master List updated v0.3 - QTC Master List updated for Batch 3 v0.2 - Pro Forma added v0.1 - Initial Draft Catalogue
STATUS: | Interim Version
Please supply the following information below; NOTE: You must define the team for each MPID/ROLE explicitly.
| Company Information |  | MSS
Organisation: | (legal name) | required for configuration | MSA
MPID: |  | required for configuration | SDS
ROLE: |  | required for configuration | ADS
PPOC (name): |  | required for MHHS Teams | SUP
EMAIL: |  | must be @mhhsprograme.co.uk address | UMSDS
Phone: |  | information only
| Participant Test Team (Maximum 5 QTF Users) | email addresses can be any domain
Defect Manager: |  | required for ADO/QTF access (email)
DM Alternate: |  | required for ADO/QTF access (email)
Tester 1: |  | required for QTF access only (email)
Tester 2: |  | required for QTF access only (email)
Tester 3: |  | required for QTF access only (email)
Tester 4: |  | available only if DM will not use QTF (email)
Tester 5: |  | available only if DM Alternate will not use QTF

## Guidance
How to use the Test Catalogue
Introduction
The Test Catalogue outlines all Qualfication Test Cases available for testing by Participants. Each Qualification Test Case (QTC) listed in this catalogue also contains information about the market roles applicable for each test, the number of distinct tests that will be required for each QTC e.g. incoming/outgoing/supplier-linked and the pre-requsite QTC that must be run prior to execution (800/900 series). Each Participant must review this catalogue, listing any exclusions (if they apply as agreed with the Code Bodies) and submit to the MHHS Qualification inbox for QTF configuration prior to Qualification Testing. Please note that a separate catalogue must be issued for each market role which sould be identified in the Pro Forma sheet as well as the designated test resources.
Distinct Tests to Run
Each QTC identifies the number of distinct tests that will be created in the Qualification Testing Framework (QTF) as impacted by the Role Requirements where incoming, outgoing and/or supplier-linked cases may apply. While this is represented as a single QTC within the test catalogue, a distinct test for each condition will be created within the QTF to be run by the Participant in accordance with market role. (e.g. 'Y' denotes a single test, 'Y*' denotes incoming and outgoing (2 tests) and 'Y' under 'Supplier Linked' requires a seperate test). The Participant may easily calculate the total number of tests to be run (excludes 500/800/900 series) by adding the values in the column specific to the Participants role.
Prerequsiste Tests (800/900 series)
Included in the catalogue are the Prerequisite tests that are incorporated into the execution of any Qualification Test Case where applicable. As an example, a Supplier on selecting QT-001 will be prompted to run QT-954 automatically. Where incoming and outgoing tests apply, there will be a prerequisite test identified for each condition. Please note that 500/800/900 series tests are NOT to be included in the test counts stated in the QT Test Execution Plan (Section 4.2 of the Non-SIT S&A Qualification Test Plan). Note: further detail on how the QTF manages Participants through prequisite tests will be explained in the QTF Online Guide
Effective Time and T-Shirt Sizing
As of v1.1, there is now additional columns to indicate effective time appropriate to each QTC. Also added are columns indidicating T-shirt sizing for each QTC depending on the role impacted; this is explained in supplementary guidance. (see slide deck for SAGTSG JULY 2025)
Annotating Exclusions
By default, all Qualification Test Cases in the Test Catalogue are marked as 'Included' although it is understood that many Participants will limit testing to a smaller subset of QTCs depending on agreement with the Code Bodies under Placing Reliance and/or exemptions. Where exclusions may apply, Participants are required to update the value for the relevant QTCs to 'EXCLUDE' and MUST provide a reason in the adjacent column for the exclusion; this should always align with the Participant's RTTM, PIT Approach and Plan and any Placing Reliance agreements in place. Once submitted, only those QTCs that are marked as 'INCLUDED' will be generated in the QTF for the Participant's Role proceeding through Qualification Testing. Additional tests to cover incoming, outgoing and supplier-linked conditions will be generated automatically as distinct tests.
Completing Section 4.2 of the Non-SIT S&A Qualification Test Plan (DEL3038)
The Test Catalogue should be used to derive the final test count for the QT Test Execution Plan contained with the Qualification Test Plan. As the derived counts have been provided in this catalogue, the sum of the 'Distinct Tests To Run' according to the Participant's Role should be tallied and align to the volumes stated within Section 4.2 of the Non-SIT S&A Qualification Test Plan. Participants must ensure that only QTCs marked as 'INCLUDED' are counted.
Smoke Tests
Following QTF Onboarding, Participants will have access to a set of two smoke tests specific to the role being tested. These tests will not impact Qualification and are provided to ensure throughput from the QTF via DIP/DTN to Participant systems. These tests are not to be included in the test counts stated in the Non-SIT S&A QT Test Plan.
Identfies which roles the QTC applies to.
Confirms how many tests will be created in the QTF depending on the role testing.
If the Participant is a Supplier, the sum of the values in the SUP QTC run count, for INCLUDED QTCs only, should be used to determine total tests to be run as part of the QT Execution Plan.
A Supplier will be prompted to run QT-954 automatically when selecting QT-001 for execution from the QT Test Set.
Suffix of I indicates Incoming and suffix of O indicates Outgoing (or Current if there is no change of role during the QTC)
Any QTC to be excluded from the Participant's Test Set must be marked accordingly by selecting 'EXCLUDE' next to the relevant QTC.
A rationale must be provided for each exclusion and must align to the Participant's RTTM otherwise the Test Set will be returned for correction.
DEL3038 - Non-SIT S&A Qualification Test Plan
As an example, if the Participant is testing under the 'Supplier' role, the sum of the 'SUP QTC run count' for INCLUDED QTCs should match the 'Total Test Cases' stated in Section 4.2 - Qualification Test Execution Plan.
XX
Specifies role applicable for each smoke test.
Effective Time applicable to the test.
T-Shirt Sizing applicable to each role.

## Non-SIT S&A Test Catalogue
Test ID and Exclusions |  |  | Test Details | [5 empty] | Role Requirements | [6 empty] | Distinct Tests To Run (by Role ) | [5 empty] | Prerequesite Test To Be Run | [12 empty] | QTC Scale (t-shirt size)
QT Case ID | Excluded? | Exclusion Rationale (please note that this must be reflected in your RTTM and agreed with the Code Bodies) | QT Test Type | Scope Theme | Segment | QT Test Case Title | QT Scenario | Effective Time | MSS | MSA | SDS | ADS | SUP | UMSDS | Supplier Linked | MSS QTC run count | MSA QTC run count | SDS QTC run count | ADS QTC run count | SUP QTC run count | UMSDS QTC run count | MSSO | MSSI | MSAO | MSAI | SDSO | SDSI | ADSO | ADSI | SUPO | SUPI | UMSDSO | UMSDSI | SUPL | MSS | MSA | SDS | ADS | UMSDS | SUP
QT-001 | EXCLUDE | Example: Placing Reliance; agreed exemption (REMOVE THIS EXCLUSION IF NOT INTENDED) | Functional | Change of Data Service | Advanced | Change of DS Advanced Linked | Import / Export MPANs covering agent appointments | Forward Dated 3 working days |  | Y |  | Y* | Y |  |  | 0 | 1 | 0 | 2 | 1 | 0 |  |  | QT-950 |  |  |  | QT-946 | QT-941 | QT-954 |  |  |  |  | N/A | MEDIUM | N/A | MEDIUM | N/A | MEDIUM
QT-002 | INCLUDED |  | Functional | Change of Data Service | Advanced | Change of DS Advanced Related Multiple | Related MPANs covering agent appointments | Same Day |  | Y |  | Y* | Y |  |  | 0 | 1 | 0 | 2 | 1 | 0 |  |  | QT-978 |  |  |  | QT-977 | QT-976 | QT-979 |  |  |  |  | N/A | MEDIUM | N/A | MEDIUM | N/A | MEDIUM
QT-003 | INCLUDED |  | Functional | Change of Data Service | Advanced | Change of DS Advanced Single | Single MPAN covering agent appointment | Forward Dated 3 working days |  | Y |  | Y* | Y |  |  | 0 | 1 | 0 | 2 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 | QT-901 | QT-914 |  |  |  |  | N/A | LOW | N/A | MEDIUM | N/A | MEDIUM
QT-004 | INCLUDED |  | Functional | Change of Data Service | Smart | Change of DS Smart Linked | Import / Export MPANs covering agent appointments | Same Day | Y |  | Y* |  | Y |  |  | 1 | 0 | 2 | 0 | 1 | 0 | QT-948 |  |  |  | QT-944 | QT-939 |  |  | QT-952 |  |  |  |  | LOW | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-005 | INCLUDED |  | Functional | Change of Data Service | Smart | Change of DS Smart Related | Related MPANs covering agent appointments | Same Day | Y |  | Y* |  | Y |  |  | 1 | 0 | 2 | 0 | 1 | 0 | QT-932 |  |  |  | QT-936 | QT-922 |  |  | QT-927 |  |  |  |  | LOW | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-006 | INCLUDED |  | Functional | Change of Data Service | Smart | Change of DS Smart Single | Single MPAN covering agent appointment | Same Day | Y |  | Y* |  | Y |  |  | 1 | 0 | 2 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 | QT-902 |  |  | QT-910 |  |  |  |  | LOW | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-007 | INCLUDED |  | Functional | Change of Data Service | Smart | Change of DS Traditional Single | Single MPAN covering agent appointment | Forward Dated 2 working days | Y |  | Y* |  | Y |  |  | 1 | 0 | 2 | 0 | 1 | 0 | QT-917 |  |  |  | QT-916 | QT-919 |  |  | QT-918 |  |  |  |  | MEDIUM | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-008 | INCLUDED |  | Functional | Change of Data Service | Smart | Change of DS Traditional Linked | Import / Export MPANs covering agent appointments | Retro Dated -1 working days | Y |  | Y* |  | Y |  |  | 1 | 0 | 2 | 0 | 1 | 0 | QT-949 |  |  |  | QT-945 | QT-940 |  |  | QT-953 |  |  |  |  | MEDIUM | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-009 | INCLUDED |  | Functional | Change of Data Service | Smart | Change of DS Traditional Related | Related MPANs covering agent appointments | Same Day | Y |  | Y* |  | Y |  |  | 1 | 0 | 2 | 0 | 1 | 0 | QT-933 |  |  |  | QT-937 | QT-924 |  |  | QT-929 |  |  |  |  | MEDIUM | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-010 | INCLUDED |  | Functional | Change of Data Service | Unmetered | Change of DS Unmetered Single | Single MPAN covering agent appointment | Retro Dated -1 working days |  |  |  |  | Y | Y* |  | 0 | 0 | 0 | 0 | 1 | 2 | [8 empty] | QT-911 |  | QT-906 | QT-903 |  | N/A | N/A | N/A | N/A | MEDIUM | MEDIUM
QT-011 | INCLUDED |  | Functional | Change of Metering Service | Advanced | Change of MS Advanced Linked | Import / Export MPANs covering agent appointments | Forward Dated 3 working days |  | Y* |  | Y | Y |  |  | 0 | 2 | 0 | 1 | 1 | 0 |  |  | QT-950 | QT-941 |  |  | QT-946 |  | QT-954 |  |  |  |  | N/A | HIGH | N/A | MEDIUM | N/A | MEDIUM
QT-012 | INCLUDED |  | Functional | Change of Metering Service | Advanced | Change of MS Advanced Related | Related MPANs covering agent appointments | Retro Dated -1 working days |  | Y* |  | Y | Y |  |  | 0 | 2 | 0 | 1 | 1 | 0 |  |  | QT-931 | QT-921 |  |  | QT-935 |  | QT-926 |  |  |  |  | N/A | HIGH | N/A | MEDIUM | N/A | MEDIUM
QT-013 | INCLUDED |  | Functional | Change of Metering Service | Advanced | Change of MS Advanced Single | Single MPAN covering agent appointment | Forward Dated 3 working days |  | Y* |  | Y | Y |  |  | 0 | 2 | 0 | 1 | 1 | 0 |  |  | QT-913 | QT-901 |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | HIGH | N/A | LOW | N/A | MEDIUM
QT-014 | INCLUDED |  | Functional | Change of Metering Service | Smart | Change of MS Smart Linked | Import / Export MPANs covering agent appointments | Same Day | Y* |  | Y |  | Y |  |  | 2 | 0 | 1 | 0 | 1 | 0 | QT-948 | QT-939 |  |  | QT-944 |  |  |  | QT-952 |  |  |  |  | MEDIUM | N/A | LOW | N/A | N/A | MEDIUM
QT-015 | INCLUDED |  | Functional | Change of Metering Service | Smart | Change of MS Smart Related | Related MPANs covering agent appointments | Forward Dated 2 working days | Y* |  | Y |  | Y |  |  | 2 | 0 | 1 | 0 | 1 | 0 | QT-932 | QT-922 |  |  | QT-936 |  |  |  | QT-927 |  |  |  |  | MEDIUM | N/A | LOW | N/A | N/A | MEDIUM
QT-016 | INCLUDED |  | Functional | Change of Metering Service | Smart | Change of MS Smart Single | Single MPAN covering agent appointment | Same Day | Y* |  | Y |  | Y |  |  | 2 | 0 | 1 | 0 | 1 | 0 | QT-908 | QT-902 |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | MEDIUM | N/A | LOW | N/A | N/A | MEDIUM
QT-017 | INCLUDED |  | Functional | Change of Metering Service | Smart | Change of MS Trad Linked | Import / Export MPANs covering agent appointments | Forward Dated 2 working days | Y* |  | Y |  | Y |  |  | 2 | 0 | 1 | 0 | 1 | 0 | QT-949 | QT-940 |  |  | QT-945 |  |  |  | QT-953 |  |  |  |  | HIGH | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-018 | INCLUDED |  | Functional | Change of Metering Service | Smart | Change of MS Traditional Related Multiple | Related MPANs covering agent appointments | Forward Dated 2 working days | Y* |  | Y |  | Y |  |  | 2 | 0 | 1 | 0 | 1 | 0 | QT-982 | QT-980 |  |  | QT-981 |  |  |  | QT-983 |  |  |  |  | HIGH | N/A | MEDIUM | N/A | N/A | HIGH
QT-019 | INCLUDED |  | Functional | Change of Metering Service | Smart | Change of MS Trad Single | Single MPAN covering agent appointment | Same Day | Y* |  | Y |  | Y |  |  | 2 | 0 | 1 | 0 | 1 | 0 | QT-917 | QT-919 |  |  | QT-916 |  |  |  | QT-918 |  |  |  |  | HIGH | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-026 | INCLUDED |  | Functional | Consumption | Smart | Change of Supplier Transfer Reads - Traditional | Consumption on Change of Supplier with no change of MS | Forward Dated 2 working days |  |  | Y |  | Y* |  |  | 0 | 0 | 1 | 0 | 2 | 0 |  |  |  |  | QT-937 |  |  |  | QT-929 | QT-924 |  |  |  | N/A | N/A | HIGH | N/A | N/A | HIGH
QT-027 | INCLUDED |  | Functional | Consumption | Smart | Change of Supplier Transfer Reads - Smart | Consumption on Change of Supplier with no change of MS | Forward Dated 2 working days |  |  |  |  | Y* |  |  | 0 | 0 | 0 | 0 | 2 | 0 | [8 empty] | QT-910 | QT-902 |  |  |  | N/A | N/A | N/A | N/A | N/A | HIGH
QT-029 | INCLUDED |  | Functional | Consumption | Smart | Change of Supplier Transfer Reads - Trad Agreed | Consumption on Change of Supplier with no change of MS | Forward Dated 2 working days |  |  | Y* |  | Y* |  |  | 0 | 0 | 2 | 0 | 2 | 0 |  |  |  |  | QT-916 | QT-919 |  |  | QT-918 | QT-919 |  |  |  | N/A | N/A | HIGH | N/A | N/A | HIGH
QT-030 | INCLUDED |  | Functional | Consumption | Smart | Change of Supplier Transfer Reads - Smart Agreed | Consumption on Change of Supplier with no change of MS | Forward Dated 2 working days |  |  | Y* |  | Y* |  |  | 0 | 0 | 2 | 0 | 2 | 0 |  |  |  |  | QT-905 | QT-902 |  |  | QT-910 | QT-902 |  |  |  | N/A | N/A | HIGH | N/A | N/A | HIGH
QT-031 | INCLUDED |  | Functional | Consumption | Advanced | Change of Supplier Transfer Reads - Advanced Agreed | Consumption on Change of Supplier with no change of MS | Forward Dated 3 working days |  |  |  | Y* | Y* |  |  | 0 | 0 | 0 | 2 | 2 | 0 | [6 empty] | QT-912 | QT-901 | QT-914 | QT-901 |  |  |  | N/A | N/A | N/A | MEDIUM | N/A | HIGH
QT-032 | INCLUDED |  | Functional | Change of Supplier | Smart | Change Linked To Different Suppliers - Smart Export | Import / Export MPANs covering agent appointments with different supplier | Forward Dated 2 working days | Y* |  | Y* |  | Y* |  | Y | 2 | 0 | 2 | 0 | 3 | 0 | QT-963 | QT-957 |  |  | QT-960 | QT-957 |  |  | QT-966 | QT-957 |  |  | QT-969 | MEDIUM | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-033 | INCLUDED |  | Functional | Change of Supplier | Advanced | Change Linked To Different Suppliers - Advanced Import | Change of Supplier and DS for Linked MPAN only with no change of MS | Forward Dated 3 working days |  |  |  |  | Y* |  | Y | 0 | 0 | 0 | 0 | 3 | 0 | [8 empty] | QT-965 | QT-956 |  |  | QT-968 | N/A | N/A | N/A | N/A | N/A | HIGH
QT-034 | INCLUDED |  | Functional | Change of Supplier | Smart | Change of Supplier and DS. No change of MS - Smart | Single MPAN end to end covering: Switch Request to CSS Agent Appointment (including MTD transfer) Transfer Read Settlement Calender | Forward Dated 2 working days | Y |  | Y* |  | Y* |  |  | 1 | 0 | 2 | 0 | 2 | 0 | QT-908 | QT-902 |  |  | QT-905 | QT-902 |  |  | QT-910 | QT-902 |  |  |  | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-035 | INCLUDED |  | Functional | Change of Supplier | Advanced | Change of Supplier. MS and DS - Advanced Import/Export | Import / Export CoS covering agent appointments | Forward Dated 3 working days |  | Y* |  | Y* | Y* |  |  | 0 | 2 | 0 | 2 | 2 | 0 |  |  | QT-950 | QT-941 |  |  | QT-946 | QT-941 | QT-954 | QT-941 |  |  |  | N/A | HIGH | N/A | HIGH | N/A | HIGH
QT-036 | INCLUDED |  | Functional | Change of Supplier | Smart | Change of Supplier. MS and DS - Traditional Related | Related CoS covering agent appointments | Forward Dated 2 working days | Y* |  | Y* |  | Y* |  |  | 2 | 0 | 2 | 0 | 2 | 0 | QT-982 | QT-980 |  |  | QT-981 | QT-980 |  |  | QT-983 | QT-980 |  |  |  | HIGH | N/A | HIGH | N/A | N/A | HIGH
QT-037 | INCLUDED |  | Functional | Change of Supplier | Smart | Change Lapsed Appointments - Smart | Appointment lapsed due to secured active not being received | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 | QT-902 |  |  |  | MEDIUM | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-038 | INCLUDED |  | Functional | Change of Supplier | Advanced | Change Lapsed Appointments - Advanced | Appointment lapsed due to secured active not being received | Forward Dated 3 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 | QT-901 |  |  |  | N/A | HIGH | N/A | MEDIUM | N/A | HIGH
QT-039 | INCLUDED |  | Functional | New Connection | Smart | New Connection - Traditional | End to end covering: New connection Initial Registration Agent appointment Energisation and Meter Install (single rate credit meter) | Next Day 1 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | HIGH | N/A | MEDIUM | N/A | N/A | HIGH
QT-040 | INCLUDED |  | Functional | New Connection | Advanced | New Connection - Advanced | End to end covering: New connection Initial Registration Agent appointment Energisation and Meter Install (single rate credit meter) | Next Day 1 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | MEDIUM | N/A | MEDIUM | N/A | HIGH
QT-041 | INCLUDED |  | Functional | New Connection | Unmetered | New Connection - Unmetered | End to end covering: New connection Initial Registration Agent appointment Energisation and Meter Install | Next Day 1 working days |  |  |  |  | Y | Y |  | 0 | 0 | 0 | 0 | 1 | 1 | [13 empty] | N/A | N/A | N/A | N/A | MEDIUM | MEDIUM
QT-042 | INCLUDED |  | Functional | New Connections | Unmetered | New Connection MS DS Delay - Unmetered | Create MPAN. Services not immediately appointed | Forward Dated 3 working days |  |  |  |  | Y | Y |  | 0 | 0 | 0 | 0 | 1 | 1 | [13 empty] | N/A | N/A | N/A | N/A | MEDIUM | HIGH
QT-043 | INCLUDED |  | Functional | New Connections | Advanced | New Connection MS Fail - Advanced | Appoint an MS such that the appointment fails | Forward Dated 3 working days |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [13 empty] | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-044 | INCLUDED |  | Functional | Change of Registration Data | Smart | Change of Customer Appointment - Metering Services Smart | Change of Customer Appointment MS | Same Day | Y |  |  |  | Y |  |  | 1 | 0 | 0 | 0 | 1 | 0 | QT-908 | [7 empty] | QT-910 |  |  |  |  | LOW | N/A | N/A | N/A | N/A | LOW
QT-045 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Change of Customer Appointment - Metering Services Advanced | Change of Customer Appointment MS | Same Day |  | Y |  |  | Y |  |  | 0 | 1 | 0 | 0 | 1 | 0 |  |  | QT-913 | [5 empty] | QT-914 |  |  |  |  | N/A | LOW | N/A | N/A | N/A | LOW
QT-047 | INCLUDED |  | Functional | Consumption | Smart | Change Transfer of Reads - Traditional | DS Change of Transfer of Reads | Same Day |  |  | Y* |  | Y |  |  | 0 | 0 | 2 | 0 | 1 | 0 |  |  |  |  | QT-937 | QT-924 |  |  | QT-929 |  |  |  |  | N/A | N/A | HIGH | N/A | N/A | HIGH
QT-048 | INCLUDED |  | Functional | Consumption | Smart | Change Transfer of Reads - Smart | DS Change of Transfer of Reads | Retro Dated -1 working days |  |  | Y* |  | Y |  |  | 0 | 0 | 2 | 0 | 1 | 0 |  |  |  |  | QT-905 | QT-902 |  |  | QT-910 |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-049 | INCLUDED |  | Functional | Consumption | Advanced | Change Transfer of Reads - Advanced | DS Change of Transfer of Reads | Forward Dated 3 working days |  |  |  | Y* | Y |  |  | 0 | 0 | 0 | 2 | 1 | 0 | [6 empty] | QT-912 | QT-901 | QT-914 |  |  |  |  | N/A | N/A | N/A | HIGH | N/A | HIGH
QT-051 | INCLUDED |  | Functional | Change of Registration Data | Smart | Change of Customer Appointment - Data Services Smart | Change of Customer Appointment DS | Same Day |  |  | Y |  | Y |  |  | 0 | 0 | 1 | 0 | 1 | 0 |  |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | N/A | N/A | LOW | N/A | N/A | LOW
QT-052 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Change of Customer Appointment - Data Services Advanced | Change of Customer Appointment DS | Same Day |  |  |  | Y | Y |  |  | 0 | 0 | 0 | 1 | 1 | 0 | [6 empty] | QT-912 |  | QT-914 |  |  |  |  | N/A | N/A | N/A | LOW | N/A | LOW
QT-053 | INCLUDED |  | Functional | Change of Registration | Unmetered | Change of Customer Appointment - Data Services Unmetered | Change of Customer Appointment DS | Same Day |  |  |  |  | Y | Y |  | 0 | 0 | 0 | 0 | 1 | 1 | [8 empty] | QT-911 |  | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | LOW
QT-054 | INCLUDED |  | Functional | Change of Registration | Unmetered | Change of Customer Appointment - Data Services Unmetered Reject | Change of Customer Appointment DS | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-055 | INCLUDED |  | Functional | Change of Registration | Smart | Change of Customer Appointment - Data Services Smart Reject | Change of Customer Appointment DS | Same Day |  |  | Y |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | QT-905 | [8 empty] | N/A | N/A | LOW | N/A | N/A | N/A
QT-056 | INCLUDED |  | Functional | Change of Registration | Advanced | Change of Customer Appointment - Data Services Advanced Reject | Change of Customer Appointment DS | Same Day |  |  |  | Y |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | QT-912 | [6 empty] | N/A | N/A | N/A | LOW | N/A | N/A
QT-057 | INCLUDED |  | Functional | Change of Metering Service | Smart | Change of MS and DS followed by Change of Existing Appointment - Smart | Change of MS and DS followed by Change of Existing Appointment | Forward Dated 2 working days | Y* |  |  |  | Y |  |  | 2 | 0 | 0 | 0 | 1 | 0 | QT-908 | QT-902 | [6 empty] | QT-910 |  |  |  |  | MEDIUM | N/A | N/A | N/A | N/A | HIGH
QT-058 | INCLUDED |  | Functional | Change of Metering Service | Smart | Smart Metered SDS Initiated Change of MDR | Change of MS and DS followed by Change of Existing Appointment | Forward Dated 2 working days |  |  | Y |  | Y |  |  | 0 | 0 | 1 | 0 | 1 | 0 |  |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | N/A | N/A | LOW | N/A | N/A | LOW
QT-059 | INCLUDED |  | Functional | Change of Metering Service | Advanced | Change of MS and DS followed by Change of Existing Appointment - Advanced Reject | Change of MS and DS followed by Change of Existing Appointment Reject | Forward Dated 3 working days |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [8 empty] | QT-914 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-065 | INCLUDED |  | Functional | Consumption | Advanced | Consumption Invalid - Advanced | Invalid Consumption Data | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-066 | INCLUDED |  | Functional | Consumption | Smart | Invalid Meter Readings - Traditional | Invalid Consumption Data | Same Day |  |  | Y |  | Y |  |  | 0 | 0 | 1 | 0 | 1 | 0 |  |  |  |  | QT-916 |  |  |  | QT-918 |  |  |  |  | N/A | N/A | LOW | N/A | N/A | LOW
QT-067 | INCLUDED |  | Functional | Consumption | Advanced | Invalid Meter Readings - Advanced | Invalid Consumption Data | Same Day |  |  |  | Y |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | QT-912 | [6 empty] | N/A | N/A | N/A | LOW | N/A | N/A
QT-068 | INCLUDED |  | Functional | Metering Changes | Smart | Smart Credit MS Energisation | Change of Energisation Status | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | MEDIUM | N/A | LOW | N/A | N/A | LOW
QT-069 | INCLUDED |  | Functional | Metering Changes | Advanced | Advanced LDSO Energisation | Change of Energisation Status | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | MEDIUM | N/A | MEDIUM | N/A | MEDIUM
QT-070 | INCLUDED |  | Functional | Consumption | Smart | Traditional Meter E7 with Switched Load Capability | Estimated Trad Meters Multi Rates | Same Day |  |  | Y |  | Y |  |  | 0 | 0 | 1 | 0 | 1 | 0 |  |  |  |  | QT-972 |  |  |  | QT-973 |  |  |  |  | N/A | N/A | LOW | N/A | N/A | LOW
QT-071 | INCLUDED |  | Functional | Consumption | Smart | SDS Estimation - Opt Out Method 3 | SDS Estimation | Forward Dated 2 working days |  |  | Y |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | QT-905 | [8 empty] | N/A | N/A | LOW | N/A | N/A | N/A
QT-073 | INCLUDED |  | Functional | Consumption | Advanced | Modern Advanced Meter Periodic MAR Check fails | ADS Meter Advance Reconcillation | Same Day |  |  |  | Y |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | QT-912 | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-074 | INCLUDED |  | Functional | Consumption | Advanced | Advanced Meter with Check Meter Periodic MAR Check fails | ADS Meter Advance Reconcillation | Same Day |  |  |  | Y |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | QT-943 | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-075 | INCLUDED |  | Functional | Consumption | Advanced | Advanced Meter where Check Meter data is missing - Import | ADS Import Estimation | Same Day |  |  |  | Y |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | QT-943 | [6 empty] | N/A | N/A | N/A | LOW | N/A | N/A
QT-076 | INCLUDED |  | Functional | Consumption | Advanced | Advanced Meter where Check Meter data is missing - Export | ADS Export Estimation | Same Day |  |  |  | Y |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | QT-943 | [6 empty] | N/A | N/A | N/A | LOW | N/A | N/A
QT-078 | INCLUDED |  | Functional | Consumption | Advanced | ADS Opt-Out Estimation - Method 2 | ADS Opt-Out Estimation | Same Day |  |  |  | Y |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | QT-912 | [6 empty] | N/A | N/A | N/A | LOW | N/A | N/A
QT-079 | INCLUDED |  | Functional | Consumption | Advanced | ADS Opt-Out Estimation - Method 3 | ADS Opt-Out Estimation | Forward Dated 2 working days |  |  |  | Y |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | QT-912 |  | QT-914 |  |  |  |  | N/A | N/A | N/A | LOW | N/A | N/A
QT-080 | INCLUDED |  | Functional | Consumption | Unmetered | Unmetered MPAN with Inventory and Load (Dynamic) | UMSDS Consumption Data Calculation and Estimation | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-915 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-081 | INCLUDED |  | Functional | Consumption | Unmetered | Unmetered Invalid - Incorrect UMSO | Unmetered Invalid | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-082 | INCLUDED |  | Functional | Consumption | Unmetered | Unmetered Invalid - Invalid Charge Code | Unmetered Invalid | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-083 | INCLUDED |  | Functional | Consumption | Unmetered | Unmetered Invalid - Invalid CC/SR Combination | Unmetered Invalid | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-084 | INCLUDED |  | Functional | Consumption | Unmetered | Unmetered Invalid - Incorrect Inventory Sequence Number | Unmetered Invalid | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-906 |  |  | N/A | N/A | N/A | N/A | MEDIUM | N/A
QT-086 | INCLUDED |  | Functional | Consumption | Unmetered | Unmetered Invalid - No Appointment | Unmetered Invalid | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-087 | INCLUDED |  | Functional | Consumption | Unmetered | Unmetered Invalid - Invalid Sub-Meter | Unmetered Invalid | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-088 | INCLUDED |  | Functional | Consumption | Unmetered | Unmetered Invalid - Invalid Switch Regime | Unmetered Invalid | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-089 | INCLUDED |  | Functional | Consumption | Unmetered | Unmetered Invalid - Invalid CMS Unit Reference | Unmetered Invalid | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-915 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-090 | INCLUDED |  | Functional | Metering Changes | Smart | Energisation REGS Rejection (REG1002) - Smart | Change of Energisation Status Rejection by Registration Service | Same Day | Y | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | QT-908 |  |  |  | QT-905 | [8 empty] | LOW | N/A | N/A | N/A | N/A | N/A
QT-091 | INCLUDED |  | Functional | Metering Changes | Advanced | Energisation REGS Rejection (REC1019) - Advanced | Change of Energisation Status Rejection by Registration Service | Same Day |  | Y |  |  | Y |  |  | 0 | 1 | 0 | 0 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | N/A | N/A | LOW
QT-092 | INCLUDED |  | Functional | Metering Changes | Smart | MS Failure - Unable to Action - Traditional | Change of Energisation Status Rejection by MOA | Same Day | Y |  |  |  | Y |  |  | 1 | 0 | 0 | 0 | 1 | 0 | QT-917 | [7 empty] | QT-918 |  |  |  |  | LOW | N/A | N/A | N/A | N/A | LOW
QT-093 | INCLUDED |  | Functional | ISD | All | ISD - Publish Whole Dataset | Publishing ISD | N/A | Y | Y | Y | Y | Y | Y |  | 1 | 1 | 1 | 1 | 1 | 1 | [13 empty] | LOW | LOW | LOW | LOW | LOW | N/A
QT-096 | INCLUDED |  | Functional | Metering Changes | Smart | Customer Initiated - Smart | End to end covering: Disconnection leading to IF009 Registration de-activation Auto de-appointment of agents | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | MEDIUM | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-097 | INCLUDED |  | Functional | Metering Changes | Advanced | LDSO Initiated - Advanced | End to end covering: Disconnection leading to IF009 Registration de-activation Auto de-appointment of agents | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | MEDIUM | N/A | MEDIUM | N/A | MEDIUM
QT-098 | INCLUDED |  | Functional | Metering Changes | Unmetered | LDSO Initiated - Unmetered | End to end covering: Disconnection leading to IF009 Registration de-activation Auto de-appointment of agents | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-099 | INCLUDED |  | Functional | Metering Changes | Smart | Related Disconnection - Smart | Related Disconnection | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-932 |  |  |  | QT-936 |  |  |  | QT-927 |  |  |  |  | MEDIUM | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-100 | INCLUDED |  | Functional | Metering Changes | Smart | Related Disconnection - Traditional | Related Disconnection | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-933 |  |  |  | QT-937 |  |  |  | QT-929 |  |  |  |  | HIGH | N/A | MEDIUM | N/A | N/A | HIGH
QT-101 | INCLUDED |  | Functional | Metering Changes | Advanced | Related Disconnection - Advanced | Related Disconnection | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-931 |  |  |  | QT-935 |  | QT-926 |  |  |  |  | N/A | HIGH | N/A | MEDIUM | N/A | HIGH
QT-102 | INCLUDED |  | Functional | Metering Changes | Smart | Linked Disconnection - Smart | Linked Disconnection | Same Day | Y |  | Y |  | Y |  | Y | 1 | 0 | 1 | 0 | 2 | 0 | QT-963 |  |  |  | QT-960 |  |  |  | QT-966 |  |  |  | QT-969 | MEDIUM | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-103 | INCLUDED |  | Functional | Metering Changes | Advanced | Linked Disconnection - Advanced | Linked Disconnection | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-950 |  |  |  | QT-946 |  | QT-954 |  |  |  |  | N/A | MEDIUM | N/A | MEDIUM | N/A | MEDIUM
QT-104 | INCLUDED |  | Functional | Metering Changes | Advanced/Smart | Advanced to Smart Market Segment Change | Change of Market Segment | Same Day | I | O | I | O | Y |  |  | 1 | 1 | 1 | 1 | 1 | 0 |  | QT-901 | QT-913 |  |  | QT-901 | QT-912 |  | QT-914 |  |  |  |  | MEDIUM | MEDIUM | MEDIUM | MEDIUM | N/A | HIGH
QT-105 | INCLUDED |  | Functional | Metering Changes | Smart/Advanced | Smart to Advanced Market Segment Change | Change of Market Segment | Same Day | O | I | O | I | Y |  |  | 1 | 1 | 1 | 1 | 1 | 0 | QT-908 |  |  | QT-902 | QT-905 |  |  | QT-902 | QT-910 |  |  |  |  | LOW | MEDIUM | LOW | MEDIUM | N/A | HIGH
QT-107 | INCLUDED |  | Functional | Metering Changes | Advanced | Advanced to Advanced Connection Type Change | Change of Connection Type/Market Segment Re-Evaluation | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 | [5 empty] | QT-914 |  |  |  |  | N/A | MEDIUM | N/A | MEDIUM | N/A | MEDIUM
QT-108 | INCLUDED |  | Functional | Metering Changes | Advanced | Advanced Change Of Supply where no Meter Service is appointed leading to advisory notifications to be sent | Advisory Notifications for missing Services and Invalid Market Segment | Forward Dated 3 working days |  | O |  | Y | I |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  |  | QT-901 |  |  |  | N/A | MEDIUM | N/A | MEDIUM | N/A | HIGH
QT-109 | INCLUDED |  | Functional | Metering Changes | Smart/Advanced | Smart to Advanced Connection Type Change W to LV Meter Exchange updates not sent Triggering Invalid Market Segment Advisory Notification | Advisory Notifications for missing Services and Invalid Market Segment | Same Day | O | I | O | I | Y |  |  | 1 | 1 | 1 | 1 | 1 | 0 | QT-908 |  |  | QT-902 | QT-905 |  |  | QT-902 | QT-910 |  |  |  |  | LOW | MEDIUM | LOW | MEDIUM | N/A | MEDIUM
QT-110 | INCLUDED |  | Functional | Metering Changes | Smart | Historic Meter Update Successful - Traditional | Historic Meter Update | Same Day | Y |  |  |  | Y |  |  | 1 | 0 | 0 | 0 | 1 | 0 | QT-917 |  |  |  | QT-916 |  |  |  | QT-918 |  |  |  |  | LOW | N/A | N/A | N/A | N/A | LOW
QT-111 | INCLUDED |  | Functional | Metering Changes | Smart | Historic Meter Update Rejected - Smart | Historic Meter Update | Same Day | Y |  |  |  | Y |  |  | 1 | 0 | 0 | 0 | 1 | 0 | QT-908 | [7 empty] | QT-910 |  |  |  |  | LOW | N/A | N/A | N/A | N/A | LOW
QT-112 | INCLUDED |  | Functional | Metering Changes | Advanced | Historic Meter Removal Successful - Advanced | Historic Meter Update | Same Day |  | Y |  |  | Y |  |  | 0 | 1 | 0 | 0 | 1 | 0 |  |  | QT-913 | [5 empty] | QT-914 |  |  |  |  | N/A | LOW | N/A | N/A | N/A | LOW
QT-113 | INCLUDED |  | Functional | Metering Changes | Smart | Historic Meter Removal Rejected - Traditional | Historic Meter Update | Same Day | Y |  |  |  | Y |  |  | 1 | 0 | 0 | 0 | 1 | 0 | QT-917 | [7 empty] | QT-918 |  |  |  |  | LOW | N/A | N/A | N/A | N/A | LOW
QT-114 | INCLUDED |  | Functional | Metering Changes | Smart | Historic Meter Addition Successful - Smart | Historic Meter Update | Same Day | Y |  |  |  | Y |  |  | 1 | 0 | 0 | 0 | 1 | 0 | QT-908 | [7 empty] | QT-910 |  |  |  |  | LOW | N/A | N/A | N/A | N/A | LOW
QT-115 | INCLUDED |  | Functional | Metering Changes | Smart | Historic Meter Addition Rejected - Traditional | Historic Meter Update | Same Day | Y |  |  |  | Y |  |  | 1 | 0 | 0 | 0 | 1 | 0 | QT-917 | [7 empty] | QT-918 |  |  |  |  | LOW | N/A | N/A | N/A | N/A | LOW
QT-116 | INCLUDED |  | Functional | Metering Changes | Smart | Traditional to Smart Meter Exchange | Meter Update - Install Remove Exchange | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-917 |  |  |  | QT-916 |  |  |  | QT-918 |  |  |  |  | MEDIUM | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-117 | INCLUDED |  | Functional | Metering Changes | Advanced | Advanced to Advanced Meter Exchange | Meter Update - Install Remove Exchange | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | MEDIUM | N/A | MEDIUM | N/A | MEDIUM
QT-118 | INCLUDED |  | Functional | Metering Changes | Smart | Traditional Removal and Smart Install | Meter Update - Install Remove Exchange | Same Day | Y | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | QT-917 | [12 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-119 | INCLUDED |  | Functional | Metering Changes | Smart | Traditional to Smart Meter Exchange | Meter Update Rejection | Same Day | Y |  |  |  | Y |  |  | 1 | 0 | 0 | 0 | 1 | 0 | QT-917 | [7 empty] | QT-918 |  |  |  |  | MEDIUM | N/A | N/A | N/A | N/A | MEDIUM
QT-120 | INCLUDED |  | Functional | Metering Changes | Smart | Smart to Smart Meter Exchange | Meter Update Rejection | Same Day | Y |  |  |  | Y |  |  | 1 | 0 | 0 | 0 | 1 | 0 | QT-908 | [7 empty] | QT-910 |  |  |  |  | MEDIUM | N/A | N/A | N/A | N/A | MEDIUM
QT-122 | INCLUDED |  | Functional | Metering Changes | Advanced | Advanced Install | Meter Update Rejection | Same Day |  | Y |  |  | Y |  |  | 0 | 1 | 0 | 0 | 1 | 0 |  |  | QT-913 | [5 empty] | QT-914 |  |  |  |  | N/A | MEDIUM | N/A | N/A | N/A | MEDIUM
QT-123 | INCLUDED |  | Functional | Metering Changes | Smart | Traditional Meter Removal | Meter Update Rejection | Same Day | Y |  |  |  | Y |  |  | 1 | 0 | 0 | 0 | 1 | 0 | QT-917 | [7 empty] | QT-918 |  |  |  |  | MEDIUM | N/A | N/A | N/A | N/A | MEDIUM
QT-124 | INCLUDED |  | Functional | Metering Changes | Advanced | Advanced Meter Removal | Meter Update Rejection | Same Day |  | Y |  |  | Y |  |  | 0 | 1 | 0 | 0 | 1 | 0 |  |  | QT-913 | [5 empty] | QT-914 |  |  |  |  | N/A | MEDIUM | N/A | N/A | N/A | MEDIUM
QT-125 | INCLUDED |  | Functional | Metering Changes | Smart | Smart Meter MAP Update Successful | MAP Id Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-126 | INCLUDED |  | Functional | Metering Changes | Advanced | Advanced Meter MAP Update Successful | MAP Id Update | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-127 | INCLUDED |  | Functional | Metering Changes | Smart | Smart Meter MAP Rejection | MAP Id Update Failure | Same Day | Y |  |  |  | Y |  |  | 1 | 0 | 0 | 0 | 1 | 0 | QT-908 | [7 empty] | QT-910 |  |  |  |  | LOW | N/A | N/A | N/A | N/A | LOW
QT-128 | INCLUDED |  | Functional | Change of Registration Data | Smart | MPL Address Update - Smart | Address Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-129 | INCLUDED |  | Functional | Change of Registration Data | Smart | MPL GSP Group ID Update - Traditional | GSP Group Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-917 |  |  |  | QT-916 |  |  |  | QT-918 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-130 | INCLUDED |  | Functional | Change of Registration Data | Advanced | MPL GSP Group ID Update - Advanced | GSP Group Update | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-131 | INCLUDED |  | Functional | Change of Registration Data | Unmetered | MPL GSP Group ID Update - Unmetered | GSP Group Update | Same Day |  |  |  |  | Y | Y |  | 0 | 0 | 0 | 0 | 1 | 1 | [8 empty] | QT-911 |  | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | LOW
QT-132 | INCLUDED |  | Functional | Change of Registration Data | Unmetered | MPL Address Update - Unmetered | Address Update | Same Day |  |  |  |  | Y | Y |  | 0 | 0 | 0 | 0 | 1 | 1 | [8 empty] | QT-911 |  | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | LOW
QT-133 | INCLUDED |  | Functional | Change of Registration Data | Smart | Consent Granularity - Smart Daily to HH Consent | Consent Granularity Update | Same Day |  |  | Y |  | Y |  |  | 0 | 0 | 1 | 0 | 1 | 0 |  |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | N/A | N/A | LOW | N/A | N/A | LOW
QT-134 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Consent Granularity - Advanced HH Consent to Monthly Reads Only | Consent Granularity Update | Same Day |  |  |  | Y | Y |  |  | 0 | 0 | 0 | 1 | 1 | 0 | [6 empty] | QT-912 |  | QT-914 |  |  |  |  | N/A | N/A | N/A | LOW | N/A | LOW
QT-135 | INCLUDED |  | Functional | Change of Registration Data | Smart | Update for Domestic Premise Indicator- Smart | Domestic Premises Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-136 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Update for Domestic Premise Indicator- Advanced | Domestic Premises Update | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-137 | INCLUDED |  | Functional | Change of Registration | Smart | Update for DUoS Tariff ID - Smart | Registration data update for DUoS Tariff ID | Same Day |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [8 empty] | QT-910 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | LOW
QT-138 | INCLUDED |  | Functional | Change of Registration Data | Smart | Related Removal - Smart | Related Metering Point Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-932 |  |  |  | QT-936 |  |  |  | QT-927 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-139 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Related Addition - Advanced | Related Metering Point Update | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-986 |  |  |  | QT-985 |  | QT-987 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-140 | INCLUDED |  | Functional | Change of Registration Data | Smart | Related Removal Rejection - Smart | Related Metering Point Update Rejection | Same Day |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [8 empty] | QT-927 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | LOW
QT-141 | INCLUDED |  | Functional | Change of Registration Data | Smart | Update Energy Direction Smart - Import > Export | Energy Direction Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-142 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Update Energy Direction Advanced - Export > Import | Energy Direction Update | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-145 | INCLUDED |  | Functional | Change of Registration Data | Smart | Update for SMSO Smart passes validation | SMSO Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-146 | INCLUDED |  | Functional | Change of Registration Data | Smart | Update for SMSO Smart fails validation | SMSO Update | Retro Dated -1 working days |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [8 empty] | QT-910 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | LOW
QT-147 | INCLUDED |  | Functional | Change of Registration Data | Smart | Registration Update IHD valid | IHD Update | Same Day |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [8 empty] | QT-910 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | LOW
QT-148 | INCLUDED |  | Functional | Change of Registration Data | Smart | Registration Update IHD not valid | IHD Update | Forward Dated 2 working days |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [8 empty] | QT-910 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | LOW
QT-149 | INCLUDED |  | Functional | Change of Registration Data | Smart | Import/Export Linkage Addition - Smart | Import / Export Association Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-885 |  |  |  | QT-883 |  |  |  | QT-888 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-150 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Import/Export Linkage Removal - Advanced | Import / Export Association Update | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-950 |  |  |  | QT-946 |  | QT-954 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-151 | INCLUDED |  | Functional | Change of Registration Data | Smart | Import/Export Linkage Addition different suppliers - Smart | Import / Export Association Update | Same Day | Y |  | Y |  | Y |  | Y | 1 | 0 | 1 | 0 | 2 | 0 | QT-895 |  |  |  | QT-893 |  |  |  | QT-897 |  |  |  | QT-899 | LOW | N/A | LOW | N/A | N/A | LOW
QT-152 | INCLUDED |  | Functional | Change of Registration Data | Smart | Import/Export Linkage Addition Rejection - Smart | Import / Export Association Update Rejection | Same Day |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [8 empty] | QT-888 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | LOW
QT-153 | INCLUDED |  | Functional | Change of Registration Data | Smart | Legacy Info Update - Traditional | Legacy Info Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-917 |  |  |  | QT-916 |  |  |  | QT-918 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-154 | INCLUDED |  | Functional | Change of Registration Data | Smart | Legacy Info Update - Smart | Legacy Info Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-155 | INCLUDED |  | Functional | Change of Registration Data | Smart | DCC Enrolment - Smart. Installed not Commissioned | DCC Enrolment Update | Same Day |  |  | Y |  | Y |  |  | 0 | 0 | 1 | 0 | 1 | 0 |  |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | N/A | N/A | LOW | N/A | N/A | LOW
QT-159 | INCLUDED |  | Functional | Consumption | Smart | Traditional Pre-RF validation fail | Amendment Invalid Data | Retro Dated -1 working days |  |  | Y |  | Y |  |  | 0 | 0 | 1 | 0 | 1 | 0 |  |  |  |  | QT-916 |  |  |  | QT-918 |  |  |  |  | N/A | N/A | LOW | N/A | N/A | LOW
QT-160 | INCLUDED |  | Functional | Consumption | Advanced | Advanced Pre-RF MPV validation fail | Amendment Invalid Data | Retro Dated -1 working days |  |  |  | Y | Y |  |  | 0 | 0 | 0 | 1 | 1 | 0 | [6 empty] | QT-912 |  | QT-914 |  |  |  |  | N/A | N/A | N/A | LOW | N/A | LOW
QT-162 | INCLUDED |  | Functional | Consumption | Advanced | Advanced Post-RF and Dispute Criteria met | Amendment Trading Dispute | Retro Dated -1 working days |  |  |  | Y | Y |  |  | 0 | 0 | 0 | 1 | 1 | 0 | [6 empty] | QT-912 |  | QT-914 |  |  |  |  | N/A | N/A | N/A | LOW | N/A | LOW
QT-168 | INCLUDED |  | Functional | Settlement | Smart | Smart Off-Peak E10 | Settlement impacted by IF-024 Supplier Advisory Notifications to Data Service | Forward Dated 2 working days |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [8 empty] | QT-971 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | LOW
QT-169 | INCLUDED |  | Functional | Settlement | Smart | Traditional LTV Expires | Settlement impacted by IF-024 Supplier Advisory Notifications to Data Service | Same Day |  |  | Y |  | Y |  |  | 0 | 0 | 1 | 0 | 1 | 0 |  |  |  |  | QT-916 |  |  |  | QT-918 |  |  |  |  | N/A | N/A | LOW | N/A | N/A | LOW
QT-170 | INCLUDED |  | Functional | Settlement | Advanced | Advanced LTV Expires | Settlement impacted by IF-024 Supplier Advisory Notifications to Data Service | Same Day |  |  |  | Y | Y |  |  | 0 | 0 | 0 | 1 | 1 | 0 | [6 empty] | QT-912 |  | QT-914 |  |  |  |  | N/A | N/A | N/A | LOW | N/A | LOW
QT-171 | INCLUDED |  | Functional | Settlement | Smart | Smart Cons Amend | Settlement impacted by Override Readings and Consumption Amendment | Same Day |  |  | Y |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | QT-905 | [8 empty] | N/A | N/A | LOW | N/A | N/A | N/A
QT-174 | INCLUDED |  | Functional | Settlement | Advanced | Advanced LS Default | Consumption for LSS Rejection and Default | Same Day |  |  |  | Y | Y |  |  | 0 | 0 | 0 | 1 | 1 | 0 | [6 empty] | QT-912 |  | QT-914 |  |  |  |  | N/A | N/A | N/A | MEDIUM | N/A | MEDIUM
QT-176 | INCLUDED |  | Functional | Change of Supplier | Advanced | Change Linked To Different Suppliers - Advanced Export | Import / Export CoS covering agent appointments with different supplier | Forward Dated 3 working days |  | Y* |  | Y* | Y* |  | Y | 0 | 2 | 0 | 2 | 3 | 0 |  |  | QT-962 | QT-956 |  |  | QT-959 | QT-956 | QT-965 | QT-956 |  |  | QT-968 | N/A | MEDIUM | N/A | MEDIUM | N/A | HIGH
QT-177 | INCLUDED |  | Functional | Change of Supplier | Advanced | Change of Supplier and DS. No change of MS - Advanced | Single MPAN end to end covering: Switch Request to CSS (Supplier only so could start later for MOA / DS) Agent Appointment (including MTD transfer) Transfer Read Settlement Calender | Forward Dated 3 working days |  | Y |  | Y* | Y* |  |  | 0 | 1 | 0 | 2 | 2 | 0 |  |  | QT-913 | QT-901 |  |  | QT-912 | QT-901 | QT-914 | QT-901 |  |  |  | N/A | HIGH | N/A | MEDIUM | N/A | HIGH
QT-178 | INCLUDED |  | Functional | Change of Supplier | Smart | Change of Supplier. MS and DS - Smart Import/Export | Import / Export CoS covering agent appointments | Forward Dated 2 working days | Y* |  | Y* |  | Y* |  |  | 2 | 0 | 2 | 0 | 2 | 0 | QT-948 | QT-939 |  |  | QT-944 | QT-939 |  |  | QT-952 | QT-939 |  |  |  | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-179 | INCLUDED |  | Functional | Change of Supplier | Smart | Change of Supplier. MS and DS - Traditional Import/Export | Import / Export CoS covering agent appointments | Forward Dated 2 working days | Y* |  | Y* |  | Y* |  |  | 2 | 0 | 2 | 0 | 2 | 0 | QT-964 | QT-958 |  |  | QT-961 | QT-958 |  |  | QT-967 | QT-958 |  |  |  | HIGH | N/A | HIGH | N/A | N/A | HIGH
QT-180 | INCLUDED |  | Functional | Change of Supplier | Advanced | Change of Supplier. MS and DS - Advanced Related | Related CoS covering agent appointments | Forward Dated 3 working days |  | Y* |  | Y* | Y* |  |  | 0 | 2 | 0 | 2 | 2 | 0 |  |  | QT-978 | QT-976 |  |  | QT-977 | QT-976 | QT-979 | QT-976 |  |  |  | N/A | HIGH | N/A | HIGH | N/A | HIGH
QT-181 | INCLUDED |  | Functional | Change of Supplier | Smart | Change of Supplier. MS and DS - Smart Related | Related CoS covering agent appointments | Forward Dated 2 working days | Y* |  | Y* |  | Y* |  |  | 2 | 0 | 2 | 0 | 2 | 0 | QT-990 | QT-988 |  |  | QT-989 | QT-988 |  |  | QT-991 | QT-988 |  |  |  | HIGH | N/A | HIGH | N/A | N/A | HIGH
QT-182 | INCLUDED |  | Functional | Change of Supplier | Unmetered | Change Lapsed Appointments - Unmetered | Appointment lapsed due to secured active not being received | Forward Dated 3 working days |  |  |  |  | Y | Y |  | 0 | 0 | 0 | 0 | 1 | 1 | [8 empty] | QT-911 |  | QT-906 |  |  | N/A | N/A | N/A | N/A | MEDIUM | MEDIUM
QT-183 | INCLUDED |  | Functional | New Connection | Smart | New Connection - Smart | End to end covering: New connection Initial Registration Agent appointment Energisation and Meter Install (single rate credit meter) | Next Day 1 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-185 | INCLUDED |  | Functional | Change of Metering Service | Advanced | Change of MS and DS followed by Change of Existing Appointment - Advanced | Change of MS and DS followed by Change of Existing Appointment | Forward Dated 3 working days |  | Y* |  |  | Y |  |  | 0 | 2 | 0 | 0 | 1 | 0 |  |  | QT-913 | QT-901 |  |  |  |  | QT-914 |  |  |  |  | N/A | HIGH | N/A | N/A | N/A | HIGH
QT-186 | INCLUDED |  | Functional | Metering Changes | Advanced | Advanced Credit MS Energisation | Change of Energisation Status | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | MEDIUM | N/A | MEDIUM | N/A | MEDIUM
QT-187 | INCLUDED |  | Functional | Metering Changes | Smart | Smart LDSO Energisation | Change of Energisation Status | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | MEDIUM | N/A | LOW | N/A | N/A | LOW
QT-188 | INCLUDED |  | Functional | Metering Changes | Advanced | Energisation REGS Rejection (REG1002) - Advanced | Change of Energisation Status Rejection by Registration Service | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-189 | INCLUDED |  | Functional | Metering Changes | Smart | Energisation REGS Rejection (REC1019) - Smart | Change of Energisation Status Rejection by Registration Service | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | MEDIUM | N/A | LOW | N/A | N/A | LOW
QT-190 | INCLUDED |  | Functional | Metering Changes | Advanced | MS Failure - Unable to Action - Advanced | Change of Energisation Status Rejection by MOA | Same Day |  | Y |  |  | Y |  |  | 0 | 1 | 0 | 0 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | N/A | N/A | LOW
QT-191 | INCLUDED |  | Functional | Metering Changes | Smart | Linked Disconnection - Traditional | Linked Disconnection | Same Day | Y |  | Y |  | Y |  | Y | 1 | 0 | 1 | 0 | 2 | 0 | QT-964 |  |  |  | QT-961 |  |  |  | QT-967 |  |  |  | QT-970 | MEDIUM | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-192 | INCLUDED |  | Functional | Metering Changes | Advanced/Smart | Advanced to Smart Connection Type Change LV to W Meter Exchange updates not sent Triggering Invalid Market Segment Advisory Notification | Receipt of invalid Market Segment | Same Day | I | O | I | O | Y |  |  | 1 | 1 | 1 | 1 | 1 | 0 |  | QT-901 | QT-913 |  |  | QT-901 | QT-912 |  | QT-914 |  |  |  |  | MEDIUM | LOW | LOW | LOW | N/A | MEDIUM
QT-193 | INCLUDED |  | Functional | Metering Changes | Advanced | Historic Meter Removal Rejected - Advanced | Historic Meter Update | Same Day |  | Y |  |  | Y |  |  | 0 | 1 | 0 | 0 | 1 | 0 |  |  | QT-913 | [5 empty] | QT-914 |  |  |  |  | N/A | LOW | N/A | N/A | N/A | LOW
QT-194 | INCLUDED |  | Functional | Metering Changes | Advanced | Advanced Meter MAP Rejection | MAP Id Update Failure | Same Day |  | Y |  |  | Y |  |  | 0 | 1 | 0 | 0 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | N/A | N/A | LOW
QT-195 | INCLUDED |  | Functional | Change of Registration Data | Advanced | MPL Address Update - Advanced | Address Update | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-196 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Related Removal - Advanced | Related Metering Point Update | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-931 |  |  |  | QT-935 |  | QT-926 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-197 | INCLUDED |  | Functional | Change of Registration Data | Smart | Related Addition - Smart | Related Metering Point Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-994 |  |  |  | QT-993 |  |  |  | QT-995 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-198 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Import/Export Linkage Addition - Advanced | Import / Export Association Update | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-887 |  |  |  | QT-884 |  | QT-889 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-199 | INCLUDED |  | Functional | Change of Registration Data | Smart | Import/Export Linkage Removal - Smart | Import / Export Association Update | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-948 |  |  |  | QT-944 |  |  |  | QT-952 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-200 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Import/Export Linkage Addition different suppliers - Advanced | Import / Export Association Update | Same Day |  | Y |  | Y | Y |  | Y | 0 | 1 | 0 | 1 | 2 | 0 |  |  | QT-894 |  |  |  | QT-892 |  | QT-896 |  |  |  | QT-898 | N/A | LOW | N/A | LOW | N/A | LOW
QT-201 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Legacy Info Update - Advanced | Legacy Info Update | Same Day |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-202 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Advanced | Advanced NHH Legacy to MHHS Forward Migration CoA (Import/Export) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Next Day 1 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | HIGH | N/A | HIGH | N/A | HIGH
QT-203 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Advanced | Advanced HH Legacy to MHHS Forward Migration CoA (Import/Export) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Next Day 1 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | HIGH | N/A | HIGH | N/A | HIGH
QT-204 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Smart | Smart NHH Legacy to MHHS Forward Migration CoA (Import/Export) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Next Day 1 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | HIGH | N/A | N/A | HIGH
QT-205 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Smart | Smart HH Legacy to MHHS Forward Migration CoA (Import/Export) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Next Day 1 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | HIGH | N/A | N/A | HIGH
QT-206 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | Traditional Legacy to MHHS Forward Migration CoA | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Next Day 1 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-207 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | Advanced NHH Legacy to MHHS Forward Migration CoA | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Next Day 1 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | MEDIUM | N/A | MEDIUM | N/A | MEDIUM
QT-208 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | Advanced HH Legacy to MHHS Forward Migration CoA | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Next Day 1 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | MEDIUM | N/A | MEDIUM | N/A | MEDIUM
QT-209 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | Smart NHH Legacy to MHHS Forward Migration CoA | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Next Day 1 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-210 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | Smart HH Legacy to MHHS Forward Migration CoA | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Next Day 1 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-211 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Smart | Traditional Legacy to MHHS Forward Migration CoA (Related) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Next Day 1 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | HIGH | N/A | HIGH | N/A | N/A | HIGH
QT-212 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Advanced | Advanced NHH Legacy to MHHS Forward Migration CoA (Related) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Next Day 1 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | HIGH | N/A | MEDIUM | N/A | HIGH
QT-213 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Advanced | Advanced HH Legacy to MHHS Forward Migration CoA (Related) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Next Day 1 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | HIGH | N/A | MEDIUM | N/A | HIGH
QT-214 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Smart | Smart NHH Legacy to MHHS Forward Migration CoA (Related) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Next Day 1 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-215 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Smart | Smart HH Legacy to MHHS Forward Migration CoA (Related) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Next Day 1 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-216 | INCLUDED |  | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) - Unmetered | Unmetered | Unmetered Legacy to MHHS Forward Migration CoA | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) - Unmetered | Next Day 1 working days |  |  |  |  | Y | Y |  | 0 | 0 | 0 | 0 | 1 | 1 | [13 empty] | N/A | N/A | N/A | N/A | MEDIUM | MEDIUM
QT-217 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Import/Export MPANs | Advanced | Advanced NHH Legacy to MHHS Forward Migration CoS (Import/Export) | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 3 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | HIGH | N/A | HIGH | N/A | HIGH
QT-218 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Import/Export MPANs | Advanced | Advanced HH Legacy to MHHS Forward Migration CoS (Import/Export) | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 3 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | HIGH | N/A | HIGH | N/A | HIGH
QT-219 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Import/Export MPANs | Smart | Smart NHH Legacy to MHHS Forward Migration CoS (Import/Export) | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | HIGH | N/A | HIGH | N/A | N/A | HIGH
QT-220 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Import/Export MPANs | Smart | Smart HH Legacy to MHHS Forward Migration CoS (Import/Export) | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | HIGH | N/A | HIGH | N/A | N/A | HIGH
QT-221 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | Traditional Legacy to MHHS Forward Migration CoS | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | HIGH | N/A | MEDIUM | N/A | N/A | HIGH
QT-222 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | Advanced NHH Legacy to MHHS Forward Migration CoS | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 3 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | MEDIUM | N/A | MEDIUM | N/A | HIGH
QT-223 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | Advanced HH Legacy to MHHS Forward Migration CoS | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 3 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | MEDIUM | N/A | MEDIUM | N/A | HIGH
QT-224 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | Smart NHH Legacy to MHHS Forward Migration CoS | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-225 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | Smart HH Legacy to MHHS Forward Migration CoS | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-226 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Linked Related MPANs | Smart | Traditional Legacy to MHHS Forward Migration CoS (Related) | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | HIGH | N/A | HIGH | N/A | N/A | HIGH
QT-227 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Linked Related MPANs | Advanced | Advanced NHH Legacy to MHHS Forward Migration CoS (Related) | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 3 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | HIGH | N/A | MEDIUM | N/A | HIGH
QT-228 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Linked Related MPANs | Advanced | Advanced HH Legacy to MHHS Forward Migration CoS (Related) | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 3 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 | [13 empty] | N/A | HIGH | N/A | HIGH | N/A | HIGH
QT-229 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Linked Related MPANs | Smart | Smart NHH Legacy to MHHS Forward Migration CoS (Related) | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-230 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Linked Related MPANs | Smart | Smart HH Legacy to MHHS Forward Migration CoS (Related) | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier and Agents (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | [13 empty] | MEDIUM | N/A | MEDIUM | N/A | N/A | HIGH
QT-231 | INCLUDED |  | Migration | Forward Migration CoS - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Supplier with Change of Services (Metering Service + Data Service) - Unmetered | Unmetered | Unmetered Legacy to MHHS Forward Migration CoS | Forward Migration CoS - Legacy MPAN CoS to a MHHS Qualified Supplier - Change of Supplier with Change of Services (Metering Service + Data Service) - Unmetered | Forward Dated 3 working days |  |  |  |  | Y | Y |  | 0 | 0 | 0 | 0 | 1 | 1 | [13 empty] | N/A | N/A | N/A | N/A | MEDIUM | MEDIUM
QT-232 | INCLUDED |  | Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Smart | Smart MHHS to Legacy Reverse Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-908 |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | MEDIUM
QT-233 | INCLUDED |  | Migration | Reverse Migration CoS of Import/Export or Related MHHS MPANs to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Smart | Traditional MHHS to Legacy Reverse Migration (Import/Export) | Reverse Migration CoS of Import/Export or Related MHHS MPANs to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-949 |  |  |  | QT-945 |  |  |  | QT-953 |  |  |  |  | LOW | N/A | MEDIUM | N/A | N/A | HIGH
QT-234 | INCLUDED |  | Migration | Reverse Migration CoS of Import/Export or Related MHHS MPANs to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Advanced | Advanced MHHS to Legacy Reverse Migration (Import/Export) | Reverse Migration CoS of Import/Export or Related MHHS MPANs to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Forward Dated 2 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-950 |  |  |  | QT-946 |  | QT-954 |  |  |  |  | N/A | MEDIUM | N/A | LOW | N/A | MEDIUM
QT-235 | INCLUDED |  | Migration | Reverse Migration CoS of Import/Export or Related MHHS MPANs to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Smart | Smart MHHS to Legacy Reverse Migration (Import/Export) | Reverse Migration CoS of Import/Export or Related MHHS MPANs to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-948 |  |  |  | QT-944 |  |  |  | QT-952 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | MEDIUM
QT-236 | INCLUDED |  | Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Smart | Traditional MHHS to Legacy Reverse Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-917 |  |  |  | QT-916 |  |  |  | QT-918 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | MEDIUM
QT-237 | INCLUDED |  | Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Advanced | Advanced MHHS to Legacy Reverse Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Forward Dated 2 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-913 |  |  |  | QT-912 |  | QT-914 |  |  |  |  | N/A | LOW | N/A | LOW | N/A | MEDIUM
QT-238 | INCLUDED |  | Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) - Related MPAN | Smart | Traditional MHHS to Legacy Reverse Migration (Related) | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) - Related MPAN | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-933 |  |  |  | QT-937 |  |  |  | QT-929 |  |  |  |  | LOW | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-239 | INCLUDED |  | Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) - Related MPAN | Advanced | Advanced MHHS to Legacy Reverse Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) - Related MPAN | Forward Dated 2 working days |  | Y |  | Y | Y |  |  | 0 | 1 | 0 | 1 | 1 | 0 |  |  | QT-931 |  |  |  | QT-935 | QT-921 | QT-926 |  |  |  |  | N/A | MEDIUM | N/A | LOW | N/A | MEDIUM
QT-240 | INCLUDED |  | Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) - Related MPAN | Smart | Smart MHHS to Legacy Reverse Migration (Related) | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) - Related MPAN | Forward Dated 2 working days | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-932 |  |  |  | QT-936 |  |  |  | QT-927 |  |  |  |  | LOW | N/A | LOW | N/A | N/A | MEDIUM
QT-241 | INCLUDED |  | Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) - Related MPAN | Unmetered | Unmetered MHHS to Legacy Reverse Migration | Reverse Migration CoS - MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN). This includes a Change of Services (Metering Service + Data Service) | Next Day 1 working days |  |  |  |  | Y | Y |  | 0 | 0 | 0 | 0 | 1 | 1 | [8 empty] | QT-911 |  | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | MEDIUM
QT-242 | INCLUDED |  | Functional | Consumption | Smart | SDS Estimation - Adj Cons Amd Method 0 - Export | SDS Estimation | Same Day |  |  | Y |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | QT-905 | [8 empty] | N/A | N/A | LOW | N/A | N/A | N/A
QT-243 | INCLUDED |  | Functional | Consumption | Advanced | Modern Advanced Meter Periodic MAR Check fails - Export | ADS Meter Advance Reconcillation | Same Day |  |  |  | Y |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | QT-912 | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-244 | INCLUDED |  | Functional | Consumption | Advanced | Advanced Meter with Check Meter Periodic MAR Check fails - Export | ADS Meter Advance Reconcillation | Same Day |  |  |  | Y |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | QT-943 | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-251 | INCLUDED |  | Functional | Metering Changes | Advanced | Advanced Meter Removal and Advanced Meter Install | Meter Update - Install Remove Exchange | Same Day |  | Y | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 |  |  | QT-913 | [10 empty] | N/A | HIGH | N/A | N/A | N/A | N/A
QT-252 | INCLUDED |  | Functional | Change of Registration Data | Smart | Change of Customer Appointment - Metering Services Smart Reject | Change of Customer Appointment MS | Same Day | Y | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | QT-908 | [12 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-253 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Change of Customer Appointment - Metering Services Advanced Reject | Change of Customer Appointment MS | Same Day |  | Y | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 |  |  | QT-913 | [10 empty] | N/A | LOW | N/A | N/A | N/A | N/A
QT-254 | INCLUDED |  | Functional | Change of Registration Data | Smart | Change of Customer Appointment - Metering Services Smart Remove CDC | Change of Customer Appointment MS | Same Day | Y | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | QT-908 | [12 empty] | LOW | N/A | N/A | N/A | N/A | N/A
QT-255 | INCLUDED |  | Functional | Change of Registration Data | Advanced | Change of Customer Appointment - Metering Services Advanced Remove CDC | Change of Customer Appointment MS | Same Day |  | Y | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 |  |  | QT-913 | [10 empty] | N/A | LOW | N/A | N/A | N/A | N/A
QT-257 | INCLUDED |  | Functional | Change of Registration | Smart | Change of Customer Appointment - Smart Remove CDC | Change of Customer Appointment DS | Same Day |  |  | Y |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | QT-905 | [8 empty] | N/A | N/A | LOW | N/A | N/A | N/A
QT-258 | INCLUDED |  | Functional | Metering Changes | Smart | Traditional Prepay MS Energisation | Change of Energisation Status | Same Day | Y |  | Y |  | Y |  |  | 1 | 0 | 1 | 0 | 1 | 0 | QT-917 |  |  |  | QT-916 |  |  |  | QT-918 |  |  |  |  | MEDIUM | N/A | MEDIUM | N/A | N/A | MEDIUM
QT-259 | INCLUDED |  | Functional | Consumption | Unmetered | Inventory with Load (Dynamic) using PECU Array Data Unmetered MPAN with Inventory and Load (Dynamic) using PECU Array Data | UMSDS Consumption Data Calculation and Estimation | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-906 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-260 | INCLUDED |  | Functional | Metering Changes | Smart | Smart Disconnection/Reconnection | End to end covering: Disconnection leading to IF009 Registration de-activation Auto de-appointment of agents | Same Day |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [8 empty] | QT-996 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | LOW
QT-267 | INCLUDED |  | Functional | Change of Registration | Advanced | SITFTS-0180 TC08 Advanced Remove CDC | Change of Customer Appointment DS | Same Day |  |  |  | Y |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [6 empty] | QT-912 | [6 empty] | N/A | N/A | N/A | LOW | N/A | N/A
QT-268 | INCLUDED |  | Functional | Change of Registration Data | Smart | SITFTS-1000 TC04 Traditional, linkage addition MS Alignment | Import / Export Association Update | Same Day | Y | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | QT-886 | [12 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-269 | INCLUDED |  | Functional | Consumption | Smart | SITFTS-1090 TC03 Override Read Submission Smart | Amendment Invalid Data | Same Day |  |  | Y |  | Y |  |  | 0 | 0 | 1 | 0 | 1 | 0 |  |  |  |  | QT-905 |  |  |  | QT-910 |  |  |  |  | N/A | N/A | LOW | N/A | N/A | LOW
QT-270 | INCLUDED |  | Functional | Consumption | Advanced | SITFTS-1090 TC04 Override Read Submission Advanced | Amendment Invalid Data | Same Day |  |  |  | Y | Y |  |  | 0 | 0 | 0 | 1 | 1 | 0 | [6 empty] | QT-912 |  | QT-914 |  |  |  |  | N/A | N/A | N/A | LOW | N/A | LOW
QT-272 | INCLUDED |  | Functional | Consumption | Advanced | SITFTS-1095 TC04 Advanced Pre-RF and Dispute Criteria met | Amendment Trading Dispute | Same Day |  |  |  | Y | Y |  |  | 0 | 0 | 0 | 1 | 1 | 0 | [6 empty] | QT-912 |  | QT-914 |  |  |  |  | N/A | N/A | N/A | LOW | N/A | LOW
QT-274 | INCLUDED |  | Functional | Reporting | Advanced | Settlement Reports from MDS/VAS/LDSO | Settlement Reports from MDS/VAS/LDSO | Same Day |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [13 empty] | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-275 | INCLUDED |  | Functional | Consumption | Unmetered | UMSDS Load Shapes | UMSDS Load Shapes | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-920 |  |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-276 | INCLUDED |  | Functional | Consumption | Advanced | Advanced Meter where Check Meter data is missing (Reactive Power) | Advanced Meter where Check Meter data is missing (Reactive Power) | Same Day |  |  |  | Y | Y |  |  | 0 | 0 | 0 | 1 | 1 | 0 | [6 empty] | QT-974 |  | QT-975 |  |  |  |  | N/A | N/A | N/A | LOW | N/A | LOW
QT-277 | INCLUDED |  | Functional | Consumption | Unmetered | UMSDS default consumption data and annual consumption receipt | UMSDS default consumption data and annual consumption receipt | Same Day | [5 empty] | Y |  | 0 | 0 | 0 | 0 | 0 | 1 | [10 empty] | QT-906 |  |  | N/A | N/A | N/A | N/A | MEDIUM | N/A
QT-278 | INCLUDED |  | Functional | Consumption | Smart | SDS default consumption data and annual consumption receipt | SDS default consumption data and annual consumption receipt | Same Day |  |  | Y |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | QT-905 | [8 empty] | N/A | N/A | LOW | N/A | N/A | N/A
QT-279 | INCLUDED |  | Functional | Metering Changes | Advanced | Advanced Disconnection/Reconnection | End to end covering: Disconnection leading to IF009 Registration de-activation Auto de-appointment of agents | Same Day |  |  |  |  | Y |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [8 empty] | QT-997 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A

## Prerequisite Tests (800-900)
Test ID | Test Details | [5 empty] | Role Requirements | [6 empty] | QTC Scale (t-shirt size)
QT Case ID | QT Test Type | Scope Theme | Segment | QT Test Case Title | QT Scenario | Effective Time | MSS | MSA | SDS | ADS | SUP | UMSDS | Supplier Linked | MSS | MSA | SDS | ADS | UMSDS | SUP
QT-880 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | DIP Seed Smart 2 Singles Pre-req for Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Retro Dated -5 working days | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-881 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | DIP Seed Traditional 2 Singles Pre-req for Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-882 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Advanced | DIP Seed Advanced 2 Singles Pre-req for Linked HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Retro Dated -5 working days | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-883 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Smart | SDS QP Smart 2 Singles Pre-req for Linked | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | N/A
QT-884 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Advanced | ADS QP Advanced 2 Singles Pre-req for Linked HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days |  |  |  | Y |  |  |  | N/A | N/A | N/A | MEDIUM | N/A | N/A
QT-885 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Smart | MSS QP Smart 2 Singles Pre-req for Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days | Y | [6 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-886 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | MSS QP Traditional 2 Singles Pre-req for Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | Y | [6 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-887 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Advanced | MSA QP Advanced 2 Singles Pre-req for Linked HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days |  | Y | [5 empty] | N/A | MEDIUM | N/A | N/A | N/A | N/A
QT-888 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Smart | SUP QP Smart 2 Singles Pre-req for Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-889 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Advanced | SUP QP Advanced 2 Singles Pre-req for Linked HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-890 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | DIP Seed Advanced 2 Singles Pre-req for Linked HH diff Suppliers, SUPI/C/O Import, SUPL Export | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-891 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | DIP Seed Smart 2 Singles Pre-req for Linked NHH diff Suppliers, SUPI/C/O Export, SUPL Import | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-892 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | ADS QP Advanced 2 Singles Pre-req for Linked HH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  | Y |  |  |  | N/A | N/A | N/A | MEDIUM | N/A | N/A
QT-893 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SDS QP Smart 2 Singles Pre-req for Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | N/A
QT-894 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | MSA QP Advanced 2 Singles Pre-req for Linked HH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  | Y | [5 empty] | N/A | MEDIUM | N/A | N/A | N/A | N/A
QT-895 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | MSS QP Smart 2 Singles Pre-req for Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | Y | [6 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-896 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | SUP QP Advanced 2 Singles Pre-req for Linked HH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-897 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SUP QP Smart 2 Singles Pre-req for Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-898 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | SUP QP Advanced 2 Singles Pre-req for Linked HH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | [6 empty] | Y | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-899 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SUP QP Smart 2 Singles Pre-req for Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | [6 empty] | Y | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-901 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | DIP Seed Advanced Single | Advanced Single - Appoint all stubs | Retro Dated -5 working days | I | I | I | I | I |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-902 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | DIP Seed Smart Single | Smart Single - Appoint all stubs | Retro Dated -5 working days | I | I | I | I | I |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-903 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Unmetered | DIP Seed Unmetered Single (always HH) | Unmetered Single - Appoint all stubs | Retro Dated -5 working days | [5 empty] | I |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-904 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | ADS QP Advanced Single NHH | Advanced Single NHH - Appoint DS QP and remainder stubs | Forward Dated 1 working days |  |  |  | Y |  |  |  | N/A | N/A | N/A | LOW | N/A | N/A
QT-905 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SDS QP Smart Single HH | Smart Single - Appoint DS QP and remainder stubs | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | LOW | N/A | N/A | N/A
QT-906 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Unmetered | UMSDS QP Unmetered Single non-CMS (always HH) | Unmetered Single - Appoint DS QP and remainder stubs | Forward Dated 1 working days | [5 empty] | Y |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-907 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | MSA QP Advanced Single NHH | Advanced Single NHH - Appoint MS QP and remainder stubs | Forward Dated 1 working days |  | Y | [5 empty] | N/A | MEDIUM | N/A | N/A | N/A | N/A
QT-908 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | MSS QP Smart Single HH | Smart Single - Appoint MS QP and remainder stubs | Forward Dated 1 working days | Y | [6 empty] | LOW | N/A | N/A | N/A | N/A | N/A
QT-909 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | SUP QP Advanced Single NHH | Advanced Single NHH - Appoint SUP QP and remainder stubs | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-910 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SUP QP Smart Single NHH | Smart Single NHH - Appoint SUP QP and remainder stubs | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-911 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Unmetered | SUP QP Unmetered Single (always HH) | Unmetered Single - Appoint SUP QP and remainder stubs | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-912 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | ADS QP Advanced Single HH | Advanced Single HH - Appoint DS QP and remainder stubs | Forward Dated 1 working days |  |  |  | Y |  |  |  | N/A | N/A | N/A | LOW | N/A | N/A
QT-913 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | MSA QP Advanced Single HH | Advanced Single HH - Appoint MS QP and remainder stubs | Forward Dated 1 working days |  | Y | [5 empty] | N/A | MEDIUM | N/A | N/A | N/A | N/A
QT-914 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | SUP QP Advanced Single HH | Advanced Single HH - Appoint SUP QP and remainder stubs | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-915 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Unmetered | UMSDS QP Unmetered Single CMS (always HH) | Unmetered Single - Appoint DS QP and remainder stubs | Forward Dated 1 working days | [5 empty] | Y |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-916 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SDS QP Traditional Single (always NHH) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | LOW | N/A | N/A | N/A
QT-917 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | MSS QP Traditional Single (always NHH) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | Y | [6 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-918 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SUP QP Traditional Single (always NHH) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-919 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | DIP Seed Traditional Single (always NHH) | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days | I |  | I |  | I |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-920 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Unmetered | UMSDS QP Unmetered Single non-CMS (always HH) no inventory | Unmetered Single - Appoint DS QP and remainder stubs, no inventory | Forward Dated 1 working days | [5 empty] | Y |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-921 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Advanced | DIP Seed Advanced Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Retro Dated -5 working days |  | I |  | I |  |  |  | N/A | LOW | N/A | LOW | N/A | N/A
QT-922 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Smart | DIP Seed Smart Related NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Retro Dated -5 working days | I |  | I |  |  |  |  | LOW | N/A | LOW | N/A | N/A | N/A
QT-924 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Traditional | DIP Seed Traditional Related NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Retro Dated -5 working days |  |  | I |  | I |  |  | N/A | N/A | LOW | N/A | N/A | LOW
QT-926 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Advanced | SUP QP Advanced Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-927 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Smart | SUP QP Smart Related NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-929 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Traditional | SUP QP Traditional Related NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-931 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Advanced | MSA QP Advanced Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 1 working days |  | Y | [5 empty] | N/A | MEDIUM | N/A | N/A | N/A | N/A
QT-932 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Smart | MSS QP Smart Related NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 1 working days | Y | [6 empty] | LOW | N/A | N/A | N/A | N/A | N/A
QT-933 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Traditional | MSS QP Traditional Related NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 1 working days | Y | [6 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-935 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Advanced | ADS QP Advanced Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 1 working days |  |  |  | Y |  |  |  | N/A | N/A | N/A | LOW | N/A | N/A
QT-936 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Smart | SDS QP Smart Related NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | N/A
QT-937 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Traditional | SDS QP Traditional Related NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | N/A
QT-939 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | DIP Seed Smart Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Retro Dated -5 working days | I |  | I |  | I |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-940 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | DIP Seed Traditional Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days | I |  | I |  |  |  |  | LOW | N/A | LOW | N/A | N/A | N/A
QT-941 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Advanced | DIP Seed Advanced Linked HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Retro Dated -5 working days |  | I |  | I | I |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-942 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | DIP Seed Advanced Single 2 meters | Advanced Single - Appoint all stubs | Retro Dated -5 working days | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-943 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | ADS QP Advanced Single HH 2 meters | Advanced Single HH - Appoint DS QP and remainder stubs | Forward Dated 1 working days |  |  |  | Y |  |  |  | N/A | N/A | N/A | LOW | N/A | N/A
QT-944 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Smart | SDS QP Smart Linked | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | N/A
QT-945 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | SDS QP Traditional Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | N/A
QT-946 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Advanced | ADS QP Advanced Linked HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days |  |  |  | Y |  |  |  | N/A | N/A | N/A | MEDIUM | N/A | N/A
QT-948 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Smart | MSS QP Smart Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days | Y | [6 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-949 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | MSS QP Traditional Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | Y | [6 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-950 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Advanced | MSA QP Advanced Linked HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days |  | Y | [5 empty] | N/A | MEDIUM | N/A | N/A | N/A | N/A
QT-952 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Smart | SUP QP Smart Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-953 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | SUP QP Traditional Linked NHH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-954 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Advanced | SUP QP Advanced Linked HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Import/Export MPANs | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-956 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | DIP Seed Advanced Linked HH diff Suppliers, SUPI/C/O Import, SUPL Export | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days |  | I |  | I | I |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-957 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | DIP Seed Smart Linked NHH diff Suppliers, SUPI/C/O Export, SUPL Import | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days | I |  | I |  | I |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-958 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | DIP Seed Traditional Linked NHH diff Suppliers, SUPI/C/O Export, SUPL Import | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days | I |  | I |  | I |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-959 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | ADS QP Advanced Linked HH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  | Y |  |  |  | N/A | N/A | N/A | MEDIUM | N/A | N/A
QT-960 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SDS QP Smart Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | N/A
QT-961 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | SDS QP Traditional Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | N/A
QT-962 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | MSA QP Advanced Linked HH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  | Y | [5 empty] | N/A | MEDIUM | N/A | N/A | N/A | N/A
QT-963 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | MSS QP Smart Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | Y | [6 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-964 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | MSS QP Traditional Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | Y | [6 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-965 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | SUP QP Advanced Linked HH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-966 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SUP QP Smart Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-967 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | SUP QP Traditional Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-968 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | SUP QP Advanced Linked HH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-969 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SUP QP Smart Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | [6 empty] | Y | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-970 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | SUP QP Traditional Linked NHH diff Suppliers | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | [6 empty] | Y | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-971 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) 2 rate meter | Smart | SUP QP Smart Single NHH 2 rate meter | Smart Single NHH - Appoint SUP QP and remainder stubs 2 rate meter | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-972 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) 2 rate meter | Smart | SDS QP Traditional Single (always NHH) 2 rate meter | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) 2 rate meter | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | LOW | N/A | N/A | N/A
QT-973 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) 2 rate meter | Smart | SUP QP Traditional Single (always NHH) 2 rate meter | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) 2 rate meter | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-974 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) RI register | Advanced | ADS QP Advanced Single HH 2 meters RI register | Advanced Single HH - Appoint DS QP and remainder stubs RI register | Forward Dated 1 working days |  |  |  | Y |  |  |  | N/A | N/A | N/A | LOW | N/A | N/A
QT-975 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) RI register | Advanced | SUP QP Advanced Single HH 2 meters RI register | Advanced Single HH - Appoint SUP QP and remainder stubs RI register | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-976 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | DIP Seed Advanced Related HH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days |  | I |  | I | I |  |  | N/A | LOW | N/A | LOW | N/A | LOW
QT-977 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Advanced | ADS QP Advanced Related HH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) for Linked Related MPANs | Forward Dated 1 working days |  |  |  | Y |  |  |  | N/A | N/A | N/A | MEDIUM | N/A | N/A
QT-978 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | MSA QP Advanced Related HH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  | Y | [5 empty] | N/A | MEDIUM | N/A | N/A | N/A | N/A
QT-979 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | SUP QP Advanced Related HH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-980 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | DIP Seed Traditional Related NHH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days | I |  | I |  | I |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-981 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | SDS QP Traditional Related NHH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | N/A
QT-982 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | MSS QP Traditional Related NHH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | Y | [6 empty] | HIGH | N/A | N/A | N/A | N/A | N/A
QT-983 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Traditional | SUP QP Traditional Related NHH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | HIGH
QT-984 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | DIP Seed Advanced Single + Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-985 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | ADS QP Advanced Single + Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  | Y |  |  |  | N/A | N/A | N/A | MEDIUM | N/A | N/A
QT-986 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | MSA QP Advanced Single + Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  | Y | [5 empty] | N/A | MEDIUM | N/A | N/A | N/A | N/A
QT-987 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | SUP QP Advanced Single + Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-988 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | DIP Seed Smart Related HH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days | I |  | I |  | I |  |  | LOW | N/A | LOW | N/A | N/A | LOW
QT-989 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SDS QP Smart Related HH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | N/A
QT-990 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | MSS QP Smart Related HH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | Y | [6 empty] | LOW | N/A | N/A | N/A | N/A | N/A
QT-991 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SUP QP Smart Related HH 2 Secondaries | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | MEDIUM
QT-992 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | DIP Seed Smart Single + Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Retro Dated -5 working days | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A
QT-993 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SDS QP Smart Single + Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  | Y |  |  |  |  | N/A | N/A | MEDIUM | N/A | N/A | N/A
QT-994 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | MSS QP Smart Single + Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days | Y | [6 empty] | MEDIUM | N/A | N/A | N/A | N/A | N/A
QT-995 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SUP QP Smart Single + Related HH | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | HIGH
QT-996 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Smart | SUP QP Smart Single NHH no meter | Smart Single NHH - Appoint SUP QP and remainder stubs no meter | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | LOW
QT-997 | Migration | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service) | Advanced | SUP QP Advanced Single HH no meter | Advanced Single HH - Appoint SUP QP and remainder stubs no meter | Forward Dated 1 working days |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | LOW

## Smoke Tests (500)
Test ID | Test Details | [5 empty] | Role Requirements | [6 empty] | QTC Scale (t-shirt size)
QT Case ID | QT Test Type | Scope Theme | Segment | QT Test Case Title | QT Scenario | Effective Time | MSS | MSA | SDS | ADS | SUP | UMSDS | Supplier Linked | MSS | MSA | SDS | ADS | UMSDS | SUP
QT-501 | Functional | Smoke Test | Advanced | Supplier DIP Smoke Test | Supplier DIP Smoke Test | Same Day |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | LOW
QT-502 | Functional | Smoke Test | Advanced | Supplier DTN Smoke Test | Supplier DTN Smoke Test | Same Day |  |  |  |  | Y |  |  | N/A | N/A | N/A | N/A | N/A | LOW
QT-503 | Functional | Smoke Test | Advanced | MSA DIP Smoke Test | MSA DIP Smoke Test | Same Day |  | Y | [5 empty] | N/A | LOW | N/A | N/A | N/A | N/A
QT-504 | Functional | Smoke Test | Advanced | MSA DTN Smoke Test | MSA DTN Smoke Test | Same Day |  | Y | [5 empty] | N/A | LOW | N/A | N/A | N/A | N/A
QT-505 | Functional | Smoke Test | Smart | MSS DIP Smoke Test | MSS DIP Smoke Test | Same Day | Y | [6 empty] | LOW | N/A | N/A | N/A | N/A | N/A
QT-506 | Functional | Smoke Test | Smart | MSS DTN Smoke Test | MSS DTN Smoke Test | Same Day | Y | [6 empty] | LOW | N/A | N/A | N/A | N/A | N/A
QT-507 | Functional | Smoke Test | Advanced | ADS DIP Smoke Test | ADS DIP Smoke Test | Same Day |  |  |  | Y |  |  |  | N/A | N/A | N/A | LOW | N/A | N/A
QT-508 | Functional | Smoke Test | Advanced | ADS DTN Smoke Test | ADS DTN Smoke Test | Same Day |  |  |  | Y |  |  |  | N/A | N/A | N/A | LOW | N/A | N/A
QT-509 | Functional | Smoke Test | Smart | SDS DIP Smoke Test | SDS DIP Smoke Test | Same Day |  |  | Y |  |  |  |  | N/A | N/A | LOW | N/A | N/A | N/A
QT-510 | Functional | Smoke Test | Smart | SDS DTN Smoke Test | SDS DTN Smoke Test | Same Day |  |  | Y |  |  |  |  | N/A | N/A | LOW | N/A | N/A | N/A
QT-511 | Functional | Smoke Test | Unmetered | UMSDS DTN Smoke Test | UMSDS DTN Smoke Test | Same Day | [5 empty] | Y |  | N/A | N/A | N/A | N/A | LOW | N/A
QT-512 | Functional | Smoke Test | Unmetered | UMSDS DIP Smoke Test | UMSDS DIP Smoke Test | Same Day | [5 empty] | Y |  | N/A | N/A | N/A | N/A | LOW | N/A

## QTC Timeline Introduction
Qualifying Parties are required to run Onboarding QTCs as a pre-requisite to many of the QTCs in their test set. The Onboarding QTC will appoint the relevant Supplier (where required) and Agents required at the start of the QTC. This may be the Qualifying Party themselves, or the QTF stubs. BSCP708 mandates that MHHS migrations must have an effective date between +1 and +28 days. As such, the Onboarding QTCs which include the appointment of a Qualifying Party as a pre-requisite to the QTC, now have an effective date of +1 working day. If the QTF stubs are appointed to all roles as a pre-requisite to the QTC, these will be retrospective with an appointment date of -5 working days. This spreadsheet lists all the QTCs, and the Onboarding Date (OD) and Earliest QTC run date (QD), to provide clarity to Qualifying Parties.

## QTC Timeline Example
QTC | Effective Time | Role | Test Role | Onboarding QTC run date OD | MHHS Effective date | Earliest QTC run date QD | QTC Effective date | Comment
QT-001 | Forward Dated 3 working days | ADS | Outgoing | OD | OD+1 | QD=OD+1 | QD+3 | Wait steps exist in QTCs to support any required pauses in running relevant steps until QTC effective date
QT-001 | Forward Dated 3 working days | ADS | Outgoing | 2025-09-08 | 2025-09-09 | 2025-09-09 | 2025-09-12 | Example
QT-001 | Forward Dated 3 working days | ADS | Incoming | OD | OD-5 | QD=OD | QD+3 | MHHS Effective date is D-5 because MHHS appointment in the Onboarding QTC has no QP involvement - only QTF stubs appointed. The QTC can be run immediately after the Onboarding QTC has completed.
QT-001 | Forward Dated 3 working days | ADS | Incoming | 2025-09-08 | 2025-09-01 | 2025-09-08 | 2025-09-11 | Example
QT-004 | Same day | MSS/SUP | Current | OD | OD+1 | QD=OD+2 | QD | Some "Same day" MHHS processes cannot be carried out on the same day as the MHHS migration, therefore it is recommended that all same day QTCs be executed no earlier that the day after the MHHS effective date.
QT-004 | Same day | MSS/SUP | Current | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-10 | Example
QT-004 | Same day | SDS | Outgoing | OD | OD+1 | QD=OD+2 | QD | Some MHHS processes cannot be carried out on the same day as the MHHS migration, therefore it is recommended that all same day QTCs be executed no earlier that the day after the MHHS effective date.
QT-004 | Same day | SDS | Outgoing | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-10 | Example
QT-004 | Same day | SDS | Incoming | OD | OD-5 | QD=OD | QD | MHHS Effective date is D-5 because MHHS appointment in the Onboarding QTC has no QP involvement - only QTF stubs appointed. The QTC can be run immediately after the Onboarding QTC has completed.
QT-004 | Same day | SDS | Incoming | 2025-09-08 | 2025-09-01 | 2025-09-08 | 2025-09-08 | Example
QT-012 | Retro Dated -1 working day | MSA | Outgoing | OD | OD+1 | QD=OD+3 | QD-1=OD+3-1=OD+2 | Some MHHS processes cannot be carried out on the same day as the MHHS migration, therefore an additional days delay should be included in all retro dated QTCs.
QT-012 | Retro Dated -1 working day | MSA | Outgoing | 2025-09-08 | 2025-09-09 | 2025-09-11 | 2025-09-10 | Example
QT-012 | Retro Dated -1 working day | MSA | Incoming | OD | OD-5 | QD=OD | QD-1=OD-1 | MHHS Effective date is D-5 because MHHS appointment in the Onboarding QTC has no QP involvement - only QTF stubs appointed. The QTC can be run immediately after the Onboarding QTC has completed.
QT-012 | Retro Dated -1 working day | MSA | Incoming | 2025-09-08 | 2025-09-01 | 2025-09-08 | 2025-09-05 | Example

## QTC Timeline all QTCs
QTC | Effective Time | Effective Date Offset - working days | Role | Test Role | Onboarding QTC run date OD | Example OD Day | MHHS Effective date | Example MHHS Effective Day | Earliest QTC run date QD | Example QD Day | QTC Effective date wrt QD | QTC Effective date wrt OD | QTC Effective date wrt OD Simplified | Example QTC Effective Day
QT-001 | Forward Dated 3 working days | 3 | ADS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-001 | Forward Dated 3 working days | 3 | ADS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-001 | Forward Dated 3 working days | 3 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-001 | Forward Dated 3 working days | 3 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-002 | Same Day | 0 | ADS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-002 | Same Day | 0 | ADS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-002 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-002 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-003 | Forward Dated 3 working days | 3 | ADS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-003 | Forward Dated 3 working days | 3 | ADS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-003 | Forward Dated 3 working days | 3 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-003 | Forward Dated 3 working days | 3 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-004 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-004 | Same Day | 0 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-004 | Same Day | 0 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-004 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-005 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-005 | Same Day | 0 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-005 | Same Day | 0 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-005 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-006 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-006 | Same Day | 0 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-006 | Same Day | 0 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-006 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-007 | Forward Dated 2 working days | 2 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-007 | Forward Dated 2 working days | 2 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-007 | Forward Dated 2 working days | 2 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-007 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-008 | Retro Dated -1 working days | -1 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-008 | Retro Dated -1 working days | -1 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD-1 | OD-1 | OD-1 | Fri
QT-008 | Retro Dated -1 working days | -1 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-008 | Retro Dated -1 working days | -1 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-009 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-009 | Same Day | 0 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-009 | Same Day | 0 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-009 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-010 | Retro Dated -1 working days | -1 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-010 | Retro Dated -1 working days | -1 | UMSDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD-1 | OD-1 | OD-1 | Fri
QT-010 | Retro Dated -1 working days | -1 | UMSDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-011 | Forward Dated 3 working days | 3 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-011 | Forward Dated 3 working days | 3 | MSA | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-011 | Forward Dated 3 working days | 3 | MSA | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-011 | Forward Dated 3 working days | 3 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-012 | Retro Dated -1 working days | -1 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-012 | Retro Dated -1 working days | -1 | MSA | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD-1 | OD-1 | OD-1 | Fri
QT-012 | Retro Dated -1 working days | -1 | MSA | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-012 | Retro Dated -1 working days | -1 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-013 | Forward Dated 3 working days | 3 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-013 | Forward Dated 3 working days | 3 | MSA | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-013 | Forward Dated 3 working days | 3 | MSA | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-013 | Forward Dated 3 working days | 3 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-014 | Same Day | 0 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-014 | Same Day | 0 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-014 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-014 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-015 | Forward Dated 2 working days | 2 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-015 | Forward Dated 2 working days | 2 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-015 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-015 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-016 | Same Day | 0 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-016 | Same Day | 0 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-016 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-016 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-017 | Forward Dated 2 working days | 2 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-017 | Forward Dated 2 working days | 2 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-017 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-017 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-018 | Forward Dated 2 working days | 2 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-018 | Forward Dated 2 working days | 2 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-018 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-018 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-019 | Same Day | 0 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-019 | Same Day | 0 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-019 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-019 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-026 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-026 | Forward Dated 2 working days | 2 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-026 | Forward Dated 2 working days | 2 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-027 | Forward Dated 2 working days | 2 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-027 | Forward Dated 2 working days | 2 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-029 | Forward Dated 2 working days | 2 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-029 | Forward Dated 2 working days | 2 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-029 | Forward Dated 2 working days | 2 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-029 | Forward Dated 2 working days | 2 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-030 | Forward Dated 2 working days | 2 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-030 | Forward Dated 2 working days | 2 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-030 | Forward Dated 2 working days | 2 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-030 | Forward Dated 2 working days | 2 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-031 | Forward Dated 3 working days | 3 | ADS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-031 | Forward Dated 3 working days | 3 | ADS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-031 | Forward Dated 3 working days | 3 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-031 | Forward Dated 3 working days | 3 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-032 | Forward Dated 2 working days | 2 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-032 | Forward Dated 2 working days | 2 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-032 | Forward Dated 2 working days | 2 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-032 | Forward Dated 2 working days | 2 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-032 | Forward Dated 2 working days | 2 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-032 | Forward Dated 2 working days | 2 | SUP | Linked | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-032 | Forward Dated 2 working days | 2 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-033 | Forward Dated 3 working days | 3 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-033 | Forward Dated 3 working days | 3 | SUP | Linked | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-033 | Forward Dated 3 working days | 3 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-034 | Forward Dated 2 working days | 2 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-034 | Forward Dated 2 working days | 2 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-034 | Forward Dated 2 working days | 2 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-034 | Forward Dated 2 working days | 2 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-034 | Forward Dated 2 working days | 2 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-035 | Forward Dated 3 working days | 3 | ADS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-035 | Forward Dated 3 working days | 3 | ADS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-035 | Forward Dated 3 working days | 3 | MSA | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-035 | Forward Dated 3 working days | 3 | MSA | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-035 | Forward Dated 3 working days | 3 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-035 | Forward Dated 3 working days | 3 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-036 | Forward Dated 2 working days | 2 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-036 | Forward Dated 2 working days | 2 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-036 | Forward Dated 2 working days | 2 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-036 | Forward Dated 2 working days | 2 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-036 | Forward Dated 2 working days | 2 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-036 | Forward Dated 2 working days | 2 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-037 | Forward Dated 2 working days | 2 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-037 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-037 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-038 | Forward Dated 3 working days | 3 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-038 | Forward Dated 3 working days | 3 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-038 | Forward Dated 3 working days | 3 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-039 | Next Day 1 working day | 1 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-039 | Next Day 1 working day | 1 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-039 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-040 | Next Day 1 working day | 1 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-040 | Next Day 1 working day | 1 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-040 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-041 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-041 | Next Day 1 working day | 1 | UMSDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-042 | Forward Dated 3 working days | 3 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-042 | Forward Dated 3 working days | 3 | UMSDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-043 | Forward Dated 3 working days | 3 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-044 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-044 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-045 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-045 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-047 | Same Day | 0 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-047 | Same Day | 0 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-047 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-048 | Retro Dated -1 working days | -1 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD-1 | OD-1 | OD-1 | Fri
QT-048 | Retro Dated -1 working days | -1 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-048 | Retro Dated -1 working days | -1 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-049 | Forward Dated 3 working days | 3 | ADS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-049 | Forward Dated 3 working days | 3 | ADS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-049 | Forward Dated 3 working days | 3 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-051 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-051 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-052 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-052 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-053 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-053 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-054 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-055 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-056 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-057 | Forward Dated 2 working days | 2 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-057 | Forward Dated 2 working days | 2 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-057 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-058 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-058 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-059 | Forward Dated 3 working days | 3 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-065 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-065 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-065 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-066 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-066 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-067 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-068 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-068 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-068 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-069 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-069 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-069 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-070 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-070 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-071 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-073 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-074 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-075 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-076 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-078 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-079 | Forward Dated 2 working days | 2 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-080 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-081 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-082 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-083 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-084 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-086 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-087 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-088 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-089 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-090 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-091 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-091 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-092 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-092 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-093 | Same Day | 0 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD | N/A | N/A | Mon
QT-093 | Same Day | 0 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD | N/A | N/A | Mon
QT-093 | Same Day | 0 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD | N/A | N/A | Mon
QT-093 | Same Day | 0 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD | N/A | N/A | Mon
QT-093 | Same Day | 0 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD | N/A | N/A | Mon
QT-093 | Same Day | 0 | UMSDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD | N/A | N/A | Mon
QT-096 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-096 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-096 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-097 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-097 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-097 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-098 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-099 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-099 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-099 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-100 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-100 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-100 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-101 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-101 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-101 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-102 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-102 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-102 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-102 | Same Day | 0 | SUP | Linked | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-103 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-103 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-103 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-104 | Same Day | 0 | ADS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-104 | Same Day | 0 | MSA | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-104 | Same Day | 0 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-104 | Same Day | 0 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-104 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-105 | Same Day | 0 | ADS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-105 | Same Day | 0 | MSA | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-105 | Same Day | 0 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-105 | Same Day | 0 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-105 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-107 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-107 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-107 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-108 | Forward Dated 3 working days | 3 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-108 | Forward Dated 3 working days | 3 | MSA | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-108 | Forward Dated 3 working days | 3 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-109 | Same Day | 0 | ADS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-109 | Same Day | 0 | MSA | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-109 | Same Day | 0 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-109 | Same Day | 0 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-109 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-110 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-110 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-111 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-111 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-112 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-112 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-113 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-113 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-114 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-114 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-115 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-115 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-116 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-116 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-116 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-117 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-117 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-117 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-118 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-119 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-119 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-120 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-120 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-122 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-122 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-123 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-123 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-124 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-124 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-125 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-125 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-125 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-126 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-126 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-126 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-127 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-127 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-128 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-128 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-128 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-129 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-129 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-129 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-130 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-130 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-130 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-131 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-131 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-132 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-132 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-133 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-133 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-134 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-134 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-135 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-135 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-135 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-136 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-136 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-136 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-137 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-138 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-138 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-138 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-139 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-139 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-139 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-140 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-141 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-141 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-141 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-142 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-142 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-142 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-145 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-145 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-145 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-146 | Retro Dated -1 working days | -1 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-147 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-148 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-149 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-149 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-149 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-150 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-150 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-150 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-151 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-151 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-151 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-151 | Same Day | 0 | SUP | Linked | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-152 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-153 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-153 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-153 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-154 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-154 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-154 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-155 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-155 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-159 | Retro Dated -1 working days | -1 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-159 | Retro Dated -1 working days | -1 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-160 | Retro Dated -1 working days | -1 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-160 | Retro Dated -1 working days | -1 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-162 | Retro Dated -1 working days | -1 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-162 | Retro Dated -1 working days | -1 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+3 | Thu | QD-1 | OD+3-1 | OD+2 | Wed
QT-168 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-169 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-169 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-170 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-170 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-171 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-174 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-174 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-176 | Forward Dated 3 working days | 3 | ADS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-176 | Forward Dated 3 working days | 3 | ADS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-176 | Forward Dated 3 working days | 3 | MSA | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-176 | Forward Dated 3 working days | 3 | MSA | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-176 | Forward Dated 3 working days | 3 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-176 | Forward Dated 3 working days | 3 | SUP | Linked | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-176 | Forward Dated 3 working days | 3 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-177 | Forward Dated 3 working days | 3 | ADS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-177 | Forward Dated 3 working days | 3 | ADS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-177 | Forward Dated 3 working days | 3 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-177 | Forward Dated 3 working days | 3 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-177 | Forward Dated 3 working days | 3 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-178 | Forward Dated 2 working days | 2 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-178 | Forward Dated 2 working days | 2 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-178 | Forward Dated 2 working days | 2 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-178 | Forward Dated 2 working days | 2 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-178 | Forward Dated 2 working days | 2 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-178 | Forward Dated 2 working days | 2 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-179 | Forward Dated 2 working days | 2 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-179 | Forward Dated 2 working days | 2 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-179 | Forward Dated 2 working days | 2 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-179 | Forward Dated 2 working days | 2 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-179 | Forward Dated 2 working days | 2 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-179 | Forward Dated 2 working days | 2 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-180 | Forward Dated 3 working days | 3 | ADS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-180 | Forward Dated 3 working days | 3 | ADS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-180 | Forward Dated 3 working days | 3 | MSA | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-180 | Forward Dated 3 working days | 3 | MSA | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-180 | Forward Dated 3 working days | 3 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-180 | Forward Dated 3 working days | 3 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-181 | Forward Dated 2 working days | 2 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-181 | Forward Dated 2 working days | 2 | MSS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-181 | Forward Dated 2 working days | 2 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-181 | Forward Dated 2 working days | 2 | SDS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-181 | Forward Dated 2 working days | 2 | SUP | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+2 | OD+2 | OD+2 | Wed
QT-181 | Forward Dated 2 working days | 2 | SUP | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-182 | Forward Dated 3 working days | 3 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-182 | Forward Dated 3 working days | 3 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-183 | Next Day 1 working day | 1 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-183 | Next Day 1 working day | 1 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-183 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-185 | Forward Dated 3 working days | 3 | MSA | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD+3 | OD+3 | OD+3 | Thu
QT-185 | Forward Dated 3 working days | 3 | MSA | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-185 | Forward Dated 3 working days | 3 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+3 | OD+1+3 | OD+4 | Fri
QT-186 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-186 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-186 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-187 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-187 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-187 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-188 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-188 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-188 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-189 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-189 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-189 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-190 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-190 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-191 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-191 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-191 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-191 | Same Day | 0 | SUP | Linked | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-192 | Same Day | 0 | ADS | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-192 | Same Day | 0 | MSA | Outgoing | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-192 | Same Day | 0 | MSS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-192 | Same Day | 0 | SDS | Incoming | OD | Mon | OD-5 | Prev Mon | QD=OD | Mon | QD | OD | OD | Mon
QT-192 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-193 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-193 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-194 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-194 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-195 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-195 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-195 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-196 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-196 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-196 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-197 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-197 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-197 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-198 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-198 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-198 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-199 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-199 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-199 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-200 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-200 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-200 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-200 | Same Day | 0 | SUP | Linked | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-201 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-201 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-201 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-202 | Next Day 1 working day | 1 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-202 | Next Day 1 working day | 1 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-202 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-203 | Next Day 1 working day | 1 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-203 | Next Day 1 working day | 1 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-203 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-204 | Next Day 1 working day | 1 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-204 | Next Day 1 working day | 1 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-204 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-205 | Next Day 1 working day | 1 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-205 | Next Day 1 working day | 1 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-205 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-206 | Next Day 1 working day | 1 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-206 | Next Day 1 working day | 1 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-206 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-207 | Next Day 1 working day | 1 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-207 | Next Day 1 working day | 1 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-207 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-208 | Next Day 1 working day | 1 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-208 | Next Day 1 working day | 1 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-208 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-209 | Next Day 1 working day | 1 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-209 | Next Day 1 working day | 1 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-209 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-210 | Next Day 1 working day | 1 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-210 | Next Day 1 working day | 1 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-210 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-211 | Next Day 1 working day | 1 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-211 | Next Day 1 working day | 1 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-211 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-212 | Next Day 1 working day | 1 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-212 | Next Day 1 working day | 1 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-212 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-213 | Next Day 1 working day | 1 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-213 | Next Day 1 working day | 1 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-213 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-214 | Next Day 1 working day | 1 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-214 | Next Day 1 working day | 1 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-214 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-215 | Next Day 1 working day | 1 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-215 | Next Day 1 working day | 1 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-215 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-216 | Next Day 1 working day | 1 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-216 | Next Day 1 working day | 1 | UMSDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+1 | N/A | N/A | Tue
QT-217 | Forward Dated 3 working days | 3 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-217 | Forward Dated 3 working days | 3 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-217 | Forward Dated 3 working days | 3 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-218 | Forward Dated 3 working days | 3 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-218 | Forward Dated 3 working days | 3 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-218 | Forward Dated 3 working days | 3 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-219 | Forward Dated 2 working days | 2 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-219 | Forward Dated 2 working days | 2 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-219 | Forward Dated 2 working days | 2 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-220 | Forward Dated 2 working days | 2 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-220 | Forward Dated 2 working days | 2 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-220 | Forward Dated 2 working days | 2 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-221 | Forward Dated 2 working days | 2 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-221 | Forward Dated 2 working days | 2 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-221 | Forward Dated 2 working days | 2 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-222 | Forward Dated 3 working days | 3 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-222 | Forward Dated 3 working days | 3 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-222 | Forward Dated 3 working days | 3 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-223 | Forward Dated 3 working days | 3 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-223 | Forward Dated 3 working days | 3 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-223 | Forward Dated 3 working days | 3 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-224 | Forward Dated 2 working days | 2 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-224 | Forward Dated 2 working days | 2 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-224 | Forward Dated 2 working days | 2 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-225 | Forward Dated 2 working days | 2 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-225 | Forward Dated 2 working days | 2 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-225 | Forward Dated 2 working days | 2 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-226 | Forward Dated 2 working days | 2 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-226 | Forward Dated 2 working days | 2 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-226 | Forward Dated 2 working days | 2 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-227 | Forward Dated 3 working days | 3 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-227 | Forward Dated 3 working days | 3 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-227 | Forward Dated 3 working days | 3 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-228 | Forward Dated 3 working days | 3 | ADS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-228 | Forward Dated 3 working days | 3 | MSA | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-228 | Forward Dated 3 working days | 3 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-229 | Forward Dated 2 working days | 2 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-229 | Forward Dated 2 working days | 2 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-229 | Forward Dated 2 working days | 2 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-230 | Forward Dated 2 working days | 2 | MSS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-230 | Forward Dated 2 working days | 2 | SDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-230 | Forward Dated 2 working days | 2 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+2 | N/A | N/A | Wed
QT-231 | Forward Dated 3 working days | 3 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-231 | Forward Dated 3 working days | 3 | UMSDS | Current | N/A | N/A | N/A | N/A | QD | Mon | QD+3 | N/A | N/A | Thu
QT-232 | Forward Dated 2 working days | 2 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-232 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-232 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-233 | Forward Dated 2 working days | 2 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-233 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-233 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-234 | Forward Dated 2 working days | 2 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-234 | Forward Dated 2 working days | 2 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-234 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-235 | Forward Dated 2 working days | 2 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-235 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-235 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-236 | Forward Dated 2 working days | 2 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-236 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-236 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-237 | Forward Dated 2 working days | 2 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-237 | Forward Dated 2 working days | 2 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-237 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-238 | Forward Dated 2 working days | 2 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-238 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-238 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-239 | Forward Dated 2 working days | 2 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-239 | Forward Dated 2 working days | 2 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-239 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-240 | Forward Dated 2 working days | 2 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-240 | Forward Dated 2 working days | 2 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-240 | Forward Dated 2 working days | 2 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+2 | OD+1+2 | OD+3 | Thu
QT-241 | Next Day 1 working day | 1 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+1 | OD+1+1 | OD+2 | Wed
QT-241 | Next Day 1 working day | 1 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+1 | Tue | QD+1 | OD+1+1 | OD+2 | Wed
QT-242 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-243 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-244 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-251 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-252 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-253 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-254 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-255 | Same Day | 0 | MSA | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-257 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-258 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-258 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-258 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-259 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-260 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-267 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-268 | Same Day | 0 | MSS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-269 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-269 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-270 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-270 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-272 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-272 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-274 | Same Day | 0 | SUP | Current | N/A | N/A | N/A | N/A | QD | Mon | QD | N/A | N/A | Mon
QT-275 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-276 | Same Day | 0 | ADS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-276 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-277 | Same Day | 0 | UMSDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-278 | Same Day | 0 | SDS | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed
QT-279 | Same Day | 0 | SUP | Current | OD | Mon | OD+1 | Tue | QD=OD+2 | Wed | QD | OD+2 | OD+2 | Wed

## Output (hidden)
Test ID and Exclusions |  |  | FILE
QT Case ID | Excluded? | Exclusion Rationale (please note that this must be reflected in your RTTM and agreed with the Code Bodies)
QT-001 | EXCLUDE | Example: Placing Reliance; agreed exemption (REMOVE THIS EXCLUSION IF NOT INTENDED) | QT-001
QT-002 | INCLUDED |  | --QT-002
QT-003 | INCLUDED |  | --QT-003
QT-004 | INCLUDED |  | --QT-004
QT-005 | INCLUDED |  | --QT-005
QT-006 | INCLUDED |  | --QT-006
QT-007 | INCLUDED |  | --QT-007
QT-008 | INCLUDED |  | --QT-008
QT-009 | INCLUDED |  | --QT-009
QT-010 | INCLUDED |  | --QT-010
QT-011 | INCLUDED |  | --QT-011
QT-012 | INCLUDED |  | --QT-012
QT-013 | INCLUDED |  | --QT-013
QT-014 | INCLUDED |  | --QT-014
QT-015 | INCLUDED |  | --QT-015
QT-016 | INCLUDED |  | --QT-016
QT-017 | INCLUDED |  | --QT-017
QT-018 | INCLUDED |  | --QT-018
QT-019 | INCLUDED |  | --QT-019
QT-026 | INCLUDED |  | --QT-026
QT-027 | INCLUDED |  | --QT-027
QT-029 | INCLUDED |  | --QT-029
QT-030 | INCLUDED |  | --QT-030
QT-031 | INCLUDED |  | --QT-031
QT-032 | INCLUDED |  | --QT-032
QT-033 | INCLUDED |  | --QT-033
QT-034 | INCLUDED |  | --QT-034
QT-035 | INCLUDED |  | --QT-035
QT-036 | INCLUDED |  | --QT-036
QT-037 | INCLUDED |  | --QT-037
QT-038 | INCLUDED |  | --QT-038
QT-039 | INCLUDED |  | --QT-039
QT-040 | INCLUDED |  | --QT-040
QT-041 | INCLUDED |  | --QT-041
QT-042 | INCLUDED |  | --QT-042
QT-043 | INCLUDED |  | --QT-043
QT-044 | INCLUDED |  | --QT-044
QT-045 | INCLUDED |  | --QT-045
QT-047 | INCLUDED |  | --QT-047
QT-048 | INCLUDED |  | --QT-048
QT-049 | INCLUDED |  | --QT-049
QT-051 | INCLUDED |  | --QT-051
QT-052 | INCLUDED |  | --QT-052
QT-053 | INCLUDED |  | --QT-053
QT-054 | INCLUDED |  | --QT-054
QT-055 | INCLUDED |  | --QT-055
QT-056 | INCLUDED |  | --QT-056
QT-057 | INCLUDED |  | --QT-057
QT-058 | INCLUDED |  | --QT-058
QT-059 | INCLUDED |  | --QT-059
QT-065 | INCLUDED |  | --QT-065
QT-066 | INCLUDED |  | --QT-066
QT-067 | INCLUDED |  | --QT-067
QT-068 | INCLUDED |  | --QT-068
QT-069 | INCLUDED |  | --QT-069
QT-070 | INCLUDED |  | --QT-070
QT-071 | INCLUDED |  | --QT-071
QT-073 | INCLUDED |  | --QT-073
QT-074 | INCLUDED |  | --QT-074
QT-075 | INCLUDED |  | --QT-075
QT-076 | INCLUDED |  | --QT-076
QT-078 | INCLUDED |  | --QT-078
QT-079 | INCLUDED |  | --QT-079
QT-080 | INCLUDED |  | --QT-080
QT-081 | INCLUDED |  | --QT-081
QT-082 | INCLUDED |  | --QT-082
QT-083 | INCLUDED |  | --QT-083
QT-084 | INCLUDED |  | --QT-084
QT-086 | INCLUDED |  | --QT-086
QT-087 | INCLUDED |  | --QT-087
QT-088 | INCLUDED |  | --QT-088
QT-089 | INCLUDED |  | --QT-089
QT-090 | INCLUDED |  | --QT-090
QT-091 | INCLUDED |  | --QT-091
QT-092 | INCLUDED |  | --QT-092
QT-093 | INCLUDED |  | --QT-093
QT-096 | INCLUDED |  | --QT-096
QT-097 | INCLUDED |  | --QT-097
QT-098 | INCLUDED |  | --QT-098
QT-099 | INCLUDED |  | --QT-099
QT-100 | INCLUDED |  | --QT-100
QT-101 | INCLUDED |  | --QT-101
QT-102 | INCLUDED |  | --QT-102
QT-103 | INCLUDED |  | --QT-103
QT-104 | INCLUDED |  | --QT-104
QT-105 | INCLUDED |  | --QT-105
QT-107 | INCLUDED |  | --QT-107
QT-108 | INCLUDED |  | --QT-108
QT-109 | INCLUDED |  | --QT-109
QT-110 | INCLUDED |  | --QT-110
QT-111 | INCLUDED |  | --QT-111
QT-112 | INCLUDED |  | --QT-112
QT-113 | INCLUDED |  | --QT-113
QT-114 | INCLUDED |  | --QT-114
QT-115 | INCLUDED |  | --QT-115
QT-116 | INCLUDED |  | --QT-116
QT-117 | INCLUDED |  | --QT-117
QT-118 | INCLUDED |  | --QT-118
QT-119 | INCLUDED |  | --QT-119
QT-120 | INCLUDED |  | --QT-120
QT-122 | INCLUDED |  | --QT-122
QT-123 | INCLUDED |  | --QT-123
QT-124 | INCLUDED |  | --QT-124
QT-125 | INCLUDED |  | --QT-125
QT-126 | INCLUDED |  | --QT-126
QT-127 | INCLUDED |  | --QT-127
QT-128 | INCLUDED |  | --QT-128
QT-129 | INCLUDED |  | --QT-129
QT-130 | INCLUDED |  | --QT-130
QT-131 | INCLUDED |  | --QT-131
QT-132 | INCLUDED |  | --QT-132
QT-133 | INCLUDED |  | --QT-133
QT-134 | INCLUDED |  | --QT-134
QT-135 | INCLUDED |  | --QT-135
QT-136 | INCLUDED |  | --QT-136
QT-137 | INCLUDED |  | --QT-137
QT-138 | INCLUDED |  | --QT-138
QT-139 | INCLUDED |  | --QT-139
QT-140 | INCLUDED |  | --QT-140
QT-141 | INCLUDED |  | --QT-141
QT-142 | INCLUDED |  | --QT-142
QT-145 | INCLUDED |  | --QT-145
QT-146 | INCLUDED |  | --QT-146
QT-147 | INCLUDED |  | --QT-147
QT-148 | INCLUDED |  | --QT-148
QT-149 | INCLUDED |  | --QT-149
QT-150 | INCLUDED |  | --QT-150
QT-151 | INCLUDED |  | --QT-151
QT-152 | INCLUDED |  | --QT-152
QT-153 | INCLUDED |  | --QT-153
QT-154 | INCLUDED |  | --QT-154
QT-155 | INCLUDED |  | --QT-155
QT-159 | INCLUDED |  | --QT-159
QT-160 | INCLUDED |  | --QT-160
QT-162 | INCLUDED |  | --QT-162
QT-168 | INCLUDED |  | --QT-168
QT-169 | INCLUDED |  | --QT-169
QT-170 | INCLUDED |  | --QT-170
QT-171 | INCLUDED |  | --QT-171
QT-174 | INCLUDED |  | --QT-174
QT-176 | INCLUDED |  | --QT-176
QT-177 | INCLUDED |  | --QT-177
QT-178 | INCLUDED |  | --QT-178
QT-179 | INCLUDED |  | --QT-179
QT-180 | INCLUDED |  | --QT-180
QT-181 | INCLUDED |  | --QT-181
QT-182 | INCLUDED |  | --QT-182
QT-183 | INCLUDED |  | --QT-183
QT-185 | INCLUDED |  | --QT-185
QT-186 | INCLUDED |  | --QT-186
QT-187 | INCLUDED |  | --QT-187
QT-188 | INCLUDED |  | --QT-188
QT-189 | INCLUDED |  | --QT-189
QT-190 | INCLUDED |  | --QT-190
QT-191 | INCLUDED |  | --QT-191
QT-192 | INCLUDED |  | --QT-192
QT-193 | INCLUDED |  | --QT-193
QT-194 | INCLUDED |  | --QT-194
QT-195 | INCLUDED |  | --QT-195
QT-196 | INCLUDED |  | --QT-196
QT-197 | INCLUDED |  | --QT-197
QT-198 | INCLUDED |  | --QT-198
QT-199 | INCLUDED |  | --QT-199
QT-200 | INCLUDED |  | --QT-200
QT-201 | INCLUDED |  | --QT-201
QT-202 | INCLUDED |  | --QT-202
QT-203 | INCLUDED |  | --QT-203
QT-204 | INCLUDED |  | --QT-204
QT-205 | INCLUDED |  | --QT-205
QT-206 | INCLUDED |  | --QT-206
QT-207 | INCLUDED |  | --QT-207
QT-208 | INCLUDED |  | --QT-208
QT-209 | INCLUDED |  | --QT-209
QT-210 | INCLUDED |  | --QT-210
QT-211 | INCLUDED |  | --QT-211
QT-212 | INCLUDED |  | --QT-212
QT-213 | INCLUDED |  | --QT-213
QT-214 | INCLUDED |  | --QT-214
QT-215 | INCLUDED |  | --QT-215
QT-216 | INCLUDED |  | --QT-216
QT-217 | INCLUDED |  | --QT-217
QT-218 | INCLUDED |  | --QT-218
QT-219 | INCLUDED |  | --QT-219
QT-220 | INCLUDED |  | --QT-220
QT-221 | INCLUDED |  | --QT-221
QT-222 | INCLUDED |  | --QT-222
QT-223 | INCLUDED |  | --QT-223
QT-224 | INCLUDED |  | --QT-224
QT-225 | INCLUDED |  | --QT-225
QT-226 | INCLUDED |  | --QT-226
QT-227 | INCLUDED |  | --QT-227
QT-228 | INCLUDED |  | --QT-228
QT-229 | INCLUDED |  | --QT-229
QT-230 | INCLUDED |  | --QT-230
QT-231 | INCLUDED |  | --QT-231
QT-232 | INCLUDED |  | --QT-232
QT-233 | INCLUDED |  | --QT-233
QT-234 | INCLUDED |  | --QT-234
QT-235 | INCLUDED |  | --QT-235
QT-236 | INCLUDED |  | --QT-236
QT-237 | INCLUDED |  | --QT-237
QT-238 | INCLUDED |  | --QT-238
QT-239 | INCLUDED |  | --QT-239
QT-240 | INCLUDED |  | --QT-240
QT-241 | INCLUDED |  | --QT-241
QT-242 | INCLUDED |  | --QT-242
QT-243 | INCLUDED |  | --QT-243
QT-244 | INCLUDED |  | --QT-244
QT-251 | INCLUDED |  | --QT-251
QT-252 | INCLUDED |  | --QT-252
QT-253 | INCLUDED |  | --QT-253
QT-254 | INCLUDED |  | --QT-254
QT-255 | INCLUDED |  | --QT-255
QT-257 | INCLUDED |  | --QT-257
QT-258 | INCLUDED |  | --QT-258
QT-259 | INCLUDED |  | --QT-259
QT-260 | INCLUDED |  | --QT-260
QT-267 | INCLUDED |  | --QT-267
QT-268 | INCLUDED |  | --QT-268
QT-269 | INCLUDED |  | --QT-269
QT-270 | INCLUDED |  | --QT-270
QT-272 | INCLUDED |  | --QT-272
QT-274 | INCLUDED |  | --QT-274
QT-275 | INCLUDED |  | --QT-275
QT-276 | INCLUDED |  | --QT-276
QT-277 | INCLUDED |  | --QT-277
QT-278 | INCLUDED |  | --QT-278
QT-279 | INCLUDED |  | --QT-279
EOF | EOF | EOF | --EOF