## Sheet1
MHHS-DEL4386 - Qualification Approach & Plan Appendix C Consultation Comments Log v1.0
*Organisation:
*Constituency:
*Date:
Comment ID | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner | *Comment Owner to be anonymised | Theme | Decision | Action | Response
QA&P5.1-01 | 5.4.2 | Amendment spelt incorrectly - withn | within | Clerical error |  |  |  | Accept | Update Document | Thank you for your comment, the spelling has been corrected.
QA&P5.1-02 |  | Confirmation
QA&P5.1-03 |  | Confirmation
QA&P5.1-04 |  | Confirmation
QA&P5.1-05 |  | Confirmation
QA&P5.1-06 |  | Confirmation
QA&P5.1-07 | REF1 - updated version 5.1 of the QA&P | We challenge where Code Bodies do not believe that the proposed updates to the QT Execution Window impacts Non-Systems Integration Testing (SIT) QT participant's ability to hit the deadlines for the Qualification steps that take place after QT. Under the grounds of shortening the effective runway disallows contingency for no clear or material benefit. Our plans have been tooled for the current drop dead dates, any changes without due consideration to this offer greater risk for little reward. The issue would not be concern regarding ability, it would be the lack of discourse or perceived benefit to reducing this where smaller suppliers who are more personnel and resource strained will feel a potentially disproportionate impact and risk. | Remove reduction the planned update of the QT Execution Window by one week for every Qualification Wave from the planned 5.1 QA&P changes. | Admin overhead in realigning to newer dates, resource congestion risk and shortened worst case defect and regression management abilities without clear material benefits. |  | Yes | Qualification | Accept | Respond | Thank you for your comment. Code Bodies assessed the impact of the date change based on the received QT Test Plans from PPs which showed the majority of parties were intending to finish testing well ahead of the QT Execution deadline, which is supported by the execution rates, and therefore should not require any change to plans. While Code Bodies do appreciate the concern that this reduces the contingency for test execution, ensuring there are a clear 10WD for test assurance activities reduces the risk that later activities may be delays. Where individual participants are concerned by their ability to meet the new QT Execution End Date, Code Bodies would ask that they reach out directly to discuss their circumstances and any support required.