## QA&P Annex 4 Comments
MHHS-DEL4575 - Qualification Approach and Plan & Annex 5 v2.0 Consultation Comments Log Consolidated
Please use this tab to populate comments relating to the QA&P
Comment ID | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner | *Comment Owner to be anonymised | Code Body Response
A5.01 | General | We believe that in addition to P495 references, there should also be recognition of P514, which seeks to amend the same BSC section 12.12.6 to reflect that this applies to the Supplier being included in ISD rather than achieving qualification from the relevent PAB. | We are of the view that the wording should be updated to reflect the intent of P514, with a similar caveat as is currently applied to P495 | if P514 is approced, there will be a misalignment in the processes and documentation, which may cause confusion with parties | Anon | Y | Included reference and intention of Mod P514 in Footnote
A5.02 | 2 | Typo - BSc | Amend to BSC | Low impact - typo | Anon | Y | Corrected
A5.03 | 2 | The section title refers to the wording being dependent on the P495 outcome - P495 has been approved by Ofgem and was implemented on 30/4/26. | Update out of date wording | Current wording could be confusing. | Anon | Y | Revised to remove note
A5.04 | 2 | Typo - Impact | Amend to impact | Low impact - typo | Anon | Y | Corrected
A5.05 | 2.3 - 2.6 | The formatting of this section of the document should align to that used in Annex 4 - i.e. these section should be bullet points under section 2.2 rather than separate numbered sections. | Amend formatting | Current formatting could be confusing | Anon | Y | updated
A5.06 | 4 | Typo - BSC Section 12.12.6 | Amend to BSC Section C 12.12.6 | Current wording could be confusing. | Anon | Y | Corrected
A5.07 | 5 | Typo - BSc | Amend to BSC | Low impact - typo | Anon | Y | Corrected
A5.08 | 5.2 | The wording of this section isn’t very clear - when it says 'Any Supplier that does not intend to pursue MHHS Qualification may voluntarily remove additional Supplier ID(s)' - does this apply to Suppliers that have achieved MHHS Qualification for one or more of its MPIDs but does not intend to achieve MHHS Qualification for the remainder of its MPIDs? That is that path that we intend to take and it hard to determine from this document exactly which requirements we will need to meet. | Clarify wording | Current wording could be confusing. | Anon | Y | Updated to "Any Supplier that does not intend to pursue MHHS Qualification for one or more of their Supplier MPIDs may voluntarily remove additional those unqualified Supplier MPID(s)."
A5.09 | 5.5 | Reference to an MPID being exited | Amend to retired to keep it consistent with other references in this document (e.g in section 5.4) | Current wording could be confusing. | Anon | Y | updated to "retired"
A5.10 | 6 | Missing hyperlink for Schedule 19 - Market Exit and Supplier of Last Resort | Include hyperlink to this Schedule - other REC Schedules mentioned in this document have been hyperlinked. | Low impact - just inconsistent. | Anon | Y | included a link to Schedule 19
A5.11 | 7 | Typo - BSc | Amend to BSC | Low impact - typo | Anon | Y | Corrected
A5.12 | 7 | Typo - arrangements or do not | Amend to 'arrangements and do not' - surely Suppliers are only in breach of the BSC if they have an MPID that is not Qualified and there is no plan - if they have either there isn't a breach? | Current wording could be confusing. | Anon | Y | updated to "and"
A5.13 | 8 | Typo - BSc | Amend to BSC | Low impact - typo | Anon | Y | Corrected
A5.14 | 9 (multiple refences within both tables) | Typo - BSc | Amend to BSC | Low impact - typo | Anon | Y | Corrected
A5.15 | 9 | I don’t agree that a 'Supplier with unqualified MPIDs with MPANs' would undergo the Breach and Default Process as noted - as long as they have submitted a plan to the PAB (which has been accepted) that will ensure that they migrate those MPANs away from those unqualified MPIDs and on to Qualified MPIDs by M15 then they should not be in breach under the changes made under P495. | Amend the wording to reflect that this situation is not necessarly a breach of the BSC. | Current wording is incorrect. | Anon | Y | updated to "Supplier that does not provide a plan for their unqualified MPIDs with MPANs"
A5.16 | 9 | Similar to the comment above I don’t agree that a 'Supplier with unqualified MPIDs without MPANs' would undergo the Breach and Default Process as noted - as long as they have submitted an assertion to the PAB that those unqualified MPIDs will remain dormant and will be Qualified before they are used in the future, then they should not be in breach under the changes made under P495. | Amend the wording to reflect that this situation is not necessarly a breach of the BSC. | Current wording is incorrect. | Anon | Y | updated to "Supplier that does not provide a plan for their unqualified MPIDs without MPANs"
A5.17 | 9 (Detailed Process Table) | Typo - BSC Section 12.12.6 | Amend to BSC Section C 12.12.6 | Current wording could be confusing. | Anon | Y | resolved
A5.18 | 9 (Detailed Process Table) | In line with previous comments, REF shouldn't refer to 'Notify all Parties with unqualified MPIDs that they are in Breach of the BSC' - it should say that 'Notify all Parties with unqualified MPIDs that have not had a plan accepted by the PAB that they are in Breach of the BSC' | Amend the wording to reflect that this situation is not necessarly a breach of the BSC. | Current wording is incorrect. | Anon | Y | updated to "Notify all Parties that do not provide a plan for their unqualified MPIDs that they are in Breach of the BSC "
A5.19 | Alignment with REC Change Management Work | Could Elexon provide further detail on how this proposal aligns with the work recently undertaken by the REC Change Management team, including the workshops attended by industry participants? Our understanding is that the working group activity was focused on the management of SoLR events, and it would be helpful to understand how the outputs of both initiatives are being aligned and coordinated. |  |  | Anon | Y | Code Bodies to engage with those teams responsible and ensure there is alignment across the Code Bodies. However Annex 5 is focused on the Data Clensing of Participant MPIDs that do not provide a plan for their unqualified MPIDs as set out in Annex 4.
A5.20 | Definition and Anticipated Use of Unqualified MPIDs | We would welcome additional detail in the document detailing Elexon's view of the circumstances under which a participant may hold unqualified MPIDs. This would help consumers of the document understand how this situation may arise. Our current understanding is that an MPID would only be considered unqualified where the owning participant has not successfully completed qualification for the relevant market role at the point they are required to operate under MHHS obligations and within that role. If this interpretation is correct, does Elexon have visibility of the number of participants who may remain unqualified at the time of Market-wide Half-Hourly Settlement (M15)? If so, could this information be shared with industry participants to support operational planning? Additionally, without a party having the necessary qualification in place, it would appear impractical, and potentially impossible, for a participant to operate within that market role under the MHHS obligations. |  |  | Anon | Y | Code Bodies can confirm that unqualified MPIDs are not able to operate in the MHHS Arrnagements. Code Bodies are regularly reporting the numbers of and circumstances of participants in the below catagories to OFGEM, the MHHS Programme and BSC PAB. Updated to include "Code Bodies have assessed those Participants that have unqualified MPIDs and catagorised them according to their circumstances. Code Bodies have engaged with these particpants to support them in the next steps available to them. There are seven catagories of participants that have unqualified MPIDs: Participant to confirm intentions for unqualified MPID - Code Bodies are actively seeking engagement with participant through available contacts. Participant will have atleast one MHHS qualified MPID - Code Bodies are supporting the Participant to fulfil their requirements in relation to MHHS QA&P Annex 4, and the options available to them for the unqualified MPID. Participant MPID undergoing retirement - Participant is engaged in the process to retire their MPID. Participant MPID being expelled - Where Participants no longer meet the conditions of their qualification, Code Bodies are expelling them from the BSC. Licence Ready Entity MPID - Code Bodies are unable to consider the Qualification of License Ready Entities (LRE) where there is not an identified operator of the company, and where they do not yet hold an Energy Licence. Additionally, where there is a subsequent Change of Ownership at an LRE, this would likely result in the requirement for an LRE to undergo Re-Qualification. License Ready Entities are able to utilise the conditions in BSC Section C 12.12.6G, or retire the unqualified MPID. Participant qualifiying in Enduring Arrangements - Participants that were unable to join the MHHS Qualification Wave Transitional Arrangements are able to join the Enduring MHHS Qualification process. Unqualified MPID retired - Code Bodies have actively supported Participants in their retirement of unqualified MPIDs in preparation for M14. "
A5.21 | Qualifications of the Appointed SoLR | With reference to section b(ii), our assumption is that any supplier appointed as the SoLR would have previously qualified for the market role(s) associated with the “failed” supplier. We believe this would be essential, as appointing a supplier that had not yet completed qualification would significantly extend the time required to migrate customers with potentially negative consumer journeys. The receiving supplier would first need to complete qualification activities before assuming responsibility for the relevant MPIDs or MPANs. Without having done this, this could introduce unnecessary delays and potentially impact consumers. |  |  | Anon | Y | Added bullet point into the requirements for consideration by Code Bodies and Suppliers: "Participants that are appointed as a Supplier of Last Resort must follow the requirements set out in BSC Section C 12.12.6H(b), where a party does not follow their requirements, Elexon will utilise it’s Performance Assurance Techniques to support the Participant in meeting their requirements."
A5.22 | Appointment of Non-Qualified Parties as SoLR | On that basis, we would not expect a non-qualified participant to be appointed as a receiving supplier during a SoLR process. |  |  | Anon | Y | BSC Section C 12.12.6H outlines the requirements on a Pariticpant that is appointed as the Supplier of Last Resort on an unqualified MPID.
A5.23 | Applicability of Section b(iii) | With reference to section b(iii), we believe this point is closely linked to the assumptions outlined above. Where a receiving SoLR supplier is already qualified for the relevant market role, they will have both the qualified systems and operational processes necessary to assume responsibility for the affected portfolio. Whether the migration is completed through an ETL process or the more conventional Change of Supplier (CoS) route, the MPIDs and associated MPxNs would ultimately move from an unqualified participant's environment into a qualified participant's environment. Given the above, we would appreciate further detail regarding the use cases where Elexon envisages where the provisions of this clause would apply. Based on our experience and involvement in previous SoLR events, it would be helpful to understand whether the clause remains fully applicable in practice or whether further review may be warranted. We would welcome any additional clarification Elexon can provide on the above points and look forward to supporting the ongoing development of this process. |  |  | Anon | Y | Code Bodies require Participants with unqualified MPIDs to provide a Plan as laid out in MHHS QA&P Annex 4 and seek agreement with the PAB for the plan - this process is analogous to how Code Bodies would manage a Participant appointed as a SoLR on their unqualifed MPID.

## Control (hidden)
Constituency | Artefacts
Central Party | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments
Large Supplier | MHHS-DES242-Transitional BMU Aggreated Data
Medium Supplier | MHHS-DES241 - Transitional Scaling Weights
Small Supplier
I&C Supplier
Supplier Agent
Independent Supplier Agent
DNO
IDNO
Software Provider
Other- MHHS Participant

## Design Artefacts (hidden)
Published Documents |  | Lists
Design Artefact | Version Number | Version Number | Status
METH001 - ADV Validation and Estimation | 1 | v1.1 | Accepted
Rejected
Requires Further Clarification
Action
Submitted