## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Front Cover (hidden)
SWITCHING PROGRAMME
E2E Test Scenarios
Reference: NCT-0045
Version: v0.3

## Change Control (hidden)
Confidentiality Statement
The information contained herein is for the purpose of the MHHS Programme. This document may not be copied, or communicated to a third party, or used, for any purpose other than that for which it is supplied without the express written consent of the MHHS Programme
Distribution List
Name | Organisation
Document History
Issue No. | Issue Date | Issued by | Change Description
0.1 | 2023-02-10 | Dean Bailey | First Draft & QA Checked
Reviewed By
Version | Date | Name | Title / Responsibility
0.1
Approvals
Version | Date | Name | Title / Responsibility

## Sheet1 (hidden)
(empty)

## Sheet2 (hidden)
Data returned for Distinct Count of Profile, 1 - Dual (First 1000 rows).
ListTestCases[Test Case Category] | ListTestCases[E2E Scenario] | ListTestCases[Test Case Id] | ListTestCases[Test Case Title] | ListTestCases[Domestic] | ListTestCases[Non Domestic] | ListTestCases[Smart] | ListTestCases[Non Smart] | ListTestCases[Associated Test Scenario Id] | ListTestCases[Pre-Requisite Test Case] | ListTestCases[Regression Tests] | ListTestCases[Profile] | ListTestCases[Unique ID]
Switch Request Objection | E2E-D001 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-004-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-004-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity)) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-G001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  | X | X | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-004-03 | Gaining Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-G001 | E2E-010-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-007-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-010-04 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-004-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-L001 | E2E-010-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-L001 | E2E-007-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-004-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-L001 | E2E-010-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-L001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Traditional - Gas, Smart Meter - Electricity) | X |  | X | X | E2E-010-L001 | E2E-007-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-004-06 | Losing Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-L001 | E2E-010-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Successful | E2E-D002 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-013-01 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-016-01 | Gaining Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-G001 | E2E-013-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-013-02 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-016-02 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-G001 | E2E-013-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-013-03 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-016-03 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-G001 | E2E-013-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-013-04 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-016-04 | Gaining Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-G001 | E2E-013-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-013-05 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-016-05 | Losing Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-L001 | E2E-013-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-013-06 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-016-06 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-L001 | E2E-013-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-013-07 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-016-07 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-L001 | E2E-013-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-013-08 | Losing Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-016-08 | Losing Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-L001 | E2E-013-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Withdrawal | E2E-D003 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-019-01 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-G001 | E2E-10-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-019-02 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-019-03 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-019-04 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-G001 | E2E-010-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-019-05 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-010-06 | LosingSupplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-019-06 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-019-07 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-019-08 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-L001 | E2E-010-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Annulment | E2E-D004 | E2E-007-01 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-010-01 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-022-01 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-007-02 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-010-02 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-022-02 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-007-03 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-010-03 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meter with Primary MPAN) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-022-03 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-007-04 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-G001 | NA |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-010-04 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic,Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-022-04 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-G001 | E2E-010-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-007-05 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-010-05 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-022-05 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-007-06 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-010-06 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-022-06 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-007-07 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-010-07 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic smart Meter with Primary MPAN) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-022-07 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-007-08 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-010-08 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-022-08 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-L001 | E2E-010-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4

## Summary (hidden)
Test Scenario View |  |  |  |  | Summary
Priority | Fuel Type | E2E Scenario | Profile | Test Cases | Priority | Fuel Type | Profile | Distinct Count of Profile | Distinct Count of E2E Scenario | Test Cases
1 |  |  |  |  | 1
| All |  |  |  |  | All
|  | E2E-GED-001 |  |  |  |  | Domestic, Smart Meter | 1 | 1 | 6
|  |  | Domestic, Smart Meter | 6 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  |  | Domestic, Traditional Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 1 | 3
|  |  | Non Domestic, Smart Meter | 3 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 5
|  |  | Non Domestic, Traditional Meter | 5 |  | All Total |  | 4 | 1 | 18
|  | E2E-GED-001 Total |  | 18 |  | Dual
| All Total |  |  | 18 |  |  | Domestic, Smart Meter | 1 | 4 | 14
| Dual | [5 empty] | Domestic, Traditional Meter | 1 | 4 | 14
|  | E2E-D001 |  |  |  |  | Non Domestic, Smart Meter | 1 | 4 | 14
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 4 | 14
|  |  | Domestic, Traditional Meter | 2 |  | Dual Total |  | 4 | 4 | 56
|  |  | Non Domestic, Smart Meter | 2 |  | Electricity
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Smart Meter | 1 | 6 | 18
|  | E2E-D001 Total |  | 8 |  |  | Domestic, Traditional Meter | 1 | 6 | 16
|  | E2E-D002 |  |  |  |  | Non Domestic, Smart Meter | 1 | 6 | 20
|  |  | Domestic, Smart Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 6 | 16
|  |  | Domestic, Traditional Meter | 8 |  | Electricity Total |  | 4 | 6 | 70
|  |  | Non Domestic, Smart Meter | 8 |  | Gas
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Domestic, Smart Meter | 1 | 7 | 17
|  | E2E-D002 Total |  | 32 |  |  | Domestic, Traditional Meter | 1 | 7 | 17
|  | E2E-D003 |  |  |  |  | Non Domestic, Smart Meter | 1 | 7 | 21
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 7 | 17
|  |  | Domestic, Traditional Meter | 2 |  | Gas Total |  | 4 | 7 | 72
|  |  | Non Domestic, Smart Meter | 2 |  | SMS
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Service management | 1 | 1 | 7
|  | E2E-D003 Total |  | 8 |  | SMS Total |  | 1 | 1 | 7
|  | E2E-D004 |  |  | 1 Total |  |  | 5 | 19 | 223
|  |  | Domestic, Smart Meter | 2 | 2
|  |  | Domestic, Traditional Meter | 2 |  | Dual
|  |  | Non Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 2 | 6
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  | E2E-D004 Total |  | 8 |  |  | Non Domestic, Smart Meter | 1 | 1 | 4
| Dual Total |  |  | 56 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 4
| Electricity |  |  |  |  | Dual Total |  | 4 | 2 | 18
|  | E2E-E001 |  |  |  | Electricity
|  |  | Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 10 | 15
|  |  | Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 9 | 14
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 9 | 13
|  | E2E-E001 Total |  | 10 |  | Electricity Total |  | 4 | 11 | 54
|  | E2E-E002 |  |  |  | Gas
|  |  | Domestic, Smart Meter | 10 |  |  | Domestic, Smart Meter | 1 | 11 | 16
|  |  | Domestic, Traditional Meter | 8 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 10 |  |  | Non Domestic, Smart Meter | 1 | 8 | 13
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 8 | 11
|  | E2E-E002 Total |  | 36 |  | Gas Total |  | 4 | 11 | 54
|  | E2E-E003 |  |  | 2 Total |  |  | 4 | 24 | 126
|  |  | Domestic, Smart Meter | 2 | Grand Total |  |  | 5 | 43 | 349
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E003 Total |  | 8
E2E-E004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E004 Total |  | 8
E2E-E005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E005 Total |  | 4
E2E-E009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E009 Total |  | 4
| Electricity Total |  |  | 70
Gas
E2E-G001
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G001 Total |  | 10
E2E-G002
|  |  | Domestic, Smart Meter | 8
|  |  | Domestic, Traditional Meter | 8
|  |  | Non Domestic, Smart Meter | 10
|  |  | Non Domestic, Traditional Meter | 8
|  | E2E-G002 Total |  | 34
E2E-G003
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G003 Total |  | 8
E2E-G004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G004 Total |  | 8
E2E-G005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G005 Total |  | 4
E2E-G006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G006 Total |  | 4
E2E-G010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G010 Total |  | 4
| Gas Total |  |  | 72
SMS
E2E-SMS-001
|  |  | Service management | 7
|  | E2E-SMS-001 Total |  | 7
| SMS Total |  |  | 7
1 Total |  |  |  | 223
2
Dual
E2E-D005
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-D005 Total |  | 16
E2E-D006
|  |  | Domestic, Smart Meter | 2
|  | E2E-D006 Total |  | 2
| Dual Total |  |  | 18
Electricity
E2E-E006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E006 Total |  | 4
E2E-E007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E007 Total |  | 4
E2E-E008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E008 Total |  | 4
E2E-E010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E010 Total |  | 4
E2E-E011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E011 Total |  | 4
E2E-E012
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E012 Total |  | 6
E2E-E013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E013 Total |  | 4
E2E-E014
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-E014 Total |  | 16
E2E-E015
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E015 Total |  | 2
E2E-E016
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-E016 Total |  | 4
E2E-E017
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  | E2E-E017 Total |  | 2
| Electricity Total |  |  | 54
Gas
E2E-G007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G007 Total |  | 4
E2E-G008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G008 Total |  | 4
E2E-G009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G009 Total |  | 4
E2E-G011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G011 Total |  | 4
E2E-G012
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G012 Total |  | 4
E2E-G013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 3
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G013 Total |  | 6
E2E-G014
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G014 Total |  | 4
E2E-G015
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-G015 Total |  | 16
E2E-G016
|  |  | Domestic, Smart Meter | 2
|  | E2E-G016 Total |  | 2
E2E-G017
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-G017 Total |  | 4
E2E-G018
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  | E2E-G018 Total |  | 2
| Gas Total |  |  | 54
2 Total |  |  |  | 126
Grand Total |  |  |  | 349

## How To Use (hidden)
How To Use
Contents
1. How to Navigate this document
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Overview of the Test Case worksheets
1. How to Navigate this document
This section aims to provide an overview on how to navigate through this workbook.
The workbook consists of a number of worksheets arranged in a hieracrchy working from left to right.
The 'List of Test Scenarios' is broken down into a 'List of Test Cases', which consist of individual Test Cases.
Within the 'List of Test Scenarios' worksheet each of the Scenarios has a hyperlink ('Click to See Test Cases') which when selected takes the user to the Test Cases associated to the selected scenario on the 'List of Test Cases' worksheet.
. | From here, the user can then navigate to a more detailed view of the Test Scenario by clicking on the 'Click to view Test' link
To return to the 'List of Test Scenarios' worksheet the user would select 'Back to list of Test Scenarios', which will return the user to the top of the List of Test Scenarios worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
This section aims to provide an overview of the information contained in the List of Test Scenarios worksheet
The List of 'Test Scenarios' worksheet details each Test Scenario that will be part of the testing phase and provides links to the scenario and list of test cases that make up the basic scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Scenario Category | A short title of the Scenario being defined
| E2E Scenario | A Unique reference for each Scenario (e.g. E2E-G001 is the first Gas Scenario)
| E2E Scenario Title | A Unique Title for each Test Scenario consisting of the E2E Scenario & Test Scenario Category
| Link | A link to the List of Test Cases appropriate to the Test Scenario
| Test ID | A scenario will require one or more Test Cases to deliver the Test Scenario. The same Test might be used in multiple scenarios. Each Test Case that delivers a particular scenario will be listed in the order they would be executed.
| Link | A link to each Test and Steps that will be used within the scenario
| Test Title | The title of the Test ID. This is defined on the individual Test Case worksheets.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Priority | Test Priority for any Risk Based Testing
| Pre-Requisite Test Scenario | The ID of the Test that must be executed prior to this one to complete a Test Scenario
| Comments | Any additional information regarding the Test Scenario will be provided here
| CSS | Indicates the number of steps the Test Case has defined that interact with CSS
| UK Link | Indicates the number of steps the Test Case has defined that interact with UK Link
| DES | Indicates the number of steps the Test Case has defined that interact with DES
| MPAS | Indicates the number of steps the Test Case has defined that interact with MPAS
| ECOES | Indicates the number of steps the Test Case has defined that interact with ECOES
| Smart Metering | Indicates the number of steps the Test Case has defined that interact with Smart Metering
| Gaining Shipper | Indicates the number of steps the Test Case has defined that interact with a Single Shipper or Gaining Shipper where the Test Scenario involves a two parties
| Losing Shipper | Indicates the number of steps the Test Case has defined that interact with a Losing Shipper where the Test Scenario involves a two parties
| Gas Transporter | Indicates the number of steps the Test Case has defined that interact with a GT or iGT
| Data Collector | Indicates the number of steps the Test Case has defined that interact with a DC
| Data Aggregator | Indicates the number of steps the Test Case has defined that interact with a DA
| MEM | Indicates the number of steps the Test Case has defined that interact with a MEM
| MAP | Indicates the number of steps the Test Case has defined that interact with a MAP
| DNO | Indicator as to whether the Test Case defined has steps that interact with a DNO/iDNO
| Gaining Supplier | Indicates the number of steps the Test Case has defined that interact with a single Supplier or a Gaining Supplier where the Test Scenario involves a two parties
| Losing Supplier | Indicates the number of steps the Test Case has defined that interact with a Losing Supplier where the Test Scenario involves a two parties
Third-Party IT Provider
3. Overview of the 'List of Test Cases' worksheet
This section aims to provide an overview of the information contained in the 'List of Test Cases' worksheet
The List of Test Cases details each variation of the Test Scenarios as Test Cases that will form part of the testing phase, and provides links to the Tests & the steps that make up the each scenario. Which Test Cases an E2E participant needs to execute will depend on the Licensed Parties profile
(see '1. How to Navigate this document' for details on how to navigate to & from the List of Test Cases worksheet)
Where Switching functionality is being tested there will be a matching 'GAIN' and a 'LOSE' Test Case. When executing a Test Case with a paired Supplier, the gaining supplier will execute the GAIN test case, and the losing supplier will execute the matching LOSE test case.
A green line separates the GAIN and LOSE test cases for the same scenario.
A blue line separates each Test Scenario, and the Test Case ID will indicate the Tests that make up a single Test Case for a Scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Case Category | The short title of the Scenario that the Test Case variations cover
| E2E Scenario | The Test Scenario ID of the Scenario that the Test Case variations cover
| Test Case Id | The Test Case ID is a combination of the Test Scenario ID and a unique reference to link each of the Tests that make up the Test Case
| Associated Test Id | Details the actual Test ID
| Link | A hyperlink to each Test Case worksheet that forms part of the Test Case
| Test Case Title | Details the Title of the Test Case from the associated Test Case worksheet, plus the variants in place for this particular Test Case.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Day(s) | Details the number of Days each Switch Test will be assigned. This will be blank where the number of days is not relevant to the Test Case
| Domestic | This will be marked with an 'X' where the Test Case is intended for a Domestic Customer.
| Non Domestic | This will be marked with an 'X' where the Test Case is intended for a Non Domestic Customer.
| OFAF | This will be marked with an 'X' where the Test Case is intended for a Switch of more than one Fuel Type or more than one Meter of the same Fuel Type to ensure the 'One Fail, All Fail' switching rule. The Test Case may not test a Failure in all cases.
| Related MPAN | This will be marked with an 'X' where the Test Case is intended to include related MPANs (Electricity only).
| Pre-Requisite Test Case | Details the Test ID that must have been executed prior to this Test
| Profile | The profile describes the options selected for each Test Case (i.e. where X's have been placed in the previous fields)
| Requirements | The requirements listed are the unique Abacus references documented against the in the relevant Test Case Worksheet
4. Overview of the Test Case worksheets
This section aims to provide an overview of the information contained in each of the Test Case worksheets. For example worksheet E2E-002.
Each Test Case worksheet gives an overview of the Case and the agreed steps that need to be executed. These will be loaded to Jira to form each Test Case per LP and the LP will then be able to expand on the Test Steps within Jira to make them more pertinent to the specific LP's systems and processes.
(see '1. How to Navigate this document' for details on how to navigate to & from each Test Case worksheet)
| The following are the Test Case overview Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Scenario ID | The Test ID (as per the worksheet Name) that is used in the 'List of Test Scenarios' and 'List of Test Cases' worksheets to link Tests to Scenarios and Test Cases
| Title | The Short Title of the Test
| Description | An overview of the objectives of the Test
| Pre-Requisites | Any Pre-Requisites that need to be in place prior to this Test Case being executed
| Test Case Variable | A list of the Test Case variables that this particular Test should cater for.
| Mapped Requirements | A summary of the Abacus requirements that the Test Case covers
| Exception Codes | Exception Codes will not be applicable during E2E Testing, these will have been covered previously in SIT and/or UEPT
| The following are the Test Step Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Mapped Requirements | The Abacus requirement reference(s) that each step covers
| Step Title | A short title outlining the purpose of the step
| Evidence Required | A 'Y' or 'N' indicator to highlight whether the Test Participant would be expected to provide evidence for the step. An 'O' indicates evidence is optional based on whether the agents and registered and have agreed to provide support during testing.
| Step Description | A more detailed description of the purpose of the step
| Related System | The system where the step would be executed
| Pre-requisite | Any Pre-Requisites that this step is dependent upon
| Expected Result | A description of the outcome of this Step
| API (Inbound to CSS) | API details retained from the original SIT tests
| Route | Route details retained from the original SIT tests
| Webhook context (Outbound from CSS) | Webhook context details retained from the original SIT tests
| Event Type | Event Type details retained from the original SIT tests
| Acknowledgement Messages | Acknowledgement Message details retained from the original SIT tests
| Comments | Any additional information / comments regarding the step
At the bottom of each Test Case worksheet are the list of Test Cases where this Test Case is called.
| The following is a brief description of each field in this section: |  | Example:
| Field | Details
| No. | Incremental number for each linked Test Case
| Unique Test Id | The Unique Test ID from the 'List of Test Cases' worksheet for each Test Case where this Test Case is called
| Return to Test Case | A Hyperlink to return directly to the current Test within the Test Case in the 'List of Test Cases' worksheet
| Test Case Title | The Test Case Title from the 'List of Test Cases' worksheet of the Unique Test ID Test Case
| Test Case ID | The Test Case ID from the 'List of Test Cases' worksheet of the Test Case
| E2E Scenario | The E2E Scenario ID from the 'List of Test Cases' worksheet of the Test Case
| Test Case Category | The Test Case Category from the 'List of Test Cases' worksheet of the Test Case
List of Test Scenarios
List of Test Cases

## List MASTER (hidden)
High
Medium
Low
MPAN Ownership
Metering Changes
Meter to Bank
Trad
Smart
Advanced
Unmetered
In Progress
Blocked - Reqt Query
Drafted
Peer Reviewed
Rework
Design Reviewed
WG Reviewed (Working Group Drops)​
WG Approved
TMAG Approved

## Change Log
Date | Author | Release | Defect ID | Reason for change
2023-09-18 | Shaun Magee |  |  | Include missing requirements MHHS-BR-RS-052, MHHS-BR-RS-053, MHHS-BR-RS-054, MHHS-BR-RS-057 and appointment queue processing for Future Dated appointments
2023-09-21 | Shaun Magee |  |  | Missing BR MHHS-BR-RS-075 added to Step 0930 for Customer Direct Contract processing
2023-09-22 | Shaun Magee |  |  | Include missing requirement MHHS-BR-RS-073 by adding extra steps to Related MPAN test cases. Secondary MPANs require a reason of 'RELATED'
2023-09-25 | Shaun Magee |  |  | Following design call, missing BP003 processing applied here to add steps where the published IF-036 and IF-037 are also received by MDS including for Linked/Related steps where appropriate [Note: only applies to Data Service processing]
2023-09-26 | Shaun Magee |  |  | MHHS-BR-RS-073 and MHHS-BR-RS-074 added to Related MPAN Steps where the IF-036 Domestic Premise Indicator notified should be as held in the Registration System as provided by CSS.
2023-09-29 | Shaun Magee |  |  | Replace standard BP002/BP003 processing with shared steps.
2023-10-02 | Shaun Magee |  |  | Updated TC03 to cover off IF-038 that fails validation
2023-10-23 | Shaun Magee |  |  | Removed all data sheet and replaced them with a standard Data Requirement. Added Boundaries and Key Journey events to Overview.
2023-11-27 | Shaun Magee | 5.2.1 v0.1 |  | Remove columns Message Output and Message Output Event Code and Publish
2023-11-29 | Dan Gee | 5.2.1 v0.1 |  | Updated against BP010E as this now falls under this business process. Re mapped step numbers to BP010E
2023-12-20 | Shaun Magee | 5.2.1 v0.2 |  | Acronym changes: UDSI -> UMSDS
2024-03-05 | Shaun Magee | 5.2.1 v0.3 |  | Add 3 new Test Cases to cover IF-038 being rejected via the IF-039. Note: BR MHHS-BR-RS-077 covers both Accepted and Rejected IF-038 Files.
2024-03-15 | Shaun Magee | 5.2.1 v0.3 |  | Merge shared steps
2024-04-05 | Shaun Magee | 5.2.1 v0.4 | 31395 | 1. Amend all test cases to be stand-alone CDC Updates only by removing Change of DS processing 2. Correct recipients of the rejected IF-039 for Smart and Advanced 3. Add 3 new test cases to cover Data Service using Event Code [DirectContractDSRemove] 4 Correct various BR References and all acronyms are now set to current Data Service 5. All MPANs are now Single MPAN with Same Day Effective Time
2024-05-21 | Dan Gee | IR7 v0.5 |  | Updated DIP response message from http 202 response from DIP to http 201 response from DIP
2024-05-30 | Dan Gee | IR7 v0.5.1 | 32494 | Removed less than marker from TC03 test is for current day CDC not retrospective
2024-08-16 | Bhavin Sikotra | IR7 v0.5.2 |  | MHHS-BR-DS-035 Included for all test cases where DS issues out IF-038
2024-08-29 | Bhavin Sikotra | IR7 v0.5.2 |  | MHHS-BR-DS-035 only included to test cases 2 & 8. This has been removed from the other test cases.
2024-09-12 | Izhan Ahsan | IR7 v0.5.2 |  | Removed invalid mapping for MHHS-BR-DS-034 in TC01 & TC02
2024-09-12 | Izhan Ahsan | IR7 v0.5.2 |  | Removed invalid mapping for MHHS-BR-DS-035 from TC02
2024-09-12 | Izhan Ahsan | IR7 v0.5.2 |  | Removed invalid mapping for MHHS-BR-DS-037 from TC06 & TC07
2024-09-13 | Bhavin Sikotra | IR7 v0.5.2 |  | Added MHHSP-BRS001-Data Service-BR-DS-035 to TC05 step 6
2024-09-16 | Izhan Ahsan | IR7 v0.5.2 |  | Removed mapping for MHHS-BR-DS-034 in TC03 and mapping for MHHS-BR-DS-037 TC04
2024-10-09 | Dan Gee | IR7 v0.5.3 | Requirements Update | SITFTS-0180 TC09 updated with coverage mapping for requirement MHHSP-BRS001-Data Service-BR-DS-035
2024-10-24 | Nanda | IR7 v0.5.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC01 for steps 1 and 4
2024-10-24 | Nanda | IR7 v0.5.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC02 for steps 1 and 4
2024-10-24 | Nanda | IR7 v0.5.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC07 for steps 1 and 4
2024-10-24 | Nanda | IR7 v0.5.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC09 for steps 1 and 4
2024-10-28 | Aman Shimpi | IR7 v0.5.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC08 for steps 1 and 4
2024-11-05 | Nanda | IR7 v0.5.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC03 for steps 1 and 4
2024-11-05 | Nanda | IR7 v0.5.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC04 for steps 1 and 4
2024-11-05 | Nanda | IR7 v0.5.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC05 for steps 1 and 4
2025-05-02 | Dan Gee | v0.5.4 | Requirements Update | Removed invalid mapping - TC05 MHHS-BR-DS-037

## SITFTS0180 Overview
Scenario ID | SITFTS-0180
Scenario Title | Appoint DS - Customer Direct Contract
Theme | Registration Data
Description | Existing MPAN - Change Customer Direct Contract via DS Variables 1-3 - Handle scenario where the Customer Direct Contract Add Request is accepted Variable 4-6 - Handle scenario where the Customer Direct Contract Add Request is rejected Variables 7-9 - Handle scenario where the Customer Direct Contract Remove Request is accepted
Functional Category | Appoint DS - Customer Direct Contract
Functional Area 1 | Apply & Maintain Customer Direct Contract (CDC) Marker
Functional Area 2 | Customer contract
Creator | Shaun Magee, Dan Gee
Priority | High
Scenario size | Medium
Design Document Ref
Business Process | BP010E
Pre-Requisites
Boundaries | Processing ends once the Customer Direct Contract have been accepted/rejected
Test Case Variables | (1) smart, Same-day, single MPAN [Add] (2) advanced, Same-day, single MPAN [Add] (3) unmetered, Same-day, single MPAN [Add] (4) unmetered, Same-day, single MPAN and IF-038 fails validation check (5) smart, Same-day, single MPAN and IF-038 fails validation check (6) advanced, Same-day, single MPAN and IF-038 fails validation check (7) smart, Same-day, single MPAN [Remove] (8) advanced, Same-day, single MPAN [Remove] (9) unmetered, Same-day, single MPAN [Remove]
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Case Link | Test Case Version | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITFTS-0180 TC01 | SITFTS-0180 Smart Add CDC | SITFTS-0180 Smart Add | 0.5.2 | Smart Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) | Smart Meter | Single | Same-day
2 | SITFTS-0180 TC02 | SITFTS-0180 Advanced Add CDC | SITFTS-0180 - Advanced Add | 0.5.2 | Advanced Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) | Advanced | Single | Same-day
3 | SITFTS-0180 TC03 | SITFTS-0180 Unmetered Add CDC | SITFTS-0180 - Unmetered Add | 0.5.3 | Unmetered Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) | Unmetered | Single | Same-day
4 | SITFTS-0180 TC04 | SITFTS-0180 Unmetered Reject | SITFTS-0180 - Unmetered Reject | 0.5.2 | Unmetered Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) where the IF-038 Request is rejected | Unmetered | Single | Same-day
5 | SITFTS-0180 TC05 | SITFTS-0180 Smart Reject | SITFTS-0180 - Smart Reject | 0.5.2 0.5.3 | Smart Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) where the IF-038 Request is rejected | Smart Meter | Single | Same-day
6 | SITFTS-0180 TC06 | SITFTS-0180 Advanced Reject | SITFTS-0180 - Advanced Reject | 0.5.2 | Advanced Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) where the IF-038 Request is rejected | Advanced | Single | Same-day
7 | SITFTS-0180 TC07 | SITFTS-0180 Smart Remove CDC | SITFTS-0180 Smart Remove | 0.5.2 | Smart Single MPAN, Same-day Remove Customer Direct Contract with Data Service (as per DES138 data specification) | Smart Meter | Single | Same-day
8 | SITFTS-0180 TC08 | SITFTS-0180 Advanced Remove CDC | SITFTS-0180 Advanced Remove | 0.5.2 | Advanced Single MPAN, Same-day Remove Customer Direct Contract with Data Service (as per DES138 data specification) | Advanced | Single | Same-day
9 | SITFTS-0180 TC09 | SITFTS-0180 Unmetered Remove CDC | SITFTS-0180 Unmetered Remove | 0.5.2 | Unmetered Single MPAN, Same-day Remove Customer Direct Contract with Data Service (as per DES138 data specification) | Unmetered | Single | Same-day
Back to List of
Test Scenarios

## SITFTS0180- Smart Add
| Test Case Id |  |  |  |  | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITFTS-0180 TC01 |  |  |  |  | 0.5.2 | SITFTS-0180 Smart Add CDC | SITFTS-0180 Smart Add | Smart Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) | Smart Meter | Single | Same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0180 Smart Add CDC | Customer Direct Contract Advisory Request | 1 | BP010E | 10 15 20 | MHHS-BR-DS-031 | SDSC | IF-038 | [DirectContractDSAdd] | DIP | SDSC sends IF-038 to DIP | http 201 response from DIP | N
|  | 2 | BP010E | 25 |  | DIP | PUB-038 | [DirectContractDSAdd] | REGS | DIP sends PUB-038 to REGS |  | N
|  | 3 | BP010E | 30 35 | MHHS-BR-RS-075 MHHS-BR-RS-076 | DIP | PUB-038 | [DirectContractDSAdd] | REGS | Registration Service receives PUB-038 | Registration Service receives PUB-038 DirectContractDSAdd with relevant information of customer direct contract. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Customer Direct Contract Advisory Accepted | 4 | BP010E | 60 | MHHS-BR-RS-077 | REGS | IF-039 | [DirectContractDSAdd] & [DI-979] = 'A' | DIP | REGS sends IF-039 to DIP | http 201 response from DIP | N
|  | 5 | BP010E | 65 |  | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | SDSC, SUPC, EES | DIP sends PUB-039 to SDSC, SUPC & EES |  | N
|  | 6 | BP010E | 70 | MHHS-BR-DS-032 MHHS-BR-DS-033 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | SDSC | SDSC receives PUB-039 | SDSC receives PUB-039 DirectContractDSAdd and [DI-979] = 'A' with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 7 | BP010E | 85 | MHHS-BR-SU-030 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | SUPC | Supplier receives PUB-039 | Supplier receives PUB-039 DirectContractDSAdd and [DI-979] = 'A' with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 8 | BP010E | 75 | MHHS-BR-EES-016.3 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | EES | EES receives PUB-039 | EES receives PUB-039 DirectContractDSAdd and [DI-979] = 'A' with relevant information of customer direct contract advisory responses. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS0180- Advanced Add
No. | Test Case Id |  |  |  |  | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
2 | SITFTS-0180 TC02 |  |  |  |  | 0.5.1 | SITFTS-0180 Advanced Add CDC | SITFTS-0180 - Advanced Add | Advanced Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) | Advanced | Single | Same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0180 Advanced Add CDC | Customer Direct Contract Advisory Request | 1 | BP010E | 10 15 20 | MHHS-BR-DS-034 MHHS-BR-DS-031 | ADSC | IF-038 | [DirectContractDSAdd] | DIP | Advanced Data Service sends IF-038 to DIP | http 201 response from DIP | N
|  | 2 | BP010E | 25 |  | DIP | PUB-038 | [DirectContractDSAdd] | REGS | Advanced Data Service sends IF-038 to REGS |  | N
|  | 3 | BP010E | 30 35 | MHHS-BR-RS-075 MHHS-BR-RS-076 | DIP | PUB-038 | [DirectContractDSAdd] | REGS | Registration Service receives PUB-038 | Registration Service receives PUB-038 DirectContractDSAdd with relevant information of customer direct contract. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Customer Direct Contract Advisory Accepted | 4 | BP010E | 60 | MHHS-BR-RS-077 | REGS | IF-039 | [DirectContractDSAdd] & [DI-979] = 'A' | DIP | REGS sends IF-039 to DIP | http 201 response from DIP | N
|  | 5 | BP010E | 65 |  | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | ADSC, SUPC, EES | DIP sends PUB-039 to ADSC, SUPC & EES |  | N
|  | 6 | BP010E | 70 | MHHS-BR-DS-032 MHHS-BR-DS-033 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | ADSC | Advanced data service receives PUB-039 | Advanced data service receives PUB-039 DirectContractDSAdd and [DI-979] = 'A' with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 7 | BP010E | 85 | MHHS-BR-SU-030 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | SUPC | Supplier receives PUB-039 | Supplier receives PUB-039 DirectContractDSAdd and [DI-979] = 'A' with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 8 | BP010E | 75 | MHHS-BR-EES-016.3 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | EES | EES receives PUB-039 | EES receives PUB-039 DirectContractDSAdd and [DI-979] = 'A' with relevant information of customer direct contract advisory responses. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS0180- Unmetered Add
No. | Test Case Id | [5 empty] | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
3 | SITFTS-0180 TC03 | [5 empty] | 0.5.3 | SITFTS-0180 Unmetered Add CDC | SITFTS-0180 - Unmetered Add | Unmetered Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) | Unmetered | Single | Same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0180 Unmetered Add CDC | Customer Direct Contract Advisory Request | 1 | BP010E | 10 15 20 | MHHS-BR-DS-034 | UMSDS | IF-038 | [DirectContractDSAdd] | DIP | Unmetered Data Service sends IF-038 to DIP | http 201 response from DIP | N
|  | 2 | BP010E | 25 |  | DIP | PUB-038 | [DirectContractDSAdd] | REGS | DIP sends PUB-038 to REGS |  | N
|  | 3 | BP010E | 30 40 | MHHS-BR-RS-075 MHHS-BR-RS-076 | DIP | PUB-038 | [DirectContractDSAdd] | REGS | Registration Service receives PUB-038 | Registration Service receives PUB-038 DirectContractDSAdd with relevant information of customer direct contract. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Customer Direct Contract Advisory Accepted | 4 | BP010E | 60 | MHHS-BR-RS-077 | REGS | IF-039 | [DirectContractDSAdd] & [DI-979] = 'A' | DIP | REGS sends IF-039 to DIP | http 201 response from DIP | N
|  | 5 | BP010E | 65 |  | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | UMSDS, SUPC, EES | DIP sends PUB-039 to UMSDS, SUPC & EES |  | N
|  | 6 | BP010E | 70 | MHHS-BR-DS-032 MHHS-BR-DS-033 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | UMSDS | UMSDS receives PUB-039 | UMSDS receives PUB-039 DirectContractDSAdd and [DI-979] = 'A' with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 7 | BP010E | 85 | MHHS-BR-SU-030 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | SUPC | Supplier receives PUB-039 | Supplier receives PUB-039 DirectContractDSAdd and [DI-979] = 'A' with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 8 | BP010E | 75 | MHHS-BR-EES-016.3 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'A' | EES | EES receives PUB-039 | EES receives PUB-039 DirectContractDSAdd and [DI-979] = 'A' with relevant information of customer direct contract advisory responses. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS0180- Unmetered Reject
No. | Test Case Id | [5 empty] | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
4 | SITFTS-0180 TC04 | [5 empty] | 0.5.2 | SITFTS-0180 Unmetered Reject | SITFTS-0180 - Unmetered Reject | Unmetered Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) where the IF-038 Request is rejected | Unmetered | Single | Same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0180 Unmetered Reject | Customer Direct Contract Advisory Request | 1 | BP010E | 10 15 20 | MHHS-BR-DS-034 MHHS-BR-DS-031 | UMSDS | IF-038 | [DirectContractDSAdd] | DIP | Unmetered Data Service sends IF-038 to DIP where the Customer Direct Contract Data Service EffectiveTo Date is < Current Date | http 201 response from DIP | N
|  | 2 | BP010E | 25 |  | DIP | PUB-038 | [DirectContractDSAdd] | REGS | DIP sends PUB-038 to REGS where the Customer Direct Contract Data Service EffectiveTo Date is < Current Date |  | N
|  | 3 | BP010E | 30 35 | MHHS-BR-RS-075 MHHS-BR-RS-076 | DIP | PUB-038 | [DirectContractDSAdd] | REGS | Registration Service receives PUB-038 | Registration Service receives PUB-038 DirectContractDSAdd with relevant information of customer direct contract. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Customer Direct Contract Advisory Rejected | 4 | BP010E | 40 | MHHS-BR-RS-077 | REGS | IF-039 | [DirectContractDSAdd] & [DI-979] = 'R' | DIP | REGS sends IF-039 to DIP with Response Message = 'REG1071 - Contract End Date [DI-146] cannot be in the past' | http 202 response from DIP | N
|  | 5 | BP010E | 45 |  | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'R' | UMSDS | DIP sends PUB-039 to UMSDS with Response Message = 'REG1071 - Contract End Date [DI-146] cannot be in the past' |  | N
|  | 6 | BP010E | 50 | MHHS-BR-DS-032 MHHS-BR-DS-036 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'R' | UMSDS | Unmetered data service receives PUB-039 | Unmetered data service receives PUB-039 DirectContractDSAdd and [DI-979] = 'R' with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS0180- Smart Reject
No. | Test Case Id |  |  |  |  | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
5 | SITFTS-0180 TC05 |  |  |  |  | 0.5.2 0.5.3 |  | SITFTS-0180 - Smart Reject | Smart Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) where the IF-038 Request is rejected | Smart Meter | Single | Same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0180 Smart Reject | Customer Direct Contract Advisory Request | 1 | BP010E | 10 15 20 | MHHS-BR-DS-034 MHHS-BR-DS-031 | SDSC | IF-038 | [DirectContractDSAdd] | DIP | SDSC sends IF-038 to DIP where Customer Direct Contract Data Service EffectiveTo Date < Current Date | http 201 response from DIP | N
|  | 2 | BP010E | 25 |  | DIP | PUB-038 | [DirectContractDSAdd] | REGS | DIP sends PUB-038 to REGS |  | N
|  | 3 | BP010E | 30 35 | MHHS-BR-RS-075 MHHS-BR-RS-076 | DIP | PUB-038 | [DirectContractDSAdd] | REGS | Registration Service receives PUB-038 | Registration Service receives PUB-038 DirectContractDSAdd with relevant information of customer direct contract. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Customer Direct Contract Advisory Rejected | 4 | BP010E | 40 | MHHS-BR-RS-077 | REGS | IF-039 | [DirectContractDSAdd] & [DI-979] = 'R' | DIP | REGS sends IF-039 to DIP where Response Message [DI-980] = 'REG1071 - Contract End Date [DI-146] cannot be in the past' | http 201 response from DIP | N
|  | 5 | BP010E | 45 |  | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'R' | SDSC | DIP sends PUB-039 to SDSC |  | N
|  | 6 | BP010E | 50 | MHHS-BR-DS-032 MHHS-BR-DS-036 MHHS-BR-DS-037 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'R' | SDSC | SDSC receives PUB-039 and manages the CDC Request Rejection | SDSC receives PUB-039 DirectContractDSAdd and [DI-979] = 'R' with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS0180- Advanced Reject
No. | Test Case Id |  |  |  |  | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
6 | SITFTS-0180 TC06 |  |  |  |  | 0.5.2 | SITFTS-0180 Advanced Reject | SITFTS-0180 - Advanced Reject | Advanced Single MPAN, Same-day Add Customer Direct Contract with Data Service (as per DES138 data specification) where the IF-038 Request is rejected | Advanced | Single | Same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0180 Advanced Reject | Customer Direct Contract Advisory Request | 1 | BP010E | 10 15 20 | MHHS-BR-DS-034 MHHS-BR-DS-031 | ADSC | IF-038 | [DirectContractDSAdd] | DIP | ADSC sends IF-038 to DIP where Customer Direct Contract Data Service EffectiveTo Date > System Date + 3 years | http 201 response from DIP | N
|  | 2 | BP010E | 25 |  | DIP | PUB-038 | [DirectContractDSAdd] | REGS | Advanced Data Service sends IF-038 to REGS |  | N
|  | 3 | BP010E | 30 35 | MHHS-BR-RS-075 MHHS-BR-RS-076 | DIP | PUB-038 | [DirectContractDSAdd] | REGS | Registration Service receives PUB-038 | Registration Service receives PUB-038 DirectContractDSAdd with relevant information of customer direct contract. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
SITFTS-0180 - Advanced Reject | Customer Direct Contract Advisory Rejected | 4 | BP010E | 40 | MHHS-BR-RS-077 | REGS | IF-039 | [DirectContractDSAdd] & [DI-979] = 'R' | DIP | REGS sends IF-039 to DIP where Response Message [DI-980] = ' REG1072 - Customer Direct Contract End Date [DI-146] cannot extend beyond 3 years' | http 201 response from DIP | N
|  | 5 | BP010E | 45 |  | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'R' | ADSC | DIP sends PUB-039 to ADSC |  | N
|  | 6 | BP010E | 50 | MHHS-BR-DS-032 MHHS-BR-DS-036 | DIP | PUB-039 | [DirectContractDSAdd] & [DI-979] = 'R' | ADSC | ADSC receives PUB-039 and manages the CDC Request Rejection | ADSC receives PUB-039 DirectContractDSAdd and [DI-979] = 'R' with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS0180- Smart Remove
No. | Test Case Id |  |  |  |  | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
7 | SITFTS-0180 TC07 |  |  |  |  | 0.5.2 |  | SITFTS-0180 Smart Remove | Smart Single MPAN, Same-day Remove Customer Direct Contract with Data Service (as per DES138 data specification) | Smart Meter | Single | Same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0180 Smart Remove CDC | Customer Direct Contract Advisory Request | 1 | BP010E | 10 15 20 | MHHS-BR-DS-034 MHHS-BR-DS-031 MHHSP-BRS001-Data Service-BR-DS-035 | SDSC | IF-038 | [DirectContractDSRemove] | DIP | SDSC sends IF-038 to DIP | http 201 response from DIP | N
|  | 2 | BP010E | 25 |  | DIP | PUB-038 | [DirectContractDSRemove] | REGS | DIP sends PUB-038 to REGS |  | N
|  | 3 | BP010E | 30 35 | MHHS-BR-RS-075 MHHS-BR-RS-076 | DIP | PUB-038 | [DirectContractDSRemove] | REGS | Registration Service receives PUB-038 | Registration Service receives PUB-038 DirectContractDSRemove with relevant information of customer direct contract. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Customer Direct Contract Advisory Accepted | 4 | BP010E | 60 | MHHS-BR-RS-077 | REGS | IF-039 | [DirectContractDSRemove] | DIP | REGS sends IF-039 to DIP | http 201 response from DIP | N
|  | 5 | BP010E | 65 |  | DIP | PUB-039 | [DirectContractDSRemove] | SDSC, EES | DIP sends PUB-039 to SDSC & EES |  | N
|  | 6 | BP010E | 70 | MHHS-BR-DS-032 MHHS-BR-DS-033 | DIP | PUB-039 | [DirectContractDSRemove] | SDSC | SDSC receives PUB-039 | SDSC receives PUB-039 DirectContractDSRemove with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 7 | BP010E | 75 | MHHS-BR-EES-016.3 | DIP | PUB-039 | [DirectContractDSRemove] | EES | EES receives PUB-039 | EES receives PUB-039 DirectContractDSRemove with relevant information of customer direct contract advisory responses. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS0180- Advanced Remove
No. | Test Case Id |  |  |  |  | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
8 | SITFTS-0180 TC08 |  |  |  |  | 0.5.2 | SITFTS-0180 Advanced Remove CDC | SITFTS-0180 Advanced Remove | Advanced Single MPAN, Same-day Remove Customer Direct Contract with Data Service (as per DES138 data specification) | Advanced | Single | Same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0180 Advanced Remove CDC | Customer Direct Contract Advisory Request | 1 | BP010E | 10 15 20 | MHHS-BR-DS-034 MHHS-BR-DS-031 MHHS-BR-DS-035 | ADSC | IF-038 | [DirectContractDSRemove] | DIP | ADSC sends IF-038 to DIP | http 201 response from DIP | N
|  | 2 | BP010E | 25 |  | DIP | PUB-038 | [DirectContractDSRemove] | REGS | DIP sends PUB-038 to REGS |  | N
|  | 3 | BP010E | 30 35 | MHHS-BR-RS-075 MHHS-BR-RS-076 | DIP | PUB-038 | [DirectContractDSRemove] | REGS | Registration Service receives PUB-038 | Registration Service receives PUB-038 DirectContractDSRemove with relevant information of customer direct contract. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Customer Direct Contract Advisory Accepted | 4 | BP010E | 60 | MHHS-BR-RS-077 | REGS | IF-039 | [DirectContractDSRemove] | DIP | REGS sends IF-039 to DIP | http 201 response from DIP | N
|  | 5 | BP010E | 65 |  | DIP | PUB-039 | [DirectContractDSRemove] | ADSC, EES | DIP sends PUB-039 to ADSC & EES |  | N
|  | 6 | BP010E | 70 | MHHS-BR-DS-032 MHHS-BR-DS-033 | DIP | PUB-039 | [DirectContractDSRemove] | ADSC | ADSC receives PUB-039 | ADSC receives PUB-039 DirectContractDSRemove with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 7 | BP010E | 75 | MHHS-BR-EES-016.3 | DIP | PUB-039 | [DirectContractDSRemove] | EES | EES receives PUB-039 | EES receives PUB-039 DirectContractDSRemove with relevant information of customer direct contract advisory responses. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS0180- Unmetered Remove
No. | Test Case Id |  |  |  |  | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
9 | SITFTS-0180 TC09 |  |  |  |  | 0.5.2 | SITFTS-0180 Unmetered Remove CDC | SITFTS-0180 Unmetered Remove | Unmetered Single MPAN, Same-day Remove Customer Direct Contract with Data Service (as per DES138 data specification) | Unmetered | Single | Same-day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0180 Unmetered Remove CDC | Customer Direct Contract Advisory Request | 1 | BP010E | 10 15 20 | MHHS-BR-DS-034 MHHS-BR-DS-031 MHHSP-BRS001-Data Service-BR-DS-035 | UMSDS | IF-038 | [DirectContractDSRemove] | DIP | UMSDS sends IF-038 to DIP | http 201 response from DIP | N
|  | 2 | BP010E | 25 |  | DIP | PUB-038 | [DirectContractDSRemove] | REGS | DIP sends PUB-038 to REGS |  | N
|  | 3 | BP010E | 30 35 | MHHS-BR-RS-075 MHHS-BR-RS-076 | DIP | PUB-038 | [DirectContractDSRemove] | REGS | Registration Service receives PUB-038 | Registration Service receives PUB-038 DirectContractDSRemove with relevant information of customer direct contract. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Customer Direct Contract Advisory Accepted | 4 | BP010E | 60 | MHHS-BR-RS-077 | REGS | IF-039 | [DirectContractDSRemove] | DIP | REGS sends IF-039 to DIP | http 201 response from DIP | N
|  | 5 | BP010E | 65 |  | DIP | PUB-039 | [DirectContractDSRemove] | UMSDS, EES | DIP sends PUB-039 to UMSDS & EES |  | N
|  | 6 | BP010E | 70 | MHHS-BR-DS-032 MHHS-BR-DS-033 | DIP | PUB-039 | [DirectContractDSRemove] | UMSDS | UMSDS receives PUB-039 | UMSDS receives PUB-039 DirectContractDSRemove with relevant information of customer direct contract updates. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 7 | BP010E | 75 | MHHS-BR-EES-016.3 | DIP | PUB-039 | [DirectContractDSRemove] | EES | EES receives PUB-039 | EES receives PUB-039 DirectContractDSRemove with relevant information of customer direct contract advisory responses. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## DPCache_List of Test Scenarios (hidden)
Test Category | Test Scenario | Scenario Title | Test Cases Link | Test ID | Test Scenario Link | Status Date | Status | Test Title | Priority | Pre-Requisite Test Scenario
Advisory Notification | E2E-001 | SITFTS-001 - Advisory Notification | Click to See Test Cases | E2E-001 | Click to view Test | 2023-02-09 | WG Reviewed (Working Group Drops)​ | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Advisory Notification | E2E-E004 | E2E-E004 - Advisory Notification | Click to See Test Cases | E2E-004 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-G006 |  | Click to See Test Cases | E2E-006 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-E007 | E2E-E007 - Switch Request Objection | Click to See Test Cases | E2E-007 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Objection | E2E-D008 |  | Click to See Test Cases | E2E-008 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Successful | E2E-G012 | E2E-G012 - Switch Request Successful | Click to See Test Cases | E2E-012 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA
Switch Request Successful | E2E-E011 |  | Click to See Test Cases | E2E-011 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA