## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Front Cover (hidden)
SWITCHING PROGRAMME
E2E Test Scenarios
Reference: NCT-0045
Version: v0.3

## Change Control (hidden)
Confidentiality Statement
The information contained herein is for the purpose of the MHHS Programme. This document may not be copied, or communicated to a third party, or used, for any purpose other than that for which it is supplied without the express written consent of the MHHS Programme
Distribution List
Name | Organisation
Document History
Issue No. | Issue Date | Issued by | Change Description
0.1 | 2023-02-10 | Dean Bailey | First Draft & QA Checked
Reviewed By
Version | Date | Name | Title / Responsibility
0.1
Approvals
Version | Date | Name | Title / Responsibility

## Sheet1 (hidden)
(empty)

## Sheet2 (hidden)
Data returned for Distinct Count of Profile, 1 - Dual (First 1000 rows).
ListTestCases[Test Case Category] | ListTestCases[E2E Scenario] | ListTestCases[Test Case Id] | ListTestCases[Test Case Title] | ListTestCases[Domestic] | ListTestCases[Non Domestic] | ListTestCases[Smart] | ListTestCases[Non Smart] | ListTestCases[Associated Test Scenario Id] | ListTestCases[Pre-Requisite Test Case] | ListTestCases[Regression Tests] | ListTestCases[Profile] | ListTestCases[Unique ID]
Switch Request Objection | E2E-D001 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-004-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-004-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity)) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-G001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  | X | X | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-004-03 | Gaining Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-G001 | E2E-010-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-007-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-010-04 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-004-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-L001 | E2E-010-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-L001 | E2E-007-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-004-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-L001 | E2E-010-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-L001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Traditional - Gas, Smart Meter - Electricity) | X |  | X | X | E2E-010-L001 | E2E-007-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-004-06 | Losing Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-L001 | E2E-010-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Successful | E2E-D002 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-013-01 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-016-01 | Gaining Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-G001 | E2E-013-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-013-02 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-016-02 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-G001 | E2E-013-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-013-03 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-016-03 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-G001 | E2E-013-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-013-04 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-016-04 | Gaining Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-G001 | E2E-013-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-013-05 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-016-05 | Losing Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-L001 | E2E-013-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-013-06 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-016-06 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-L001 | E2E-013-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-013-07 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-016-07 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-L001 | E2E-013-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-013-08 | Losing Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-016-08 | Losing Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-L001 | E2E-013-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Withdrawal | E2E-D003 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-019-01 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-G001 | E2E-10-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-019-02 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-019-03 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-019-04 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-G001 | E2E-010-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-019-05 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-010-06 | LosingSupplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-019-06 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-019-07 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-019-08 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-L001 | E2E-010-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Annulment | E2E-D004 | E2E-007-01 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-010-01 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-022-01 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-007-02 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-010-02 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-022-02 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-007-03 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-010-03 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meter with Primary MPAN) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-022-03 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-007-04 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-G001 | NA |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-010-04 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic,Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-022-04 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-G001 | E2E-010-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-007-05 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-010-05 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-022-05 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-007-06 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-010-06 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-022-06 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-007-07 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-010-07 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic smart Meter with Primary MPAN) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-022-07 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-007-08 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-010-08 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-022-08 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-L001 | E2E-010-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4

## Summary (hidden)
Test Scenario View |  |  |  |  | Summary
Priority | Fuel Type | E2E Scenario | Profile | Test Cases | Priority | Fuel Type | Profile | Distinct Count of Profile | Distinct Count of E2E Scenario | Test Cases
1 |  |  |  |  | 1
| All |  |  |  |  | All
|  | E2E-GED-001 |  |  |  |  | Domestic, Smart Meter | 1 | 1 | 6
|  |  | Domestic, Smart Meter | 6 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  |  | Domestic, Traditional Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 1 | 3
|  |  | Non Domestic, Smart Meter | 3 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 5
|  |  | Non Domestic, Traditional Meter | 5 |  | All Total |  | 4 | 1 | 18
|  | E2E-GED-001 Total |  | 18 |  | Dual
| All Total |  |  | 18 |  |  | Domestic, Smart Meter | 1 | 4 | 14
| Dual | [5 empty] | Domestic, Traditional Meter | 1 | 4 | 14
|  | E2E-D001 |  |  |  |  | Non Domestic, Smart Meter | 1 | 4 | 14
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 4 | 14
|  |  | Domestic, Traditional Meter | 2 |  | Dual Total |  | 4 | 4 | 56
|  |  | Non Domestic, Smart Meter | 2 |  | Electricity
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Smart Meter | 1 | 6 | 18
|  | E2E-D001 Total |  | 8 |  |  | Domestic, Traditional Meter | 1 | 6 | 16
|  | E2E-D002 |  |  |  |  | Non Domestic, Smart Meter | 1 | 6 | 20
|  |  | Domestic, Smart Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 6 | 16
|  |  | Domestic, Traditional Meter | 8 |  | Electricity Total |  | 4 | 6 | 70
|  |  | Non Domestic, Smart Meter | 8 |  | Gas
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Domestic, Smart Meter | 1 | 7 | 17
|  | E2E-D002 Total |  | 32 |  |  | Domestic, Traditional Meter | 1 | 7 | 17
|  | E2E-D003 |  |  |  |  | Non Domestic, Smart Meter | 1 | 7 | 21
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 7 | 17
|  |  | Domestic, Traditional Meter | 2 |  | Gas Total |  | 4 | 7 | 72
|  |  | Non Domestic, Smart Meter | 2 |  | SMS
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Service management | 1 | 1 | 7
|  | E2E-D003 Total |  | 8 |  | SMS Total |  | 1 | 1 | 7
|  | E2E-D004 |  |  | 1 Total |  |  | 5 | 19 | 223
|  |  | Domestic, Smart Meter | 2 | 2
|  |  | Domestic, Traditional Meter | 2 |  | Dual
|  |  | Non Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 2 | 6
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  | E2E-D004 Total |  | 8 |  |  | Non Domestic, Smart Meter | 1 | 1 | 4
| Dual Total |  |  | 56 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 4
| Electricity |  |  |  |  | Dual Total |  | 4 | 2 | 18
|  | E2E-E001 |  |  |  | Electricity
|  |  | Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 10 | 15
|  |  | Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 9 | 14
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 9 | 13
|  | E2E-E001 Total |  | 10 |  | Electricity Total |  | 4 | 11 | 54
|  | E2E-E002 |  |  |  | Gas
|  |  | Domestic, Smart Meter | 10 |  |  | Domestic, Smart Meter | 1 | 11 | 16
|  |  | Domestic, Traditional Meter | 8 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 10 |  |  | Non Domestic, Smart Meter | 1 | 8 | 13
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 8 | 11
|  | E2E-E002 Total |  | 36 |  | Gas Total |  | 4 | 11 | 54
|  | E2E-E003 |  |  | 2 Total |  |  | 4 | 24 | 126
|  |  | Domestic, Smart Meter | 2 | Grand Total |  |  | 5 | 43 | 349
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E003 Total |  | 8
E2E-E004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E004 Total |  | 8
E2E-E005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E005 Total |  | 4
E2E-E009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E009 Total |  | 4
| Electricity Total |  |  | 70
Gas
E2E-G001
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G001 Total |  | 10
E2E-G002
|  |  | Domestic, Smart Meter | 8
|  |  | Domestic, Traditional Meter | 8
|  |  | Non Domestic, Smart Meter | 10
|  |  | Non Domestic, Traditional Meter | 8
|  | E2E-G002 Total |  | 34
E2E-G003
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G003 Total |  | 8
E2E-G004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G004 Total |  | 8
E2E-G005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G005 Total |  | 4
E2E-G006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G006 Total |  | 4
E2E-G010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G010 Total |  | 4
| Gas Total |  |  | 72
SMS
E2E-SMS-001
|  |  | Service management | 7
|  | E2E-SMS-001 Total |  | 7
| SMS Total |  |  | 7
1 Total |  |  |  | 223
2
Dual
E2E-D005
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-D005 Total |  | 16
E2E-D006
|  |  | Domestic, Smart Meter | 2
|  | E2E-D006 Total |  | 2
| Dual Total |  |  | 18
Electricity
E2E-E006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E006 Total |  | 4
E2E-E007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E007 Total |  | 4
E2E-E008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E008 Total |  | 4
E2E-E010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E010 Total |  | 4
E2E-E011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E011 Total |  | 4
E2E-E012
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E012 Total |  | 6
E2E-E013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E013 Total |  | 4
E2E-E014
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-E014 Total |  | 16
E2E-E015
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E015 Total |  | 2
E2E-E016
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-E016 Total |  | 4
E2E-E017
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  | E2E-E017 Total |  | 2
| Electricity Total |  |  | 54
Gas
E2E-G007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G007 Total |  | 4
E2E-G008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G008 Total |  | 4
E2E-G009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G009 Total |  | 4
E2E-G011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G011 Total |  | 4
E2E-G012
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G012 Total |  | 4
E2E-G013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 3
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G013 Total |  | 6
E2E-G014
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G014 Total |  | 4
E2E-G015
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-G015 Total |  | 16
E2E-G016
|  |  | Domestic, Smart Meter | 2
|  | E2E-G016 Total |  | 2
E2E-G017
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-G017 Total |  | 4
E2E-G018
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  | E2E-G018 Total |  | 2
| Gas Total |  |  | 54
2 Total |  |  |  | 126
Grand Total |  |  |  | 349

## How To Use (hidden)
How To Use
Contents
1. How to Navigate this document
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Overview of the Test Case worksheets
1. How to Navigate this document
This section aims to provide an overview on how to navigate through this workbook.
The workbook consists of a number of worksheets arranged in a hieracrchy working from left to right.
The 'List of Test Scenarios' is broken down into a 'List of Test Cases', which consist of individual Test Cases.
Within the 'List of Test Scenarios' worksheet each of the Scenarios has a hyperlink ('Click to See Test Cases') which when selected takes the user to the Test Cases associated to the selected scenario on the 'List of Test Cases' worksheet.
. | From here, the user can then navigate to a more detailed view of the Test Scenario by clicking on the 'Click to view Test' link
To return to the 'List of Test Scenarios' worksheet the user would select 'Back to list of Test Scenarios', which will return the user to the top of the List of Test Scenarios worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
This section aims to provide an overview of the information contained in the List of Test Scenarios worksheet
The List of 'Test Scenarios' worksheet details each Test Scenario that will be part of the testing phase and provides links to the scenario and list of test cases that make up the basic scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Scenario Category | A short title of the Scenario being defined
| E2E Scenario | A Unique reference for each Scenario (e.g. E2E-G001 is the first Gas Scenario)
| E2E Scenario Title | A Unique Title for each Test Scenario consisting of the E2E Scenario & Test Scenario Category
| Link | A link to the List of Test Cases appropriate to the Test Scenario
| Test ID | A scenario will require one or more Test Cases to deliver the Test Scenario. The same Test might be used in multiple scenarios. Each Test Case that delivers a particular scenario will be listed in the order they would be executed.
| Link | A link to each Test and Steps that will be used within the scenario
| Test Title | The title of the Test ID. This is defined on the individual Test Case worksheets.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Priority | Test Priority for any Risk Based Testing
| Pre-Requisite Test Scenario | The ID of the Test that must be executed prior to this one to complete a Test Scenario
| Comments | Any additional information regarding the Test Scenario will be provided here
| CSS | Indicates the number of steps the Test Case has defined that interact with CSS
| UK Link | Indicates the number of steps the Test Case has defined that interact with UK Link
| DES | Indicates the number of steps the Test Case has defined that interact with DES
| MPAS | Indicates the number of steps the Test Case has defined that interact with MPAS
| ECOES | Indicates the number of steps the Test Case has defined that interact with ECOES
| Smart Metering | Indicates the number of steps the Test Case has defined that interact with Smart Metering
| Gaining Shipper | Indicates the number of steps the Test Case has defined that interact with a Single Shipper or Gaining Shipper where the Test Scenario involves a two parties
| Losing Shipper | Indicates the number of steps the Test Case has defined that interact with a Losing Shipper where the Test Scenario involves a two parties
| Gas Transporter | Indicates the number of steps the Test Case has defined that interact with a GT or iGT
| Data Collector | Indicates the number of steps the Test Case has defined that interact with a DC
| Data Aggregator | Indicates the number of steps the Test Case has defined that interact with a DA
| MEM | Indicates the number of steps the Test Case has defined that interact with a MEM
| MAP | Indicates the number of steps the Test Case has defined that interact with a MAP
| DNO | Indicator as to whether the Test Case defined has steps that interact with a DNO/iDNO
| Gaining Supplier | Indicates the number of steps the Test Case has defined that interact with a single Supplier or a Gaining Supplier where the Test Scenario involves a two parties
| Losing Supplier | Indicates the number of steps the Test Case has defined that interact with a Losing Supplier where the Test Scenario involves a two parties
Third-Party IT Provider
3. Overview of the 'List of Test Cases' worksheet
This section aims to provide an overview of the information contained in the 'List of Test Cases' worksheet
The List of Test Cases details each variation of the Test Scenarios as Test Cases that will form part of the testing phase, and provides links to the Tests & the steps that make up the each scenario. Which Test Cases an E2E participant needs to execute will depend on the Licensed Parties profile
(see '1. How to Navigate this document' for details on how to navigate to & from the List of Test Cases worksheet)
Where Switching functionality is being tested there will be a matching 'GAIN' and a 'LOSE' Test Case. When executing a Test Case with a paired Supplier, the gaining supplier will execute the GAIN test case, and the losing supplier will execute the matching LOSE test case.
A green line separates the GAIN and LOSE test cases for the same scenario.
A blue line separates each Test Scenario, and the Test Case ID will indicate the Tests that make up a single Test Case for a Scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Case Category | The short title of the Scenario that the Test Case variations cover
| E2E Scenario | The Test Scenario ID of the Scenario that the Test Case variations cover
| Test Case Id | The Test Case ID is a combination of the Test Scenario ID and a unique reference to link each of the Tests that make up the Test Case
| Associated Test Id | Details the actual Test ID
| Link | A hyperlink to each Test Case worksheet that forms part of the Test Case
| Test Case Title | Details the Title of the Test Case from the associated Test Case worksheet, plus the variants in place for this particular Test Case.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Day(s) | Details the number of Days each Switch Test will be assigned. This will be blank where the number of days is not relevant to the Test Case
| Domestic | This will be marked with an 'X' where the Test Case is intended for a Domestic Customer.
| Non Domestic | This will be marked with an 'X' where the Test Case is intended for a Non Domestic Customer.
| OFAF | This will be marked with an 'X' where the Test Case is intended for a Switch of more than one Fuel Type or more than one Meter of the same Fuel Type to ensure the 'One Fail, All Fail' switching rule. The Test Case may not test a Failure in all cases.
| Related MPAN | This will be marked with an 'X' where the Test Case is intended to include related MPANs (Electricity only).
| Pre-Requisite Test Case | Details the Test ID that must have been executed prior to this Test
| Profile | The profile describes the options selected for each Test Case (i.e. where X's have been placed in the previous fields)
| Requirements | The requirements listed are the unique Abacus references documented against the in the relevant Test Case Worksheet
4. Overview of the Test Case worksheets
This section aims to provide an overview of the information contained in each of the Test Case worksheets. For example worksheet E2E-002.
Each Test Case worksheet gives an overview of the Case and the agreed steps that need to be executed. These will be loaded to Jira to form each Test Case per LP and the LP will then be able to expand on the Test Steps within Jira to make them more pertinent to the specific LP's systems and processes.
(see '1. How to Navigate this document' for details on how to navigate to & from each Test Case worksheet)
| The following are the Test Case overview Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Scenario ID | The Test ID (as per the worksheet Name) that is used in the 'List of Test Scenarios' and 'List of Test Cases' worksheets to link Tests to Scenarios and Test Cases
| Title | The Short Title of the Test
| Description | An overview of the objectives of the Test
| Pre-Requisites | Any Pre-Requisites that need to be in place prior to this Test Case being executed
| Test Case Variable | A list of the Test Case variables that this particular Test should cater for.
| Mapped Requirements | A summary of the Abacus requirements that the Test Case covers
| Exception Codes | Exception Codes will not be applicable during E2E Testing, these will have been covered previously in SIT and/or UEPT
| The following are the Test Step Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Mapped Requirements | The Abacus requirement reference(s) that each step covers
| Step Title | A short title outlining the purpose of the step
| Evidence Required | A 'Y' or 'N' indicator to highlight whether the Test Participant would be expected to provide evidence for the step. An 'O' indicates evidence is optional based on whether the agents and registered and have agreed to provide support during testing.
| Step Description | A more detailed description of the purpose of the step
| Related System | The system where the step would be executed
| Pre-requisite | Any Pre-Requisites that this step is dependent upon
| Expected Result | A description of the outcome of this Step
| API (Inbound to CSS) | API details retained from the original SIT tests
| Route | Route details retained from the original SIT tests
| Webhook context (Outbound from CSS) | Webhook context details retained from the original SIT tests
| Event Type | Event Type details retained from the original SIT tests
| Acknowledgement Messages | Acknowledgement Message details retained from the original SIT tests
| Comments | Any additional information / comments regarding the step
At the bottom of each Test Case worksheet are the list of Test Cases where this Test Case is called.
| The following is a brief description of each field in this section: |  | Example:
| Field | Details
| No. | Incremental number for each linked Test Case
| Unique Test Id | The Unique Test ID from the 'List of Test Cases' worksheet for each Test Case where this Test Case is called
| Return to Test Case | A Hyperlink to return directly to the current Test within the Test Case in the 'List of Test Cases' worksheet
| Test Case Title | The Test Case Title from the 'List of Test Cases' worksheet of the Unique Test ID Test Case
| Test Case ID | The Test Case ID from the 'List of Test Cases' worksheet of the Test Case
| E2E Scenario | The E2E Scenario ID from the 'List of Test Cases' worksheet of the Test Case
| Test Case Category | The Test Case Category from the 'List of Test Cases' worksheet of the Test Case
List of Test Scenarios
List of Test Cases

## List MASTER (hidden)
High
Medium
Low
MPAN Ownership
Metering Changes
Meter to Bank
Trad
Smart
Advanced
Unmetered
In Progress
Blocked - Reqt Query
Drafted
Peer Reviewed
Rework
Design Reviewed
WG Reviewed (Working Group Drops)​
WG Approved
TMAG Approved

## Change Log
Date | Author | Release | Defect ID | Reason for change
2023-10-27 | Shaun Magee |  |  | Initial Draft started
2023-12-13 | Dan Gee | 5.2.1 v0.1 |  | Removed D0383 & D0384 from advanced scenarios and added commentry of the back of the issing of D0142 based on PP feedback
2023-12-14 | Dan Gee | 5.2.1 v0.1 |  | Updated Data Service and Meter service Acronyms inline with DES138. Message Output and Message output code removed
2024-02-15 | Dan Gee | 5.2.1 v0.2 |  | Updated Effective Time on TC04 to match what is in overview - Current Day
2024-03-07 | Dan Gee | 5.2.1 v0.3 |  | Updated sender on Tests 01,02 & 03 To SMSC from AMSC these are smart and trad tests
2024-03-28 | Dan Gee | 5.2.1 v0.4 | 31391 | Removed D0149 Based on Defect 31391 D0150 and D0010 confirmed to remain in test case by design team for removed Trad meter
2024-04-24 | Dan Gee | 5.2.1 v0.5 | 32126 | Removed D0149 on TC05 Meter removals do not receive the D0149
2024-05-15 | Suraj Kadam | IR7 v0.6 |  | Replaced DIP response from "http 202 response from DIP" to "http 201 response from DIP" wherever needed
2024-05-15 | Suraj Kadam | IR7 v0.6 |  | Added column "Test Case Version" in SITFTS0905 Overview and TC01 to TC06
2024-06-04 | Dan Gee | IR7 v0.6.1 | 32727 & 32854 | Amended wording on TC's 01, 02, 03, 04 & 06 that IF-041 still gets issued of the back of completion of meter work with the IF-005 and will be received however will not be processed due to not receving MTD's due to validation failure. Pre Req also added for PP's to understand the process.
2024-08-15 | Dan Gee | IR7 v0.6.2 | RTTM Updates | New Test case created TC07 that covers requirements for sending D0002 & D0211 By the meter service and receiving those flows by the supplier - MHHS-BR-MS-052, MHHS-BR-MS-053, MHHS-BR-SU-067 & MHHS-BR-SU-068
2024-08-27 | Dan Gee | IR7 v0.6.3 | 38986 | Updated Data flow on TC07 from D0211 to D0221 removed D0002 steps from TC07 and created new test case TC08 to cover trigger of D0002 Fault Resolution Report and its requirments MHHSP-BRS002-MSA-MSS-BR-MS-052 & MHHSP-BRS004-Supplier-BR-SU-067
2024-09-13 | Dan Gee | IR7 v0.6.4 | 40622 | Amended incorrect text to TC04 refering to meter removal when test is to install a a meter not remove
2024-10-08 | Dan Gee | IR7 v0.6.5 | Requirements Update | SITFTS-0905 TC09 & TC10 created to add Advanced coverage to requirements MHHSP-BRS002-MSA-MSS-BR-MS-052 & MHHSP-BRS002-MSA-MSS-BR-MS-053

## SITFTS0905 Overview
Scenario ID | SITFTS-0905
Scenario Title | Change of meter - Registration Service and Meter Service Rejections
Theme | Metering Changes
Description | Changes of Meter where the Registration Update (IF-005) is rejected TC01 to TC06 or Metering work has not been completed by the metering service TC07 to TC10
Functional Category | Metering Changes (install, exchange or removal)
Functional Area 1 | Metering Changes
Functional Area 2 | Change of meter
Creator | Shaun Magee
Priority | High
Scenario size | Large (TC01 to TC06) Small (TC07 to TC10)
Design Document Ref
Business Process | BP009
Pre-Requisites
Boundaries | The test ends once the Rejection Message has been sent TC01 to TC06 The test ends when Supplier is notified that metering work has not been completed (TC07 to TC10)
Test Case Variables | (1) traditional--> smart SMETS2 exchange (2) smart SMETS1 --> smart SMETS2 exchange (3) Smart SMETS2 installation (4) Advanced installation (5) traditional, removal (6) Advanced, removal (7) Smart Install (Metering work does not go ahead) (8) Smart Install (Fault Resolution Report) (9) Advanced (Metering work does not go ahead) (10) Advanced (Fault Resolution Report)
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Case Link | Test Case Version | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITFTS-0905 TC01 | SITFTS-0905 - Traditional to Smart Meter Exchange | SITFTS-0905 TC01 | 0.6.2 | Single Traditional Meter to be Exchanged to Smart SMETS 2 Meter (as per DES138 data specification) where the reported Meter ID removed does not match the currently installed Meter ID | Traditional --> Smart SMETS2 | Single | Current Day
2 | SITFTS-0905 TC02 | SITFTS-0905 - Smart to Smart Meter Exchange | SITFTS-0905 TC02 | 0.6.2 | Single Smart Meter SMETS 1 to be Exchanged to Smart SMETS 2 Meter (as per DES138 data specification) where the reported Meter Removal Date is before the current Meter Install Date | Smart SMETS1 --> Smart SMETS2 | Single | Current Day
3 | SITFTS-0905 TC03 | SITFTS-0905 - Smart Install | SITFTS-0905 TC03 | 0.6.2 | Non metered site install Smart SMETS 2 Meter (as per DES138 data specification) where the reported Meter ID installed already exists on another MPAN | Smart SMETS 2 | Single | Current Day
4 | SITFTS-0905 TC04 | SITFTS-0905 - Advanced Install | SITFTS-0905 TC04 | 0.6.3 | Non metered site install Advanced Meter (as per DES138 data specification) where the reported Modified Meter ID has been entered | Advanced | Single | Current Day
5 | SITFTS-0905 TC05 | SITFTS-0905 - Traditional Meter Removal | SITFTS-0905 TC05 | 0.6.1 | Single Traditional Meter to be removed (as per DES138 data specification) where the reported Modified Meter ID has been entered | Traditional | Single | Current Day
6 | SITFTS-0905 TC06 | SITFTS-0905 - Advanced Meter Removal | SITFTS-0905 TC06 | 0.6.2 | Single Advanced Meter to be removed (as per DES138 data specification) where the reported Meter Removal Date is in the future | Advanced | Single | Current Day
7 | SITFTS-0905 TC07 | SITFTS-0905 - Smart Meter Install request - Notification of Failure to Install or Energise Metering System | SITFTS-0905 TC07 | 0.6.3 | Single Smart Meter request to be where metering service are unable to complete metering work & D0221 is issued | Smart | Single | Current Day
8 | SITFTS-0905 TC08 | SITFTS-0905 - Smart Meter Install request - Fault Resolution Report | SITFTS-0905 TC08 | 0.6.3 | Single Smart Meter request to be where metering service are unable to complete metering work & D0002 is issued | Smart | Single | Current Day
9 | SITFTS-0905 TC09 | SITFTS-0905 - Advanced Meter Install request - Notification of Failure to Install or Energise Metering System | SITFTS-0905 TC09 | 0.6.1 | Single Advanced Meter request to be where metering service are unable to complete metering work & D0221 is issued | Advanced | Single | Current Day
10 | SITFTS-0905 TC10 | SITFTS-0905 - Advanced Meter Install request - Fault Resolution Report | SITFTS-0905 TC10 | 0.6.1 | Single Advanced Meter request to be where metering service are unable to complete metering work & D0002 is issued | Advanced | Single | Current Day
Back to List of
Test Scenarios

## SITFTS-0905 TC01
No. | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITFTS-0905 TC01 |  |  | 0.6.2 |  | SITFTS-0905 - Traditional to Smart Meter Exchange | SITFTS-0905 TC01 | Single Traditional Meter to be Exchanged to Smart SMETS 2 Meter (as per DES138 data specification) where the reported Meter ID removed does not match the currently installed Meter ID | Traditional --> Smart SMETS2 | Single | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0905 - Traditional to Smart Meter Exchange where Registration Update is rejected | Pre Req | Pre Req | [7 empty] | This test is designed to trigger a validation failure the meter read IF-041 will be issued at the same time as the IF-005 meter change event and so the test steps have to progress one message time before the other, but in reality, there is no guaranteed delivery order from the systems. Please also note that the metering Job read is still issued as part of this process as this is done prior to validation rule failure confirmation.
| Meter Exchange - Start | 1 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142 | N/A | SMSC | Supplier issues out D0142 to Metering service requesting Meter installation works to be taken out |  | Y
|  | 2 | BP009 | 30 40 | MHHS-BR-MS-051 MHHS-BR-MS-056 | SMSC | D0142 | N/A | N/A | Metering Service (Currently Appointed) receives D0142 via the DTN or the Service Provider Portal accepts and Metering will complete the required metering works requested by Supplier and update their systems to reflect the changes made. |  | Y
| Issue Removed Meter Readings - Register Reads and MTDs | 3 | BP009 | 75 | MHHS-BR-MS-063 | SMSC | D0150/D0010 | N/A | SUPC, SDSC, LDSO | Metering Service (Currently Appointed) issues dataflows D0150/D0010 with information of removed traditional meter including read to Supplier, Data Service and LDSO |  | Y
|  | 4 | BP009 | 115 | MHHS-BR-SU-070 | SMSC | D0150/D0010 | N/A | SUPC | Supplier receives dataflows D0150/D0010 with information of removed meter including read |  | Y
|  | 5 | BP009 | 120 | MHHS-BR-LD-027 | SMSC | D0150/D0010 | N/A | LDSO | LDSO receives dataflows D0150/D0010 with information of removed meter including read |  | Y
|  | 6 | BP009 | 175 | MHHS-BR-DS-119 MHHS-BR-DS-120 | SMSC | D0150/D0010 | N/A | SDSC | Data service receives dataflows D0150/D0010 with information of removed meter including read |  | Y
|  | 7 | BP009 | 60 | MHHS-BR-MS-061 | SMSC | IF-041 | [ReadingInstl] | DIP | SMSC sends IF-041 to DIP | http 201 response from DIP | Y
| Issue Installed Meter Readings | 8 | BP009 | 60 | MHHS-BR-MS-061 | DIP | PUB-041 | [ReadingInstl] | SUPC, LDSO, SDSC | DIP sends PUB-041 to the SUPC, LDSO and SDSC. |  | N
|  | 9 | BP009 | 220 215 | MHHS-BR-SU-072 MHHS-BR-SU-071 | DIP | PUB-041 | [ReadingRemv] | SUPC | Supplier receives PUB-041 | Supplier receives PUB-041 Meter Install Read | Y
|  | 10 | BP009 | 190 | MHHS-BR-LD-029 | DIP | PUB-041 | [ReadingInstl] | LDSO | LDSO receives PUB-041. | LDSO receives PUB-041 Meter Install Read | Y
|  | 11 | BP009 | 180 | MHHS-BR-DS-118 | DIP | PUB-041 | [ReadingInstl] | SDSC | SDS (Current) receives PUB-041. | Data Service receives PUB-041 Meter Install Read | Y
|  | 12 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | SMSC | IF-005 | [MeterExchange] | DIP | SMSC sends IF-005 to DIP | http 201 response from DIP | Y
| Issue MTD Update to REGS | 13 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | DIP | PUB-005 | [MeterExchange] | REGS | DIP sends PUB-005 to the REGS where the Meter ID removed does not match the currently installed Meter ID |  | N
|  | 14 | BP009 | 95 | MHHS-BR-RS-108 | DIP | PUB-005 | [MeterExchange] | REGS | REGS receives PUB-005 | REGS receives PUB-005 Updating Meter Exchange confirming old and new meter details and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 15 | BP009 | 100 135 145 | MHHS-BR-RS-109 | REGS | IF-006 | [MeterExchange] | DIP | REGS sends IF-006 to DIP | http 201 response from DIP | Y
| Issue MTD Update Rejection | 16 | BP009 | 100 135 145 | MHHS-BR-RS-109 | DIP | PUB-006 | [MeterExchange] | SMSC, SUPC | Registration Service carries out validation of the MTD Update and DIP issues a PUB-006 to the Metering Service (Currently Appointed) and SUPC confirming that the update has been rejected with the appropriate Response Message |  | N
|  | 17 | BP009 | 155 165 | MHHS-BR-MS-073.1 MHHS-BR-MS-060 | DIP | PUB-006 | [MeterExchange] and Response Code = "R" | SMSC | Metering Service (Currently Appointed) receives PUB-006 confirming Rejection with Response Message = "REG1004 - Meter ID [DI-056] does not match currently installed Meter ID " | Metering Service (Currently Appointed) receives PUB-006 Notifying the MTD Update following the Meter Exchange has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 18 | BP009 |  | DES138 | DIP | PUB-006 | [MeterExchange] and Response Code = "R" | SUPC | Supplier receives PUB-006 confirming Rejection with Response Message = "REG1004 - Meter ID [DI-056] does not match currently installed Meter ID " | Supplier receives PUB-006 Notifying the MTD Update of the Meter Exchange has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS-0905 TC02
No. | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
2 | SITFTS-0905 TC02 |  |  | 0.6.2 |  | SITFTS-0905 - Smart to Smart Meter Exchange | SITFTS-0905 TC02 | Single Smart Meter SMETS 1 to be Exchanged to Smart SMETS 2 Meter (as per DES138 data specification) where the reported Meter Removal Date is before the current Meter Install Date | Smart SMETS1 --> Smart SMETS2 | Single | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0905 - Smart to Smart Meter Exchange where Registration Update is rejected | Pre Req | Pre Req | [7 empty] | This test is designed to trigger a validation failure the meter read IF-041 will be issued at the same time as the IF-005 meter change event and so the test steps have to progress one message time before the other, but in reality, there is no guaranteed delivery order from the systems. Please also note that the metering Job read is still issued as part of this process as this is done prior to validation rule failure confirmation.
| Meter Exchange - Start | 1 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142 | N/A | SMSC | Supplier issues out D0142 to Metering service requesting Meter installation works to be taken out |  | Y
|  | 2 | BP009 | 30 40 | MHHS-BR-MS-051 MHHS-BR-MS-056 | SMSC | D0142 | N/A | N/A | Metering Service (Currently Appointed) receives D0142 via the DTN or the Service Provider Portal accepts and Metering will complete the required metering works requested by Supplier and update their systems to reflect the changes made. |  | Y
|  | 3 | BP009 | 60 85 | MHHS-BR-MS-061 | SMSC | IF-041 | [ReadingRemv] | DIP | SMSC sends IF-041 to DIP | http 201 response from DIP | Y
| Issue Removed Meter Readings | 4 | BP009 | 60 85 | MHHS-BR-MS-061 | DIP | PUB-041 | [ReadingRemv] | SUPC, LDSO, SDSC | DIP sends PUB-041 to the SUPC, LDSO and SDSC. |  | N
|  | 5 | BP009 | 220 215 | MHHS-BR-SU-072 MHHS-BR-SU-071 | DIP | PUB-041 | [ReadingRemv] | SUPC | Supplier receives PUB-041 . | Supplier receives PUB-041 Meter Removal Read | Y
|  | 6 | BP009 | 190 | MHHS-BR-LD-029 | DIP | PUB-041 | [ReadingRemv] | LDSO | LDSO receives PUB-041. | LDSO receives PUB-041 Meter Removal Read | Y
|  | 7 | BP009 | 180 | MHHS-BR-DS-118 | DIP | PUB-041 | [ReadingRemv] | SDSC | SDS (Current) receives PUB-041. | Data Service receives PUB-041 Meter Removal Read | Y
|  | 8 | BP009 | 60 85 | MHHS-BR-MS-061 | SMSC | IF-041 | [ReadingInstl] | DIP | SMSC sends IF-041 to DIP | http 201 response from DIP | Y
| Issue Installed Meter Readings | 9 | BP009 | 60 85 | MHHS-BR-MS-061 | DIP | PUB-041 | [ReadingInstl] | SUPC, LDSO, SDSC | DIP sends PUB-041 to the SUPC, LDSO and SDSC. |  | N
|  | 10 | BP009 | 220 215 | MHHS-BR-SU-072 MHHS-BR-SU-071 | DIP | PUB-041 | [ReadingRemv] | SUPC | Supplier receives PUB-041 | Supplier receives PUB-041 Meter Install Read | Y
|  | 11 | BP009 | 190 | MHHS-BR-LD-029 | DIP | PUB-041 | [ReadingInstl] | LDSO | LDSO receives PUB-041. | LDSO receives PUB-041 Meter Install Read | Y
|  | 12 | BP009 | 180 | MHHS-BR-DS-118 | DIP | PUB-041 | [ReadingInstl] | SDSC | SDS (Current) receives PUB-041. | Data Service receives PUB-041 Meter Install Read | Y
|  | 13 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | SMSC | IF-005 | [MeterExchange] | DIP | SMSC sends IF-005 to DIP | http 201 response from DIP | Y
| Issue MTD Update to REGS | 14 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | DIP | PUB-005 | [MeterExchange] | REGS | DIP sends PUB-005 to the REGS where the Meter Removal Date is before the current Meter Install Date |  | N
|  | 15 | BP009 | 95 | MHHS-BR-RS-108 | DIP | PUB-005 | [MeterExchange] | REGS | REGS receives PUB-005 | REGS receives PUB-005 Updating Meter Exchange confirming old and new meter details and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 16 | BP009 | 100 135 145 | MHHS-BR-RS-109 | REGS | IF-006 | [MeterExchange] | DIP | REGS sends IF-006 to DIP | http 201 response from DIP | Y
| Issue MTD Update Rejection | 17 | BP009 | 100 135 145 | MHHS-BR-RS-109 | DIP | PUB-006 | [MeterExchange] | SMSC, SUPC | Registration Service carries out validation of the MTD Update and DIP issues an PUB-006 to the Metering Service (Currently Appointed) and SUPC confirming that the update has been rejected with the appropriate Response Message |  | N
|  | 18 | BP009 | 155 165 | MHHS-BR-MS-073.1 MHHS-BR-MS-060 | DIP | PUB-006 | [MeterExchange] and Response Code = "R" | SMSC | Metering Service (Currently Appointed) receives PUB-006 confirming Rejection with Response Message = "REG1005 -MeterID [DI-053] Meter Removal Date [DI-058] is prior to current Meter Install Date [REG.MtrInstlDate] " | Metering Service (Currently Appointed) receives PUB-006 Notifying the MTD Update following the Meter Exchange has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 19 | BP009 |  | DES138 | DIP | PUB-006 | [MeterExchange] and Response Code = "R" | SUPC | Supplier receives PUB-006 confirming Rejection with Response Message = "REG1005 -MeterID [DI-053] Meter Removal Date [DI-058] is prior to current Meter Install Date [REG.MtrInstlDate]" | Supplier receives PUB-006 Notifying the MTD Update of the Meter Exchange has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS-0905 TC03
No. |  | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
3 |  | SITFTS-0905 TC03 |  |  | 0.6.2 |  | SITFTS-0905 - Smart Install | SITFTS-0905 TC03 | Non metered site install Smart SMETS 2 Meter (as per DES138 data specification) where the reported Meter ID installed already exists on another MPAN | Smart SMETS 2 | Single | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0905 - Smart Meter Install where Registration Update is rejected | Pre Req | Pre Req | [7 empty] | This test is designed to trigger a validation failure the meter read IF-041 will be issued at the same time as the IF-005 meter change event and so the test steps have to progress one message time before the other, but in reality, there is no guaranteed delivery order from the systems. Please also note that the metering Job read is still issued as part of this process as this is done prior to validation rule failure confirmation.
| Change of Metering - MS accepts request to Install a Meter | 1 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142 | N/A | SMSC | Supplier issues out D0142 to Metering service requesting Meter installation works to be taken out |  | Y
|  | 2 | BP009 | 30 40 | MHHS-BR-MS-051 MHHS-BR-MS-056 | SMSC | D0142 | N/A | N/A | Metering Service (Currently Appointed) receives D0142 via the DTN or the Service Provider Portal accepts and Metering will complete the required metering works requested by Supplier and update their systems to reflect the changes made once works are complete this will move to change of energisation. |  | Y
|  | 3 | BP009 | 60 85 | MHHS-BR-MS-061 | SMSC | IF-041 | [ReadingInstl] | DIP | SMSC sends IF-041 to DIP | http 201 response from DIP | Y
| Issue Installed Meter Readings | 4 | BP009 | 60 85 | MHHS-BR-MS-061 | DIP | PUB-041 | [ReadingInstl] | SUPC, LDSO & SDSC. | DIP sends PUB-041 to the SUPC, LDSO & SDSC. |  | N
|  | 5 | BP009 | 220 215 | MHHS-BR-SU-072 MHHS-BR-SU-071 | DIP | PUB-041 | [ReadingInstl] | SUPC | Supplier receives PUB-041 | Supplier receives PUB-041 Meter Install Read | Y
|  | 6 | BP009 | 190 | MHHS-BR-LD-029 | DIP | PUB-041 | [ReadingInstl] | LDSO | LDSO receives PUB-041. | LDSO receives PUB-041 Meter Install Read | Y
|  | 7 | BP009 | 180 | MHHS-BR-DS-118 | DIP | PUB-041 | [ReadingInstl] | SDSC | SDS (Current) receives PUB-041. | Data Service receives PUB-041 Meter Install Read | Y
|  | 8 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | SMSC | IF-005 | [MeterInstall] | DIP | SMSC sends IF-005 to DIP | http 201 response from DIP | Y
| Issue MTD Update to REGS | 9 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | DIP | PUB-005 | [MeterInstall] | REGS | DIP sends PUB-005 to the REGS where the Meter ID installed already exists on another MPAN |  | N
|  | 10 | BP009 | 95 | MHHS-BR-RS-108 | DIP | PUB-005 | [MeterInstall] | REGS | REGS receives PUB-005 | REGS receives PUB-005 Updating Meter Install confirming new meter details and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 11 | BP009 | 100 135 145 | MHHS-BR-RS-109 | REGS | IF-006 | [MeterInstall] | DIP | REGS sends IF-006 to DIP | http 201 response from DIP | Y
| Issue MTD Update Rejection | 12 | BP009 | 100 135 145 | MHHS-BR-RS-109 | DIP | PUB-006 | [MeterInstall] | SMSC, SUPC | Registration Service carries out validation of the MTD Update and DIP issues an PUB-006 to the Metering Service (Currently Appointed) and SUPC confirming that the update has been rejected with the appropriate Response Message |  | N
|  | 13 | BP009 | 155 165 | MHHS-BR-MS-073.1 MHHS-BR-MS-060 | DIP | PUB-006 | [MeterInstall] and Response Code = "R" | SMSC | Metering Service (Currently Appointed) receives PUB-006 confirming Rejection with Response Message = "REG1006 - Meter ID [DI-056] already installed for MPAN [DI-063] " | Metering Service (Currently Appointed) receives PUB-006 Notifying the MTD Update following the Meter Install has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 14 | BP009 |  | DES138 | DIP | PUB-006 | [MeterInstall] and Response Code = "R" | SUPC | Supplier receives PUB-006 confirming Rejection with Response Message = "REG1006 - Meter ID [DI-056] already installed for MPAN [DI-063]" | Supplier receives PUB-006 Notifying the MTD Update of the Meter Install has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS-0905 TC04
No. |  | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
4 |  | SITFTS-0905 TC04 |  |  | 0.6.3 |  | SITFTS-0905 - Advanced Install | SITFTS-0905 TC04 | Non metered site install Advanced Meter (as per DES138 data specification) where the reported Modified Meter ID has been entered | Advanced | Single | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0905 - Advanced Meter Install where Registration Update is rejected | Pre Req | Pre Req | [7 empty] | This test is designed to trigger a validation failure the meter read IF-041 will be issued at the same time as the IF-005 meter change event and so the test steps have to progress one message time before the other, but in reality, there is no guaranteed delivery order from the systems. Please also note that the metering Job read is still issued as part of this process as this is done prior to validation rule failure confirmation.
| Change of Metering - MS accepts request to Install a Meter | 1 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142 | N/A | AMSC | Supplier issues out D0142 to Metering service requesting Meter installation works to be taken out |  | Y
|  | 2 | BP009 | 30 40 | MHHS-BR-MS-051 MHHS-BR-MS-056 | AMSC | D0142 | N/A | N/A | Metering Service (Currently Appointed) receives D0142 via the DTN or the Service Provider Portal accepts and Metering will complete the required metering works requested by Supplier and update their systems to reflect the changes made. |  | Y
| Issue Installed Meter MTD | 3 | BP009 | 75 | MHHS-BR-MS-063 | AMSC | D0268/D0010 | N/A | SUPC, LDSO, ADSC | Metering Service (Currently Appointed) issues dataflows D0268/D0010 with information of Installed meter (including D0010 if the IF-041 is not available) to Supplier, Data Service and LDSO |  | Y
|  | 4 | BP009 | 115 | MHHS-BR-SU-070 | AMSC | D0268/D0010 | N/A | SUPC | Supplier receives dataflows D0268/D0010 with information of new meter installed (including D0010 if the IF-041 is not available) |  | Y
|  | 5 | BP009 | 120 | MHHS-BR-LD-027 | AMSC | D0268/D0010 | N/A | LDSO | LDSO receives dataflows D0268/D0010 with information of new meter installed (including D0010 if the IF-041 is not available) |  | Y
|  | 6 | BP009 | 175 | MHHS-BR-DS-119 MHHS-BR-DS-120 | AMSC | D0268/D0010 | N/A | ADSC | Data service receives dataflows D0268/D0010 with information of new meter installed (including D0010 if the IF-041 is not available) |  | Y
|  | 7 | BP009 | 60 85 | MHHS-BR-MS-061 | AMSC | IF-041 | [ReadingInstl] | DIP | AMSC sends IF-041 to DIP | http 201 response from DIP | Y
| Issue Installed Meter Readings - Cumulative Meter Read(s) ** If Advanced Meter supports Cumulative Reads | 8 | BP009 | 60 85 | MHHS-BR-MS-061 | DIP | PUB-041 | [ReadingInstl] | SUPC, LDSO and ADSC. | DIP sends PUB-041 to Supplier, LDSO and ADSC Note: IF-041 only generated if Advance Meter has the capability to record Cumulative Reads otherwise the Data Service will use the D0010 Flow data. |  | N
|  | 9 | BP009 | 220 215 | MHHS-BR-SU-072 MHHS-BR-SU-071 | DIP | PUB-041 | [ReadingInstl] | SUPC | Supplier receives PUB-041 from DIP | Supplier receives PUB-041 Meter Install Read | Y
|  | 10 | BP009 | 190 | MHHS-BR-LD-029 | DIP | PUB-041 | [ReadingInstl] | LDSO | LDSO receives PUB-041 from DIP | LDSO receives PUB-041 Meter Install Read | Y
|  | 11 | BP009 | 180 | MHHS-BR-DS-118 | DIP | PUB-041 | [ReadingInstl] | ADSC | Data Service receives PUB-041 from DIP | Data Service receives PUB-041 Meter Install Read | Y
|  | 12 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | AMSC | IF-005 | [MeterInstall] | DIP | AMSC sends IF-005 to DIP | http 201 response from DIP | Y
| Issue MTD Update to REGS | 13 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | DIP | PUB-005 | [MeterInstall] | REGS | DIP sends PUB-005 to the REGS where the Modified Meter ID has been entered |  | N
|  | 14 | BP009 | 95 | MHHS-BR-RS-108 | DIP | PUB-005 | [MeterInstall] | REGS | REGS receives PUB-005 | REGS receives PUB-005 Updating Meter Install confirming new meter details and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 15 | BP009 | 100 135 145 | MHHS-BR-RS-109 | REGS | IF-006 | [MeterInstall] | DIP | REGS sends IF-006 to DIP | http 201 response from DIP | Y
| Issue MTD Update Rejection | 16 | BP009 | 100 135 145 | MHHS-BR-RS-109 | DIP | PUB-006 | [MeterInstall] | AMSC, SUPC | Registration Service carries out validation of the MTD Update and DIP issues an PUB-006 to the Metering Service (Currently Appointed) and SUPC confirming that the update has been rejected with the appropriate Response Message |  | N
|  | 17 | BP009 | 155 165 | MHHS-BR-MS-073.1 MHHS-BR-MS-060 | DIP | PUB-006 | [MeterInstall] and Response Code = "R" | AMSC | Metering Service (Currently Appointed) receives PUB-006 confirming Rejection with Response Message = "REG1029 - Modified Meter Id Must be Null " | Metering Service (Currently Appointed) receives PUB-006 Notifying the MTD Update following the Meter Install has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 18 | BP009 |  | DES138 | DIP | PUB-006 | [MeterInstall] and Response Code = "R" | SUPC | Supplier receives PUB-006 confirming Rejection with Response Message = "REG1029 - Modified Meter Id Must be Null" | Supplier receives PUB-006 Notifying the MTD Update of the Meter Install has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS-0905 TC05
No. |  | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
5 |  | SITFTS-0905 TC05 |  |  | 0.6.1 |  | SITFTS-0905 - Traditional Meter Removal | SITFTS-0905 TC05 | Single Traditional Meter to be removed (as per DES138 data specification) where the reported Modified Meter ID has been entered | Traditional | Single | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0905 - Traditional Meter Removal where Registration Update is rejected | Change of Metering - MS accepts request for meter removal | 1 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142 | N/A | SMSC | Supplier issues out D0142 to Metering service requesting Meter installation works to be taken out |  | Y
|  | 2 | BP009 | 30 40 | MHHS-BR-MS-051 MHHS-BR-MS-056 | SMSC | D0142 | N/A | N/A | Metering Service (Currently Appointed) receives D0142 via the DTN or the Service Provider Portal accepts and Metering will complete the required metering works requested by Supplier and update their systems to reflect the changes made. |  | Y
| Issue Removed Meter Readings - Register Reads and MTD | 3 | BP009 | 75 | MHHS-BR-MS-063 | SMSC | D0150/D0010 | N/A | SUPC, SDSC, LDSO | Metering Service (Currently Appointed) issues dataflows D0150/D0010 with information of removed meter including read to Supplier, Data Service and LDSO |  | Y
|  | 4 | BP009 | 115 | MHHS-BR-SU-070 | SMSC | D0150/D0010 | N/A | SUPC | Supplier receives dataflows D0150/D0010 with information of removed meter including read |  | Y
|  | 5 | BP009 | 120 | MHHS-BR-LD-027 | SMSC | D0150/D0010 | N/A | LDSO | LDSO receives dataflows D0150/D0010 with information of removed meter including read |  | Y
|  | 6 | BP009 | 175 | MHHS-BR-DS-119 MHHS-BR-DS-120 | SMSC | D0150/D0010 | N/A | SDSC | Data service receives dataflows D0150/D0010 with information of removed meter including read |  | Y
|  | 7 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | SMSC | IF-005 | [MeterRemoval] | DIP | SMSC sends IF-005 to DIP | http 201 response from DIP | Y
| Issue MTD Update to REGS | 8 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | DIP | PUB-005 | [MeterRemoval] | REGS | DIP sends PUB-005 to the REGS where the Meter Removal Date is outside the Meter Service Ownership period |  | N
|  | 9 | BP009 | 95 | MHHS-BR-RS-108 | DIP | PUB-005 | [MeterRemoval] | REGS | REGS receives PUB-005 | REGS receives PUB-005 Updating Meter Exchange confirming old and new meter details and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 10 | BP009 | 100 135 145 | MHHS-BR-RS-109 | REGS | IF-006 | [MeterRemoval] | DIP | REGS sends IF-006 to DIP | http 201 response from DIP | Y
| Issue MTD Update Rejection | 11 | BP009 | 100 135 145 | MHHS-BR-RS-109 | DIP | PUB-006 | [MeterRemoval] | SMSC, SUPC | Registration Service carries out validation of the MTD Update and DIP issues an PUB-006 to the Metering Service (Currently Appointed) and SUPC confirming that the update has been rejected with the appropriate Response Message |  | N
|  | 12 | BP009 | 155 165 | MHHS-BR-MS-073.1 MHHS-BR-MS-060 | DIP | PUB-006 | [MeterRemoval] and Response Code = "R" | SMSC, SUPC | Metering Service (Currently Appointed) receives PUB-006 confirming Rejection with Response Message = "REG1019 - Meter Removal Date [DI-058] should be within Metering Service Period of Ownership " | Metering Service (Currently Appointed) receives PUB-006 Notifying the MTD Update following the Meter Removal has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 13 | BP009 |  | DES138 | DIP | PUB-006 | [MeterRemoval] and Response Code = "R" | SUPC | Supplier receives PUB-006 confirming Rejection with Response Message = "REG1019 - Meter Removal Date [DI-058] should be within Metering Service Period of Ownership " | Supplier receives PUB-006 Notifying the MTD Update following the Meter Removal has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS-0905 TC06
No. |  | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
6 |  | SITFTS-0905 TC06 |  |  | 0.6.2 |  | SITFTS-0905 - Advanced Meter Removal | SITFTS-0905 TC06 | Single Advanced Meter to be removed (as per DES138 data specification) where the reported Meter Removal Date is in the future | Advanced | Single | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0905 - Advanced Meter Removal where Registration Update is rejected | Pre Req | Pre Req | [7 empty] | This test is designed to trigger a validation failure the meter read IF-041 will be issued at the same time as the IF-005 meter change event and so the test steps have to progress one message time before the other, but in reality, there is no guaranteed delivery order from the systems. Please also note that the metering Job read is still issued as part of this process as this is done prior to validation rule failure confirmation.
| Change of Metering - MS accepts request for meter removal | 1 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142 | N/A | AMSC | Supplier issues out D0142 to Metering service requesting Meter installation works to be taken out |  | Y
|  | 2 | BP009 | 30 40 | MHHS-BR-MS-051 MHHS-BR-MS-056 | AMSC | D0142 | N/A | N/A | Metering Service (Currently Appointed) receives D0142 via the DTN or the Service Provider Portal accepts and Metering will complete the required metering works requested by Supplier and update their systems to reflect the changes made. |  | Y
| Issue Removed Meter MTD | 3 | BP009 | 80 | MHHS-BR-MS-062 | AMSC | D0268/D0010 | N/A | SUPC, ADSC, LDSO | Metering Service (Currently Appointed) issues dataflows D0268/D0010 with information of removed meter (including D0010 if the IF-041 is not available) to Supplier, Data Service and LDSO |  | Y
|  | 4 | BP009 | 115 | MHHS-BR-SU-070 | AMSC | D0268/D0010 | N/A | SUPC | Supplier receives dataflows D0268/D0010 with information of removed meter (including D0010 if the IF-041 is not available) |  | Y
|  | 5 | BP009 | 120 | MHHS-BR-LD-027 | AMSC | D0268/D0010 | N/A | LDSO | LDSO receives dataflows D0268/D0010 with information of removed meter (including D0010 if the IF-041 is not available) |  | Y
|  | 6 | BP009 | 175 | MHHS-BR-DS-119 MHHS-BR-DS-120 | AMSC | D0268/D0010 | N/A | ADSC | Data service receives dataflows D0268/D0010 with information of removed meter (including D0010 if the IF-041 is not available) |  | Y
|  | 7 | BP009 | 60 85 | MHHS-BR-MS-061 | AMSC | IF-041 | [ReadingRemv] | DIP | AMSC sends IF-041 to DIP | http 201 response from DIP | Y
| Issue Installed Meter Readings - Cumulative Meter Read(s) ** If Advanced Meter supports Cumulative Reads | 8 | BP009 | 60 85 | MHHS-BR-MS-061 | DIP | PUB-041 | [ReadingRemv] | SUPC | DIP sends PUB-041 to Supplier, LDSO and Advanced Data Service. Note: IF-041 only generated if Advance Meter has the capability to record Cumulative Reads otherwise the Data Service will use the D0010 Flow data. |  | N
|  | 9 | BP009 | 220 215 | MHHS-BR-SU-072 MHHS-BR-SU-071 | DIP | PUB-041 | [ReadingRemv] | SUPC | Supplier receives PUB-041 from DIP | Supplier receives PUB-041 Meter Removal Read | Y
|  | 10 | BP009 | 190 | MHHS-BR-LD-029 | DIP | PUB-041 | [ReadingRemv] | LDSO | LDSO receives PUB-041 from DIP | LDSO receives PUB-041 Meter Removal Read | Y
|  | 11 | BP009 | 180 | MHHS-BR-DS-118 | DIP | PUB-041 | [ReadingRemv] | ADSC | Data Service receives PUB-041 from DIP | Data Service receives PUB-041 Meter Removal Read | Y
|  | 12 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | AMSC | IF-005 | [MeterRemoval] | DIP | AMSC sends IF-005 to DIP | http 201 response from DIP | Y
| Issue MTD Update to REGS | 13 | BP009 | 55 65 90 | MHHS-BR-MS-058 MHHS-BR-MS-058.3 | DIP | PUB-005 | [MeterRemoval] | REGS | DIP sends PUB-005 to the REGS where the Meter Removal Date is in the future |  | N
|  | 14 | BP009 | 95 | MHHS-BR-RS-108 | DIP | PUB-005 | [MeterRemoval] | REGS | REGS receives PUB-005 | REGS receives PUB-005 Updating Meter Removal confirming new meter details and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 15 | BP009 | 100 135 145 | MHHS-BR-RS-109 | REGS | IF-006 | [MeterRemoval] | DIP | REGS sends IF-006 to DIP | http 201 response from DIP | Y
| Issue MTD Update Rejection | 16 | BP009 | 100 135 145 | MHHS-BR-RS-109 | DIP | PUB-006 | [MeterRemoval] | AMSC, SUPC | Registration Service carries out validation of the MTD Update and DIP issues an PUB-006 to the Metering Service (Currently Appointed) and SUPC confirming that the update has been rejected with the appropriate Response Message |  | N
|  | 17 | BP009 | 155 165 | MHHS-BR-MS-073.1 MHHS-BR-MS-060 | DIP | PUB-006 | [MeterRemoval] and Response Code = "R" | AMSC | Metering Service (Currently Appointed) receives PUB-006 confirming Rejection with Response Message = "REG1020 - Meter Removal Date [DI-058] cannot take place in the future" | Metering Service (Currently Appointed) receives PUB-006 Notifying the MTD Update following the Meter Removal has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 18 | BP009 |  | DES138 | DIP | PUB-006 | [MeterRemoval] and Response Code = "R" | SUPC | Supplier receives PUB-006 confirming Rejection with Response Message = "REG1020 - Meter Removal Date [DI-058] cannot take place in the future" | Supplier receives PUB-006 Notifying the MTD Update of the Meter Removal has been rejected by the Registration Service and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS-0905 TC07
No. |  | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
7 |  | SITFTS-0905 TC07 |  |  | 0.6.3 |  | SITFTS-0905 - Smart Meter Install request - Notification of Failure to Install or Energise Metering System | SITFTS-0905 TC07 | Single Smart Meter request to be where metering service are unable to complete metering work & D0221 is issued | Smart | Single | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0905 - Smart Meter Install request - Notification of Failure to Install or Energise Metering System | Change of Metering - Supplier requests for meter Install | 1 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142 | N/A | SMSC | Supplier issues out D0142 to Metering service requesting Meter Install works to be taken out | Meter install Job requested Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 2 | BP009 | 30 | MHHS-BR-MS-051 | SMSC | D0142 | N/A | N/A | Metering Service receives D0142 via the DTN or the Service Provider Portal and is unable to perform meter Install | D0142 Received and processed Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering - Meter Service sends notifications of work not being carried out - Start | 3 | BP009 | 30 | MHHSP-BRS002-MSA-MSS-BR-MS-053 | SMSC | D0221 | N/A | SUPC | Metering Service issues out D0221 via the DTN or the Service Provider Portal to Supplier to notify metering work has not gone ahead |  | Y
| Change of Metering - Supplier receives notifications of work not being carried out - End | 4 | BP009 | 20 | MHHSP-BRS004-Supplier-BR-SU-068 | SUPC | D0221 | N/A | N/A | Supplier receives via the DTN or the Service Provider Portal Notification of Failure to Install meter through D0221 | D0221 Received and processed Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS-0905 TC08
No. |  | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
8 |  | SITFTS-0905 TC08 |  |  | 0.6.3 |  | SITFTS-0905 - Smart Meter Install request - Fault Resolution Report | SITFTS-0905 TC08 | Single Smart Meter request to be where metering service are unable to complete metering work & D0002 is issued | Smart | Single | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0905 - Smart Meter Install request - Fault Resolution Report | Change of Metering - Supplier requests for meter Install | 1 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142 | N/A | SMSC | Supplier issues out D0142 to Metering service requesting Meter Install works to be taken out | Meter install Job requested Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 2 | BP009 | 30 | MHHS-BR-MS-051 | SMSC | D0142 | N/A | N/A | Metering Service receives D0142 via the DTN or the Service Provider Portal and is unable to perform meter Install | D0142 Received and processed Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering - Meter Service sends Fault Resolution Report- Start | 3 | BP009 | 30 | MHHSP-BRS002-MSA-MSS-BR-MS-052 | SMSC | D0002 | N/A | SUPC | Metering Service issues out D0002 to Supplier via the DTN or the Service Provider Portal to notify a Fault Resolution Report or Request for decision on Further action |  | Y
| Change of Metering - Meter Service sends Fault Resolution Report- End | 4 | BP009 | 20 | MHHSP-BRS004-Supplier-BR-SU-067 | SUPC | D0002 | N/A | N/A | Supplier receives Fault Resolution Report or Request for decision on Further action through D0002 via the DTN or the Service Provider Portal | D0002 Received and processed Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS-0905 TC09
No. |  | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
9 |  | SITFTS-0905 TC09 |  |  | 0.6.1 |  | SITFTS-0905 - Advanced Meter Install request - Notification of Failure to Install or Energise Metering System | SITFTS-0905 TC09 | Single Advanced Meter request to be where metering service are unable to complete metering work & D0221 is issued | Advanced | Single | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0905 - Advanced Meter Install request - Notification of Failure to Install or Energise Metering System | Change of Metering - Supplier requests for meter Install | 1 | BP009 | 20 | MHHSP-BRS004-Supplier-BR-SU-066 | SUPC | D0142 | N/A | AMSC | Supplier issues out D0142 to Metering service requesting Meter Install works to be taken out | Meter install Job requested Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 2 | BP009 | 30 | MHHSP-BRS002-MSA-MSS-BR-MS-051 | AMSC | D0142 | N/A | N/A | Metering Service receives D0142 via the DTN or the Service Provider Portal and is unable to perform meter Install | D0142 Received and processed Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering - Meter Service sends notifications of work not being carried out - Start | 3 | BP009 | 30 | MHHSP-BRS002-MSA-MSS-BR-MS-053 | AMSC | D0221 | N/A | SUPC | Metering Service issues out D0221 via the DTN or the Service Provider Portal to Supplier to notify metering work has not gone ahead |  | Y
| Change of Metering - Supplier receives notifications of work not being carried out - End | 4 | BP009 | 20 | MHHSP-BRS004-Supplier-BR-SU-068 | SUPC | D0221 | N/A | N/A | Supplier receives via the DTN or the Service Provider Portal Notification of Failure to Install meter through D0221 | D0221 Received and processed Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS-0905 TC10
No. |  | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
10 |  | SITFTS-0905 TC10 |  |  | 0.6.1 |  | SITFTS-0905 - Advanced Meter Install request - Fault Resolution Report | SITFTS-0905 TC10 | Single Advanced Meter request to be where metering service are unable to complete metering work & D0002 is issued | Advanced | Single | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0905 - Advanced Meter Install request - Fault Resolution Report | Change of Metering - Supplier requests for meter Install | 1 | BP009 | 20 | MHHSP-BRS004-Supplier-BR-SU-066 | SUPC | D0142 | N/A | AMSC | Supplier issues out D0142 to Metering service requesting Meter Install works to be taken out | Meter install Job requested Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 2 | BP009 | 30 | MHHSP-BRS002-MSA-MSS-BR-MS-051 | AMSC | D0142 | N/A | N/A | Metering Service receives D0142 via the DTN or the Service Provider Portal and is unable to perform meter Install | D0142 Received and processed Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering - Meter Service sends Fault Resolution Report- Start | 3 | BP009 | 30 | MHHSP-BRS002-MSA-MSS-BR-MS-052 | AMSC | D0002 | N/A | SUPC | Metering Service issues out D0002 to Supplier via the DTN or the Service Provider Portal to notify a Fault Resolution Report or Request for decision on Further action |  | Y
| Change of Metering - Meter Service sends Fault Resolution Report- End | 4 | BP009 | 20 | MHHSP-BRS004-Supplier-BR-SU-067 | SUPC | D0002 | N/A | N/A | Supplier receives Fault Resolution Report or Request for decision on Further action through D0002 via the DTN or the Service Provider Portal | D0002 Received and processed Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## DPCache_List of Test Scenarios (hidden)
Test Category | Test Scenario | Scenario Title | Test Cases Link | Test ID | Test Scenario Link | Status Date | Status | Test Title | Priority | Pre-Requisite Test Scenario
Advisory Notification | E2E-001 | SITFTS-001 - Advisory Notification | Click to See Test Cases | E2E-001 | Click to view Test | 2023-02-09 | WG Reviewed (Working Group Drops)​ | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Advisory Notification | E2E-E004 | E2E-E004 - Advisory Notification | Click to See Test Cases | E2E-004 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-G006 |  | Click to See Test Cases | E2E-006 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-E007 | E2E-E007 - Switch Request Objection | Click to See Test Cases | E2E-007 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Objection | E2E-D008 |  | Click to See Test Cases | E2E-008 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Successful | E2E-G012 | E2E-G012 - Switch Request Successful | Click to See Test Cases | E2E-012 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA
Switch Request Successful | E2E-E011 |  | Click to See Test Cases | E2E-011 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA