## Change Log
Date | Author | Release |  | Reason for change
05.03.2024 | Ankur Pande | 0.1 |  | New Migration Test Scenario document
26.03.2024 | Ankur Pande | 0.2 |  | Uplifted comments by PPs. Please see Release Notes.
10.04.2024 | Ankur Pande | 0.3 |  | Uplifted further comments by PPs & internal reviews. Please see Release Notes.
29.05.2024 | Ankur Pande | 0.4 |  | No changes made to this document. Skipping version to keep all Unmetered versions in sync.
29.05.2024 | Ankur Pande | 0.5 |  | Corrected typos. Changes to script for ADO upload: - Added default values to empty cells - Removed blank lines
30.05.2024 | Aman shimpi | 0.6 |  | Replaced DIP response from "http 202 response from DIP" to "http 201 response from DIP"
30.05.2024 | Aman shimpi | 0.6 |  | Added (If opted in) to IF-036/PUB-036 for LDSO
12.Jun.2024 | Ankur Pande | 0.7 |  | Changed Test Step sequence from 5-10-15... to 1-2-3...
2024-11-13 | Suraj Kadam | 0.7 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC04 for steps 1,5,10,13,16,19,22,25,29,33,37,43

## Terminology
Terminology Used | Description | Type of Meter | Data Service | Description
BAU Process | This refers to a process within the MHHS arrangements as set out within the MHHS Core Design | Smart | SDSC | Smart Meter Data Service - Curent
CoA | Change of Agent |  | SDSI | Smart Meter Data Service - Incoming
CoS | Change of Supplier |  | SDSO | Smart Meter Data Service - Outgoing
CSS | Central Switching Service | Traditional | SDSC | Traditional Meter Data Service - Current
Data Cleanse Plan | The approach and activities required to improve and populate data prior to Migration start |  | SDSI | Traditional Meter Data Service - Incoming
DC | Data Collector |  | SDSO | Traditional Meter Data Service - Outgoing
DIP | Data Integration Platform | Advanced | ADSC | Advanced Meter Data Service - Current
DS | Data Service |  | ADSI | Advanced Meter Data Service - Incoming
Forward Migration | The process through which MPANs will move from Legacy arrangements to MHHS arrangements. |  | ADSO | Advanced Meter Data Service - Outgoing
Incoming / New MS | Incoming / New Metering Service | Unmetered | UMSDS | Unmetered Data Service
Incoming DS / New DS | Incoming Data Services
ISD | Industry Standing Data | Type of Meter | Metering Service | Description
LDSO | Licensed Distribution System Operator | Smart | SMSC | Smart Meter Metering Service - Current
MHHS | Market-Wide Half-Hourly Settlement |  | SMSI | Smart Meter Metering Service - Incoming
MHHS Arrangements | The new MHHS arrangements as set out in the MHHS Core Design Artefacts. |  | SMSO | Smart Meter Metering Service - Outgoing
Migration Design | The technical articulation of how MPANs will move from Legacy to new MHHS arrangements. | Traditional | SMSC | Traditional Meter Metering Service - Current
Migration Period | The period denoted by the Programme as occurring between the M11 and M15 milestones. |  | SMSI | Traditional Meter Metering Service - Incoming
MOP | Meter Operator |  | SMSO | Traditional Meter Metering Service - Outgoing
MPAN | Metering Point Administration Number | Advanced | AMSC | Advanced Meter Metering Service - Current
MS | Metering Service |  | AMSI | Advanced Meter Metering Service - Incoming
Outgoing MOP | Outgoing Meter Operator |  | AMSO | Advanced Meter Metering Service - Outgoing
Qualified Supplier | A Supplier recognised in ISD as both having passed the relevant System Integration Testing (SIT) requirements or BSC qualification requirements; and declared that their service is operational within the MHHS arrangements. | Unmetered | UMSO | Unmetered Metering Service
Registration Service | The service operated by LDSOs
REGS | Registration Services | Format | Description
Reverse Migration | The process through which MPANs will move from MHHS arrangements to Legacy arrangements. | Text in GREEN | NEW steps introduced for MIGRATION
Secondary MPAN | The MPAN, within a Related MPAN arrangement, for which a Forward Migration occurs when an IF-031 is received for a Primary MPAN. | Participants in RED | Out of scope participants - substituted by stubs or out of scope for testing
SUPC | Current Supplier | MS | Step in the "Change of Service - Metering Service" process
SUPI | Incoming Supplier | DS | Step in the "Change of Service - Data Service" process
SUPL | Linked Supplier | MS & DS | Common step for "Metering Service" and "Data Service" processes
SUPS | Sending Supplier
Switch | The process by which a new Supplier Registration supersedes an existing Supplier Registration, managed by the CSS.
XDSC | Data Service - Current
XDSP | Data Service – Proposed (denotes that multiple entries for same MAPN (but different DIP ID/Additional Info combinations) may exist for sniffer value)
XDSS | Data Service - Sending
XMIG | Migration Status (IF-036/IF-003)
XMSC | Metering Service – Current
XMSP | Metering Service – Proposed (denotes that multiple entries for same MAPN (but different DIP ID/Additional Info combinations) may exist for sniffer value )
XMSS | Metering Service - Sending
XMSU | Incumbent Metering Service (IF-035)
XMTR | Meter Type (IF-006)
XSEG | Segment (IF-044)
UMSO | Unmetered Metering Service
UMSDS | Unmetered Data Service

## SIT-M-FM-COA-UNMET Overview
Scenario ID | SIT-M-FM-COA-UNMET
Theme | Exception Handling And Other Scenarios
Scenario Title | Forward Migration CoA - Change of Services (MS + DS) for Unmetered meter types
Description | This is a Forward Migration CoA Scenario for Unmetered Market segment. Supplier choses to migrate an existing Legacy System Unmetered MPAN to new MHHS compliant systems. The Supplier remains the same - the Data Services will change. This document lists DS changes for Unmetered MPANs. For CoA, the Incoming/Prospective Supplier = Outgoing/Incumbent Supplier.
Functional Category | Legacy MPAN CoA to a MHHS Qualified Supplier
Functional Area 1
Functional Area 2
Creator | Ankur Pande
Priority | High
Scenario size | Large
Design Document Ref
Business Process | BP003
Pre-Requisites
Note
Test Case Variables | These test are specific to Prospective Appointments only as the process covers all functionality. (1) Unmetered MPANs
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Case Version | Test Description | Meter Type | HH / NHH | Effective Date | Status
1 | SIT-M-FM-COA-UNMET-TC01 | SIT-M-FM-COA-UNMET-TC01 | 0.7.1 | Under this scenario a MHHS Qualified Supplier chooses to migrate an Unmetered MPAN from Legacy NHH settlements to MHHS arrangements. This test is specific to Prospective Appointments only as it covers all functionality. | Unmetered | HH | Next Day | Ready for review

## SIT-M-FM-COA-UNMET-TC01
Test Case Title | Key Journey Events | Test Step | Business Process | BP Step | Service Type | Test Steps | Trigger Sender | Interface ID | Trigger Receipient | Traceability Requirement | Message Input Event Code | Evidence Required | Key Validation & Test Evidence
Based on SIT Functional Tests - DEL1831
SIT-M-FM-COA-UNMET-TC01 | Supplier Appointment Request | 1 | BP002 | 10, 20 | MS | SUPC sends IF-031 to the DIP for a MS Appointment. | SUPC | IF-031 | DIP | MHHS-BR-SU-005 MHHS-BR-SU-006 MHHS-BR-SU-007 | [MSApp] | N | http 201 response from DIP
|  | 2 | BP002 | 30 | MS | DIP sends PUB-031 to REGS for a MS Appointment. | DIP | PUB-031 | REGS | MHHS-BR-RS-009 | [MSApp] | N | N/A
|  | 3 | BP002 | 40 | MS | REGS receives PUB-031 - Supplier Service Appointment Request from the DIP. | DIP | PUB-031 | REGS | MHHS-BR-RS-010 | [MSApp] | Y | REGS receives PUB-031 and confirms the Supplier Service Appointment Request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 4 | BP003 |  | MS | Supplier de-appoints MA via a D0151 with data item "Termination Reason" (J0279) with the value "CA" as per a Legacy CoA. | SUPC | D0151 | Outgoing MA | N/A | N/A | N | N/A
|  | 5 | BP003 | 10, 20 | DS | SUPC sends IF-031 to DIP - for a DS Appointment | SUPC | IF-031 | DIP | MHHS-BR-SU-019 MHHS-BR-SU-020 MHHS-BR-SU-021 | [DSApp] | N | http 201 response from DIP
|  | 6 | BP003 | 30 | DS | DIP sends PUB-031 to REGS for a DS Appointment | DIP | PUB-031 | REGS | N/A | [DSApp] | N
|  | 7 | BP003 | 40 | DS | REGS receives PUB-031 - Supplier Service Appointment Request from the Supplier. | DIP | PUB-031 | REGS | MHHS-BR-RS-043 MHHS-BR-RS-044 | [DSApp] | Y | REGS receives PUB-031 DSApp with details of Data Services Appointment and confims the supplier service appointment request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 8 | BP003 |  | DS | Supplier de-appoints HHDC via a D0151 with data item "Termination Reason" (J0279) with the value "CA" as per a Legacy CoA de-appointment | SUPC | D0151 | Outgoing HHDC | N/A | N/A | N | N/A
|  | 9 | BP003 |  | DS | Outgoing HHDC will receive a D0170 to notify them that a Migration is occurring so that they operate the required Migration process. | REGS | D0170 | Outgoing HHDC | N/A | N/A | N | N/A
| Supplier Appointment Request Accepted | 10 | BP002 | 45 | MS | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | REGS | IF-032 | DIP | MHHS-BR-RS-011 | [MSAppSPResponse] | N | http 201 response from DIP
|  | 11 | BP002 | 50 | MS | DIP sends PUB-032 to the Supplier. | DIP | PUB-032 | SUPC | N/A | [MSAppSPResponse] | N | N/A
|  | 12 | BP002 | 55 | MS | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | DIP | PUB-032 | SUPC | MHHS-BR-SU-008 MHHS-BR-SU-009 | [MSAppSPResponse] | Y | Supplier receives PUB-032 and confirms the Supplier Service Provider Appointment Request Response and waits for Acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 13 | BP003 | 45 | DS | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | REGS | IF-032 | DIP | MHHS-BR-RS-045 MHHS-BR-RS-046 | [DSAppInitialResp] | N | http 201 response from DIP
|  | 14 | BP003 | 50 | DS | DIP sends PUB-032 - Supplier Service Provider Appointment Request Response to the DIP. | DIP | PUB-032 | SUPC | N/A | [DSAppInitialResp] | N | N/A
|  | 15 | BP003 | 55 | DS | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | DIP | PUB-032 | SUPC | MHHS-BR-SU-022 MHHS-BR-SU-023 | [DSAppInitialResp] | Y | Supplier receives PUB-032 DSAppInitialResp with details of Data Services Appointment Initial Response and confims Supplier Service Provider Appointment Request Response and waits for acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
| RS Appointment Request | 16 | BP002 | 60 | MS | REGS sends IF-033 to the DIP. | REGS | IF-033 | DIP | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | [MSAppSPRequest] | N | http 201 response from DIP
|  | 17 | BP002 | 65 | MS | DIP sends PUB-033 to the UMSO. | DIP | PUB-033 | UMSO | N/A | [MSAppSPRequest] | N | N/A
|  | 18 | BP002 | 70 | MS | UMSO receives PUB-033. | DIP | PUB-033 | UMSO | MHHS-BR-MS-001 | [MSAppSPRequest] | Y | UMSO receives PUB-033 from the REGS which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 19 | BP003 | 60 | DS | REGS sends IF-033 to DIP | REGS | IF-033 | DIP | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | [DSAppSPRequest] | N | http 201 response from DIP
|  | 20 | BP003 | 65 | DS | DIP sends PUB-033 to the UMSDS (Incoming). | DIP | PUB-033 | UMSDSI (Incoming DS) | N/A | [DSAppSPRequest] | N | N/A
|  | 21 | BP003 | 220 | DS | UMSDS (Incoming) receives PUB-033 from the DIP. | DIP | PUB-033 | UMSDSI (Incoming DS) | MHHS-BR-DS-007 MHHS-BR-DS-011 | [DSAppSPRequest] | Y | UMSDS (Incoming) receives PUB-033 DSAppSPResponse with details of Data Services Appointment PR Response and confirms the REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
| RS Appointment Request Accepted | 22 | BP002 | 75 | MS | UMSO (Incoming) sends IF-034 to the DIP. | UMSO (Incoming MS) | IF-034 | DIP | MHHS-BR-MS-002 MHHS-BR-MS-003 | [MSAppSPResponse] | N | http 201 response from DIP
|  | 23 | BP002 | 80 | MS | DIP sends PUB-034 to the REGS. | DIP | PUB-034 | REGS | N/A | [MSAppSPResponse] | N | N/A
|  | 24 | BP002 | 85 | MS | REGS receives PUB-034. | DIP | PUB-034 | REGS | MHHS-BR-RS-016 MHHS-BR-RS-017 | [MSAppSPResponse] | Y | REGS receives PUB-034 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 25 | BP003 | 221 | DS | UMSDS (Incoming) sends IF-034 to the DIP. | UMSDSI (Incoming DS) | IF-034 | DIP | MHHS-BR-DS-008 MHHS-BR-DS-011 | [DSAppSPResponse] | N | http 201 response from DIP
|  | 26 | BP003 | 80 | DS | DIP sends PUB-034 to the REGS. | DIP | PUB-034 | REGS | N/A | [DSAppSPResponse] | N | N/A
|  | 27 | BP003 | 85, 100 | DS | REGS receives PUB-034 and determines processing treatment | DIP | PUB-034 | REGS | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-054 MHHS-BR-RS-056 MHHS-BR-RS-057 | [DSAppSPResponse] | Y | REGS receives PUB-034 DSAppSPResponse with relevant information of service appointment to determine processing treatment Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 28 | BP003 |  | DS | REGS sends a D0170 to Outgoing HHDC | REGS | D0170 | Outgoing HHDC | N/A | N/A | N | N/A
| RS Appointment Accepted | 29 | BP002 | 87 | MS | REGS sends IF-035 to the DIP. | REGS | IF-035 | DIP | MHHS-BR-RS-018 | [MSAppAccepted] | N | http 201 response from DIP
|  | 30 | BP002 | 91 | MS | DIP sends PUB-035 to the Supplier and UMS (Incoming) | DIP | PUB-035 | SUPC, UMSO | N/A | [MSAppAccepted] | N | N/A
|  | 31 | BP002 | 95 | MS | Supplier receives PUB-035. | DIP | PUB-035 | SUPC | MHHS-BR-SU-010 MHHS-BR-SU-011 | [MSAppAccepted] | Y | Supplier receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 32 | BP002 | 92 | MS | UMSO receives PUB-035. | DIP | PUB-035 | UMSO | MHHS-BR-MS-006.1 | [MSAppAccepted] | Y | UMSO receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 33 | BP003 | 86, 87 | DS | REGS sends IF-035 to the DIP | REGS | IF-035 | DIP | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-052 | [DSAppAccepted] | N | http 201 response from DIP
|  | 34 | BP003 | 215 | DS | DIP sends PUB-035 to the Supplier and UMSDS (Incoming) | DIP | PUB-035 | SUPC, UMSDSI (Incoming DS) | N/A | [DSAppAccepted] | N | N/A
|  | 35 | BP003 | 95 | DS | Supplier receives PUB-035. | DIP | PUB-035 | SUPC | MHHS-BR-SU-024 MHHS-BR-SU-025 | [DSAppAccepted] | Y | Supplier receives PUB-035 with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 36 | BP003 | 91 | DS | UMSDS (Incoming) receives PUB-035. | DIP | PUB-035 | UMSDSI (Incoming DS) | MHHS-BR-DS-012.1 | [DSAppAccepted] | Y | UMSDS (Incoming) receives PUB-035 successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
| RS Appointment Notification | 37 | BP002 | 240 | MS | REGS sends IF-036 to DIP. | REGS | IF-036 | DIP | MHHS-BR-RS-033 | [MSAppActive] | N | http 201 response from DIP
|  | 38 | BP002 | 245 | MS | DIP sends PUB-036 to SUPC, LDSO, EES, UMSO and UMSDS. | DIP | PUB-036 | UMSO | N/A | [MSAppActive] | N | N/A
|  | 39 | BP002 | 260 | MS | Supplier receives PUB-036 | DIP | PUB-036 | SUPC | MHHS-BR-SU-013 | [MSAppActive] | Y | Supplier receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 40 | BP002 | 280 | MS | LDSO(If opted in) receives PUB-036 | DIP | PUB-036 | LDSO(If opted in) | MHHS-BR-LD-003 | [MSAppActive] | Y | LDSO(If opted in) receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 41 | BP002 | 283 | MS | EES receives PUB-036 | DIP | PUB-036 | EES | MHHS-BR-EES-016.3 | [MSAppActive] | Y | EES receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 42 | BP002 | 195 | MS | UMSO receives PUB-036 | DIP | PUB-036 | UMSO | MHHS-BR-MS-007 | [MSAppActive] | Y | UMSO receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 43 | BP003 | 250 | DS | REGS sends IF-036 to DIP | REGS | IF-036 | DIP | MHHS-BR-RS-067 | [DSAppActive] | N | http 201 response from DIP
|  | 44 | BP003 | 255 | DS | DIP sends PUB-036 to SUPC, UMSO, LDSO(If opted in), EES, UMSDS (Incoming) and MDS confirming DS Appointment | DIP | PUB-036 | SUPC, UMSO, LDSO(If opted in), EES, UMSDSI, MDS | N/A | [DSAppActive] | N | N/A
|  | 45 | BP003 | 260 | DS | Supplier receives PUB-036 | DIP | PUB-036 | SUPC | MHHS-BR-SU-027 | [DSAppActive] | Y | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 46 | BP003 | 281 | DS | UMSO receives PUB-036 | DIP | PUB-036 | UMSO | MHHS-BR-MS-030 | [DSAppActive] | Y | UMSO receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 47 | BP003 | 280 | DS | LDSO(If opted in) receives PUB-036 | DIP | PUB-036 | LDSO(If opted in) | MHHS-BR-LD-005 | [DSAppActive] | Y | LDSO(If opted in) receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 48 | BP003 | 279 | DS | EES receives PUB-036 | DIP | PUB-036 | EES | MHHS-BR-EES-016.3 | [DSAppActive] | Y | EES receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 49 | BP003 | 284 (TBC) | DS | MDS receives PUB-036 | DIP | PUB-036 | MDS | N/A | [DSAppActive] | Y | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
|  | 50 | BP003 | 340 | DS | UMSDS (Incoming) receives PUB-036 | DIP | PUB-036 | UMSDSI (Incoming DS) | MHHS-BR-DS-013 | [DSAppActive] | Y | UMSDS (Incoming) receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
| Transfer Inventory Data | 51 | BP002 |  | MS | Incoming MS (UMSO) shares Inventory Data with the Incoming DS (UMDS) | UMSO (Incoming MS) | D0388 | UMSDS (Incoming DS) | N/A | N/A | N | N/A
|  | 52 | BP003 |  | DS | Incoming MS (UMSO) shares Inventory Data with the Incoming DS (UMDS) | UMSO (Incoming MS) | D0388 | UMSDS (Incoming DS) | N/A | N/A | N | N/A
| Transfer of Readings | 53 | BP002 |  | MS | The outgoing DC will collect data to their Effective To Date and provide through to those parties that require it following the legacy processes | Outgoing HHDC | D0036 | SUPC | N/A | N/A | N | N/A
|  | 54 | BP003 |  | DS | The outgoing DC will collect data to their Effective To Date and provide through to those parties that require it following the legacy processes | Outgoing HHDC | D0036 | SUPC | N/A | N/A | N | N/A