## Change Log
Date | Author | Release | Defect ID | Reason for change
08.04.2024 | Ankur Pande | 0.1 |  | New Migration Test Scenario document
19.04.2024 | Ankur Pande | 0.2 |  | Incorporated ISD check & non-MHHS verification steps
30.04.2024 | Ankur Pande | 0.4 |  | Added ISD check and corrected COS step sequence
Changed sequence of BP003A CSS/DCC Update Steps for Smart Meters
Clarified D0209 being sent by REGS to Incoming DA
10.05.2024 | Ankur Pande | 0.5 |  | Corrected CSS/DCC Update steps for Reverse Migration
Corrected Typos Made tests ready for ADO upload - added default values for empty cells - removed blank lines - Replaced DIP response from "http 202 response from DIP" to "http 201 response from DIP" - Added (If opted in) to IF-036/PUB-036 for LDSO for TC01 to TC05 - Changed Test Step sequence from 5-10-15... to 1-2-3...
22.10.2024 | Ayasha Kirana, Mahjabeen Newaz | 0.4 | DIN-762 | Changes made: - Updated terminology: 'Reverse migration de-appointment notification' for all applicable steps - Removed Step 34 in TC01, Step 31 in TC02, Step 40 in TC03 - Updating step numbering - Added correct event codes in applicable steps with [ReverseMigNotification], [MSDeAppRM], and [DSDeAppRM] - Added requirement MHHS-RMigration-CoA(DS)-ECS-001 to step where MDS will process the Reverse Migration De-Appointment Notification
30.10.2024 | Ayasha Kirana | 0.5 |  | - Amended Step 49 TC01, Step 39 TC02 to replace 'Incoming Supplier' with SDSO. - Step 50 and 51 evidence flagged to N - Removed 'LDSO' from Step 35 TC03 - Replaced LDSO with 'MDS' in Step 37 TC03
2014-11-05 | Vidya Shitole | 0.5 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC01 for steps 25,27
2014-11-05 | Vidya Shitole | 0.5 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC02 for steps 25,27
2014-11-05 | Vidya Shitole | 0.5 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC03 for steps 34,36,53
27.Nov.2024 | Ankur Pande | 0.5.1 | 43756 | Removed reference to IF-001 for all tests
09.Jan.2025 | Ankur Pande | 0.5.2 | 47010 | Change OOS SUPI role to DCC Stub in all tests to make the test case clearer
2025-01-15 | Hrishikesh Namade | 0.5.2 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC01 for step 06
2025-01-15 | Hrishikesh Namade | 0.5.2 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC02 for step 06
2025-01-15 | Hrishikesh Namade | 0.5.2 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC03 for step 06
24.Jan.2025 | Ankur Pande | 0.5.3 | 46309 | Changed DCC/CSS update steps as requested by REGS (SCS)

## Terminology
Terminology Used | Description | Type of Meter | Data Service | Description
BAU Process | This refers to a process within the MHHS arrangements as set out within the MHHS Core Design | Smart | SDSC | Smart Meter Data Service - Current
CoA | Change of Agent |  | SDSI | Smart Meter Data Service - Incoming
CoS | Change of Supplier |  | SDSO | Smart Meter Data Service - Outgoing
CSS | Central Switching Service | Traditional | SDSC | Traditional Meter Data Service - Current
Data Cleanse Plan | The approach and activities required to improve and populate data prior to Migration start |  | SDSI | Traditional Meter Data Service - Incoming
DC | Data Collector |  | SDSO | Traditional Meter Data Service - Outgoing
DIP | Data Integration Platform | Advanced | ADSC | Advanced Meter Data Service - Current
DS | Data Service |  | ADSI | Advanced Meter Data Service - Incoming
Forward Migration | The process through which MPANs will move from Legacy arrangements to MHHS arrangements. |  | ADSO | Advanced Meter Data Service - Outgoing
Incoming / New MS | Incoming / New Metering Service | Unmetered | UMSDS | Unmetered Data Service
Incoming DS / New DS | Incoming Data Services
ISD | Industry Standing Data | Type of Meter | Metering Service | Description
LDSO | Licensed Distribution System Operator | Smart | SMSC | Smart Meter Metering Service - Current
MHHS | Market-Wide Half-Hourly Settlement |  | SMSI | Smart Meter Metering Service - Incoming
MHHS Arrangements | The new MHHS arrangements as set out in the MHHS Core Design Artefacts. |  | SMSO | Smart Meter Metering Service - Outgoing
Migration Design | The technical articulation of how MPANs will move from Legacy to new MHHS arrangements. | Traditional | SMSC | Traditional Meter Metering Service - Current
Migration Period | The period denoted by the Programme as occurring between the M11 and M15 milestones. |  | SMSI | Traditional Meter Metering Service - Incoming
MOP | Meter Operator |  | SMSO | Traditional Meter Metering Service - Outgoing
MPAN | Metering Point Administration Number | Advanced | AMSC | Advanced Meter Metering Service - Current
MS | Metering Service |  | AMSI | Advanced Meter Metering Service - Incoming
Outgoing MOP | Outgoing Meter Operator |  | AMSO | Advanced Meter Metering Service - Outgoing
Qualified Supplier | A Supplier recognised in ISD as both having passed the relevant System Integration Testing (SIT) requirements or BSC qualification requirements; and declared that their service is operational within the MHHS arrangements. | Unmetered | UMSO | Unmetered Metering Service
Registration Service | The service operated by LDSOs
REGS | Registration Services | Format | Description
Reverse Migration | The process through which MPANs will move from MHHS arrangements to Legacy arrangements. | Text in GREEN | NEW steps introduced for MIGRATION
Secondary MPAN | The MPAN, within a Related MPAN arrangement, for which a Forward Migration occurs when an IF-031 is received for a Primary MPAN. | Participants in RED | Out of scope participants - substituted by stubs or out of scope for testing
SUPC | Current Supplier | MS | Step in the "Change of Service - Metering Service" process
SUPI | Incoming Supplier | DS | Step in the "Change of Service - Data Service" process
SUPL | Linked Supplier | MS & DS | Common step for "Metering Service" and "Data Service" processes
SUPS | Sending Supplier
Switch | The process by which a new Supplier Registration supersedes an existing Supplier Registration, managed by the CSS.
XDSC | Data Service - Current
XDSP | Data Service – Proposed (denotes that multiple entries for same MAPN (but different DIP ID/Additional Info combinations) may exist for sniffer value)
XDSS | Data Service - Sending
XMIG | Migration Status (IF-036/IF-003)
XMSC | Metering Service – Current
XMSP | Metering Service – Proposed (denotes that multiple entries for same MAPN (but different DIP ID/Additional Info combinations) may exist for sniffer value )
XMSS | Metering Service - Sending
XMSU | Incumbent Metering Service (IF-035)
XMTR | Meter Type (IF-006)
XSEG | Segment (IF-044)
UMSO | Unmetered Metering Service
UMSDS | Unmetered Data Service

## SIT-M-RM-COS-DfltVal Overview
Scenario ID | SIT-M-RM-COS-DfltVal
Theme | Reverse Migration CoS
Scenario Title | Reverse Migration CoS - Change of Services (MS + DS) - REGS defaults values in a D0217 when Supplier doesn't send them for an MPAN.
Description | This is a Reverse Migration CoS Scenario for when Legacy Supplier initiates the migration of an existing MHHS compliant system to the Legacy System. The Supplier, Metering Service and Data Services are changed. The test handles the exception when REGS has to default values in a D0217 when the Supplier doesn't send these for an MPAN Important Pre-requisites: Traditional Meter - The CoS steps are the same as for New Connection. Please see MHHS-DEL1757 SITFTS-0050 New Connection v0.7 (Worksheet = SITFTS0050- Traditional) for detailed steps Advanced Meter - The CoS steps are the same as for New Connection. Please see MHHS-DEL1757 SITFTS-0050 New Connection v0.7 (Worksheet = SITFTS0050- Advanced) for detailed steps. Smart Meter - The CoS steps are the same as for New Connection. Please see MHHS-DEL1757 SITFTS-0050 New Connection v0.7 (Worksheet = SITFTS0050- Smart) for detailed steps.
Functional Category | MHHS MPAN CoS to a Supplier that is not MHHS Qualified (Legacy MPAN) - REGS defaults values in a D0217 when Supplier doesn't send them for an MPAN.
Functional Area 1
Functional Area 2
Creator | Ankur Pande
Priority | High
Scenario size | Large
Design Document Ref
Business Process | BPM-001, BPM-002, BPM-003
Pre-Requisites | Traditional Meter - The CoS steps are the same as for New Connection. Please see MHHS-DEL1757 SITFTS-0050 New Connection v0.7 (Worksheet = SITFTS0050- Traditional) for detailed steps Advanced Meter - The CoS steps are the same as for New Connection. Please see MHHS-DEL1757 SITFTS-0050 New Connection v0.7 (Worksheet = SITFTS0050- Advanced) for detailed steps. Smart Meter - The CoS steps are the same as for New Connection. Please see MHHS-DEL1757 SITFTS-0050 New Connection v0.7 (Worksheet = SITFTS0050- Smart) for detailed steps.
Boundaries | Processing ends once the MTDs & reads have been received, and ingested
Verification Checks | Following checks will be conducted on completion of the Change of Agent (Data Service or Metering Service) to verify a successful transition. (1) MTDs have been received by relevant PPs (2) Readings are passed to DS/Suppliers
Test Case Variables | (1) Traditional Meter (2) Advanced Metering (3) Smart Metering
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Case Version | Test Description | Meter Type | Effective Date | Status
1 | SIT-M-RM-COS-DfltVal-TC01 | SIT-M-RM-COS-DfltVal-TC01 - Traditional | 0.5.2 | This scenario is for when a Traditional metered MPAN has been migrated to the MHHS arrangements by its current supplier and is subsequently lost to a non-MHHS enabled supplier | Traditional | Next Day | Ready for review
2 | SIT-M-RM-COS-DfltVal-TC02 | SIT-M-RM-COS-DfltVal-TC02 - Advanced | 0.5.2 | This scenario is for when an Advanced metered MPAN has been migrated to the MHHS arrangements by its current supplier and is subsequently lost to a non-MHHS enabled supplier | Advanced Meter | Next Day | Ready for review
3 | SIT-M-RM-COS-DfltVal-TC03 | SIT-M-RM-COS-DfltVal-TC03 - Smart | 0.5.3 | This scenario is for when a Smart metered MPAN has been migrated to the MHHS arrangements by its current supplier and is subsequently lost to a non-MHHS enabled supplier | Smart Meter | Next Day | Ready for review

## SIT-M-RM-COS-DfltVal-TC01 Trad
Test Case Title | Key Journey Events | Test Step # | Business Process | BP Step | Service Type | Test Steps | Test Description | Interface Sender | Interface ID | Interface Recipient | Traceability Requirement | Message Input Event Code | Evidence Required? | Key Validation & Test Evidence
SIT-M-RM-COS-MS-DS-TC01 Trad | Traditional MPAN Setup | 1 | BP001 |  |  | Create an MPAN through new connection process, appoint services and install meter & Energise the MPAN | The CoS steps are the same as for New Connection. Please see MHHS-DEL1757 SITFTS-0050 New Connection v0.7 (Worksheet = SITFTS0050- Traditional) for detailed steps. | N/A | N/A | N/A | N/A | N/A | N | N/A
| Change of Supply - Start | 2 | BP001 | 60 | MS & DS | Initial Registration or Change of Supplier Required | Incoming Supplier sends a Switch Request to the CSS In the absence of the Incoming Supplier, we're expecting the use of a DCC Stub to generate the CSS01800. | DCC Stub | CSS01800 | CSS | N/A | N/A | Y | Evidence that DCC Stub generates a CSS01800; log screenshots in downstream systems.
|  | 3 | BP001 | 65 | MS & DS | MPAN EES Interaction (if required) | Suppliers may need to use the MPAN EES in order to establish criteria for taking Supply. In the absence of the Incoming Supplier, we're expecting the use of a DCC Stub to generate the CSS01800. | DCC Stub | CSS01800 | CSS | N/A | N/A | Y | Evidence that DCC Stub generates a CSS01800; log screenshots in downstream systems.
| COS status at Pending Registration Sync | 4 | BP001 | 70 | MS & DS | COS status at Pending Registration Sync | CSS sends CSS2800 (pending Supplier request via CSS flow) to the REGS Registration Service receives pending Supplier request via CSS flow. | CSS | CSS02800 | REGS | MHHS-BR-RS-005 | N/A | Y | Evidence that CSS produces a CSS02800 which is consumed by REGS; log screenshots in downstream systems.
|  | 5 | BP001 |  |  | Check ISD for qualifications status of Supplier | Confirm that the check returns Incoming Supplier is not MHHS qualified to initiate Reverse Migration. | N/A | N/A | N/A | N/A | N/A | Y | Evidence that the Incoming Supplier's status is for a non-MHHS qualified supplier.
|  | 6 | BP001 | 185 | MS & DS | REGS populates the D0217 / D0260 with default data and sends it to Incoming Supplier (SUPI) | REGS identifies NULL legacy data in the system but cannot find it own system (REGS). REGS populates the D0217 / D0260 with default data and sends it to Incoming Supplier (SUPI) - Default MPID of "MHHS" - Default Measurement Class "F", Meter Timeswitch "800" | REGS | D0217 / D0260 | DCC Stub | MHHS-Migration-CoS-SUP-001 MHHS-Migration-CoS-SUP-002 | N/A | N | REGS populates the D0217 / D0260 with default data as mentioned.
| CSS sends COS Secured notification to SUPI | 7 | BP001 | 100 | MS & DS | CSS sends a COS "Secure Active" notification to SUPI (Legacy) (DCC Stub) | Suppliers (DCC Stub) will receive notification from CSS that COS has a "Secure Active" status | CSS | CSS02370 | DCC Stub | MHHS-BR-SU-003 MHHS-BR-SU-048 | N/A | Y | Evidence that CSS produces a CSS02370. Log screenshots in downstream systems.
| CSS sends COS Secured notification to REGS | 8 | BP001 | 130 | MS & DS | CSS sends a COS "Secure Active" notification to REGS | The Registration Service will receive a COS "Secure Active" notification from CSS. | CSS | CSS02860 | REGS | MHHS-BR-RS-007 MHHS-BR-RS-008 MHHS-BR-RS-094 MHHS-BR-RS-096 | N/A | Y | Evidence that CSS produces a CSS02860 which is consumed by REGS; log screenshots in downstream systems.
| New Supplier Receives Secured Active Notification | 9 | BP001 | 195 | MS & DS | Reverse Migration Change of Service BPM-002 / BPM-003 | Once the new Supplier receives the 'Secure Active' notification from the CSS, The New Supplier will then reverse migrate the MPAN and follow the Reverse migration change of Agent processes (note: Reverse migration can only occur via a CoS, however the CoA process diagrams are used to demonstrate the process of changing to legacy agents). | N/A | N/A | N/A | N/A | N/A | N | N/A
|  | 10 | BP001 | 200 | MS & DS | Confirm Reverse Migration | The Registration Service will send MHHS-IF-003 to inform parties that a Reverse Migration is confirmed | REGS | IF-003 | SUPO, MDS, EES, LDSO | N/A | [ReverseMigNotification] | Y | (1) Evidence that REGS produces an IF-003 which is consumed by the Outgoing Supplier, MDS, EES and LDSO. (2) Log screenshots in downstream systems.
|  | 11 | BP001 | 205 | MS & DS | Receive and Publish Reverse Migration notification | The DIP will receive MHHS-IF003 and send PUB-003 to the Outgoing Supplier, MDS, EES and LDSO | DIP | PUB-003 | SUPO, MDS, EES, LDSO | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the Outgoing Supplier, MDS, EES and LDSO. (2) Log screenshots in downstream systems.
|  | 12 | BP001 | 210 | MS & DS | Receive Reverse Migration notification | MDS will receive PUB-003 and update it's records that the MPAN is in legacy settlement | DIP | PUB-003 | MDS | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the MDS (2) Log screenshots in downstream systems.
|  | 13 | BP001 | 215 | MS & DS | Receive Reverse Migration notification | LDSO will receive PUB-003 and update its records that the MPAN is in legacy DUoS Billing | DIP | PUB-003 | LDSO | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the LDSO (2) Log screenshots in downstream systems.
|  | 14 | BP001 | 220 | MS & DS | Receive Reverse Migration notification | EES will receive PUB-003 and update its records that the MPAN has reverse migrated Note: The EES will need to set a status that the MPAN has reverted to Legacy arrangements. Parties should be able to enquire via the portal and the API and see this status. | DIP | PUB-003 | EES | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the EES (2) Log screenshots in downstream systems.
|  | 15 | BP001 | 225 | MS & DS | Receive Reverse Migration notification | Outgoing Supplier will receive PUB-003 and update its records that the MPAN has reverse migrated | DIP | PUB-003 | SUPO | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the SUPO (2) Log screenshots in downstream systems.
| Setup Appointments | 16 | BPM-002 | 1001 | MS | Appoint Legacy Agents - Send Notification of Meter Operator or Data Collector Appointment and Terms | The Incoming Supplier (DCC Stub) will send an appointment notification to the Incoming MOP via a D0155. A specific value is used in the 'Contract Reference' data field to indicate that a Reverse Migration is occurring. | DCC Stub | D0155 | Incoming MOP (Stubbed) | MHHS-RMigration-CoA(MS)-SUP-001 | N/A | N | N/A
|  | 17 | BPM-003 | 1001 | DS | Appoint Legacy Agents | The Incoming Supplier (DCC Stub) will send an appointment notification to the new DC via a D0155. Will use a specific value in the 'Contract Reference' data field to indicate a Reverse Migration is occurring. | DCC Stub | D0155 | Incoming DC (Stubbed) | MHHS-RMigration-CoA(DS)-SUP-001 | N/A | N | N/A
| Accept Appointments | 18 | BPM-002 | 1002 | MS | Accept Appointment - Agreement of Contractual Terms | The Incoming MOP will accept the appointment and share a D0011 with the Incoming Supplier (DCC Stub) | Incoming MOP (Stubbed) | D0011 | DCC Stub | MHHS-RMigration-CoA(MS)-MOP-002 | N/A | N | N/A
|  | 19 | BPM-003 | 1002 | DS | Accept Appointment | The incoming DC will accept the appointment and share a D0011 with the incoming Supplier (DCC Stub) | Incoming DC (Stubbed) | D0011 | DCC Stub | MHHS-RMigration-CoA(DS)-DC-004 | N/A | N | N/A
| Update Agent Appointment | 20 | BPM-002 | 1003 | MS | Update agent appointment and settlement details | The Incoming Supplier (DCC Stub) will update the agent appointment and settlement details via a D0205 to the Registration Service. | DCC Stub | D0205 | REGS | MHHS-RMigration-CoA(MS)-SUP-002 | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
|  | 21 | BPM-002 | 1004 | MS | Update agent appointment and settlement details | The Registration Service will use this D0205 to update the agent appointment and settlement details. | DCC Stub | D0205 | REGS | MHHS-RMigration-CoA(MS)-RS-004 | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
|  | 22 | BPM-003 | 1003 | DS | Update Agent appointment and settlement details | The incoming Supplier (DCC Stub) will update the Agent appointment and settlement details via a D0205 to the Registration Service. | DCC Stub | D0205 | REGS | MHHS-RMigration-CoA(DS)-SUP-002 | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
|  | 23 | BPM-003 | 1004 | DS | Update Agent appointment and settlement detailsUpdate agent appointment and settlement details | The Registration Service will use this D0205 to update the Agent appointment and settlement details. | DCC Stub | D0205 | REGS | MHHS-RMigration-CoA(DS)-RS-003 MHHS-RMigration-CoA(DS)-RS-004 | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
|  | 24 | BPM-003 |  | DS | REGS sends D0209 with Incoming DA | REGS sends D0209 with Incoming DA | REGS | D0209 | Incoming DA | N/A | N/A | Y | Evidence that the REGS sends a D0209 to the Incoming DA and it gets consumed.
| Issue Deappointment & Reverse Migration Process | 25 | BPM-002 | 1008 | MS | Issue MS Reverse Migration De-Appointment Notification to Outgoing MS | An IF-003 will be sent to the DIP which informs that the MS is being de-appointed. | REGS | IF-003 | DIP | MHHS-RMigration-CoA(MS)-RS-001 MHHS-RMigration-CoA(MS)-RS-005 MHHS-RMigration-CoA(MS)-SUP-004 MHHS-RMigration-CoA(MS)-MOP-003 MHHS-RMigration-CoA(MS)-MS-003 MHHS-RMigration-CoA(MS)-RS-007 | [MSDeAppRM] | N | http 201 response from DIP
|  | 26 | BPM-002 | 1009 | MS | Publish MS Reverse Migration De-Appointment Notification | The DIP will publish the PUB-003 to the outgoing MS, the outgoing Supplier, and the EES | DIP | PUB-003 | SMSO SUPO EES | MHHS-RMigration-CoA(MS)-ECS-001 | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Metering Service, Outgoing Supplier, and EES. (2) Log screenshots in downstream systems.
|  | 27 | BPM-003 | 1008 | DS | Issue DS Reverse Migration De-Appointment Notification | An IF-003 will be sent to the DIP which informs that the DS is being de-appointed. | REGS | IF-003 | DIP | MHHS-RMigration-CoA(DS)-RS-005 MHHS-RMigration-CoA(DS)-RS-007 | [DSDeAppRM] | N | http 201 response from DIP
|  | 28 | BPM-003 | 1009 | DS | Publish DS Reverse Migration De-Appointment Notification | The DIP will publish the PUB-003 to the outgoing DS, the outgoing Supplier, MDS and the EES. | DIP | PUB-003 | SDSO SUPO EES MDS | MHHS-RMigration-CoA(DS)-ECS-001 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Data Service, SUPO, MDS and EES. (2) Log screenshots in downstream systems.
| EES - Close out MHHS Arrangement | 29 | BPM-002 | 1010 | MS | Process MS Reverse Migration De-Appointment Notification | The EES will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | EES | MHHS-RMigration-CoA(MS)-EES-001 MHHS-RMigration-CoA(MS)-EES-002 | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by EES. (2) Log screenshots in downstream systems.
|  | 30 | BPM-003 | 1010 | DS | Process DS Reverse Migration De-Appointment Notification | The EES will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | EES | MHHS-RMigration-CoA(DS)-EES-001 MHHS-RMigration-CoA(DS)-EES-002 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by EES. (2) Log screenshots in downstream systems.
| MDS - Close out MHHS Arrangement | 31 | BPM-003 | 1011 | DS | Process Reverse Migration De-Appointment Notification | The MDS will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | MDS | MHHS-RMigration-CoA(DS)-ECS-001 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by MDS. (2) Log screenshots in downstream systems.
| Outgoing Supplier Processes Reverse Migration & De-Appointment Notification | 32 | BPM-002 | 1012 | MS | Process MS Reverse Migration De-Appointment Notification | The outgoing Supplier will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | SUPO | MHHS-RMigration-CoA(MS)-SUP-003 | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by SUPO. (2) Log screenshots in downstream systems.
|  | 33 | BPM-003 | 1012 | DS | Process DS Reverse Migration De-Appointment Notification | The outgoing Supplier will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | SUPO | MHHS-RMigration-CoA(DS)-SUP-004 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by SUPO. (2) Log screenshots in downstream systems.
| Outgoing Metering & Data Servicees Process Reverse Migration & De-Appointment Notification | 34 | BPM-002 | 1013 | MS | Process MS Reverse Migration De-Appointment Notification | The outgoing MS will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | SMSO | N/A | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Metering Service. (2) Log screenshots in downstream systems.
|  | 35 | BPM-003 | 1013 | DS | Process DS Reverse Migration De-Appointment Notification | The outgoing DS will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | SDSO | N/A | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Data Service. (2) Log screenshots in downstream systems.
| Issue MTDs | 36 | BPM-002 | 1014 (160) | MS | Issue MTD to Prospective/Incoming MOP | The existing Metering Service will receive notification from the Registrations service of who the prospective MOP is. Metering Service will send the meter technical details to the prospective Metering Service. - Metering Services must issue all MTD's for linked export/related MPANS | SMSO | D0149 D0150 | Incoming MOP (Stubbed) | MHHS-RMigration-CoA(MS)-MS-002 | N/A | Y | (1) Evidence that SMSO produces a D0149/D0150 which is consumed by New MOP. (2) Log screenshots in downstream systems.
|  | 37 | BPM-002 | 1015 (165) | MS | Send D0149/D0150 for Traditional Meters | Traditional Metering flows that will need to be sent from the existing Metering Service to the incoming MOP | SMSO | D0149 D0150 | Incoming MOP (Stubbed) | N/A | N/A | Y | (1) Evidence that Existing Metering Service produces a D0149 and D0150 which is consumed by Incoming MOP. (2) Log screenshots in downstream systems.
| Receive MTDs | 38 | BPM-002 | 1019 (175) | MS | Receive MTDs | The incoming MOP will receive Meter technical details from the existing Metering Service via data flows. | SMSO | D0149 D0150 | Incoming MOP (Stubbed) | N/A | N/A | Y | (1) Evidence that Existing Metering Service produces a D0149 and D0150 which is consumed by Incoming MOP.
|  | 39 | BPM-002 | 1020 (180) | MS | Issue MTDs via DTN | The Incoming MOP will issue the meter technical details to Supplier (DCC Stub), Incoming DC and LDSO via the DTN | Incoming MOP (Stubbed) | D0149 D0150 | DCC Stub Incoming DC (Stubbed) LDSO | MHHS-RMigration-CoA(MS)-MOP-001 | N/A | Y | (1) Evidence that Incoming MOP stub produces a D0149 and D0150 which is consumed by LDSO.
| Incoming DC receives incoming MTDS from Incoming MOP via DTN | 40 | BPM-002 | 1021 (190) | MS | Incoming DC receives incoming MTDS from Incoming MOP via DTN | The incoming DC will receive the meter technical details from the incoming MOP via the DTN | Incoming MOP (Stubbed) | D0149 D0150 | Incoming DC (Stubbed) | N/A | N/A | N | N/A
|  | 41 | BPM-002 | 1022 | MS | END POINT FOR THIS LOGIC THREAD | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
| The Incoming MOP will send the MTDs to the Incoming Supplier | 42 | BPM-002 | 1023 | MS | The incoming MOP will send the meter technical details to the incoming Supplier (DCC Stub) | The incoming MOP will send the meter technical details to the incoming Supplier (DCC Stub) | Incoming MOP (Stubbed) | D0149 D0150 | DCC Stub | N/A | N/A | N | N/A
|  | 43 | BPM-002 | 1024 | MS | END POINT FOR THIS LOGIC THREAD | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
| Issue MTDs | 44 | BPM-003 | 1015 (160) | DS | Issue MTD to Incoming DC | The incoming MOP will send the meter technical details to the incoming DC. Traditional Metering Services will send D0150 & D0149. | Incoming MOP (Stubbed) | D0149 D0150 | Incoming DC (Stubbed) | N/A | N/A | N | N/A
|  | 45 | BPM-003 | 1017 (165) | DS | Send D0149/D0150 | The Incoming MOP will send the MTDs to the incoming DC via a D0149/D0150. | Incoming MOP (Stubbed) | D0149 D0150 | Incoming DC (Stubbed) | N/A | N/A | N | N/A
| Receive MTDs | 46 | BPM-003 | 1019 (345) | DS | Receive MTDs from MOP | The incoming DC will receive the MTDs from the incoming MOP via the D0149/D0150. | Incoming MOP (Stubbed) | D0149 D0150 | Incoming DC (Stubbed) | N/A | N/A | N | N/A
|  | 47 | BPM-003 | 1020 (346) | DS | Manage MTD Discrepancies if required | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
| The Incoming Supplier obtains a CoS read & sends it to the Outgoing Supplier via a D0010 | 48 | BPM-003 | 1021 | DS | Obtain a CoS Read via a COR | The Incoming Supplier (DCC Stub) will obtain a CoS read and share this with the outgoing Supplier via a D0010. | DCC Stub | D0010 | SUPO | MHHS-RMigration-CoA(DS)-SUP-005 | N/A | Y | (1) Evidence that the D0010 is consumed by Outgoing Supplier. (2) Log screenshots in downstream systems.
|  | 49 | BPM-003 | 1022 | DS | Outgoing Supplier validates read | The outgoing Supplier will validate the read and re-share it with the incoming Supplier (DCC Stub) via a D0010. They will also share this with the outgoing DS via a D0010. Note: If the outgoing supplier cannot validate the read or does not receive a read, they will estimate a read to share with the DS / Incoming Supplier (DCC Stub) within 5 days of the CoS | SUPO | D0010 | DCC Stub SDSO | MHHS-RMigration-CoA(DS)-SUP-003 MHHS-RMigration-CoA(DS)-SUP-006 | N/A | Y | (1) Evidence that Outgoing Supplier produces a D0010 which is consumed by SDSO. (2) Log screenshots in downstream systems.
|  | 50 | BPM-003 | 1023 | DS | Outgoing supplier provides validated read to Incoming Supplier (DCC Stub) | The incoming Supplier (DCC Stub) will then share this validated read with the incoming DC via a D0010. | DCC Stub | D0010 | Incoming DC (Stubbed) | MHHS-RMigration-CoA(DS)-DC-003 MHHS-RMigration-CoA(DS)-SUP-007 | N/A | N | N/A
|  | 51 | BPM-003 | 1024 | DS | Incoming Supplier (DCC Stub) sends read to Incoming Data Collector and commences Legacy settlement activities | The incoming DC will then receive the read from the Incoming Supplier (DCC Stub) | DCC Stub | D0010 | Incoming DC (Stubbed) | MHHS-RMigration-CoA(DS)-DC-005 | N/A | N | N/A
|  | 52 | BPM-003 | 1025 | DS | END POINT FOR THIS LOGIC THREAD | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
| Outgoing Data Service receives read from Outgoing Supplier | 53 | BPM-003 | 1026 | DS | Receive read | The outgoing DS will then receive this read. | SDSO | D0010 | SUPO | N/A | N/A | Y | (1) Evidence that Outgoing Data Service produces a D0010 which is consumed by Outgoing Supplier. (2) Log screenshots in downstream systems.
| Outgoing Data Service receives read from Outgoing Supplier | 54 | BPM-003 | 1027 | DS | Receive Estimates / reads | The outgoing Supplier will then receive the estimates / reads. | SDSO | D0010 | SUPO | N/A | N/A | Y | (1) Evidence that Outgoing Data Service produces a D0010 which is consumed by Outgoing Supplier. (2) Log screenshots in downstream systems.
|  | 55 | BPM-003 | 1028 | DS | END POINT FOR THIS LOGIC THREAD | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
| Update Legacy Data Items | 56 |  |  | MS & DS | These steps have been added for e2e completeness and will be executed as end-of-day processing. REGS generates an end-of-day file to update legacy data items and sends it to EES. | These steps have been added for e2e completeness and will be executed as end-of-day processing. REGS generates an end-of-day file to update legacy data items and sends it to EES. | REGS | N/A | EES | N/A | N/A | Y | REGS provides evidence that the batch extract included data items for the Reverse Migrated MPAN.
|  | 57 |  |  | MS & DS | EES receives the end-of-day legacy data item update file from REGS and processes it | EES receives the end-of-day legacy data item update file from REGS and processes it | REGS | N/A | EES | N/A | N/A | Y | EES evidences that the sent data items have been updated appropriately

## SIT-M-RM-COS-DfltVal-TC02 Adv
Test Case Title | Key Journey Events | Test Step # | Business Process | BP Step | Service Type | Test Steps | Test Description | Interface Sender | Interface ID | Interface Recipient | Traceability Requirement | Message Input Event Code | Evidence Required? | Key Validation & Test Evidence
SIT-M-RM-COS-MS-DS-TC02 Adv | Advanced MPAN Setup | 1 | BP001 |  |  | Create an MPAN through new connection process, appoint services and install meter & Energise the MPAN | The CoS steps are the same as for New Connection. Please see MHHS-DEL1757 SITFTS-0050 New Connection v0.7 (Worksheet = SITFTS0050- Advanced) for detailed steps. | N/A | N/A | N/A | N/A | N/A | N | N/A
| Change of Supply - Start | 2 | BP001 | 60 | MS & DS | Initial Registration or Change of Supplier Required | SUPI sends Switch Request to CSS | DCC Stub | CSS01800 | CSS | N/A | N/A | Y | Evidence that DCC Stub generates a CSS01800; log screenshots in downstream systems.
|  | 3 | BP001 | 65 | MS & DS | MPAN EES Interaction (if required) | Suppliers may need to use the MPAN EES in order to establish criteria for taking Supply | DCC Stub | CSS01800 | CSS | N/A | N/A | Y | Evidence that DCC Stub generates a CSS01800; log screenshots in downstream systems.
| COS status at Pending Registration Sync | 4 | BP001 | 70 | MS & DS | COS status at Pending Registration Sync | CSS sends CSS2800 (pending Supplier request via CSS flow) to the REGS Registration Service receives pending Supplier request via CSS flow. | CSS | CSS02800 | REGS | MHHS-BR-RS-005 | N/A | Y | Evidence that CSS produces a CSS02800 which is consumed by REGS; log screenshots in downstream systems.
|  | 5 | BP001 |  |  | Check ISD for qualifications status of Supplier | Confirm that the check returns Incoming Supplier (DCC Stub) is not MHHS qualified to initiate Reverse Migration. | N/A | N/A | N/A | N/A | N/A | N | N/A
|  | 6 | BP001 | 185 | MS & DS | REGS populates the D0217 / D0260 with default data and sends it to Incoming Supplier (SUPI - DCC Stub) | REGS identifies NULL legacy data in the system but cannot find it own system (REGS). REGS populates the D0217 / D0260 with default data and sends it to Incoming Supplier (SUPI - DCC Stub) - Default MPID of "MHHS" - Default Measurement Class "F", Meter Timeswitch "800" | REGS | D0217 / D0260 | DCC Stub | MHHS-Migration-CoS-SUP-001 MHHS-Migration-CoS-SUP-002 | N/A | N | REGS populates the D0217 / D0260 with default data as mentioned.
| CSS sends COS Secured notification to SUPI | 7 | BP001 | 100 | MS & DS | CSS sends a COS "Secure Active" notification to SUPI (Legacy) (DCC Stub) | Suppliers will receive notification from CSS that COS has a "Secure Active" status | CSS | CSS02370 | DCC Stub | MHHS-BR-SU-003 MHHS-BR-SU-048 | N/A | Y | Evidence that CSS produces a CSS02370. Log screenshots in downstream systems.
| CSS sends COS Secured notification to REGS | 8 | BP001 | 130 | MS & DS | CSS sends COS Active/COS "Secure Active" notification to REGS | The Registration Service will receive a COS "Secure Active" notification from CSS. | CSS | CSS02860 | REGS | MHHS-BR-RS-007 MHHS-BR-RS-008 MHHS-BR-RS-094 MHHS-BR-RS-096 | N/A | Y | Evidence that CSS produces a CSS02860 which is consumed by REGS; log screenshots in downstream systems.
| New Supplier Receives Secured Active Notification | 9 | BP001 | 195 | MS & DS | Reverse Migration Change of Service BPM-002 / BPM-003 | Once the new Supplier receives the 'Secure Active' notification from the CSS, The New Supplier will then reverse migrate the MPAN and follow the Reverse migration change of Agent processes (note: Reverse migration can only occur via a CoS, however the CoA process diagrams are used to demonstrate the process of changing to legacy agents). | N/A | N/A | N/A | N/A | N/A | N | N/A
|  | 10 | BP001 | 200 | MS & DS | Confirm Reverse Migration | The Registration Service will send MHHS-IF-003 to inform parties that a Reverse Migration is confirmed | REGS | IF-003 | SUPO, MDS, EES, LDSO | N/A | [ReverseMigNotification] | Y | (1) Evidence that REGS produces an IF-003 which is consumed by the Outgoing Supplier, MDS, EES and LDSO. (2) Log screenshots in downstream systems.
|  | 11 | BP001 | 205 | MS & DS | Receive and Publish Reverse Migration notification | The DIP will receive MHHS-IF003 and send PUB-003 to the Outgoing Supplier, MDS, EES and LDSO | DIP | PUB-003 | SUPO, MDS, EES, LDSO | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the Outgoing Supplier, MDS, EES and LDSO. (2) Log screenshots in downstream systems.
|  | 12 | BP001 | 210 | MS & DS | Receive Reverse Migration notification | MDS will receive PUB-003 and update it's records that the MPAN is in legacy settlement | DIP | PUB-003 | MDS | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the MDS (2) Log screenshots in downstream systems.
|  | 13 | BP001 | 215 | MS & DS | Receive Reverse Migration notification | LDSO will receive PUB-003 and update its records that the MPAN is in legacy DUoS Billing | DIP | PUB-003 | LDSO | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the LDSO (2) Log screenshots in downstream systems.
|  | 14 | BP001 | 220 | MS & DS | Receive Reverse Migration notification | EES will receive PUB-003 and update its records that the MPAN has reverse migrated Note: The EES will need to set a status that the MPAN has reverted to Legacy arrangements. Parties should be able to enquire via the portal and the API and see this status. | DIP | PUB-003 | EES | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the EES (2) Log screenshots in downstream systems.
|  | 15 | BP001 | 225 | MS & DS | Receive Reverse Migration notification | Outgoing Supplier will receive PUB-003 and update its records that the MPAN has reverse migrated | DIP | PUB-003 | SUPO | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the SUPO (2) Log screenshots in downstream systems.
| Setup Appointments | 16 | BPM-002 | 1001 | MS | Appoint Legacy Agents - Send Notification of Meter Operator or Data Collector Appointment and Terms | The Supplier (DCC Stub) will send an appointment notification to the Incoming MOP via a D0155. A specific value is used in the 'Contract Reference' data field to indicate that a Reverse Migration is occurring. | DCC Stub | D0155 | Incoming MOP (Stubbed) | MHHS-RMigration-CoA(MS)-SUP-001 | N/A | N | N/A
|  | 17 | BPM-003 | 1001 | DS | Appoint Legacy Agents | The Supplier (DCC Stub) will send an appointment notification to the new DC via a D0155. Will use a specific value in the 'Contract Reference' data field to indicate a Reverse Migration is occurring. | DCC Stub | D0155 | Incoming DC (Stubbed) | MHHS-RMigration-CoA(DS)-SUP-001 | N/A | N | N/A
| Accept Appointments | 18 | BPM-002 | 1002 | MS | Accept Appointment - Agreement of Contractual Terms | The Incoming MOP will accept the appointment and share a D0011 with the Incoming Supplier (DCC Stub). | Incoming MOP (Stubbed) | D0011 | DCC Stub | MHHS-RMigration-CoA(MS)-MOP-002 | N/A | N | N/A
|  | 19 | BPM-003 | 1002 | DS | Accept Appointment | The incoming DC will accept the appointment and share a D0011 with the incoming Supplier (DCC Stub). | Incoming DC (Stubbed) | D0011 | DCC Stub | MHHS-RMigration-CoA(DS)-DC-004 | N/A | N | N/A
| Update Agent Appointment | 20 | BPM-002 | 1003 | MS | Update agent appointment and settlement details | The Incoming Supplier (DCC Stub) will update the agent appointment and settlement details via a D0205 to the Registration Service. | DCC Stub | D0205 | REGS | MHHS-RMigration-CoA(MS)-SUP-002 | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
|  | 21 | BPM-002 | 1004 | MS | Update agent appointment and settlement details | The Registration Service will use this D0205 to update the agent appointment and settlement details. | DCC Stub | D0205 | REGS | MHHS-RMigration-CoA(MS)-RS-004 | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
|  | 22 | BPM-003 | 1003 | DS | Update Agent appointment and settlement details | The incoming Supplier (DCC Stub) will update the Agent appointment and settlement details via a D0205 to the Registration Service. | DCC Stub | D0205 | REGS | MHHS-RMigration-CoA(DS)-SUP-002 | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
|  | 23 | BPM-003 | 1004 | DS | Update Agent appointment and settlement detailsUpdate agent appointment and settlement details | The Registration Service will use this D0205 to update the Agent appointment and settlement details. | DCC Stub | D0205 | REGS | MHHS-RMigration-CoA(DS)-RS-003 MHHS-RMigration-CoA(DS)-RS-004 | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
|  | 24 | BPM-003 |  | DS | REGS sends D0209 with Incoming DA | REGS sends D0209 with Incoming DA | REGS | D0209 | Incoming DA | N/A | N/A | Y | Evidence that the REGS sends a D0209 to the Incoming DA and it gets consumed.
| Issue Deappointment & Reverse Migration Process | 25 | BPM-002 | 1008 | MS | Issue MS De-Appointment and Reverse Migration De-Appointment Notification to Outgoing MS | An IF-003 will be sent to the DIP which informs that the MS is being de-appointed. | REGS | IF-003 | DIP | MHHS-RMigration-CoA(MS)-RS-001 MHHS-RMigration-CoA(MS)-RS-005 MHHS-RMigration-CoA(MS)-SUP-004 MHHS-RMigration-CoA(MS)-MOP-003 MHHS-RMigration-CoA(MS)-MS-003 MHHS-RMigration-CoA(MS)-RS-007 | [MSDeAppRM] | N | http 201 response from DIP
|  | 26 | BPM-002 | 1009 | MS | Publish MS Reverse Migration and Reverse Migration De-Appointment Notification | The DIP will publish the PUB-003 to the outgoing MS, the outgoing Supplier, and the EES | DIP | PUB-003 | AMSO SUPO EES | MHHS-RMigration-CoA(MS)-ECS-001 | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Metering Service, Outgoing Supplier, and EES. (2) Log screenshots in downstream systems.
|  | 27 | BPM-003 | 1008 | DS | Issue DS Reverse Migration De-Appointment Notification | An IF-003 will be sent to the DIP which informs that the DS is being de-appointed. | REGS | IF-003 | DIP | MHHS-RMigration-CoA(DS)-RS-005 MHHS-RMigration-CoA(DS)-RS-007 | [DSDeAppRM] | N | http 201 response from DIP
|  | 28 | BPM-003 | 1009 | DS | Publish DS Reverse Migration De-Appointment Notification | The DIP will publish the PUB-003 to the outgoing DS, the outgoing Supplier, the LDSO and the EES. | DIP | PUB-003 | ADSO SUPO LDSO EES | MHHS-RMigration-CoA(DS)-ECS-001 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the Outgoing Data Service, SUPO, LDSO and EES. (2) Log screenshots in downstream systems.
| EES - Close out MHHS Arrangement | 29 | BPM-002 | 1010 | MS | Process MS Reverse Migration and Reverse Migration De-Appointment Notification | The EES will process the de-appointment and reverse migration notification. | DIP | PUB-003 | EES | MHHS-RMigration-CoA(MS)-EES-001 MHHS-RMigration-CoA(MS)-EES-002 | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by EES. (2) Log screenshots in downstream systems.
|  | 30 | BPM-003 | 1010 | DS | Process DS Reverse Migration De-Appointment Notification | The EES will process the Reverse Migration De-Appointment Notification. | DIP | PUB-003 | EES | MHHS-RMigration-CoA(DS)-EES-001 MHHS-RMigration-CoA(DS)-EES-002 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by EES. (2) Log screenshots in downstream systems.
| MDS - Close out MHHS Arrangement | 31 | BPM-003 | 1011 | DS | Process DS Reverse Migration De-Appointment Notification | The MDS will process the Reverse Migration De-Appointment Notification. | DIP | PUB-003 | MDS | MHHS-RMigration-CoA(DS)-ECS-001 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by MDS. (2) Log screenshots in downstream systems.
| Outgoing Supplier Processes Reverse Migration & De-Appointment Notification | 32 | BPM-002 | 1012 | MS | Process MS Reverse Migration and De-Appointment Notification | The outgoing Supplier will process the Reverse Migration De-Appointment Notification. | DIP | PUB-003 | SUPO | MHHS-RMigration-CoA(MS)-SUP-003 | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by SUPO. (2) Log screenshots in downstream systems.
|  | 33 | BPM-003 | 1012 | DS | Process DS Reverse Migration De-Appointment Notification | The outgoing Supplier will process the Reverse Migration De-Appointment Notification. | DIP | PUB-003 | SUPO | MHHS-RMigration-CoA(DS)-SUP-004 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by SUPO. (2) Log screenshots in downstream systems.
| Outgoing Metering & Data Services Process Reverse Migration & De-Appointment Notification | 34 | BPM-002 | 1013 | MS | Process MS Reverse Migration and De-Appointment Notification | The outgoing MS will process the Reverse Migration De-Appointment Notification. | DIP | PUB-003 | AMSO | N/A | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Metering Service. (2) Log screenshots in downstream systems.
|  | 35 | BPM-003 | 1013 | DS | Process DS Reverse Migration De-Appointment Notification | The outgoing DS will process the Reverse Migration De-Appointment Notification. | DIP | PUB-003 | ADSO | N/A | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Data Service. (2) Log screenshots in downstream systems.
| Issue MTDs | 36 | BPM-002 | 1014 (160) | MS | Issue MTD to Prospective/Incoming MOP | The existing Metering Service will receive notification from the Registrations service of who the prospective MOP is. Metering Service will send the meter technical details to the prospective Metering Service. - Advanced Metering Services will send a D0268. - Metering Services must issue all MTD's for linked export/related MPANS | SMSO | D0268 | Incoming MOP (Stubbed) | MHHS-RMigration-CoA(MS)-MS-002 | N/A | Y | (1) Evidence that SMSO produces a D0268 (2) Log screenshots in downstream systems.
|  | 37 | BPM-002 | 1016 (170) | MS | Send D268 & D0383 / D0384 for Advanced Meters (if currently a CT meter) | Advanced Metering flows that will need to be sent from the existing Metering Service to the prospective Metering Service Note: the commissioning flows should be sent in line with current REC SLAs and are shown in this diagram for completeness, but may be sent as a separate activity. | AMSO | D0268 D0383/D0384 | Incoming MOP (Stubbed) | N/A | N/A | Y | (1) Evidence that Existing Metering Service produces a D0268, D0383/D0384 (2) Log screenshots in downstream systems.
| Receive MTDs | 38 | BPM-002 | 1019 (175) | MS | Receive MTDs | The incoming MOP will receive Meter technical details from the existing Metering Service via data flows. | AMSO | D0268 D0383 D0384 | Incoming MOP (Stubbed) | N/A | N/A | Y | (1) Evidence that Existing Metering Service produces a D0268, D0383 and D0384
|  | 39 | BPM-002 | 1020 (180) | MS | Issue MTDs via DTN (Trad & Advanced Only) | The Incoming MOP will issue the meter technical details to Incoming Supplier (DCC Stub), Data Service and LDSO via the DTN | Incoming MOP (Stubbed) | D0268 | DCC Stub Incoming DC (Stubbed) | MHHS-RMigration-CoA(MS)-MOP-001 | N/A | N | N/A
| Incoming DC receives incoming MTDS from Incoming MOP via DTN | 40 | BPM-002 | 1021 (190) | MS | Incoming DC receives incoming MTDS from Incoming MOP via DTN | The incoming DC will receive the meter technical details from the incoming MOP via the DTN | Incoming MOP (Stubbed) | D0268 | Incoming DC (Stubbed) | N/A | N/A | N | N/A
|  | 41 | BPM-002 | 1022 | MS | END POINT FOR THIS LOGIC THREAD | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
| The Incoming MOP will send the MTDs to the Incoming Supplier | 42 | BPM-002 | 1023 | MS | The incoming MOP will send the meter technical details to the incoming Supplier (DCC Stub) | The incoming MOP will send the meter technical details to the incoming Supplier (DCC Stub) | Incoming MOP (Stubbed) | D0268 D0383 D0384 | SUPI DCC Stub | N/A | N/A | N | N/A
|  | 43 | BPM-002 | 1024 | MS | END POINT FOR THIS LOGIC THREAD | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
| Issue MTDs | 44 | BPM-003 | 1015 (160) | DS | Issue MTD to Incoming DC | The incoming MOP will send the meter technical details to the incoming DC. Advanced Metering Services will send a D0268 | Incoming MOP (Stubbed) | D0268 | Incoming DC (Stubbed) | N/A | N/A | N | N/A
| Receive MTDs | 45 | BPM-003 | 1019 (345) | DS | Receive MTDs from MOP | The incoming DC will receive the MTDs from the incoming MOP via the D0149/D0150. | Incoming MOP (Stubbed) | D0268 | Incoming DC (Stubbed) | N/A | N/A | N | N/A
|  | 46 | BPM-003 | 1020 (346) | DS | Manage MTD Discrepancies if required | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
|  | 47 | BPM-003 | 1029 | DS | Begin Legacy HH or NHH data collection processes | At this stage, the DC will begin the relevant data collection processes. Note: They will not receive historical read data however they will operate legacy collection processes without any historical data. | N/A | N/A | N/A | MHHS-RMigration-CoA(DS)-DC-002 | N/A | N | N/A
|  | 48 | BPM-003 | 1042 | DS | END POINT FOR THIS LOGIC THREAD | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
| Update Legacy Data Items | 49 |  |  | MS & DS | These steps have been added for e2e completeness and will be executed as end-of-day processing. REGS generates an end-of-day file to update legacy data items and sends it to EES. | These steps have been added for e2e completeness and will be executed as end-of-day processing. REGS generates an end-of-day file to update legacy data items and sends it to EES. | REGS | N/A | EES | N/A | N/A | Y | REGS provides evidence that the batch extract included data items for the Reverse Migrated MPAN.
|  | 50 |  |  | MS & DS | EES receives the end-of-day legacy data item update file from REGS and processes it | EES receives the end-of-day legacy data item update file from REGS and processes it | REGS | N/A | EES | N/A | N/A | Y | EES evidences that the sent data items have been updated appropriately

## SIT-M-RM-COS-DfltVal-TC03 Smart
Test Case Title | Key Journey Events | Test Step # | Business Process | BP Step | Service Type | Test Steps | Test Description | Interface Sender | Interface ID | Interface Recipient | Traceability Requirement | Message Input Event Code | Evidence Required? | Key Validation & Test Evidence
SIT-M-RM-COS-DfltVal-TC03 - Smart | Smart MPAN Setup | 1 | BP001 |  |  | Create an MPAN through new connection process, appoint services and install meter & Energise the MPAN | The CoS steps are the same as for New Connection. Please see MHHS-DEL1757 SITFTS-0050 New Connection v0.7 (Worksheet = SITFTS0050- Smart) for detailed steps. | N/A | N/A | N/A | N/A | N/A | N | N/A
| Change of Supply - Start | 2 | BP001 | 60 | MS & DS | Initial Registration or Change of Supplier Required | Incoming Supplier sends a Switch Request to the CSS In the absence of the Incoming Supplier, we're expecting the use of a DCC Stub to generate the CSS01800. | DCC Stub | CSS01800 | CSS | N/A | N/A | Y | Evidence that DCC Stub generates a CSS01800; log screenshots in downstream systems.
|  | 3 | BP001 | 65 | MS & DS | MPAN EES Interaction (if required) | Suppliers may need to use the MPAN EES in order to establish criteria for taking Supply. In the absence of the Incoming Supplier, we're expecting the use of a DCC Stub to generate the CSS01800. | DCC Stub | CSS01800 | CSS | N/A | N/A | Y | Evidence that DCC Stub generates a CSS01800; log screenshots in downstream systems.
| COS status at Pending Registration Sync | 4 | BP001 | 70 | MS & DS | COS status at Pending Registration Sync | CSS sends CSS2800 (pending Supplier request via CSS flow) to the REGS Registration Service receives pending Supplier request via CSS flow. | CSS | CSS02800 | REGS | MHHS-BR-RS-005 | N/A | Y | Evidence that CSS produces a CSS02800 which is consumed by REGS; log screenshots in downstream systems.
|  | 5 | BP001 |  |  | Check ISD for qualifications status of Supplier | Confirm that the check returns Incoming Supplier (DCC Stub) is not MHHS qualified to initiate Reverse Migration. | N/A | N/A | N/A | N/A | N/A | N | N/A
|  | 6 | BP001 | 185 | MS & DS | REGS populates the D0217 / D0260 with default data and sends it to Incoming Supplier (SUPI - DCC Stub) | REGS identifies NULL legacy data in the system but cannot find it own system (REGS). REGS populates the D0217 / D0260 with default data and sends it to Incoming Supplier (SUPI - DCC Stub) - Default MPID of "MHHS" - Default Measurement Class "F", Meter Timeswitch "800" | REGS | D0217 / D0260 | DCC Stub | MHHS-Migration-CoS-SUP-001 MHHS-Migration-CoS-SUP-002 | N/A | N | REGS populates the D0217 / D0260 with default data as mentioned.
| BP003A CSS/DCC Update Steps | 7 | BP003A |  | MS & DS | CSS receives defaulted Legacy appointments | CSS0200 confirmationRequred:false should be sent to CSS to update CSS of the default supplierArrnageAppointments (SAA) | REGS | CSS0200 | CSS |  | confirmationRequired:false | Y | Evidence that REGS produces the CSS0200 correctly
| Update Agent Appointment | 8 | BP002 | 1003 | MS & DS | Update agent appointment and settlement details | The Incoming Supplier (DCC Stub) will update the agent appointment and settlement details via a D0205 to the Registration Service. | DCC Stub | D0205 | REGS | MHHS-RMigration-CoA(MS)-SUP-002 MHHS-RMigration-CoA(MS)-RS-004 MHHS-RMigration-CoA(DS)-SUP-002 MHHS-RMigration-CoA(DS)-RS-003 MHHS-RMigration-CoA(DS)-RS-004 | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
| BP003A CSS/DCC Update Steps | 9 | BP003A |  | MS & DS | CSS receives CSS0200 to update Legacy appointments | CSS0200 confirmationRequred:false should be sent to CSS to update CSS of the D0205 supplierArrnageAppointments (SAA) | REGS | CSS0200 | CSS |  | confirmationRequired:false | Y | Evidence that REGS produces the CSS0200 correctly
| CSS sends COS Secured notification to SUPI | 10 | BP001 | 100 | MS & DS | CSS sends COS Active/COS "Secure Active" notification to SUPI (DCC Stub) | Incoming Suppliers (DCC Stub) will receive notification from CSS that COS has a "Secure Active" status | CSS | CSS02370 | DCC Stub | MHHS-BR-SU-003 MHHS-BR-SU-048 | N/A | Y | Evidence that CSS produces a CSS02370; Log screenshots in downstream systems.
| CSS sends COS Secured notification to REGS | 11 | BP001 | 130 | MS & DS | CSS sends COS Active/COS "Secure Active" notification to REGS | The Registration Service will receive a COS "Secure Active" notification from CSS. | CSS | CSS02860 | REGS | MHHS-BR-RS-007 MHHS-BR-RS-008 MHHS-BR-RS-094 MHHS-BR-RS-096 | N/A | Y | Evidence that CSS produces a CSS02860 which is consumed by REGS; log screenshots in downstream systems.
| New Supplier Receives Secured Active Notification | 12 | BP001 | 195 | MS & DS | Reverse Migration Change of Service BPM-002 / BPM-003 | Once the new Supplier receives the 'Secure Active' notification from the CSS, The New Supplier will then reverse migrate the MPAN and follow the Reverse migration change of Agent processes (note: Reverse migration can only occur via a CoS, however the CoA process diagrams are used to demonstrate the process of changing to legacy agents). | N/A | N/A | N/A | N/A | N/A | N | N/A
|  | 13 | BP001 | 200 | MS & DS | Confirm Reverse Migration | The Registration Service will send MHHS-IF-003 to inform parties that a Reverse Migration is confirmed | REGS | IF-003 | SUPO, MDS, EES, LDSO | N/A | [ReverseMigNotification] | Y | (1) Evidence that REGS produces an IF-003 which is consumed by the Outgoing Supplier, MDS, EES and LDSO. (2) Log screenshots in downstream systems.
|  | 14 | BP001 | 205 | MS & DS | Receive and Publish Reverse Migration notification | The DIP will receive MHHS-IF003 and send PUB-003 to the Outgoing Supplier, MDS, EES and LDSO | DIP | PUB-003 | SUPO, MDS, EES, LDSO | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the Outgoing Supplier, MDS, EES and LDSO. (2) Log screenshots in downstream systems.
|  | 15 | BP001 | 210 | MS & DS | Receive Reverse Migration notification | MDS will receive PUB-003 and update it's records that the MPAN is in legacy settlement | DIP | PUB-003 | MDS | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the MDS (2) Log screenshots in downstream systems.
|  | 16 | BP001 | 215 | MS & DS | Receive Reverse Migration notification | LDSO will receive PUB-003 and update its records that the MPAN is in legacy DUoS Billing | DIP | PUB-003 | LDSO | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the LDSO (2) Log screenshots in downstream systems.
|  | 17 | BP001 | 220 | MS & DS | Receive Reverse Migration notification | EES will receive PUB-003 and update its records that the MPAN has reverse migrated Note: The EES will need to set a status that the MPAN has reverted to Legacy arrangements. Parties should be able to enquire via the portal and the API and see this status. | DIP | PUB-003 | EES | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the EES (2) Log screenshots in downstream systems.
|  | 18 | BP001 | 225 | MS & DS | Receive Reverse Migration notification | Outgoing Supplier will receive PUB-003 and update its records that the MPAN has reverse migrated | DIP | PUB-003 | SUPO | N/A | [ReverseMigNotification] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by the SUPO (2) Log screenshots in downstream systems.
| Setup Appointments | 19 | BPM-002 | 1001 | MS | Appoint Legacy Agents - Send Notification of Meter Operator or Data Collector Appointment and Terms | The Incoming Supplier (DCC Stub) will send an appointment notification to the Incoming MOP via a D0155. A specific value is used in the 'Contract Reference' data field to indicate that a Reverse Migration is occurring. | DCC Stub | D0155 | Incoming MOP (Stubbed) | MHHS-RMigration-CoA(MS)-SUP-001 | N/A | N | N/A
|  | 20 | BPM-003 | 1001 | DS | Appoint Legacy Agents | The Incoming Supplier (DCC Stub) will send an appointment notification to the new DC via a D0155. Will use a specific value in the 'Contract Reference' data field to indicate a Reverse Migration is occurring. | DCC Stub | D0155 | Incoming DC (Stubbed) | MHHS-RMigration-CoA(DS)-SUP-001 | N/A | N | N/A
| Accept Appointments | 21 | BPM-002 | 1002 | MS | Accept Appointment - Agreement of Contractual Terms | The Incoming MOP will accept the appointment and share a D0011 with the Incoming Supplier (DCC Stub) | Incoming MOP (Stubbed) | D0011 | DCC Stub | MHHS-RMigration-CoA(MS)-MOP-002 | N/A | N | N/A
|  | 22 | BPM-003 | 1002 | DS | Accept Appointment | The incoming DC will accept the appointment and share a D0011 with the incoming Supplier (DCC Stub) | Incoming DC (Stubbed) | D0011 | DCC Stub | MHHS-RMigration-CoA(DS)-DC-004 | N/A | N | N/A
| Update Agent Appointment |  | BPM-002 | 1003 | MS | Update agent appointment and settlement details | The Incoming Supplier (DCC Stub) will update the agent appointment and settlement details via a D0205 to the Registration Service. | SUPI DCC Stub (Stubbed) | D0205 | REGS | MHHS-RMigration-CoA(MS)-SUP-002 | N/A | Y | (1) Evidence that the D0205 generated by the stub is consumed by the REGS. (2) Log screenshots in downstream systems.
|  |  | BPM-002 | 1004 | MS | Update agent appointment and settlement details | The Registration Service will use this D0205 to update the agent appointment and settlement details. | DCC Stub | D0205 | REGS |  | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
|  |  | BPM-003 | 1003 | DS | Update Agent appointment and settlement details | The incoming Supplier (DCC Stub) will update the Agent appointment and settlement details via a D0205 to the Registration Service. | DCC Stub | D0205 | REGS |  | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
|  |  | BPM-003 | 1004 | DS | Update Agent appointment and settlement detailsUpdate agent appointment and settlement details | The Registration Service will use this D0205 to update the Agent appointment and settlement details. | DCC Stub | D0205 | REGS |  | N/A | Y | (1) Evidence that the D0205 is consumed by Registration Service. (2) Log screenshots in downstream systems.
|  | 23 | BPM-003 |  | DS | REGS sends D0209 with Incoming DA | REGS sends D0209 with Incoming DA | REGS | D0209 | Incoming DA | N/A | N/A | Y | Evidence that the REGS sends a D0209 to the Incoming DA and it gets consumed.
| BP003A CSS/DCC Update Steps | 27 | BP003A |  | MS & DS | BP003A - CSS/DCC Update Steps | The Registration Service may need to update CSS or DCC with the MDR details. | N/A | N/A | N/A | N/A | N/A | N | N/A
|  | 28 | BP003A |  | MS & DS | REGS sends a MDR de-appointment |  | REGS | CSS0200 | CSS | N/A | N/A | N | N/A
|  | 29 | BP003A |  | MS & DS | REGS sends a MS change request |  | REGS | CSS0200 | CSS | N/A | N/A | N | N/A
|  | 30 | BP003A |  | MS & DS | CSS Updates internal records | CSS will update their internal records | N/A | N/A | N/A | CSS | N/A | N | N/A
|  | 31 | BP003A |  | MS & DS | CSS Updates DCC | CSS will update the DCC with the amended Service provider details | CSS | N/A | DCC | CSS | N/A | N | N/A
|  | 32 | BP003A |  | MS & DS | DCC Receives Update from CSS | DCC will receive from the CSS with the amended Service provider details | CSS | N/A | DCC | DCC | [DCC-MDROutcome] | N | N/A
|  | 33 | BP003A |  | MS & DS | DCC Updates MDR Access Control Register | DCC will update their systems to reflect the access control register | DCC | N/A | CSS | DCC | N/A | N | N/A
|  | 34 | BP003A |  | MS & DS | Forward DCC Response to Registrations | DCC sends CSS0200 to CSS to confirm update and CSS will update the Registration Service | CSS | CSS0200 | REGS | CSS | N/A | N | N/A
|  | 35 | BP003A |  | MS & DS | CSS Response | CSS will issue DCC response to the Registration Service | CSS | N/A | REGS | MHHS-BR-RS-079 | N/A | N | N/A
| Issue Deappointment & Reverse Migration Process | 24 | BPM-002 | 1008 | MS | Issue MS Reverse Migration De-Appointment Notification to Outgoing MS | An IF-003 will be sent to the DIP which informs that the MS is being de-appointed. | REGS | IF-003 | DIP | MHHS-RMigration-CoA(MS)-RS-001 MHHS-RMigration-CoA(MS)-RS-005 MHHS-RMigration-CoA(MS)-SUP-004 MHHS-RMigration-CoA(MS)-MOP-003 MHHS-RMigration-CoA(MS)-MS-003 MHHS-RMigration-CoA(MS)-RS-007 | [MSDeAppRM] | N | http 201 response from DIP
|  | 25 | BPM-002 | 1009 | MS | Publish MS Reverse Migration De-Appointment Notification | The DIP will publish the PUB-003 to the outgoing MS, the outgoing Supplier and the EES | DIP | PUB-003 | SMSO SUPO EES | MHHS-RMigration-CoA(MS)-ECS-001 | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Metering Service, Outgoing Supplier, and EES. (2) Log screenshots in downstream systems.
|  | 26 | BPM-003 | 1008 | DS | Issue DS Reverse Migration De-Appointment Notification | An IF-003 will be sent to the DIP which informs that the DS is being de-appointed. | REGS | IF-003 | DIP | MHHS-RMigration-CoA(DS)-RS-005 MHHS-RMigration-CoA(DS)-RS-007 | [DSDeAppRM] | N | http 201 response from DIP
|  | 27 | BPM-003 | 1009 | DS | Publish DS Reverse Migration De-Appointment Notification | The DIP will publish the PUB-003 to the outgoing DS, the outgoing Supplier, the MDS and the EES. | DIP | PUB-003 | SDSO SUPO EES MDS | MHHS-RMigration-CoA(DS)-ECS-001 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Data Service, SUPO, MDS and EES. (2) Log screenshots in downstream systems.
| EES - Close out MHHS Arrangement | 28 | BPM-002 | 1010 | MS | Process MS Reverse Migration De-Appointment Notification | The EES will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | EES | MHHS-RMigration-CoA(MS)-EES-001 MHHS-RMigration-CoA(MS)-EES-002 | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by EES. (2) Log screenshots in downstream systems.
|  | 29 | BPM-003 | 1010 | DS | Process DS Reverse Migration De-Appointment Notification | The EES will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | EES | MHHS-RMigration-CoA(DS)-EES-001 MHHS-RMigration-CoA(DS)-EES-002 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by EES. (2) Log screenshots in downstream systems.
| MDS - Close out MHHS Arrangement | 30 | BPM-003 | 1011 | DS | Process Reverse Migration De-Appointment Notification | The MDS will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | MDS | MHHS-RMigration-CoA(DS)-ECS-001 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by MDS. (2) Log screenshots in downstream systems.
| Outgoing Supplier Processes Reverse Migration & De-Appointment Notification | 31 | BPM-002 | 1012 | MS | Process MS Reverse Migration De-Appointment Notification | The outgoing Supplier will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | SUPO | MHHS-RMigration-CoA(MS)-SUP-003 | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by SUPO. (2) Log screenshots in downstream systems.
|  | 32 | BPM-003 | 1012 | DS | Process DS Reverse Migration De-Appointment Notification | The outgoing Supplier will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | SUPO | MHHS-RMigration-CoA(DS)-SUP-004 | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by SUPO. (2) Log screenshots in downstream systems.
|  | 33 | BPM-003 | 1039 | DS | Attempt to Gather Smart Reads | The outgoing Supplier will attempt to gather Smart Reads | N/A | N/A | N/A | N/A | N/A | N | N/A
| Outgoing Metering & Data Services Process Reverse Migration & De-Appointment Notification | 34 | BPM-002 | 1013 | MS | Process MS Reverse Migration De-Appointment Notification | The outgoing MS will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | SMSO | N/A | [MSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Metering Service. (2) Log screenshots in downstream systems.
|  | 35 | BPM-003 | 1013 | DS | Process DS Reverse Migration De-Appointment Notification | The outgoing DS will process the Reverse Migration De-Appointment Notification | DIP | PUB-003 | SDSO | N/A | [DSDeAppRM] | Y | (1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Data Service. (2) Log screenshots in downstream systems.
| Receive & issue MTDs | 36 | BPM-002 | 1014 (160) | MS | Receive MTDs and determine Meter Type | Receive MTDs and determine Meter Type | N/A | N/A | N/A | MHHS-RMigration-CoA(MS)-MS-002 | N/A | Y | (1) Evidence that SMSO produces a D0149/D0150 which is consumed by New MOP. (2) Log screenshots in downstream systems.
|  | 37 | BPM-002 | 1017 | MS | Send "skeleton" D0150 for Smart Meters Non Half-hourly Meter Technical Details | A 'Skeleton' D0150 will be sent by the outgoing MS to the incoming MOP and the incoming Supplier (DCC Stub) for Smart Meters. In this case 'Skeleton' D0150 means that only the mandatory fields need to be populated. | SMSO | Skeleton D0150 | Incoming MOP DCC Stub | MHHS-RMigration-CoA(MS)-MS-001 | N/A | Y | (1) Evidence that Existing Metering Service produces a skeleton D0150 (2) Log screenshots in downstream systems.
|  | 38 | BPM-002 | 1018 | MS | Receive D0150 and Send Smart meter configuration details | The incoming Supplier (DCC Stub) will receive the 'Skeleton' D0150 from the outgoing MS and share the Smart Meter Configuration details with the incoming MOP via a D0367 | DCC Stub | D0367 | Incoming MOP (Stubbed) | N/A | N/A | N | N/A
|  | 39 | BPM-002 | 1019 (175) | MS | Receive MTDs | The incoming MOP will receive Meter technical details from the existing Metering Service via data flows. | SMSO | Skeleton D0150 | Incoming MOP (Stubbed) | N/A | N/A | Y | (1) Evidence that Existing Metering Service produces a "skeleton" D0150 which is consumed by Incoming MOP. (2) Log screenshots in downstream systems.
| Receive & issue MTDs | 40 | BPM-003 | 1015 (160) | DS | Issue MTD to Incoming DC | The incoming MOP will send the meter technical details to the incoming DC. Smart Metering Services will send D0150 & D0149. | N/A | N/A | N/A | N/A | N/A | N | N/A
|  | 41 | BPM-003 | 1016 (161) | DS | Receive MTDs and manage any discrepancies | The incoming DC to receive MTDs from the incoming MOP via a D0149/D0150 and manage any discrepancies if required. | Incoming MOP (Stubbed) | D0149/D0150 | Incoming DC (Stubbed) | N/A | N/A | N | N/A
| Gather Smart Reads | 42 | BPM-003 | 1030 | DS | Attempt to Gather Smart Reads | The outgoing DS will attempt to gather Smart Reads | N/A | N/A | N/A | N/A | N/A | N | N/A
|  | 43 | BPM-003 | 1031 | DS | Issue Daily Read Log Reading | The outgoing DS will send the daily read log reading via an IF-041 to the DIP | SDSO | IF-041 | DIP | N/A | [ReadingCOS] | N | http 201 response from DIP
|  | 44 | BPM-003 | 1032 | DS | Issue PUB-041 | The DIP will share the read log with the outgoing Supplier via a PUB-041 | DIP | PUB-041 | SUPO | N/A | [ReadingCOS] | Y | (1) Evidence that DIP produces a PUB-041 which is consumed by Outgoing Supplier. (2) Log screenshots in downstream systems.
| LDSO receives Register Reads | 45 | BPM-003 | 1043 | DS | Receive Register Reads | The LDSO will receive Register Reads via a PUB-41 | DIP | PUB-041 | LDSO | N/A | [ReadingCOS] | Y | (1) Evidence that DIP produces a PUB-041 which is consumed by LDSO. (2) Log screenshots in downstream systems.
| Outgoing Supplier receives Register Reads | 46 | BPM-003 | 1033 | DS | Receive Register Reads | The outgoing Supplier will then receive the Register reads from the DIP | DIP | PUB-041 | SUPO | N/A | [ReadingCOS] | Y | (1) Evidence that DIP produces a PUB-041 which is consumed by Outgoing Supplier. (2) Log screenshots in downstream systems.
|  | 47 | BPM-003 | 1034 | DS | Compare and validate actuals | The outgoing Supplier will then validate the actual reads | N/A | N/A | N/A | N/A | N/A | N | N/A
|  | 48 | BPM-003 | 1035 | DS | Issue cumulative read to new Supplier | The outgoing Supplier will then issue the cumulative read to the incoming Supplier (DCC Stub) via a D0010 | SUPO | D0010 | DCC Stub | MHHS-RMigration-CoA(DS)-SUP-008 | N/A | Y | (1) Evidence that Outgoing Supplier produces a D0010 (2) Log screenshots in downstream systems.
|  | 49 | BPM-003 | 1036 | DS | Receive Cumulative Readings | The incoming Supplier (DCC Stub) will then receive the cumulative readings and share them with the incoming DC via a D0010 | DCC Stub | D0010 | Incoming DC (Stubbed) | MHHS-RMigration-CoA(DS)-DC-003 MHHS-RMigration-CoA(DS)-SUP-009 | N/A | N | N/A
|  | 50 | BPM-003 | 1037 | DS | Receive Time of use Register Reads | The incoming DC will then receive the time of use register read from the incoming Supplier (DCC Stub) | DCC Stub | D0010 | Incoming DC (Stubbed) | N/A | N/A | N | N/A
|  | 51 | BPM-003 | 1040 | DS | END POINT FOR THIS LOGIC THREAD | N/A | N/A | N/A | N/A | N/A | N/A | N | N/A
| Attempt to Gather Smart Reads after Supply Start | 52 | BPM-003 | 1041 | DS | Start Point - Following SSD | This start point is following the supply start date | N/A | N/A | N/A | N/A | N/A | N | N/A
|  | 53 | BPM-003 | 1038 | DS | Attempt to Gather Smart Reads | The incoming Supplier (DCC Stub) will attempt to gather Smart Reads | N/A | N/A | N/A | N/A | N/A | N | N/A
| Update Legacy Data Items | 54 |  |  | MS & DS | These steps have been added for e2e completeness and will be executed as end-of-day processing. REGS generates an end-of-day file to update legacy data items and sends it to EES. | These steps have been added for e2e completeness and will be executed as end-of-day processing. REGS generates an end-of-day file to update legacy data items and sends it to EES. | REGS | N/A | EES | N/A | N/A | Y | REGS provides evidence that the batch extract included data items for the Reverse Migrated MPAN.
|  | 55 |  |  | MS & DS | EES receives the end-of-day legacy data item update file from REGS and processes it | EES receives the end-of-day legacy data item update file from REGS and processes it | REGS | N/A | EES | N/A | N/A | Y | EES evidences that the sent data items have been updated appropriately

## BKP (hidden)
Test Case Title | Key Journey Events | Test Step | BP | BP Step | Service Type | Meter Type | Test Steps | Test Description | Trigger Sender | Interface ID | Trigger Receipient | Traceability Requirement | Message Input Event Code | Evidence Required | Key Validation & Test Evidence
|  |  |  | 1000 | DS | C | Reverse Migration BP001 CoS | This process follows on from the end of the BP002 Reverse Migration CoA (MS) process.
|  |  |  | 1001 | DS | C | Appoint Legacy Agents | The Supplier will send an appointment notification to the new DC via a D0155. Will use a specific value in the 'Contract Reference' data field to indicate a Reverse Migration is occurring. | Incoming Supplier | D0155 | Incoming DC | MHHS-RMigration-CoA(DS)-SUP-001
|  |  |  | 1002 | DS | C | Accept Appointment | The incoming DC will accept the appointment and share a D0011 with the incoming Supplier. | Incoming DC | D011 | Incoming Supplier | MHHS-RMigration-CoA(DS)-DC-004
|  |  |  | 1003 | DS | C | Update Agent appointment and settlement details | The incoming Supplier will update the Agent appointment and settlement details via a D0205 to the Registration Service. | Incoming Supplier | D0205 | Registration Service | MHHS-RMigration-CoA(DS)-SUP-002
|  |  |  | 1004 | DS | C | Update Agent appointment and settlement detailsUpdate agent appointment and settlement details and share D0209 with DA | The Registration Service will use this D0205 to update the Agent appointment and settlement details. Note: The RS will also share a D0209 with the DA at this point |  |  | Registration Service | MHHS-RMigration-CoA(DS)-RS-003 MHHS-RMigration-CoA(DS)-RS-004
|  |  |  | 1006 (120) | DS | C | Receive CSS Secured notification and process reverse migration | For prospective appointments the Registration Service will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. If the appointment does not correspond with CSS updates the Metering Service appointment will become Lapsed. This means the appointment is no longer valid and the existing Metering Service will remain in situ. |  |  |  | MHHS-RMigration-CoA(DS)-RS-002
|  |  |  | 1007 (125) | DS | C | CSS Secured Notification | For prospective appointments the Registration Service will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect.
|  |  |  | 1008 | DS | C | Issue DS Appointment De-Appointment Notification | An IF-003 will be sent to the DIP which informs that the DS is being de-appointed. | Registration Service | IF-003 | DIP | MHHS-RMigration-CoA(DS)-RS-005 MHHS-RMigration-CoA(DS)-RS-007
|  |  |  | 1009 | DS | C | Publish DS De-Appointment Notification | The DIP will publish the PUB-003 to the outgoing DS, the outgoing Supplier, the LDSO and the EES. | DIP | PUB-003 | Outgoing MS / Outgoing Supplier / LDSO /EES | MHHS-RMigration-CoA(DS)-ECS-001
|  |  |  | 1010 | DS | C | Process DS De-Appointment Notification | The EES will process the de-appointment notification. Note: The EES will need to set a status that the MPAN has reverted to Legacy arrangements after at least one PUB-003 is received. Parties should be able to enquire via the portal and the API and see this status. | DIP | PUB-003 | EES | MHHS-RMigration-CoA(DS)-EES-001 MHHS-RMigration-CoA(DS)-EES-002
|  |  |  | 1011 | DS | C | Process DS De-Appointment Notification | The LDSO will process the de-appointment notification. | DIP | PUB-003 | LDSO | MHHS-RMigration-CoA(DS)-LDSO-001 MHHS-RMigration-CoA(DS)-LDSO-002
|  |  |  | 1012 | DS | C | Process DS De-Appointment Notification | The outgoing Supplier will process the de-appointment notification. | DIP | PUB-003 | Outgoing Supplier | MHHS-RMigration-CoA(DS)-SUP-004
|  |  |  | 1013 | DS | C | Process DS De-Appointment Notification | The outgoing DS will process the de-appointment notification. | DIP | PUB-003 | Outgoing MS
|  |  |  | 1014 | DS | C | Reverse Migration BPM-002 CoA (MS)
|  |  |  | 1015 (160) | DS | T | Issue MTD to Incoming DC | The incoming MOP will send the meter technical details to the incoming DC. Advanced Metering Services will send a D0268 and Smart and Traditional Metering Services will send D0150 & D0149.
|  |  |  | 1017 (165) | DS | T | Send D0149/D0150 | The Incoming MOP will send the MTDs to the incoming DC via a D0149/D0150. | Incoming MOP | D0149 / D0150 | incoming DC
|  |  |  | 1019 (345) | DS | T | Receive MTDs from MOP | The incoming DC will receive the MTDs from the incoming MOP via the D0149/D0150. | Incoming MOP | D0149 / D0150 | incoming DC
|  |  |  | 1020 (346) | DS | T | Manage MTD Discrepancies if required
|  |  |  | 1021 | DS | T | Obtain a CoS Read via a COR | The Incoming Supplier will obtain a CoS read and share this with the outgoing Supplier via a D0010. | Incoming Supplier | D0010 | Outgoing Supplier | MHHS-RMigration-CoA(DS)-SUP-005
|  |  |  | 1022 | DS | T | Validate Read | The outgoing Supplier will validate the read and re-share it with the incoming Supplier via a D0010. They will also share this with the outgoing DS via a D0010. Note: If the outgoing supplier cannot validate the read or does not receive a read, they will estimate a read to share with the DS / Incoming Supplier within 5 days of the CoS | Outgoing Supplier | D0010 | Incoming Supplier / Outgoing DS | MHHS-RMigration-CoA(DS)-SUP-003 MHHS-RMigration-CoA(DS)-SUP-006
|  |  |  | 1023 | DS | T | Provide validated read | The incoming Supplier will then share this validated read with the incoming DC via a D0010. | Incoming Supplier | D0010 | Incoming DC | MHHS-RMigration-CoA(DS)-DC-003 MHHS-RMigration-CoA(DS)-SUP-007
|  |  |  | 1024 | DS | T | Obtain Read and commence Legacy settlement activities | The incoming DC will then receive the read from the Incoming Supplier. | Incoming Supplier | D0010 | Incoming DC | MHHS-RMigration-CoA(DS)-DC-005
|  |  |  | 1025 | DS | T | END POINT
|  |  |  | 1026 | DS | T | Receive read | The outgoing DS will then receive this read. | Outgoing DS |  | Outgoing Supplier
|  |  |  | 1027 | DS | T | Receive Estimates / reads | The outgoing Supplier will then receive the estimates / reads. | Outgoing DS |  | Outgoing Supplier
|  |  |  | 1028 | DS | T | END POINT
|  |  |  | 1015 (160) | DS | A | Issue MTD to Incoming DC | The incoming MOP will send the meter technical details to the incoming DC. Advanced Metering Services will send a D0268 and Smart and Traditional Metering Services will send D0150 & D0149.
|  |  |  | 1018 (170) | DS | A | Send D0268 | The incoming MOP will send the MTDs to the incoming DC via a D0268. | Incoming MOP | D0268 | Incoming DC
|  |  |  | 1019 (345) | DS | A | Receive MTDs from MOP | The incoming DC will receive the MTDs from the incoming MOP via the D0149/D0150. | Incoming MOP | D0149 / D0150 | incoming DC
|  |  |  | 1020 (346) | DS | A | Manage MTD Discrepancies if required
|  |  |  | 1029 | DS | A | Begin Legacy HH or NHH data collection processes | At this stage, the DC will begin the relevant data collection processes. Note: They will not receive historical read data however they will operate legacy collection processes without any historical data. |  |  |  | MHHS-RMigration-CoA(DS)-DC-002
|  |  |  | 1042 | DS | A | END POINT
|  |  |  | 1015 (160) | DS | S | Issue MTD to Incoming DC | The incoming MOP will send the meter technical details to the incoming DC. Advanced Metering Services will send a D0268 and Smart and Traditional Metering Services will send D0150 & D0149.
|  |  |  | 1016 (161) | DS | S | Receive MTDs and manage any discrepancies | The incoming DC to receive MTDs from the incoming MOP via a D0149/D0150 and manage any discrepancies if required. | Incoming MOP | D0149/D0150 | Incoming DC
|  |  |  | 1030 | DS | S | Attempt to Gather Smart Reads | The outgoing DS will attempt to gather Smart Reads
|  |  |  | 1031 | DS | S | Issue Daily Read Log Reading | The outgoing DS will send the daily read log reading via an IF-041 to the DIP | Outgoing DS | IF-041 | DIP
|  |  |  | 1032 | DS | S | Issue PUB-041 | The DIP will share the read log with the outgoing Supplier via a PUB-041 | DIP | PUB-041 | Outgoing Supplier
|  |  |  | 1033 | DS | S | Receive Register Reads | The outgoing Supplier will then receive the Register reads from the DIP
|  |  |  | 1034 | DS | S | Compare and validate actuals | The outgoing Supplier will then validate the actual reads
|  |  |  | 1035 | DS | S | Issue cumulative read to new Supplier | The outgoing Supplier will then issue the cumulative read to the incoming Supplier via a D0010 | Outgoing Supplier | D0010 | Incoming Supplier | MHHS-RMigration-CoA(DS)-SUP-008
|  |  |  | 1036 | DS | S | Receive Cumulative Readings | The incoming Supplier will then receive the cumulative readings and share them with the incoming DC via a D0010 | Incoming Supplier | D0010 | Incoming DC | MHHS-RMigration-CoA(DS)-DC-003
[5 empty] | DS | S | [5 empty] | MHHS-RMigration-CoA(DS)-SUP-009
|  |  |  | 1037 | DS | S | Receive Time of use Register Reads | The incoming DC will then receive the time of use register read from the incoming Supplier | Incoming Supplier | D0010 | Incoming DC
|  |  |  | 1038 | DS | S | Attempt to Gather Smart Reads | The incoming Supplier will attempt to gather Smart Reads
|  |  |  | 1039 | DS | S | Attempt to Gather Smart Reads | The outgoing Supplier will attempt to gather Smart Reads
|  |  |  | 1040 | DS | S | END POINT
|  |  |  | 1041 | DS | S | Start Point - Following SSD | This start point is following the supply start date
|  |  |  | 1043 | DS | S | Receive Register Reads | The LDSO will receive Register Reads via a PUB-41 | DIP | PUB-041 | LDSO