## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Change Log
Date | Author | Release | Reason for change
2024-05-16 | SI NFT Team | 0.1 | Scenario created
2025-01-23 | SI NFT Team | 0.2 | ADO References updated
2025-03-20 | SI NFT Team | 0.3 | Updated to relfect COS changes to appproach Coverage increased to cover MPAN relationships and UM from COS scripts

## SITNFT-T2 070 Overview
Scenario ID | SITNFT-T2 070
Theme | Change Of Agent
Scenario Title | Change of Agent Processing
Description | TC01 - Smart - Single MPAN, change of data and metering service TC02 - Advanced - Single, change of data and metering service TC03 - Traditional - Single, change of data and metering service TC04 - Advanced - Import/Export change of data service TC05 - Traditional - Related change of data service TC06 - Unmetered change of data service
Functional Category | Migration
Functional Area 1 | Migration
Functional Area 2
Creator | Iain Smith
Priority | High
Scenario size | Large
Design Document Ref
Business Process | Migration
Pre-Requisites
Boundaries
Test Case Variables | (1) SITNFT-T2 070 010 Smart (2) SITNFT-T2 070 020 Adv (3) SITNFT-T2 070 030 Trad (4) SITNFT-T2 070 040 Adv (5) SITNFT-T2 070 050 Trad (6) SITNFT-T2 070 060 UM
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Case Version | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITNFT-T2 070 010 | SITNFT-T2 070 010 Smart | 0.3 | MPAN Appointment Data from T2 050 010 Smart from previous day Smart - Single MPAN, change of data and metering service | Smart Meter | Single MPAN | Calendar
2 | SITNFT-T2 070 020 | SITNFT-T2 070 020 Adv | 0.3 | MPAN Appointment Data from SITNFT-T2 050 020 Adv from previous day Advanced - Single, change of data and metering service | Advanced Meter | Single MPAN | Calendar
3 | SITNFT-T2 070 030 | SITNFT-T2 070 030 Trad | 0.3 | MPAN Appointment Data from SITNFT-T2 050 030 Trad from previous day Traditional - Single, change of data and metering service | Traditional | Single MPAN | Calendar
4 | SITNFT-T2 070 040 | SITNFT-T2 070 040 Adv | 0.1 | MPAN Appointment Data from SITNFT-T2 050 040 Adv from previous day Advanced - Import/Export change of data service | Advanced Meter | Import+Export | Calendar
5 | SITNFT-T2 070 050 | SITNFT-T2 070 050 Trad | 0.1 | MPAN Appointment Data from SITNFT-T2 050 050 Trad from previous day Traditional - Related change of data service | Traditional | Related | Calendar
6 | SITNFT-T2 070 060 | SITNFT-T2 070 060 UM | 0.1 | MPAN Appointment Data from SITNFT-T2 050 060 UM from previous day Unmetered change of data service | Unmetered | Single MPAN | Calendar
Back to List of
Test Scenarios

## SITNFT-T2 070 010
No. | Test Case Id |  |  |  | Test Case Version |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITNFT-T2 070 010 |  |  |  | 0.3 |  | SITNFT-T2 070 010 Smart | MPAN Appointment Data from T2 050 010 Smart from previous day Smart - Single MPAN, change of data and metering service | Smart Meter | Single MPAN | Calendar
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITNFT-T2 070 010 Smart | RS Appointment Queue (If required) | 1 | BP002 | 100 101 | MHHS-BR-RS-020 | REGS |  |  |  | REGS Holds in appointment queue until appointment date reached (Prospective Appointments only) |  | N
| RS De-Appointment Notification | 2 | BP002 | 120 +130 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_210 | REGS | IF-037 | [MSDeApp] | DIP | Registration service sends out IF-037 to DIP | http 201 response from DIP | N
|  | 3 | BP002 | 140 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-037 | [MSDeApp] | SMSO, Supplier, LDSO, EES | DIP sends PUB-037 to Old Metering Service, Supplier, LDSO & EES |  | N
|  | 4 | BP002 | 231 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | SMSO | Old Metering Service receives PUB-037 confirming MS De-appointment | Old metering service receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 5 | BP002 | 150 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | Supplier | Supplier receives PUB-037 confirming MS De-appointment | Supplier receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 6 | BP002 | 145 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 confirming MS De-appointment | LDSO receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 7 | BP002 | 146 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 confirming MS De-appointment | EES receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS De-Appointment Notification | 8 | BP003 | 130 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_210 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 9 | BP003 | 140 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-037 | [DSDeApp] | SDSO,Supplier, LDSO, EES, MDS | DIP sends PUB-037 De-appointment to SDSO, Supplier, LDSO, EES and MDS |  | N
|  | 10 | BP003 | 96 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | SDSO | Smart Data Service (Outgoing) receives PUB-037 De-appointment and continues with their BAU processes. | Outgoing Smart Data Service receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 11 | BP003 | 150 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | Supplier | Supplier recieves PUB-037 confirming DS De-appointment | Supplier receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | N
|  | 12 | BP003 | 145 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives de appointment notification PUB-037. | LDSO receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 13 | BP003 | 146 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | EES | EES receives de appointment notification PUB-037. | EES receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 14 | BP003 | 147 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 DSDeApp with details of Data Services Appointment and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification | 15 | BP002 | 240 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_200 | REGS | IF-036 | [MSAppActive] | DIP | REGS sends IF-036 to DIP. | http 201 response from DIP | N
|  | 16 | BP002 | 245 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | SDSC | DIP sends PUB-036 to SUPC, LDSO(If Opted in), EES, SMSI and SDSC. |  | N
|  | 17 | BP002 | 260 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 18 | BP002 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | LDSO(If Opted in) | LDSO(If Opted in) receives PUB-036 | LDSO(If Opted in) receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 19 | BP002 | 283 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 20 | BP002 | 195 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 21 | BP002 | 270 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | SDSC | SDSC receives PUB-036 | SDSC receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| CSS/DCC Updates - Start | 22 | N/A | N/A |  | REGS | ERDA CSS00200 (Issue MS appointment notification ) | N/A | CSS | REGS Sends ERDA CSS00200 for MS Appointment notification |  | Y
| RS Appointment Notification | 23 | BP003 | 250 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_200 | REGS | IF-036 | [DSAppActive] | DIP | REGS sends IF-036 to DIP | http 201 response from DIP | N
|  | 24 | BP003 | 255 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-036 | [DSAppActive] | SUPC, SMSI, LDSO(If Opted in), EES, SDSI, MDS | DIP sends PUB-036 to SUPC, SMSI, LDSO(If Opted in), EES, SDSI and MDS confirming DS Appointment |  | N
|  | 25 | BP003 | 260 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 26 | BP003 | 281 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 27 | BP003 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | LDSO(If Opted in) | LDSO(If Opted in) receives PUB-036 | LDSO(If Opted in) receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 28 | BP003 | 279 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 29 | BP003 | 284 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 30 | BP003 | 340 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SDSI | SDS (Incoming) receives PUB-036 | SDS Incoming receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| CSS/DCC Updates - Start | 31 | BP003A | 20 |  | REGS | ERDA CSS00200 (Issue MDR Request) | N/A | CSS | REGS Sends end date for existing MDR appointment & Sends details of new MDR to CSS. Issues ERDA CSS00200 (Issue MDR Request) to CSS which outputs CSS07000 (Response) |  | Y
|  | 32 | BP003A | 80 | OPC_180 MHHS-BR-SU-124 MHHS-BR-LD-060 MHHS-BR-DS-14 | CSS | CSS07000 (Response) | N/A | REGS | REGS receives CSS07000 (Response) from CSS |  | Y
|  | 33 | BP003A | 90 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_190 MHHS-BR-SU-124 MHHS-BR-LD-060 MHHS-BR-DS-142 | REGS | IF-035 | [DCC-MDROutcome] | DIP | REGS sends IF-035 - (DCC MDR Outcome) to DIP | http 201 response from DIP | N
|  | 34 | BP003A | 100 110 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_190 MHHS-BR-SU-124 MHHS-BR-LD-060 MHHS-BR-DS-142 | DIP | PUB-035 | [DCC-MDROutcome] | SDSI | DIP sends PUB-035 to SDSI |  | N
| CSS/DCC Updates - Completed | 35 | BP003A | 120 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_190 MHHS-BR-SU-124 MHHS-BR-LD-060 MHHS-BR-DS-142 | DIP | PUB-035 | [DCC-MDROutcome] | SDSI | SDS (Incoming) receives PUB-035 - (DCC MDR Outcome) and manages Service Provider Update (BAU). | SDS incoming receives PUB-035 with details of DCC MDR outcome and confirms (DCC MDR Outcome) and manages Service Provider Update (BAU) successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y

## SITNFT-T2 070 020
No. | Test Case Id |  |  |  | Test Case Version |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
2 | SITNFT-T2 070 020 |  |  |  | 0.3 |  | SITNFT-T2 070 020 Adv | MPAN Appointment Data from SITNFT-T2 050 020 Adv from previous day Advanced - Single, change of data and metering service | Advanced Meter | Single MPAN | Calendar
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITNFT-T2 070 020 Adv | RS Appointment Queue (If required) | 1 | BP002 | 100 101 | MHHS-BR-RS-020 | REGS |  |  |  | REGS Holds in appointment queue until appointment date reached (Prospective Appointments only) |  | N
| RS De-Appointment Notification | 2 | BP002 | 120 +130 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_210 | REGS | IF-037 | [MSDeApp] | DIP | Registration service sends out IF-037 to DIP | http 201 response from DIP | N
|  | 3 | BP002 | 140 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-037 | [MSDeApp] | AMSO, SUPC, LDSO, EES | DIP sends PUB-037 to Old Metering Service, Supplier, LDSO & EES |  | N
|  | 4 | BP002 | 231 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | AMSO | Old Metering Service receives PUB-037 confirming MS De-appointment It also deletes or obfuscate the previously held Customer & PSR information | Old metering service receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 5 | BP002 | 150 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | SUPC | Supplier receives PUB-037 confirming MS De-appointment | Supplier receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 6 | BP002 | 145 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 confirming MS De-appointment | LDSO receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 7 | BP002 | 146 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 confirming MS De-appointment | EES receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS De-Appointment Notification | 8 | BP003 | 130 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_210 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 9 | BP003 | 140 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-037 | [DSDeApp] | ADSO, Supplier, LDSO, EES, MDS | DIP sends PUB-037 De-appointment to ADSO, Supplier, LDSO, EES and MDS |  | N
|  | 10 | BP003 | 96 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | ADSO | Advanced Data Service (Outgoing) receives PUB-037 De-appointment It also deletes or obfuscate the previously held Customer & PSR information | Outgoing Advanced Data Service receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 11 | BP003 | 150 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | SUPC | Supplier recieves PUB-037 confirming DS De-appointment | Supplier receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 12 | BP003 | 145 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives de appointment notification PUB-037. | LDSO receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 13 | BP003 | 146 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | EES | EES receives de appointment notification PUB-037. | EES receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 14 | BP003 | 147 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 DSDeApp with details of Data Services Appointment and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification | 15 | BP002 | 240 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_200 | REGS | IF-036 | [MSAppActive] | DIP | REGS sends IF-036 to DIP. | http 201 response from DIP | N
|  | 16 | BP002 | 245 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | ADSC | DIP sends PUB-036 to SUPC, LDSO(If Opted in), EES, AMSI and ADSC. |  | N
|  | 17 | BP002 | 260 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 18 | BP002 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | LDSO(If Opted in) | LDSO(If Opted in) receives PUB-036 | LDSO(If Opted in) receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 19 | BP002 | 283 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 20 | BP002 | 195 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | AMSI | AMSI receives PUB-036 | AMSI receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 21 | BP002 | 270 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | ADSC | ADSC receives PUB-036 | SDSC receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Exchange of Customer & PSR information MS - Start | 22 | BP002 | N/A |  | SUPC | D0225 | N/A | AMSC | Supplier issues out D0225 via DTN with updated PSR information to Advanced meter service |  | N
|  | 23 | BP002 | N/A |  | SUPC | D0225 | N/A | AMSC | Advanced meter service receives D0225 and updates with new PSR information |  | Y
|  | 24 | BP002 | N/A |  | SUPC | D0302 | N/A | AMSC | Supplier issues out D0302 via DTN with updated customer information to Advanced meter service |  | N
| Exchange of Customer & PSR information DS - End | 25 | BP002 | N/A |  | SUPC | D0302 | N/A | AMSC | Advanced meter service receives D0302 updates with new customer information |  | Y
| RS Appointment Notification | 26 | BP003 | 250 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_200 | REGS | IF-036 | [DSAppActive] | DIP | REGS sends IF-036 to DIP | http 201 response from DIP | N
|  | 27 | BP003 | 255 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-036 | [DSAppActive] | SUPC, AMSI, LDSO(If Opted in), EES, ADSI, MDS | DIP sends PUB-036 to SUPC, AMSI, LDSO(If Opted in), EES, ADSI and MDS confirming DS Appointment |  | N
|  | 28 | BP003 | 260 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 29 | BP003 | 281 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | AMSI | AMSI receives PUB-036 | AMSI receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 30 | BP003 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | LDSO(If Opted in) | LDSO(If Opted in) receives PUB-036 | LDSO(If Opted in) receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 31 | BP003 | 279 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 32 | BP003 | 284 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 33 | BP003 | 340 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | ADSI | ADS (Incoming) receives PUB-036 | ADS Incoming receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Exchange of Customer & PSR information DS - Start | 34 | BP003 | N/A |  | SUPC | D0225 | N/A | ADSC | Supplier issues out D0225 via DTN with updated PSR information to Advanced data service |  | N
|  | 35 | BP003 | N/A |  | SUPC | D0225 | N/A | ADSC | Advanced data service receives D0225 and updates with new PSR information |  | Y
|  | 36 | BP003 | N/A |  | SUPC | D0302 | N/A | ADSC | Supplier issues out D0302 via DTN with updated customer information to Advanced data service |  | N
| Exchange of Customer & PSR information DS - End | 37 | BP003 | N/A |  | SUPC | D0302 | N/A | ADSC | Advanced data service receives D0302 updates with new customer information |  | Y

## SITNFT-T2 070 030
No. | Test Case Id |  |  |  | Test Case Version |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
3 | SITNFT-T2 070 030 |  |  |  | 0.2 |  | SITNFT-T2 070 030 Trad | MPAN Appointment Data from SITNFT-T2 050 030 Trad from previous day Traditional - Single, change of data and metering service | Traditional | Single MPAN | Calendar
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITNFT-T2 070 030 Trad | RS Appointment Queue (If required) | 1 | BP002 | 100 101 | MHHS-BR-RS-020 | REGS |  |  |  | REGS Holds in appointment queue until appointment date reached (Prospective Appointments only) |  | N
| RS De-Appointment Notification - Primary MPAN | 2 | BP002 | 120 +130 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_210 | REGS | IF-037 | [MSDeApp] | DIP | Registration service sends out IF-037 to DIP | http 201 response from DIP | N
|  | 3 | BP002 | 140 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-037 | [MSDeApp] | SMSO, Supplier, LDSO, EES | DIP sends PUB-037 to Old Metering Service, Supplier, LDSO & EES for the Primary MPAN |  | N
|  | 4 | BP002 | 231 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | SMSO | Old Metering Service receives PUB-037 confirming MS De-appointment | Old metering service receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 5 | BP002 | 150 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | Supplier | Supplier receives PUB-037 confirming MS De-appointment | Supplier receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 6 | BP002 | 145 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 confirming MS De-appointment | LDSO receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 7 | BP002 | 146 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 confirming MS De-appointment | EES receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS De-Appointment Notification - Primary MPAN | 8 | BP003 | 130 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_210 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 9 | BP003 | 140 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-037 | [DSDeApp] | SDSO, Supplier, LDSO, EES, MDS | DIP sends PUB-037 De-appointment to SDSO, Supplier, LDSO, EES and MDS |  | N
|  | 10 | BP003 | 96 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | SDSO | Smart Data Service (Outgoing) receives PUB-037 De-appointment and continues with their BAU processes. | Outgoing Smart Data Service receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 11 | BP003 | 150 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | Supplier | Supplier receives PUB-037 confirming DS De-appointment | Supplier receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 12 | BP003 | 145 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives de appointment notification PUB-037. | LDSO receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 13 | BP003 | 146 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | EES | EES receives de appointment notification PUB-037. | EES receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 14 | BP003 | 147 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 DSDeApp with details of Data Services Appointment and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification - Primary MPAN | 15 | BP002 | 240 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_200 | REGS | IF-036 | [MSAppActive] | DIP | REGS sends IF-036 to DIP. | http 201 response from DIP | N
|  | 16 | BP002 | 245 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | SDSC | DIP sends PUB-036 to SUPC, LDSO(If Opted in), EES, SMSI and SDSC for the Primary MPAN |  | N
|  | 17 | BP002 | 260 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 18 | BP002 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | LDSO(If Opted in) | LDSO(If Opted in) receives PUB-036 | LDSO(If Opted in) receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 19 | BP002 | 283 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 20 | BP002 | 195 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 21 | BP002 | 270 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [MSAppActive] | SDSC | SDSC receives PUB-036 | SDSC receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification - Primary MPAN | 22 | BP003 | 250 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_200 | REGS | IF-036 | [DSAppActive] | DIP | REGS sends IF-036 to DIP | http 201 response from DIP | N
|  | 23 | BP003 | 255 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-036 | [DSAppActive] | SUPC, SMSI, LDSO(If Opted in), EES, SDSI, MDS | DIP sends PUB-036 to SUPC, SMSI, LDSO(If Opted in), EES, SDSI and MDS confirming DS Appointment for the Primary MPAN |  | N
|  | 24 | BP003 | 260 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 25 | BP003 | 281 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 26 | BP003 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | LDSO(If Opted in) | LDSO(If Opted in) receives PUB-036 | LDSO(If Opted in) receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 27 | BP003 | 279 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 28 | BP003 | 284 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 29 | BP003 | 340 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SDSI | SDS (Incoming) receives PUB-036 | SDS incoming receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Trad MTD Confirmed | 30 | BP002 | 180 |  | SMSI | D149/D150 Trad MTD | N/A | SUPC | SMSI sends D149/D150 Trad MTD to SUPC |  | N
|  | 31 | BP002 | 180 |  | SMSI | D149/D150 Trad MTD | N/A | SDSC | SMSI sends D149/D150 Trad MTD to SDSC |  | N
|  | 32 | BP002 | 180 |  | SMSI | D149/D150 Trad MTD | N/A | LDSO | SMSI sends D149/D150 Trad MTD to LDSO |  | N

## SITNFT-T2 050 040
No. | Test Case Id |  |  |  | Test Case Version |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
4 | SITNFT-T2 070 040 |  |  |  | 0.1 |  | SITNFT-T2 070 040 Adv | MPAN Appointment Data from SITNFT-T2 050 040 Adv from previous day Advanced - Import/Export change of data service | Advanced Meter | Import+Export | Calendar
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITNFT-T2 070 040 Adv | RS Apppointment Queue (If required) | 1 | BP003 | 100 101 120 | MHHS-BR-RS-054 MHHS-BR-RS-059 | REGS |  |  |  | REGS Holds in appointment queue until appointment date reached [Prospective Appts only] |  | N
| RS De-Appointment Notification | 2 | BP003 | 130 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_210 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 3 | BP003 | 140 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-037 | [DSDeApp] | ADSO, Supplier, LDSO, EES, MDS | DIP sends PUB-037 De-appointment to ADSO, Supplier, LDSO, EES and MDS |  | N
|  | 4 | BP003 | 96 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | ADSO | Smart Data Service (Outgoing) receives PUB-037 De-appointment and continues with their BAU processes. | Outgoing Smart Data Service receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 5 | BP003 | 150 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | Supplier | Supplier recieves PUB-037 confirming DS De-appointment | Supplier receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 6 | BP003 | 145 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives de appointment notification PUB-037. | LDSO receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 7 | BP003 | 146 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | EES | EES receives de appointment notification PUB-037. | EES receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 8 | BP003 | 147 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 DSDeApp with details of Data Services Appointment and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS De-Appointment Notification - Export MPAN | 9 | BP003 | 720 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_210 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP
|  | 10 | BP003 | 740 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-037 | [DSDeApp] | SUPC, ADSO, LDSO, EES, MDS | DIP sends PUB-037 to ADSO, Supplier, LDSO, EES and MDS confirming DS De-appointment for the Export MPAN |  | N
|  | 11 | BP003 | 760 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | ADSO | ADSO recieves PUB-037 | ADSO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 12 | BP003 | 150 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | Supplier | Supplier recieves PUB-037 confirming DS De-appointment | Supplier receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 13 | BP003 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives PUB-037 | LDSO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 14 | BP003 | 279 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | EES | EES receives PUB-037 | EES receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 15 | BP003 | 284 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037 | MDS receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification | 16 | BP003 | 250 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_200 | REGS | IF-036 | [DSAppActive] | DIP | REGS sends IF-036 to DIP | http 201 response from DIP | N
|  | 17 | BP003 | 255 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-036 | [DSAppActive] | SUPC, AMSI, LDSO (If opted in) , EES, ADSI, MDS | DIP sends PUB-036 to SUPC, AMSI, LDSO (If opted in) , EES, ADSI and MDS confirming DS Appointment |  | N
|  | 18 | BP003 | 260 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 19 | BP003 | 281 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | AMSC | Smart Meter Service receives PUB-036 | Smart Meter Service receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 20 | BP003 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | LDSO (If opted in) | LDSO receives PUB-036 (If opted in) | LDSO (If opted in) receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 21 | BP003 | 279 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 22 | BP003 | 284 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 23 | BP003 | 340 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | ADSI | ADS (Incoming) receives PUB-036 | ADS Incoming receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification - Export MPAN | 24 | BP003 | 710 | MHHS-BR-RS-068 | REGS |  |  |  | Registration service identifies Linked MPANs and processes the export MPAN | Registration services receives PUB-034 DSAppSPResponse with details of Data Services Appointment PR response and confirms identifing Linked MPANs and processes the export MPANs successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | N
|  | 25 | BP003 | 770 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_200 | REGS | IF-036 | [DSAppActive] | DIP | REGS sends IF-036 to DIP | http 201 response from DIP | N
|  | 26 | BP003 | 780 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-036 | [DSAppActive] | SUPC, AMSC, ADSI, LDSO (If opted in), EES, MDS | DIP sends PUB-036 to SUPC, Smart Meter Service, ADSI, LDSO (If opted in), EES and MDS confirming DS Appointment for the Export MPAN |  | N
|  | 27 | BP003 | 750 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 28 | BP003 | 281 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | AMSC | Smart Meter Service receives PUB-036 | Smart Meter Service receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 29 | BP003 | 790 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | ADSI | ADS (Incoming) receives PUB-036 | ADS incoming receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 30 | BP003 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | LDSO (If opted in) | LDSO receives PUB-036 (If opted in) | LDSO (If opted in) receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 31 | BP003 | 279 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 32 | BP003 | 284 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y

## SITNFT-T2 050 050
No. | Test Case Id |  |  |  | Test Case Version |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
5 | SITNFT-T2 070 050 |  |  |  | 0.1 |  | SITNFT-T2 070 050 Trad | MPAN Appointment Data from SITNFT-T2 050 050 Trad from previous day Traditional - Related change of data service | Traditional | Related | Calendar
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITNFT-T2 070 050 Trad | RS Appointment Queue (If required) | 1 | BP003 | 100 101 120 | MHHS-BR-RS-054 MHHS-BR-RS-059 | REGS |  |  |  | REGS Holds in appointment queue until appointment date reached (Prospective Appointments only)
| RS De-Appointment Notification - Primary MPAN | 2 | BP003 | 130 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_210 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 3 | BP003 | 140 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-037 | [DSDeApp] | SDSO, Supplier, LDSO, EES, MDS | DIP sends PUB-037 De-appointment to SDSO, Supplier, LDSO, EES and MDS |  | N
|  | 4 | BP003 | 96 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | SDSO | Smart Data Service (Outgoing) receives PUB-037 De-appointment and continues with their BAU processes. | Outgoing Smart Data Service receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 5 | BP003 | 150 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | Supplier | Supplier receives PUB-037 confirming DS De-appointment | Supplier receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 6 | BP003 | 145 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives de appointment notification PUB-037. | LDSO receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 7 | BP003 | 146 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | EES | EES receives de appointment notification PUB-037. | EES receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 8 | BP003 | 147 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 DSDeApp with details of Data Services Appointment and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS De-Appointment Notification - Secondary MPAN 1 | 9 | BP003 | 720 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_210 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 10 | BP003 | 720 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-037 | [DSDeApp] | SDSO, Supplier, LDSO, EES, MDS | DIP sends PUB-037 to SDSO, Supplier, LDSO, EES and MDS confirming DS De-appointment for the Secondary MPAN 1 |  | N
|  | 11 | BP003 | 760 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | SDSO | SDSO receives PUB-037 | SDSO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 12 | BP003 | 150 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | Supplier | Supplier receives PUB-037 confirming DS De-appointment | Supplier receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 13 | BP003 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives PUB-037 | LDSO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 14 | BP003 | 279 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | EES | EES receives PUB-037 | EES receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 15 | BP003 | 284 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037 | MDS receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification - Primary MPAN | 16 | BP003 | 250 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_200 | REGS | IF-036 | [DSAppActive] | DIP | REGS sends IF-036 to DIP | http 201 response from DIP | N
|  | 17 | BP003 | 255 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-036 | [DSAppActive] | SUPC, SMSI, LDSO(If Opted in), EES, SDSI, MDS | DIP sends PUB-036 to SUPC, SMSI, LDSO(If Opted in), EES, SDSI and MDS confirming DS Appointment for the Primary MPAN |  | N
|  | 18 | BP003 | 260 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 19 | BP003 | 281 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 20 | BP003 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | LDSO(If Opted in) | LDSO(If Opted in) receives PUB-036 | LDSO(If Opted in) receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 21 | BP003 | 279 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 22 | BP003 | 284 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 23 | BP003 | 340 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SDSI | SDS (Incoming) receives PUB-036 | SDS incoming receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification - Secondary MPAN 1 | 24 | BP003 | 710 | MHHS-BR-RS-072 | REGS |  |  |  | Registration service identifies Related MPANs and processes the Secondary MPAN 1 | Registration services receives PUB-034 DSAppSPResponsep with details of Data Services Appointment PR response and confirms identifying Related MPANs and processes the secondary MPANs successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | N
|  | 25 | BP003 | 770 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_200 | REGS | IF-036 | [DSAppActive] | DIP | Registration service sends IF-036 to DIP | http 201 response from DIP | N
|  | 26 | BP003 | 780 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-036 | [DSAppActive] | SUPC, SMSI, SDSI, LDSO(If Opted in), EES, MDS | DIP sends PUB-036 to SUPC, SMSI, SDSI, LDSO(If Opted in), EES and MDS confirming DS Appointment for the Secondary MPAN 1 |  | N
|  | 27 | BP003 | 750 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 28 | BP003 | 281 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 29 | BP003 | 790 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SDSI | SDS (Incoming) receives PUB-036 | SDS incoming receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 30 | BP003 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | LDSO(If Opted in) | LDSO(If Opted in) receives PUB-036 | LDSO(If Opted in) receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 31 | BP003 | 279 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 32 | BP003 | 284 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y

## SITNFT-T2 050 060
No. | Test Case Id |  |  |  | Test Case Version |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
6 | SITNFT-T2 070 060 |  |  |  | 0.1 |  | SITNFT-T2 070 060 UM | MPAN Appointment Data from SITNFT-T2 050 060 UM from previous day Unmetered change of data service | Unmetered | Single MPAN | Calendar
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITNFT-T2 070 060 UM | RS Apppointment Queue (If required) | 1 | BP003 | 100 101 120 | MHHS-BR-RS-054 MHHS-BR-RS-059 | REGS |  |  |  | REGS Holds in appointment queue until appointment date reached [Prospective Appts only] |  | N
| RS De-Appointment Notification | 2 | BP003 | 130 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_210 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 3 | BP003 | 140 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-037 | [DSDeApp] | UMSDSO, Supplier, LDSO, EES, MDS | DIP sends PUB-037 De-appointment to UMSDS (Outgoing), Supplier, LDSO, EES and MDS |  | N
|  | 4 | BP003 | 96 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | UMSDSO | UMSDS (Outgoing) receives PUB-037 De-appointment and continues with their BAU processes. | UMSDS (Outgoing) receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 5 | BP003 | 150 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | Supplier | Supplier recieves PUB-037 confirming DS De-appointment | Supplier receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 6 | BP003 | 145 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives de appointment notification PUB-037. | LDSO receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 7 | BP003 | 146 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | EES | EES receives de appointment notification PUB-037. | EES receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 8 | BP003 | 147 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_210 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 DSDeApp with details of Data Services Appointment and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification | 9 | BP003 | 250 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 OPC_200 | REGS | IF-036 | [DSAppActive] | DIP | REGS sends IF-036 to DIP | http 201 response from DIP | N
|  | 10 | BP003 | 255 | NFR0035 NFR0036 NFR0037 NFR0040 NFR0047 | DIP | PUB-036 | [DSAppActive] | SUPC, UMSO, LDSO (If opted in) , EES, UMSDSI, MDS | DIP sends PUB-036 to SUPC, UMSO, LDSO (If opted in), EES, UMSDS (Incoming) and MDS confirming DS Appointment |  | N
|  | 11 | BP003 | 260 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 12 | BP003 | 281 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | UMSO | UMSO receives PUB-036 | UMSO receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 13 | BP003 | 280 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | LDSO (If opted in) | LDSO receives PUB-036 (If opted in) | LDSO (If opted in) receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 14 | BP003 | 279 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 15 | BP003 | 284 (TBC) | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 16 | BP003 | 340 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_200 | DIP | PUB-036 | [DSAppActive] | UMSDSI | UMSDS (Incoming) receives PUB-036 | UMSDS (Incoming) receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y