## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Front Cover (hidden)
SWITCHING PROGRAMME
E2E Test Scenarios
Reference: NCT-0045
Version: v0.3

## Change Control (hidden)
Confidentiality Statement
The information contained herein is for the purpose of the MHHS Programme. This document may not be copied, or communicated to a third party, or used, for any purpose other than that for which it is supplied without the express written consent of the MHHS Programme
Distribution List
Name | Organisation
Document History
Issue No. | Issue Date | Issued by | Change Description
0.1 | 2023-02-10 | Dean Bailey | First Draft & QA Checked
Reviewed By
Version | Date | Name | Title / Responsibility
0.1
Approvals
Version | Date | Name | Title / Responsibility

## Sheet1 (hidden)
(empty)

## Sheet2 (hidden)
Data returned for Distinct Count of Profile, 1 - Dual (First 1000 rows).
ListTestCases[Test Case Category] | ListTestCases[E2E Scenario] | ListTestCases[Test Case Id] | ListTestCases[Test Case Title] | ListTestCases[Domestic] | ListTestCases[Non Domestic] | ListTestCases[Smart] | ListTestCases[Non Smart] | ListTestCases[Associated Test Scenario Id] | ListTestCases[Pre-Requisite Test Case] | ListTestCases[Regression Tests] | ListTestCases[Profile] | ListTestCases[Unique ID]
Switch Request Objection | E2E-D001 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-004-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-004-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity)) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-G001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  | X | X | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-004-03 | Gaining Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-G001 | E2E-010-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-007-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-010-04 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-004-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-L001 | E2E-010-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-L001 | E2E-007-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-004-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-L001 | E2E-010-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-L001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Traditional - Gas, Smart Meter - Electricity) | X |  | X | X | E2E-010-L001 | E2E-007-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-004-06 | Losing Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-L001 | E2E-010-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Successful | E2E-D002 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-013-01 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-016-01 | Gaining Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-G001 | E2E-013-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-013-02 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-016-02 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-G001 | E2E-013-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-013-03 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-016-03 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-G001 | E2E-013-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-013-04 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-016-04 | Gaining Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-G001 | E2E-013-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-013-05 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-016-05 | Losing Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-L001 | E2E-013-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-013-06 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-016-06 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-L001 | E2E-013-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-013-07 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-016-07 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-L001 | E2E-013-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-013-08 | Losing Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-016-08 | Losing Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-L001 | E2E-013-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Withdrawal | E2E-D003 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-019-01 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-G001 | E2E-10-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-019-02 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-019-03 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-019-04 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-G001 | E2E-010-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-019-05 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-010-06 | LosingSupplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-019-06 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-019-07 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-019-08 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-L001 | E2E-010-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Annulment | E2E-D004 | E2E-007-01 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-010-01 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-022-01 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-007-02 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-010-02 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-022-02 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-007-03 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-010-03 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meter with Primary MPAN) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-022-03 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-007-04 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-G001 | NA |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-010-04 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic,Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-022-04 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-G001 | E2E-010-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-007-05 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-010-05 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-022-05 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-007-06 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-010-06 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-022-06 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-007-07 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-010-07 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic smart Meter with Primary MPAN) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-022-07 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-007-08 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-010-08 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-022-08 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-L001 | E2E-010-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4

## Summary (hidden)
Test Scenario View |  |  |  |  | Summary
Priority | Fuel Type | E2E Scenario | Profile | Test Cases | Priority | Fuel Type | Profile | Distinct Count of Profile | Distinct Count of E2E Scenario | Test Cases
1 |  |  |  |  | 1
| All |  |  |  |  | All
|  | E2E-GED-001 |  |  |  |  | Domestic, Smart Meter | 1 | 1 | 6
|  |  | Domestic, Smart Meter | 6 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  |  | Domestic, Traditional Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 1 | 3
|  |  | Non Domestic, Smart Meter | 3 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 5
|  |  | Non Domestic, Traditional Meter | 5 |  | All Total |  | 4 | 1 | 18
|  | E2E-GED-001 Total |  | 18 |  | Dual
| All Total |  |  | 18 |  |  | Domestic, Smart Meter | 1 | 4 | 14
| Dual | [5 empty] | Domestic, Traditional Meter | 1 | 4 | 14
|  | E2E-D001 |  |  |  |  | Non Domestic, Smart Meter | 1 | 4 | 14
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 4 | 14
|  |  | Domestic, Traditional Meter | 2 |  | Dual Total |  | 4 | 4 | 56
|  |  | Non Domestic, Smart Meter | 2 |  | Electricity
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Smart Meter | 1 | 6 | 18
|  | E2E-D001 Total |  | 8 |  |  | Domestic, Traditional Meter | 1 | 6 | 16
|  | E2E-D002 |  |  |  |  | Non Domestic, Smart Meter | 1 | 6 | 20
|  |  | Domestic, Smart Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 6 | 16
|  |  | Domestic, Traditional Meter | 8 |  | Electricity Total |  | 4 | 6 | 70
|  |  | Non Domestic, Smart Meter | 8 |  | Gas
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Domestic, Smart Meter | 1 | 7 | 17
|  | E2E-D002 Total |  | 32 |  |  | Domestic, Traditional Meter | 1 | 7 | 17
|  | E2E-D003 |  |  |  |  | Non Domestic, Smart Meter | 1 | 7 | 21
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 7 | 17
|  |  | Domestic, Traditional Meter | 2 |  | Gas Total |  | 4 | 7 | 72
|  |  | Non Domestic, Smart Meter | 2 |  | SMS
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Service management | 1 | 1 | 7
|  | E2E-D003 Total |  | 8 |  | SMS Total |  | 1 | 1 | 7
|  | E2E-D004 |  |  | 1 Total |  |  | 5 | 19 | 223
|  |  | Domestic, Smart Meter | 2 | 2
|  |  | Domestic, Traditional Meter | 2 |  | Dual
|  |  | Non Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 2 | 6
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  | E2E-D004 Total |  | 8 |  |  | Non Domestic, Smart Meter | 1 | 1 | 4
| Dual Total |  |  | 56 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 4
| Electricity |  |  |  |  | Dual Total |  | 4 | 2 | 18
|  | E2E-E001 |  |  |  | Electricity
|  |  | Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 10 | 15
|  |  | Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 9 | 14
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 9 | 13
|  | E2E-E001 Total |  | 10 |  | Electricity Total |  | 4 | 11 | 54
|  | E2E-E002 |  |  |  | Gas
|  |  | Domestic, Smart Meter | 10 |  |  | Domestic, Smart Meter | 1 | 11 | 16
|  |  | Domestic, Traditional Meter | 8 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 10 |  |  | Non Domestic, Smart Meter | 1 | 8 | 13
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 8 | 11
|  | E2E-E002 Total |  | 36 |  | Gas Total |  | 4 | 11 | 54
|  | E2E-E003 |  |  | 2 Total |  |  | 4 | 24 | 126
|  |  | Domestic, Smart Meter | 2 | Grand Total |  |  | 5 | 43 | 349
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E003 Total |  | 8
E2E-E004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E004 Total |  | 8
E2E-E005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E005 Total |  | 4
E2E-E009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E009 Total |  | 4
| Electricity Total |  |  | 70
Gas
E2E-G001
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G001 Total |  | 10
E2E-G002
|  |  | Domestic, Smart Meter | 8
|  |  | Domestic, Traditional Meter | 8
|  |  | Non Domestic, Smart Meter | 10
|  |  | Non Domestic, Traditional Meter | 8
|  | E2E-G002 Total |  | 34
E2E-G003
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G003 Total |  | 8
E2E-G004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G004 Total |  | 8
E2E-G005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G005 Total |  | 4
E2E-G006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G006 Total |  | 4
E2E-G010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G010 Total |  | 4
| Gas Total |  |  | 72
SMS
E2E-SMS-001
|  |  | Service management | 7
|  | E2E-SMS-001 Total |  | 7
| SMS Total |  |  | 7
1 Total |  |  |  | 223
2
Dual
E2E-D005
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-D005 Total |  | 16
E2E-D006
|  |  | Domestic, Smart Meter | 2
|  | E2E-D006 Total |  | 2
| Dual Total |  |  | 18
Electricity
E2E-E006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E006 Total |  | 4
E2E-E007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E007 Total |  | 4
E2E-E008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E008 Total |  | 4
E2E-E010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E010 Total |  | 4
E2E-E011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E011 Total |  | 4
E2E-E012
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E012 Total |  | 6
E2E-E013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E013 Total |  | 4
E2E-E014
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-E014 Total |  | 16
E2E-E015
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E015 Total |  | 2
E2E-E016
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-E016 Total |  | 4
E2E-E017
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  | E2E-E017 Total |  | 2
| Electricity Total |  |  | 54
Gas
E2E-G007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G007 Total |  | 4
E2E-G008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G008 Total |  | 4
E2E-G009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G009 Total |  | 4
E2E-G011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G011 Total |  | 4
E2E-G012
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G012 Total |  | 4
E2E-G013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 3
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G013 Total |  | 6
E2E-G014
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G014 Total |  | 4
E2E-G015
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-G015 Total |  | 16
E2E-G016
|  |  | Domestic, Smart Meter | 2
|  | E2E-G016 Total |  | 2
E2E-G017
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-G017 Total |  | 4
E2E-G018
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  | E2E-G018 Total |  | 2
| Gas Total |  |  | 54
2 Total |  |  |  | 126
Grand Total |  |  |  | 349

## How To Use (hidden)
How To Use
Contents
1. How to Navigate this document
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Overview of the Test Case worksheets
1. How to Navigate this document
This section aims to provide an overview on how to navigate through this workbook.
The workbook consists of a number of worksheets arranged in a hieracrchy working from left to right.
The 'List of Test Scenarios' is broken down into a 'List of Test Cases', which consist of individual Test Cases.
Within the 'List of Test Scenarios' worksheet each of the Scenarios has a hyperlink ('Click to See Test Cases') which when selected takes the user to the Test Cases associated to the selected scenario on the 'List of Test Cases' worksheet.
. | From here, the user can then navigate to a more detailed view of the Test Scenario by clicking on the 'Click to view Test' link
To return to the 'List of Test Scenarios' worksheet the user would select 'Back to list of Test Scenarios', which will return the user to the top of the List of Test Scenarios worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
This section aims to provide an overview of the information contained in the List of Test Scenarios worksheet
The List of 'Test Scenarios' worksheet details each Test Scenario that will be part of the testing phase and provides links to the scenario and list of test cases that make up the basic scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Scenario Category | A short title of the Scenario being defined
| E2E Scenario | A Unique reference for each Scenario (e.g. E2E-G001 is the first Gas Scenario)
| E2E Scenario Title | A Unique Title for each Test Scenario consisting of the E2E Scenario & Test Scenario Category
| Link | A link to the List of Test Cases appropriate to the Test Scenario
| Test ID | A scenario will require one or more Test Cases to deliver the Test Scenario. The same Test might be used in multiple scenarios. Each Test Case that delivers a particular scenario will be listed in the order they would be executed.
| Link | A link to each Test and Steps that will be used within the scenario
| Test Title | The title of the Test ID. This is defined on the individual Test Case worksheets.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Priority | Test Priority for any Risk Based Testing
| Pre-Requisite Test Scenario | The ID of the Test that must be executed prior to this one to complete a Test Scenario
| Comments | Any additional information regarding the Test Scenario will be provided here
| CSS | Indicates the number of steps the Test Case has defined that interact with CSS
| UK Link | Indicates the number of steps the Test Case has defined that interact with UK Link
| DES | Indicates the number of steps the Test Case has defined that interact with DES
| MPAS | Indicates the number of steps the Test Case has defined that interact with MPAS
| ECOES | Indicates the number of steps the Test Case has defined that interact with ECOES
| Smart Metering | Indicates the number of steps the Test Case has defined that interact with Smart Metering
| Gaining Shipper | Indicates the number of steps the Test Case has defined that interact with a Single Shipper or Gaining Shipper where the Test Scenario involves a two parties
| Losing Shipper | Indicates the number of steps the Test Case has defined that interact with a Losing Shipper where the Test Scenario involves a two parties
| Gas Transporter | Indicates the number of steps the Test Case has defined that interact with a GT or iGT
| Data Collector | Indicates the number of steps the Test Case has defined that interact with a DC
| Data Aggregator | Indicates the number of steps the Test Case has defined that interact with a DA
| MEM | Indicates the number of steps the Test Case has defined that interact with a MEM
| MAP | Indicates the number of steps the Test Case has defined that interact with a MAP
| DNO | Indicator as to whether the Test Case defined has steps that interact with a DNO/iDNO
| Gaining Supplier | Indicates the number of steps the Test Case has defined that interact with a single Supplier or a Gaining Supplier where the Test Scenario involves a two parties
| Losing Supplier | Indicates the number of steps the Test Case has defined that interact with a Losing Supplier where the Test Scenario involves a two parties
Third-Party IT Provider
3. Overview of the 'List of Test Cases' worksheet
This section aims to provide an overview of the information contained in the 'List of Test Cases' worksheet
The List of Test Cases details each variation of the Test Scenarios as Test Cases that will form part of the testing phase, and provides links to the Tests & the steps that make up the each scenario. Which Test Cases an E2E participant needs to execute will depend on the Licensed Parties profile
(see '1. How to Navigate this document' for details on how to navigate to & from the List of Test Cases worksheet)
Where Switching functionality is being tested there will be a matching 'GAIN' and a 'LOSE' Test Case. When executing a Test Case with a paired Supplier, the gaining supplier will execute the GAIN test case, and the losing supplier will execute the matching LOSE test case.
A green line separates the GAIN and LOSE test cases for the same scenario.
A blue line separates each Test Scenario, and the Test Case ID will indicate the Tests that make up a single Test Case for a Scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Case Category | The short title of the Scenario that the Test Case variations cover
| E2E Scenario | The Test Scenario ID of the Scenario that the Test Case variations cover
| Test Case Id | The Test Case ID is a combination of the Test Scenario ID and a unique reference to link each of the Tests that make up the Test Case
| Associated Test Id | Details the actual Test ID
| Link | A hyperlink to each Test Case worksheet that forms part of the Test Case
| Test Case Title | Details the Title of the Test Case from the associated Test Case worksheet, plus the variants in place for this particular Test Case.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Day(s) | Details the number of Days each Switch Test will be assigned. This will be blank where the number of days is not relevant to the Test Case
| Domestic | This will be marked with an 'X' where the Test Case is intended for a Domestic Customer.
| Non Domestic | This will be marked with an 'X' where the Test Case is intended for a Non Domestic Customer.
| OFAF | This will be marked with an 'X' where the Test Case is intended for a Switch of more than one Fuel Type or more than one Meter of the same Fuel Type to ensure the 'One Fail, All Fail' switching rule. The Test Case may not test a Failure in all cases.
| Related MPAN | This will be marked with an 'X' where the Test Case is intended to include related MPANs (Electricity only).
| Pre-Requisite Test Case | Details the Test ID that must have been executed prior to this Test
| Profile | The profile describes the options selected for each Test Case (i.e. where X's have been placed in the previous fields)
| Requirements | The requirements listed are the unique Abacus references documented against the in the relevant Test Case Worksheet
4. Overview of the Test Case worksheets
This section aims to provide an overview of the information contained in each of the Test Case worksheets. For example worksheet E2E-002.
Each Test Case worksheet gives an overview of the Case and the agreed steps that need to be executed. These will be loaded to Jira to form each Test Case per LP and the LP will then be able to expand on the Test Steps within Jira to make them more pertinent to the specific LP's systems and processes.
(see '1. How to Navigate this document' for details on how to navigate to & from each Test Case worksheet)
| The following are the Test Case overview Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Scenario ID | The Test ID (as per the worksheet Name) that is used in the 'List of Test Scenarios' and 'List of Test Cases' worksheets to link Tests to Scenarios and Test Cases
| Title | The Short Title of the Test
| Description | An overview of the objectives of the Test
| Pre-Requisites | Any Pre-Requisites that need to be in place prior to this Test Case being executed
| Test Case Variable | A list of the Test Case variables that this particular Test should cater for.
| Mapped Requirements | A summary of the Abacus requirements that the Test Case covers
| Exception Codes | Exception Codes will not be applicable during E2E Testing, these will have been covered previously in SIT and/or UEPT
| The following are the Test Step Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Mapped Requirements | The Abacus requirement reference(s) that each step covers
| Step Title | A short title outlining the purpose of the step
| Evidence Required | A 'Y' or 'N' indicator to highlight whether the Test Participant would be expected to provide evidence for the step. An 'O' indicates evidence is optional based on whether the agents and registered and have agreed to provide support during testing.
| Step Description | A more detailed description of the purpose of the step
| Related System | The system where the step would be executed
| Pre-requisite | Any Pre-Requisites that this step is dependent upon
| Expected Result | A description of the outcome of this Step
| API (Inbound to CSS) | API details retained from the original SIT tests
| Route | Route details retained from the original SIT tests
| Webhook context (Outbound from CSS) | Webhook context details retained from the original SIT tests
| Event Type | Event Type details retained from the original SIT tests
| Acknowledgement Messages | Acknowledgement Message details retained from the original SIT tests
| Comments | Any additional information / comments regarding the step
At the bottom of each Test Case worksheet are the list of Test Cases where this Test Case is called.
| The following is a brief description of each field in this section: |  | Example:
| Field | Details
| No. | Incremental number for each linked Test Case
| Unique Test Id | The Unique Test ID from the 'List of Test Cases' worksheet for each Test Case where this Test Case is called
| Return to Test Case | A Hyperlink to return directly to the current Test within the Test Case in the 'List of Test Cases' worksheet
| Test Case Title | The Test Case Title from the 'List of Test Cases' worksheet of the Unique Test ID Test Case
| Test Case ID | The Test Case ID from the 'List of Test Cases' worksheet of the Test Case
| E2E Scenario | The E2E Scenario ID from the 'List of Test Cases' worksheet of the Test Case
| Test Case Category | The Test Case Category from the 'List of Test Cases' worksheet of the Test Case
List of Test Scenarios
List of Test Cases

## List MASTER (hidden)
High
Medium
Low
MPAN Ownership
Metering Changes
Meter to Bank
Trad
Smart
Advanced
Unmetered
In Progress
Blocked - Reqt Query
Drafted
Peer Reviewed
Rework
Design Reviewed
WG Reviewed (Working Group Drops)​
WG Approved
TMAG Approved

## Change Log
Date | Author | Version | Defect ID | Reason for change
2024-07-18 | Alan Younger | v7.1 |  | Scenario created
2024-09-16 | Bhavin Sikotra | v7.1 |  | Added MHHSP-BRS001-SDS-BR-DS-089 to TC01 Step 80
2024-10-03 | Alan Younger | v7.2 |  | TC01 (V7.2) simplified and consolidated into one Settlement run (II Run)
2024-10-11 | Alan Younger | v7.3 |  | TC01 (v7.3) Updated to remove superfluous IF-021 creation and to reflect additional evidence gathering. TC02 (v7.2) updated to reflect additional evidence gathering (date and time stamp)
2024-10-18 | Alan Younger | v7.3.1 |  | TC01 (v7.3.1) and TC02 (v7.2.1) updated to reflect SRO Review comments.
2024-10-22 | Alan Younger | v7.3.1 |  | TC01 (v7.3.1) updated with MHHSP-BRS007-LSS-32 mapping and clause for Helix to verify the LSS Run completed prior to the 12 noon publish time.
2024-10-24 | Alan Younger | v7.3.1 |  | TC01 (v7.3.1) updated with MHHSP-BRS008-MDS-09 and MHHSP-BRS008-MDS-10 mapping and clause for Helix to verify MDS uses ISD and applies the most recent ISD Data applicable to the Settlement Day and Settlement Period being processed including LLF data.
2024-11-08 | Alan Younger | v7.3.1 |  | TC02 (v7.2.1) Updated to include coverage for the MDS Audit Re-run requirement (MHHSP-BRS008-MDS-04).
2024-11-12 | Alan Younger | v7.3.1 |  | TC01 (v7.3.1) Step 19 updated for correct format requirements MHHSP-BRS014-ECS-BR-RD-022 and MHHSP-BRS014-ECS-BR-RD-023
2024-11-14 | Alan Younger | 7.3.1 |  | TC01 (v7.3.1) and TC02 (v7.2.1) updated for correct format MDS and VAS requirement references and to exclude the descoped MHHSP-BRS009-VAS-52 and MHHSP-BRS009-VAS-57 requirements.

## Detailed Test Data Requirements
1 | Smart single MPAN | Actual Consumption is received and settles normally in the II run with no changes within the SF and RF runs | 1 | In-Area (Distribution Id < 24), Whole Current (Connection-Type = W), | S001
2 | Advanced Import MPANs; i.e. 4 in this group | Actual Consumption is received and settles normally in the II run with no changes within the SF and RF runs. | 1 | In-Area (Distribution Id < 24), Whole Current (Connection-Type = W), | A009
|  |  | 2 | In Area (Distribution Id < 24), CT-Metering (Connection-Type <> W), | A001
|  |  | 3 | Embedded (Distribution Id > 23), Whole Current (Connection-Type = W), | A009
|  |  | 4 | Embedded (Distribution Id >23), CT-Metering (Connection-Type <> W) | A001
TOTAL: 5 MPANs in the overall data allocation for this test case.
Note: In all cases the MPANs should be present either as a result of migration or via a normal business process.

## ST0033 Overview
Scenario ID | SITFTS-ST0033
Theme | Settlement
Scenario Title | Settlement Re-Runs
Description | Settling normally variant where Central Systems (Helix) are instructed to re-run specific component level (e.g. LSS, MDS, VAS) runs. See requirements for the coverage required. The test case covers the following Requirements: MHHSP-BRS007-LSS-03: LSS has capability to undertake a re-run LSS must be able to re-run a Load shaping calculation with revised and or additional data. This can be prior to and post publication. MHHSP-BRS008-MDS-03: MDS capability to undertake a re-run MDS must be able to re-run a Market-wide calculation and increment the Run Number. If notified by BSCCo MDS must undertake a re-run (e.g. for failed validation) with corrected data. MHHSP-BRS009-VAS-05: VAS capability to undertake a re-run VAS must be able to re-run a VAS calculation and increment the Run Number. If notified by BSCCo VAS must undertake a re-run (e.g. for failed validation) with corrected data. MHHSP-BRS009-VAS-06: VAS capability to undertake a re-run for audit purposes VAS must be able to re-run a VAR VAS calculation for audit purposes. If notified by BSCCo VAS must undertake a re-run with the same data it used for the normal VAS Run as per the Master Settlement Timetable. Test case TC01 covers: Rerun of LSS run (pre- and post-publication) Rerun of MDS after SF Run Rerun of VAS after SF Run. Test case TC02 covers: Rerun of VAS for audit purposes after RF Run. Assumes the following Calendar Run is in operation with example dates:
Functional Category | Settlement
Functional Area 1 | Consumption
Functional Area 2 | Settling normally
Creator | Shaun Magee
Priority | High
Scenario size | Large
Design Document Ref
Business Process | BP004, BP005, BP018, BP019, BP020
Pre-Requisites TC01 | Calendar Check: Test Settlement Calendar is fully operational for the UTC Settlement Day (s). For the purposes of this test the following is assumed: UTC Settlement Day = [D] II Run is UTC Settlement Day + 2WD SF Run is UTC Settlement Day + 5WD RF Run is UTC Settlement Day + 8WD MPAN Data Check: MPAN Data Requirements: #Please cross-reference the Detailed Test Data Requirement field# Total of 5 MPANs required in base load data, spanning the following categories: 01: Smart single MPAN x 1 02: Advanced Import MPAN x 4 (NOTE: IN-Area MPANs to have different GSP Group to the others) In all above cases the MPANs should be present either as a result of migration or via a normal business process. All MPANs should be settling normally (as per DES138 data specification). Load Shaping Data Check: A complete set of UTC Settlement Period Consumption Actual for other MPANs in the same Load Shaping Category must be processed for the UTC Settlement Day [D]. The number of other MPANs required will be dictated by the configured De-Minimis Count which can be checked in ISD Entity ID M4 - Load Shape Categories in the Test Environment. The programme will be responsible for allocating MPANs for Load Shaping. Precursor to II Run Smart Data Service Provisioning (1 MPAN): #Please cross-reference the Detailed Test Data Requirement field# 01: Smart single MPAN x 1 [D] + 1WD Data Payload (1 MPAN): #Please cross-reference the Detailed Test Data Requirement field# 01: Smart single MPAN x 1 On the day after the selected Settlement Day [D], the Data Service generates a Data Payload that represents both the Reads and the Consumption (HH Data) from the Meter obtained via the DSP Schedule for the Settlement Day [D] . The Data Payload Reads is generated as a PUB-041 where the Event Code = "[ReadingRemote]". The Data Payload Consumption (HH Data) is generated in a format agreed between the MDR and the Data Service. Precursor to II Run Advanced Data Service Provisioning (4MPANs): #Please cross-reference the Detailed Test Data Requirement field# 02: Advanced Import MPAN x 4 [D] + 1WD Data Payload (4 MPANs): #Please cross-reference the Detailed Test Data Requirement field# 02: Advanced Import MPAN x 4 On the day after the selected Settlement Day [D], the Data Service generates a Data Payload that represents both the Reads and the Consumption (HH Data) from the Meter obtained via the DSP Schedule for the Settlement Day [D] . The Data Payload Reads is generated as a PUB-041 where the Event Code = "[ReadingRemote]". The Data Payload Consumption (HH Data) is generated in a format agreed between the MDR and the Data Service. Precursor to LSS Pre-publication Re-Run Smart Data Service creates replacement IF-021 with revised consumption values for 01: Smart single MPAN x 1 [D] + 2WD Data service creates replacement IF-021 relative to Settlement Day [D] in respect of :01: Smart single MPAN x 1 Using Load Shape, Data Service creates new Complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator indicates the IF-021 Data is Estimated. Precursor to LSS Post-publication Re-Run Smart Data Service creates replacement IF-021 with revised consumption values for 01: Smart single MPAN x 1 [D] + 2WD Data service creates replacement IF-021 relative to Settlement Day [D] in respect of :01: Smart single MPAN x 1 Using Load Shape, Data Service creates new Complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator indicates the IF-021 Data is Estimated. Precursor to MDS Re-Run Smart Data Service creates replacement IF-021 with revised consumption values for 01: Smart single MPAN x 1 [D] + 5WD Data service creates replacement IF-021 relative to Settlement Day [D] in respect of :01: Smart single MPAN x 1 Using Load Shape, Data Service creates new Complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator indicates the IF-021 Data is Estimated. Precursor to VAS Re-Run Smart Data Service creates replacement IF-021 with revised consumption values for 01: Smart single MPAN x 1 [D] + 5WD Data service creates replacement IF-021 relative to Settlement Day [D] in respect of : 01: Smart single MPAN x 1 Actual readings are received in respect of Settlement Day [D]. Data Service creates new Complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator indicates the IF-021 Data is Actual.
Pre-Requisites TC02 | Calendar Check: Test Settlement Calendar is fully operational for the UTC Settlement Day (s). For the purposes of this test the following is assumed: UTC Settlement Day = [D] II Run is UTC Settlement Day + 2WD SF Run is UTC Settlement Day + 5WD RF Run is UTC Settlement Day + 8WD MPAN Data Check: MPAN Data Requirements: This test case has no specific MPAN requirements. It does, however, require that a previous settlement day run completed (RF RUN) and that the MDS and VAS Reports from that run are available as test evidence.
Boundaries | Processing ends when Settlement has completed to the RF Run
Test Case Variables | TC01: Rerun of LSS run (pre- and post-publication) Rerun of MDS after SF Run Rerun of VAS after SF Run. TC02: Rerun of VAS for audit purposes after RF Run.
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Case Link | Test Case Version | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | ST0033 TC01 | ST0033 - Settlements Re-Runs | ST0033 - TC01 | 7.3 7.3.1 | MPAN Data Requirements: #Please cross-reference the Detailed Test Data Requirement field# Total of 5 MPANs required in base load data, spanning the following categories: 01: Smart single MPAN x 1 02: Advanced Import MPAN x 4 In all above cases the MPANs should be present either as a result of migration or via a normal business process. All MPANs should be settling normally (as per DES138 data specification). | Smart, Advanced | 01: Smart single MPAN 02: Advanced Import MPAN | UTC Settlement Day [D]
2 | ST0033 TC02 | ST0033 - VAS Audit Re-Run | ST0033 - TC02 | 7.2 7.2.1 | MPAN Data Requirements: This test case has no specific MPAN requirements. It does, however, require that a previous settlement day run completed (RF RUN) and that the MDS and VAS Reports from that run are available as test evidence. | Traditional Smart Advanced Unmetered | Traditional Smart Advanced Unmetered | UTC Settlement Day [D]

## ST0033 - TC01
No. | Test Case Id |  |  |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | ST0033 TC01 |  |  |  |  | 7.3 7.3.1 |  | ST0033 - Settlement Re-runs | ST0033 - TC01 | MPAN Data Requirements: #Please cross-reference the Detailed Test Data Requirement field# Total of 5 MPANs required in base load data, spanning the following categories: 01: Smart single MPAN x 1 02: Advanced Import MPAN x 4 In all above cases the MPANs should be present either as a result of migration or via a normal business process. All MPANs should be settling normally (as per DES138 data specification). | Smart, Advanced | 01: Smart single MPAN 02: Advanced Import MPAN | UTC Settlement Day [D]
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
ST0033 - Settlement Re-runs | Calendar Check | 1 Pre-Req | [7 empty] | Test Settlement Calendar is fully operational for the UTC Settlement Day (s). For the purposes of this test the following is assumed: UTC Settlement Day = [D] II Run is UTC Settlement Day + 2WD SF Run is UTC Settlement Day + 5WD RF Run is UTC Settlement Day + 8WD |  | N
| MPAN Data Check | 2 Pre-Req | [7 empty] | MPAN Data Requirements: #Please cross-reference the Detailed Test Data Requirement field# Total of 5 MPANs required in base load data, spanning the following categories: 01: Smart single MPAN x 1 02: Advanced Import MPAN x 4 In all above cases the MPANs should be present either as a result of migration or via a normal business process. All MPANs should be settling normally (as per DES138 data specification). |  | N
| Load Shaping Data Check | 3 Pre-Req |  |  | METH005, ID-9600 METH001, ID-10039 |  |  |  |  | A complete set of UTC Settlement Period Consumption Actual for other MPANs in the same Load Shaping Category must be processed for the UTC Settlement Day [D]. The number of other MPANs required will be dictated by the configured De-Minimis Count which can be checked in ISD Entity ID M4 - Load Shape Categories in the Test Environment. The programme will be responsible for allocating MPANs for Load Shaping. |  | N
| Precursor to II Run Smart Data Service Provisioning (1 MPAN): #Please cross-reference the Detailed Test Data Requirement field# 01: Smart single MPAN x 1 [D] + 1WD | 4 Pre-Req |  |  | MHHS-BR-DS-049 | SDSC | Data Provisioning |  |  | Data Payload (1 MPAN): #Please cross-reference the Detailed Test Data Requirement field# 01: Smart single MPAN x 1 On the day after the selected Settlement Day [D], the Data Service generates a Data Payload that represents both the Reads and the Consumption (HH Data) from the Meter obtained via the DSP Schedule for the Settlement Day [D] . The Data Payload Reads is generated as a PUB-041 where the Event Code = "[ReadingRemote]". The Data Payload Consumption (HH Data) is generated in a format agreed between the MDR and the Data Service. | The Data Service to use whatever tools available to generate the Data Payload with values which are commensurate with the test under execution. | N
| Precursor to II Run Advanced Data Service Provisioning (4MPANs): #Please cross-reference the Detailed Test Data Requirement field# 02: Advanced Import MPAN x 4 [D] + 1WD | 5 Pre-Req |  |  | MHHS-BR-DS-049 | ADSC | Data Provisioning |  |  | Data Payload (4 MPANs): #Please cross-reference the Detailed Test Data Requirement field# 02: Advanced Import MPAN x 4 On the day after the selected Settlement Day [D], the Data Service generates a Data Payload that represents both the Reads and the Consumption (HH Data) from the Meter obtained via the DSP Schedule for the Settlement Day [D] . The Data Payload Reads is generated as a PUB-041 where the Event Code = "[ReadingRemote]". The Data Payload Consumption (HH Data) is generated in a format agreed between the MDR and the Data Service. | The Data Service to use whatever tools available to generate the Data Payload with values which are commensurate with the test under execution. | N
| II Run for UTC Settlement Day [D] [D] + 2WD | 6 | BP005 | 60 | METH001, ID-9273 METH001, ID-9098 | SDSC, ADSC, UMSDS | Data Collection |  |  | The Consumption data and Load Shaping data (where available) is used by the Data Service to calculate the estimated consumptions for UTC Settlement Day [D] as part of the Calendar II Run. Note: A Complete Set of UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator indicates the IF-021 Data is Estimated. | Data Service generates IF-021 UTC Settlement Period Consumptions Re-Calculated Data with all relevant information for UTC Settlement Day [D]. Confirms successful updates on downstream systems. | N
II RUN Occurs on [D] + 2WD
| Smart MPAN | 7 | BP005 | 70 | MHHS-BR-DS-073 | SDSC |  |  |  | Prepare Data for Submission Period(s) | Data Services will prepare the data in the agreed format ready for submission | N
| Create IF-021 messages for Actual | 8 | BP005 | 80 | MHHS-BR-DS-087 | SDSC |  |  |  | Validate Read UTC Settlement Period Consumption for: 01: Smart single MPAN x 1 | SDS must prepare MPAN level UTC Period Level Consumption Data in line with the Smart Validation & Estimation Method statement | N
|  | 9 | BP005 | 130 |  | SDSC |  |  | SDSC | Create IF_021 message: IF-021 Data: 01: Smart single MPAN x 1 Complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator indicates the IF-021 Data is Actual. | SDSC must create IF-021 message | N
| Advanced MPANs | 10 | BP005 | 70 | MHHS-BR-DS-072 | ADSC |  |  |  | Prepare Data for Submission Period(s) | Data Services will prepare the data in the agreed format ready for submission | N
|  | 11 | BP005 | 80 | MHHS-BR-DS-086 | ADSC |  |  |  | Validate Read UTC Settlement Period Consumption for: 02. Advanced single MPANs x 4 | ADS must prepare MPAN level UTC Period Level Consumption Data in line with the Advanced Validation & Estimation Method statement | N
|  | 12 | BP005 | 130 |  | ADSC |  |  | ADSC | Create IF_021 message: IF-021 Data: Complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator indicates the IF-021 Data is Actual. | ADSC must create IF-021 message | N
|  | 13 | BP005 | 150 | MHHS-BR-DS-093 MHHS-BR-DS-094 MHHS-BR-DS-095 | SDSC | IF-021 | [ActivePower] & [DI-015] = W | DIP | The IF-021 data [Actual data) is sent to the DIP for: 01: Smart single MPAN x 1 | http 201 response from DIP | N
|  | 14 | BP005 | 160 200 |  | DIP | PUB-021 | [ActivePower] & [DI-015] = W | LSS | LSS receives the PUB-021 for: 01: Smart single MPAN x 1 |  | N
|  | 15 | BP005 | 150 | MHHS-BR-DS-093 MHHS-BR-DS-094 MHHS-BR-DS-095 | ADSC | IF-021 | [ActivePower] & [DI-015] = W | DIP | The IF-021 data (Actual data) is sent to the DIP for: 02. Advanced single MPANs x 4 | http 201 response from DIP | N
|  | 16 | BP005 | 160 200 |  | DIP | PUB-021 | [ActivePower] & [DI-015] = W | LSS | LSS receives the PUB-021 for: 02. Advanced single MPANs x 4 |  | N
BSCCo Requests that Helix trigger LSS Manually prior to the Scheduled run time (this to emulate the pre-publication re-run requirement) MHHSP-BRS007-LSS-03
| Helix manually trigger LSS run, prior to Scheduled run time, using Operator Portal UI | 17 |  |  | MHHSP-03 (MHHSP-BRS007-LSS-03) | Operator Portal |  |  | LSS | From the Operator Portal UI, Helix will manually trigger the LSS run prior to the Scheduled run time. Note: This is to satisfy the pre-publication element of requirement MHHSP-BRS007-LSS-03 | LSS should run successfully. Test evidence is captured (logs/screenshots) | Y
| LSS Run number is incremented by one. | 18 |  |  | MHHSP-03 (MHHSP-BRS007-LSS-03), MHHSP-BRS009-LSS-29 | Operator Portal |  |  | LSS | Helix confirms that the LSS Run Number has been correctly incremented by one. | Helix confirms increment of LSS Run number and captures test evidence, which must include date and time stamp . | Y
| Load Shaping Steps (Actual Data in same load shape category) | 19 | BP018 BP018 BP005 | 60 75 230 | MHHS-BR-RD-022 MHHS-BR-RD-023 MHHSP-BRS014-ECS-BR-RD-022 MHHSP-BRS014-ECS-BR-RD-023 | LSS | IF-022 IF-023 | [LSSPeriodData] [LSSTotalsData] | DIP | The Load Shaping Service will generate Load Shape Period Data (IF-022) and Load Shape Totals Data (IF-023) and submit to DIP. Load Shaping data requires actual IF-021 data to be processed for MPANs within the same Load Shape Category. | http 201 response from DIP | N
|  | 20 | BP005 | 240 250 |  | DIP | PUB-022 PUB-023 | [LSSPeriodData] [LSSTotalsData] | SUPC, SDSC, ADSC, UMSDS | DIP sends PUB-022 and PUB-023 to Supplier and Data Service |  | N
| SUPC receives PUB-022 NOTE: IF-022 does not contain any data item related to the Settlement Run Number | 21 | BP005 | 260 | MHHS-BR-SU-043 | DIP | PUB-022 | [LSSPeriodData] | SUPC | Supplier receives the PUB-022 for: 01. Smart single MPAN 02. Advanced Import MPANs x 4 | Supplier receives PUB-022 [LSSPeriodData]. Confirms successful updates on downstream systems. | N
| SUPC receives PUB-023 NOTE: IF-023 does not contain any data item related to the Settlement Run Number | 22 | BP005 | 260 | MHHS-BR-SU-043 | DIP | PUB-023 | [LSSTotalsData] | SUPC | Supplier receives the PUB-023 for: 01. Smart single MPAN 02. Advanced Import MPANs x 4 | Supplier receives PUB-023 [LSSTotalsData]. Confirms successful updates on downstream systems. | N
| SDSC receives PUB-022 NOTE: IF-022 does not contain any data item related to the Settlement Run Number | 23 | BP005 | 120 | MHHS-BR-DS-077 MHHS-BR-DS-080 | DIP | PUB-022 | [LSSPeriodData] | SDSC | Data Service receives the PUB-022 for: 01. Smart single MPAN | Data Service receives PUB-022 [LSSPeriodData]. Confirms successful updates on downstream systems. | N
| SDSC receives PUB-023 NOTE: IF-023 does not contain any data item related to the Settlement Run Number | 24 | BP005 | 120 | MHHS-BR-DS-077 MHHS-BR-DS-080 | DIP | PUB-023 | [LSSTotalsData] | SDSC | Data Service receives the PUB-023 for: 01. Smart single MPAN | Data Service receives PUB-023 [LSSTotalsData]. Confirms successful updates on downstream systems. | N
| ADSC receives PUB-022 NOTE: IF-022 does not contain any data item related to the Settlement Run Number | 25 | BP005 | 120 | MHHS-BR-DS-077 | DIP | PUB-022 | [LSSPeriodData] | ADSC | Data Service receives the PUB-022 for: 02. Advanced Import MPANs x 42 4 | Data Service receives PUB-022 [LSSPeriodData]. Confirms successful updates on downstream systems. | N
| ADSC receives PUB-023 NOTE: IF-023 does not contain any data item related to the Settlement Run Number | 26 | BP005 | 120 | MHHS-BR-DS-077 | DIP | PUB-023 | [LSSTotalsData] | ADSC | Data Service receives the PUB-023 for: 02. Advanced Import MPANs x 4 | Data Service receives PUB-023 [LSSTotalsData]. Confirms successful updates on downstream systems. | N
| LSS Internal Calculations are validated | 27 | BP018 |  | MHHSP-BRS007-LSS-32 MHHSP-BRS007-LSS-26 | Helix |  |  |  | LSS Run completes and Helix validates internal calculations. Helix verifies the LSS Run completed before the 12 noon publish time. Helix verifies the output data value fields are rounded to 3 decimal places. | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots from Helix Tool | Y
| IF-021 Data in queue (Actuals) | 28 | BP005 | 220 | MHHS-BR-RD-019 | SDSC, ADSC, UMSDS | PUB-021 | [ActivePower] & [DI-015] = W | MDS | The IF-021 data is now queued awaiting the next Calendar Run for the UTC Settlement Day [D] which will be processed as per the published calendar and timetable. |  | N
BSCCo irequests requests that LSS be re-run. MHHSP-BRS007-LSS-03
| Herlix Helix trigger post-publication re-run using Operator Portal UI | 29 |  |  | MHHSP-BRS007-LSS-03 | Operator Portal |  |  | LSS | From the Operator Portal UI, Helix will manually trigger the LSS re-run. Note: This is to satisfy the post-publication element of requirement MHHSP-BRS007-LSS-03 | LSS should re-run successfully. Test evidence is captured (logs/screenshots) | Y
| LSS Run number is incremented by one. | 30 |  |  | MHHSP-BRS007-LSS-03 MHHSP-BRS009-LSS-29 | Operator Portal |  |  | LSS | Helix confirms that the LSS Run Number has been correctly incremented by one. | Helix confirms increment of LSS Run number and captures test evidence, which must include date and time stamp . | Y
| Load Shaping Steps (Actual Data in same load shape category) | 31 | BP018 BP018 BP005 | 60 75 230 | MHHS-BR-RD-022 MHHS-BR-RD-023 | LSS | IF-022 IF-023 | [LSSPeriodData] [LSSTotalsData] | DIP | The Load Shaping Service will generate Load Shape Period Data (IF-022) and Load Shape Totals Data (IF-023) and submit to DIP. Load Shaping data requires actual IF-021 data to be processed for MPANs within the same Load Shape Category. | http 201 response from DIP | N
|  | 32 | BP005 | 240 250 |  | DIP | PUB-022 PUB-023 | [LSSPeriodData] [LSSTotalsData] | SUPC, SDSC, ADSC, | DIP sends PUB-022 and PUB-023 to Supplier and Data Service |  | N
| SUPC receives PUB-022 NOTE: IF-022 does not contain any data item related to the Settlement Run Number | 33 | BP005 | 260 | MHHS-BR-SU-043 | DIP | PUB-022 | [LSSPeriodData] | SUPC | Supplier receives the PUB-022 for: 01. Smart single MPAN 02. Advanced Import MPANs x 4 | Supplier receives PUB-022 [LSSPeriodData]. Confirms successful updates on downstream systems. | N
| SUPC receives PUB-023 NOTE: IF-023 does not contain any data item related to the Settlement Run Number | 34 | BP005 | 260 | MHHS-BR-SU-043 | DIP | PUB-023 | [LSSTotalsData] | SUPC | Supplier receives the PUB-023 for: 01. Smart single MPAN 02. Advanced Import MPANs x 4 | Supplier receives PUB-023 [LSSTotalsData]. Confirms successful updates on downstream systems. | N
| SDSC receives PUB-022 NOTE: IF-022 does not contain any data item related to the Settlement Run Number | 35 | BP005 | 120 | MHHS-BR-DS-077 MHHS-BR-DS-080 | DIP | PUB-022 | [LSSPeriodData] | SDSC | Data Service receives the PUB-022 for: 01. Smart single MPAN | Data Service receives PUB-022 [LSSPeriodData]. Confirms successful updates on downstream systems. | N
| SDSC receives PUB-023 NOTE: IF-023 does not contain any data item related to the Settlement Run Number | 36 | BP005 | 120 | MHHS-BR-DS-077 MHHS-BR-DS-080 | DIP | PUB-023 | [LSSTotalsData] | SDSC | Data Service receives the PUB-023 for: 01. Smart single MPAN | Data Service receives PUB-023 [LSSTotalsData]. Confirms successful updates on downstream systems. | N
| ADSC receives PUB-022 NOTE: IF-022 does not contain any data item related to the Settlement Run Number | 37 | BP005 | 120 | MHHS-BR-DS-077 | DIP | PUB-022 | [LSSPeriodData] | ADSC | Data Service receives the PUB-022 for: 02. Advanced Import MPANs x 4 | Data Service receives PUB-022 [LSSPeriodData]. Confirms successful updates on downstream systems. | N
| ADSC receives PUB-023 NOTE: IF-023 does not contain any data item related to the Settlement Run Number | 38 | BP005 | 120 | MHHS-BR-DS-077 | DIP | PUB-023 | [LSSTotalsData] | ADSC | Data Service receives the PUB-023 for: 02. Advanced Import MPANs x 4 | Data Service receives PUB-023 [LSSTotalsData]. Confirms successful updates on downstream systems. | N
| LSS Internal Calculations are validated | 39 |  |  |  | Helix |  |  | Helix | LSS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots from Helix Tool | Y
| IF-021 Data in queue (Actuals) | 40 | BP005 | 220 | MHHS-BR-RD-019 | SDSC | PUB-021 | [ActivePower] & [DI-015] = W | MDS | The PUB-021 data is now queued awaiting the next Calendar Run for the UTC Settlement Day [D] which will be processed as per the published calendar and timetable. |  | N
| II Settlement Run Commences | 41
|  | 42 | BP019 | 15 | MHHSP-07 MHHSP-BRS008-MDS-07 | DIP | PUB-021 | [ActivePower] & [DI-015] = W | MDS | MDS receives the PUB-021 for: 01. Smart single MPAN 02. Advanced Import MPANs x 4 |  | N
MDS Run Starts
| MDS Run | 43 |  |  | MHHSP-14 MHHSP-BRS008-MDS-14 MHHSP-23 MHHSP-BRS008-MDS-23 MHHSP-27 MHHSP-BRS008-MDS-27 MHHSP-30 MHHSP-BRS008-MDS-30 METH007, ID-9700 METH007, ID-9836 | MDS | REP-002 REP-002A REP-002B |  | MDS | MDS Run progresses, reports generated as normal |  | N
| MDS issues reports to parties | 44 | BP019 | 105 | MHHSP-14 MHHSP-23 MHHSP-27 MHHSP-30 METH007, ID-9700 METH007, ID-9836 | MDS | REP-002 REP-002A REP-002B |  | DIP | MDS Run completes and MDS reports are submitted for publication via DIP | http 201 response from DIP | N
|  | 45 | BP019 | 85 | REP-002 REP-002A REP-002B | DIP | REP-002 REP-002A REP-002B |  | SUPC, LDSO | DIP submits Reports for Publication to the Supplier and LDSO |  | N
|  | 46 | BP019 | N/A | REP-002 REP-006 REP-009 | DIP | REP-002 REP-006 REP-009 |  | SUPC | Supplier receives published MDS Reports | Supplier receives MDS Reports and captures test evidence (captures MDS Run Number (field DI-161 - Run Number) from report messages. | Y
|  | 47 | BP019 | N/A | REP-002A REP-002B REP-008 | DIP | REP-002A REP-002B REP-008 |  | LDSO | LDSO receives published MDS Reports | LDSO receives MDS Reports and captures test evidence (captures MDS Run Number (field DI-161 - Run Number) from report messages. | Y
| MDS Run Ends Internal MDS Calculations are validated | 48 |  |  | MHHSP-BRS008-MDS-09, MHHSP-BRS008-MDS-10 | Helix |  |  | Helix | MDS Run completes and Helix validates internal calculations and verifies that MDS: a) accessed the published Industry Standing Data (ISD) b) used the most recent ISD Data applicable to the Settlement Day and Settlement Period being processed including LLF data. | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y
|  | 49 | BP019 | 115 | VAS Requirement | MDS | HELIX-IF-11.1-MDS2DAH-AggregatedLineLosses HELIX-IF-10.1-MDS2DAH-AggregatedConsumption |  | VAS | Data that has passed validation as part of the MDS run is passed to the VAS for the Volume Allocation Run (VAR) |  | N
| VAS Run Starts VAS Reports are produced | 50 | BP020 | 75 | MHHSP-51, MHHSP-52, MHHSP-55, MHHSP-56, MHHSP-57, MHHSP-BRS009-VAS-51, MHHSP-BRS009-VAS-55, MHHSP-BRS009-VAS-56, REP-003, REP-003A, REP-004, REP-007, REP-D0397 (REP-D0081), REP-D0398 (REP-D0266), REP-D0399 (REP-D0276), REP-D0400 (REP-D0296) | VAS | REP-003, REP-003A, REP-004, REP-007, REP-D0397 (REP-D0081), REP-D0398 (REP-D0266), REP-D0399 (REP-D0276), REP-D0400 (REP-D0296) |  | DIP, DTN | VAS produces Reports for Publication via the DIP, or DTN, as applicable |  | N
| VAS issues reports to parties | 51 | BP020 |  | REP-003 | VAS | REP-003 |  | DIP | VAS issues REP-003 'BM Unit Allocated Demand Volumes to Suppliers' to DIP | http 201 response from DIP | N
|  | 52 | BP020 |  | REP-003 | DIP | REP-003 |  | SUPC | Supplier receives REP_003 'BM Unit Allocated Demand Volumes to Suppliers' ' Report | Supplier receives VAS Report and captures test evidence (captures VAS Run Number (field DI-161 - Run Number) from report messages. | Y
|  | 53 | BP020 |  | REP-003A | VAS | REP-003A |  | DIP | VAS issues REP-003A 'Aggregated BM Unit Allocated Demand Volumes to Suppliers' to DIP | http 201 response from DIP | N
|  | 54 | BP020 |  | REP-003A | DIP | REP-003A |  | SUPC | Supplier receives REP_003A 'Aggregated BM Unit Allocated Demand Volumes to Suppliers' Report | Supplier receives VAS Report and captures test evidence (captures VAS Run Number (field DI-161 - Run Number) from report messages. | Y
|  | 55 | BP020 |  | REP-004 | VAS | REP-004 |  | DIP | VAS issues REP-004 'Supplier Deemed Take Report ' to DIP | http 201 response from DIP | N
|  | 56 | BP020 |  | REP-004 | DIP | REP-004 |  | SUPC | Supplier receives REP_004 'Supplier Deemed Take Report ' Report | Supplier receives VAS Report and captures test evidence (captures VAS Run Number (field DI-161 - Run Number) from report messages. | Y
|  | 57 | BP020 |  | REP-007 | VAS | REP-007 |  | DIP | VAS issues REP-007 'VAS Exception Report to Suppliers' to DIP | http 201 response from DIP | N
|  | 58 | BP020 |  | REP-007 | DIP | REP-007 |  | SUPC | Supplier receives REP_007 'VAS Exception Report to Suppliers' Report | Supplier receives VAS Report and captures test evidence (captures VAS Run Number (field DI-161 - Run Number) from report messages. | Y
|  | 59 | BP020 |  | REP-D0397 (REP-D0081) | VAS | D0397 (D0081) |  | SUPC | VAS issues out D0397 (D0081) to Supplier |  | N
|  | 60 | BP020 |  | REP-D0397 (REP-D0081) | DTN | D0397 (D0081) |  | SUPC | Supplier receives D0397 (D0081) via DTN | Supplier receives VAS Report and captures test evidence (captures VAS Run Number (field J1087 - Run Number) from report messages. | Y
|  | 61 | BP020 |  | REP-D0398 (REP-D0266) | VAS | D0398 (D0266) |  | SUPC | VAS issues out D0398 (D0266) to Supplier |  | N
|  | 62 | BP020 |  | REP-D0398 (REP-D0266) | DTN | D0398 (D0266) |  | SUPC | Supplier receives D0398 (D0266) via DTN | Supplier receives VAS Report and captures test evidence (captures VAS Run Number (field J1087 - Run Number) from report messages. | Y
|  | 63 | BP020 |  | REP-D0399 (REP-D0276) | VAS | D0399 (D0276) |  | SUPC | VAS issues out D0399 (D0276) to Supplier |  | N
|  | 64 | BP020 |  | REP-D0399 (REP-D0276) | DTN | D0399 (D0276) |  | SUPC | Supplier receives D0399 (D0276) via DTN | Supplier receives VAS Report and captures test evidence (captures VAS Run Number (field J1087 - Run Number) from report messages. | Y
|  | 65 | BP020 |  | REP-D0400 (REP-D0296) | VAS | D0400 (D0296) |  | SUPC | VAS issues out D0400 (D0296) to Supplier |  | N
|  | 66 | BP020 |  | REP-D0400 (REP-D0296) | DTN | D0400 (D0296) |  | SUPC | Supplier receives D0400 (D0296) via DTN | Supplier receives VAS Report and captures test evidence (captures VAS Run Number (field J1087 - Run Number) from report messages. | Y
| VAS Run Ends Internal VAS Calculations are validated | 67 |  |  |  | Helix |  |  | Helix | VAS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y
| BSCCorequest that Helix trigger the MDS re-run. MHHSP-BRS008-MDS-03 | 68 | BP019 | 150 | MHHSP-BRS008-MDS-03 | Operator Portal |  |  | Helix | From the Operator Portal UI, Helix trigger the MDS re-run. | MDS should re-run successfully. Test evidence is captured (logs/screenshots) | Y
|  | 69 |  |  | MHHSP-BRS008-MDS-03 | Operator Portal |  |  | Helix | Helix compares the new MDS Run Number to the original. Run number must have been incremented by one. | MDS Run Number must have been incremented by one. Test evidence captured (screen shot) which must include date and time stamp. | Y
| MDS issues reports to parties | 70 | BP019 | 105 | MHHSP-14 MHHSP-BRS008-MDS-14 MHHSP-23 MHHSP-BRS008-MDS-23 MHHSP-27 MHHSP-BRS008-MDS-27 MHHSP-30 MHHSP-BRS008-MDS-30 METH007, ID-9700 METH007, ID-9836 | MDS | REP-002 REP-002A REP-002B |  | DIP | MDS Run completes and MDS reports are submitted for pubplication publication via DIP | http 201 response from DIP | Y N
|  | 71 | BP019 | 85 | REP-002 REP-002A REP-002B | DIP | REP-002 REP-002A REP-002B |  | SUPC, LDSO | DIP submits Reports for Publication to the Supplier and LDSO |  | N
|  | 72 | BP019 | N/A | REP-002 | DIP | REP-002 |  | SUPC | Supplier receives published MDS Reports and confirms the Settlement Run Number (field DI-161) matches the re-run settlement run number captured above. | Supplier receives MDS Reports and confirms the Settlement Run Number to be correct. Test evidence is captured (screenshots) | Y
|  | 73 | BP019 | N/A | REP-002A REP-002B | DIP | REP-002A REP-002B |  | LDSO | LDSO receives published MDS Reports and confirms the Settlement Run Number (field DI-161) matches the re-run settlement run number captured above. | LDSO receives MDS Reports and confirms the Settlement Run Number to be correct. Test evidence is captured (screenshots) | Y
| MDS Run Ends Internal MDS Calculations are validated | 74 | BP019 |  |  | Helix |  |  | Helix | MDS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y
|  | 75 | BP019 | 115 |  | MDS | HELIX-IF-11.1-MDS2DAH-AggregatedLineLosses HELIX-IF-10.1-MDS2DAH-AggregatedConsumption |  | VAS | Data that has passed validation as part of the MDS run is passed to the VAS for the Volume Allocation Run (VAR) |  | N
| BSCCo Request that Helix trigger a VAS re-run. | 76 | BP020 | 140 | MHHSP-05 (MHHSP-BRS009-VAS-05) | Operator Portal |  |  | Helix | From the Operator Portal UI, Helix trigger the VAS re-run. | VAS should re-run successfully. Test evidence is captured (logs/screenshots) | Y
|  | 77 |  |  | MHHSP-05 (MHHSP-BRS009-VAS-05), MHHSP-BRS009-VAS-54 | Operator Portal |  |  | Helix | Helix compares the new VAS Run Number to the original. Run number must have been incremented by one. | VAS Run Number must have been incremented by one. Test evidence captured (screen shot) and must include date and time stamp . | Y
| VAS Run Starts VAS Reports are produced | 78 | BP020 | 75 | MHHSP-51, MHHSP-52, MHHSP-55, MHHSP-56, MHHSP-57, MHHSP-BRS009-VAS-51, MHHSP-BRS009-VAS-54, MHHSP-BRS009-VAS-56, REP-003, REP-003A, REP-004, REP-007, REP-D0397 (REP-D0081), REP-D0398 (REP-D0266), REP-D0399 (REP-D0276), REP-D0400 (REP-D0296) | VAS | REP-003, REP-003A, REP-004, REP-007, REP-D0397 (REP-D0081), REP-D0398 (REP-D0266), REP-D0399 (REP-D0276), REP-D0400 (REP-D0296) |  | DIP, DTN | VAS produces Reports for Publication via the DIP, or DTN, as applicable |  | N
| VAS issues reports to parties | 79 | BP020 |  | REP-003 | VAS | REP-003 |  | DIP | VAS issues REP-003 'BM Unit Allocated Demand Volumes to Suppliers' to DIP | http 201 response from DIP | N
|  | 80 | BP020 |  | REP-003 | DIP | REP-003 |  | SUPC | Supplier receives REP_003 'BM Unit Allocated Demand Volumes to Suppliers' ' Report and confirms the Settlement Run Number (field DI-161) matches the re-run VAS settlement run number captured above. | Supplier receives VAS Report and confirms the VAS Settlement Run Number to be correct. Test evidence is captured (screenshots) | Y
|  | 81 | BP020 |  | REP-003A | VAS | REP-003A |  | DIP | VAS issues REP-003A 'Aggregated BM Unit Allocated Demand Volumes to Suppliers' to DIP | http 201 response from DIP | N
|  | 82 | BP020 |  | REP-003A | DIP | REP-003A |  | SUPC | Supplier receives REP_003A 'Aggregated BM Unit Allocated Demand Volumes to Suppliers' Report and confirms the Settlement Run Number (field DI-161) matches the re-run VAS settlement run number captured above. | Supplier receives VAS Report and confirms the VAS Settlement Run Number to be correct. Test evidence is captured (screenshots) | Y
|  | 83 | BP020 |  | REP-004 | VAS | REP-004 |  | DIP | VAS issues REP-004 'Supplier Deemed Take Report ' to DIP | http 201 response from DIP | N
|  | 84 | BP020 |  | REP-004 | DIP | REP-004 |  | SUPC | Supplier receives REP_004 'Supplier Deemed Take Report ' Report and confirms the Settlement Run Number (field DI-161) matches the re-run VAS settlement run number captured above. | Supplier receives VAS Report and confirms the VAS Settlement Run Number to be correct. Test evidence is captured (screenshots) | Y
|  | 85 | BP020 |  | REP-007 | VAS | REP-007 |  | DIP | VAS issues REP-007 'VAS Exception Report to Suppliers' to DIP | http 201 response from DIP | N
|  | 86 | BP020 |  | REP-007 | DIP | REP-007 |  | SUPC | Supplier receives REP_007 'VAS Exception Report to Suppliers' Report and confirms the Settlement Run Number (field DI-161) matches the re-run VAS settlement run number captured above. | Supplier receives VAS Report and confirms the VAS Settlement Run Number to be correct. Test evidence is captured (screenshots) | Y
|  | 87 | BP020 |  | REP-D0397 (REP-D0081) | VAS | D0397 (D0081) |  | SUPC | VAS issues out D0397 (D0081) to Supplier |  | N
|  | 88 | BP020 |  | REP-D0397 (REP-D0081) | DTN | D0397 (D0081) |  | SUPC | Supplier receives D0397 (D0081) via DTN and confirms the Settlement Run Number (field J1087) matches the re-run VAS settlement run number captured above. | Supplier receives VAS Report and confirms the VAS Settlement Run Number to be correct. Test evidence is captured (screenshots) | Y
|  | 89 | BP020 |  | REP-D0398 (REP-D0266) | VAS | D0398 (D0266) |  | SUPC | VAS issues out D0398 (D0266) to Supplier |  | N
|  | 90 | BP020 |  | REP-D0398 (REP-D0266) | DTN | D0398 (D0266) |  | SUPC | Supplier receives D0398 (D0266) via DTN and confirms the Settlement Run Number (field J1087) matches the re-run VAS settlement run number captured above. | Supplier receives VAS Report and confirms the VAS Settlement Run Number to be correct. Test evidence is captured (screenshots) | Y
|  | 91 | BP020 |  | REP-D0399 (REP-D0276) | VAS | D0399 (D0276) |  | SUPC | VAS issues out D0399 (D0276) to Supplier |  | N
|  | 92 | BP020 |  | REP-D0399 (REP-D0276) | DTN | D0399 (D0276) |  | SUPC | Supplier receives D0399 (D0276) via DTN and confirms the Settlement Run Number (field J1087) matches the re-run VAS settlement run number captured above. | Supplier receives VAS Report and confirms the VAS Settlement Run Number to be correct. Test evidence is captured (screenshots) | Y
|  | 93 | BP020 |  | REP-D0400 (REP-D0296) | VAS | D0400 (D0296) |  | SUPC | VAS issues out D0400 (D0296) to Supplier |  | N
|  | 94 | BP020 |  | REP-D0400 (REP-D0296) | DTN | D0400 (D0296) |  | SUPC | Supplier receives D0400 (D0296) via DTN and confirms the Settlement Run Number (field J1087) matches the re-run VAS settlement run number captured above. | Supplier receives VAS Report and confirms the VAS Settlement Run Number to be correct. Test evidence is captured (screenshots) | Y
| VAS Run Ends Internal VAS Calculations are validated | 95 |  |  |  | Helix |  |  | Helix | VAS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y

## ST0033 - TC02
No. | Test Case Id |  |  |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
2 | ST0033 TC02 |  |  |  |  | 7.2 7.2.1 |  | ST0033 - VAS Audit Re-run | ST0033 - TC02 | MPAN Data Requirements: This test case has no specific MPAN requirements. It does, however, require that a previous settlement day run completed (RF RUN) and that the MDS and VAS Reports from that run are available as test evidence. | Traditional Smart Advanced Unmetered Various, as per normal settlement run | Traditional Smart Advanced Unmetered Various, as per normal settlement run | UTC Settlement Day [D]
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
ST0033 - VAS Audit Re-Run | Calendar Check | 1 Pre-Req | [7 empty] | Test Settlement Calendar is fully operational for the UTC Settlement Day (s). For the purposes of this test the following is assumed: UTC Settlement Day = [D] II Run is UTC Settlement Day + 2WD SF Run is UTC Settlement Day + 5WD RF Run is UTC Settlement Day + 8WD |  | N
This test case covers the functional testing of both the MDS Audit Re-run and the VAS Audit Re-run requirement.
| MPAN Data Check | 2 Pre-Req | [7 empty] | MPAN Data Requirements: This test case has no specific MPAN requirements. It does, however, require that a previous settlement day run completed (RF RUN) and that the MDS and VAS Reports from that run are available as test evidence. |  | N
| Precursor to MDS Audit Re-run | 3 | [6 empty] | SUPC | SUPC identifies Settlement Day for which Settlement runs have completed successfully and for which MDS reports are available. REP-002, REP-002A, REP-002B, REP-006, REP-008, REP-009 SUPC captures those MDS reports for later comparison. | MDS reports from selected completed Settlement run day are captured as test evidence | Y
| BSCCo request MDS Audit Re-run for SF Settlement Run in respect of setllement day [D]. Audit re-run is triggered by Helix using Operator Portal UI MHHSP-BRS008-MDS-04 | 4 |  |  | MHHSP-BRS008-MDS-04 MHHSP-BRS008-MDS-23 | Operator Portal |  |  | Helix | Helix is requested to re-run a specific MDS run for audit purposes. Helix identifies the given run type, e.g. "MDS run" and associated parameters (e.g. run type and settlement run date) in the Operator Portal, making note of the current Run Number. Helix triggers the re-run. | MDS should re-run successfully. Test evidence is captured (logs/screenshots) | Y
|  | 5 |  |  | MHHSP-BRS008-MDS-04 MHHSP-BRS008-MDS-23 | Operator Portal |  |  | Helix | Helix compares the new MDS Run Number to the original. Run number must have been incremented by one. | MDS Run Number must have been incremented by one. Test evidence captured (screen shot) and must include date and time stamp. | Y
| MDS Run Starts MDS Reports are produced | 6 | BP019 |  | MHHSP-BRS008-MDS-14 MHHSP-BRS008-MDS-23 MHHSP-BRS008-MDS-27 MHHSP-BRS008-MDS-30 METH007, ID-9700 METH007, ID-9836 REP-002, REP-002A, REP-002B, REP-006, REP-008, REP-009 | MDS |  |  | DIP | MDS produces Reports for Publication via the DIP REP-002, REP-002A, REP-002B, REP-006, REP-008, REP-009 |  | N
|  | 7 | BP019 | 85 | REP-002 REP-002A REP-002B REP-006 REP-008 REP-009 | DIP | REP-002 REP-002A REP-002B REP-006 REP-008 REP-009 |  | SUPC, LDSO | DIP submits Reports for Publication to the Supplier and LDSO |  | N
|  | 8 | BP019 | N/A | REP-002 REP-006 REP-009 | DIP | REP-002 REP-006 REP-009 |  | SUPC | Supplier receives published MDS Reports | Supplier receives MDS Reports and captures test evidence (captures MDS Run Number (field DI-161 - Run Number) from report messages. | Y
|  | 9 | BP019 | N/A | REP-002 REP-006 REP-009 | DIP | REP-002 REP-006 REP-009 |  | SUPC | Supplier compares MDS reports to the originals and verifies they are identical in content | Supplier verifies the re-run reports exactly match those from the original run and that they are successfully processed by downstream systems. Test evidence is captured (screen shots, logs, etc) | Y
|  | 10 | BP019 | N/A | REP-002A REP-002B REP-008 | DIP | REP-002A REP-002B REP-008 |  | LDSO | LDSO receives published MDS Reports | LDSO receives MDS Reports and captures test evidence (captures MDS Run Number (field DI-161 - Run Number) from report messages. | Y
|  | 11 | BP019 | N/A | REP-002A REP-002B REP-008 | DIP | REP-002A REP-002B REP-008 |  | LDSO | LDSO compares MDS reports to the originals and verifies they are identical in content | LDSO verifies the re-run reports exactly match those from the original run and that they are successfully processed by downstream systems. Test evidence is captured (screen shots, logs, etc) | Y
| MDS Run Ends Internal MDS Calculations are validated | 12 |  |  | MHHSP-BRS008-MDS-09, MHHSP-BRS008-MDS-10 | Helix |  |  | Helix | MDS Run completes and Helix validates internal calculations and verifies that MDS: a) accessed the published Industry Standing Data (ISD) b) used the most recent ISD Data applicable to the Settlement Day and Settlement Period being processed including LLF data. | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y
| Precursor to VAS Report Audit Re-run | 13 |  |  |  | SUPC |  |  | SUPC | SUPC identifies Settlement Day for which Settlement runs have completed successfully and for which VAS reports are available. REP-003, REP-003A, REP-004, REP-007, REP-D0397 (REP-D0081), REP-D0398 (REP-D0266), REP-D0399 (REP-D0276), REP-D0400 (REP-D0296) SUPC captures those VAS reports for later comparison. | VAS reports from selected completed Settlement run day are captured as test evidence | Y
| BSCCo request VAS Audit Re-run for SF Settlement Run in respect of setllement day [D]. Audit re-run is triggered by Helix using Operator Portal UI MHHSP-BRS009-VAS-06 | 14 |  |  | MHHSP-06 (MHHSP-BRS009-VAS-06) MHHSP-BRS009-VAS-06 MHHSP-BRS009-VAS-54 | Operator Portal | MHHSP-BRS009-VAS-06 MHHSP-BRS009-VAS-54 |  | Helix | Helix is requested to re-run a specific VAS run for audit purposes. Helix identifies the given run type, e.g. "VAS run" and associated parameters (e.g. run type and settlement run date) in the Operator Portal, making note of the current Run Number. Helix triggers the re-run. | VAS should re-run successfully. Test evidence is captured (logs/screenshots) | Y
|  | 15 |  |  | MHHSP-06 (MHHSP-BRS009-VAS-06) MHHSP-BRS009-VAS-54 | Operator Portal | MHHSP-BRS009-VAS-06 MHHSP-BRS009-VAS-54 |  | VAS | Helix compares the new VAS Run Number to the original. Run number must have been incremented by one. | VAS Run Number must have been incremented by one. Test evidence captured (screen shot) and must include date and time stamp. | Y
| VAS Run Starts VAS Reports are produced | 16 | BP020 | 75 | MHHSP-51, MHHSP-52, MHHSP-55, MHHSP-56, MHHSP-57, MHHSP-BRS009-VAS-51, MHHSP-BRS009-VAS-55, MHHSP-BRS009-VAS-56, REP-003, REP-003A, REP-004, REP-007, REP-D0397 (REP-D0081), REP-D0398 (REP-D0266), REP-D0399 (REP-D0276), REP-D0400 (REP-D0296) | VAS | REP-003, REP-004, REP-007, REP-D0397 (REP-D0081), REP-D0398 (REP-D0266), REP-D0399 (REP-D0276), REP-D0400 (REP-D0296) |  | DIP, DTN | VAS produces Reports for Publication via the DIP, or DTN, as applicable |  | N
| VAS issues reports to parties | 17 | BP020 |  | REP-003 | VAS | REP-003 |  | DIP | VAS issues REP-003 'BM Unit Allocated Demand Volumes to Suppliers' to DIP | http 201 response from DIP | N
|  | 18 | BP020 |  | REP-003 | DIP | REP-003 |  | SUPC | Supplier receives REP_003 'BM Unit Allocated Demand Volumes to Suppliers' ' Report | Supplier receives VAS Report and captures it as test evidence. | Y
|  | 19 |  |  | REP-003 | SUPC | REP-003 |  | SUPC | SUPC compares the REP-003 report to the original REP-003 report to verify they are identical in content. Both the original and new reports have already been captured as test evidence. |  | N
|  | 20 | BP020 |  | REP-004 | VAS | REP-004 |  | DIP | VAS issues REP-004 'Supplier Deemed Take Report ' to DIP | http 201 response from DIP | N
|  | 21 | BP020 |  | REP-004 | DIP | REP-004 |  | SUPC | Supplier receives REP_004 'Supplier Deemed Take Report ' Report | Supplier receives VAS Report and captures it as test evidence. | Y
|  | 22 |  |  | REP-004 | SUPC | REP-004 |  | SUPC | SUPC compares the REP-004 report to the original REP-004 report to verify they are identical in content. Both the original and new reports have already been captured as test evidence. |  | N
|  | 23 | BP020 |  | REP-007 | VAS | REP-007 |  | DIP | VAS issues REP_007 'VAS Exception Report to Suppliers' Report to DIP | http 201 response from DIP | N
|  | 24 | BP020 |  | REP-007 | DIP | REP-007 |  | SUPC | Supplier receives REP_007 'VAS Exception Report to Suppliers' Report | Supplier receives VAS Report and captures it as test evidence. | Y
|  | 25 |  |  | REP-007 | SUPC | REP-007 |  | SUPC | SUPC compares the REP-007 report to the original REP-007 report to verify they are identical in content. Both the original and new reports have already been captured as test evidence. |  | N
|  | 26 | BP020 |  | REP-D0397 (REP-D0081) | VAS | D0397 (D0081) |  | DTN | VAS issues out D0397 (D0081) to DTN |  | N
|  | 27 | BP020 |  | REP-D0397 (REP-D0081) | DTN | D0397 (D0081) |  | SUPC | Supplier receives D0397 (D0081) | Supplier receives VAS Report and captures it as test evidence. | Y
|  | 28 |  |  | REP-D0397 (REP-D0081) | SUPC | D0397 (D0081) |  | SUPC | SUPC compares the D0397 (D0081) report to the original D0397 (D0081) report to verify they are identical in content. Both the original and new reports have already been captured as test evidence. |  | N
|  | 29 | BP020 |  | REP-D0398 (REP-D0266) | VAS | D0398 (D0266) |  | DTN | VAS issues out D0398 (D0266) to DTN |  | N
|  | 30 | BP020 |  | REP-D0398 (REP-D0266) | DTN | D0398 (D0266) |  | SUPC | Supplier receives D0398 (D0266) | Supplier receives VAS Report and captures it as test evidence. | Y
|  | 31 |  |  | REP-D0398 (REP-D0266) | SUPC | D0398 (D0266) |  | SUPC | SUPC compares the D0397 (D0081) report to the original D0397 (D0081) report to verify they are identical in content. Both the original and new reports have already been captured as test evidence. |  | N
|  | 32 | BP020 |  | REP-D0399 (REP-D0276) | VAS | D0399 (D0276) |  | DTN | VAS issues out D0399 (D0276) to DTN |  | N
|  | 33 | BP020 |  | REP-D0399 (REP-D0276) | DTN | D0399 (D0276) |  | SUPC | Supplier receives D0399 (D0276) | Supplier receives VAS Report and captures it as test evidence. | Y
|  | 34 |  |  | REP-D0399 (REP-D0276) | SUPC | D0399 (D0276) |  | SUPC | SUPC compares the D0399 (D0276) report to the original D0399 (D0276) report to verify they are identical in content. Both the original and new reports have already been captured as test evidence. |  | N
|  | 35 | BP020 |  | REP-D0400 (REP-D0296) | VAS | D0400 (D0296) |  | DTN | VAS issues out D0400 (D0296) to DTN |  | N
|  | 36 | BP020 |  | REP-D0400 (REP-D0296) | DTN | D0400 (D0296) |  | SUPC | Supplier receives D0400 (D0296) | Supplier receives VAS Report and captures it as test evidence. | Y
|  | 37 |  |  | REP-D0400 (REP-D0296) | SUPC | D0400 (D0296) |  | SUPC | SUPC compares the D0400 (D0296) report to the original D0400 (D0296) report to verify they are identical in content. Both the original and new reports have already been captured as test evidence. |  | N
| VAS Run Ends Internal VAS Calculations are validated | 38 |  |  |  | Helix |  |  | VAS | VAS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y

## DPCache_List of Test Scenarios (hidden)
Test Category | Test Scenario | Scenario Title | Test Cases Link | Test ID | Test Scenario Link | Status Date | Status | Test Title | Priority | Pre-Requisite Test Scenario
Advisory Notification | E2E-001 | SITFTS-001 - Advisory Notification | Click to See Test Cases | E2E-001 | Click to view Test | 2023-02-09 | WG Reviewed (Working Group Drops)​ | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Advisory Notification | E2E-E004 | E2E-E004 - Advisory Notification | Click to See Test Cases | E2E-004 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-G006 |  | Click to See Test Cases | E2E-006 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-E007 | E2E-E007 - Switch Request Objection | Click to See Test Cases | E2E-007 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Objection | E2E-D008 |  | Click to See Test Cases | E2E-008 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Successful | E2E-G012 | E2E-G012 - Switch Request Successful | Click to See Test Cases | E2E-012 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA
Switch Request Successful | E2E-E011 |  | Click to See Test Cases | E2E-011 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA