## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Front Cover (hidden)
SWITCHING PROGRAMME
E2E Test Scenarios
Reference: NCT-0045
Version: v0.3

## Change Control (hidden)
Confidentiality Statement
The information contained herein is for the purpose of the MHHS Programme. This document may not be copied, or communicated to a third party, or used, for any purpose other than that for which it is supplied without the express written consent of the MHHS Programme
Distribution List
Name | Organisation
Document History
Issue No. | Issue Date | Issued by | Change Description
0.1 | 2023-02-10 | Dean Bailey | First Draft & QA Checked
Reviewed By
Version | Date | Name | Title / Responsibility
0.1
Approvals
Version | Date | Name | Title / Responsibility

## Sheet1 (hidden)
(empty)

## Sheet2 (hidden)
Data returned for Distinct Count of Profile, 1 - Dual (First 1000 rows).
ListTestCases[Test Case Category] | ListTestCases[E2E Scenario] | ListTestCases[Test Case Id] | ListTestCases[Test Case Title] | ListTestCases[Domestic] | ListTestCases[Non Domestic] | ListTestCases[Smart] | ListTestCases[Non Smart] | ListTestCases[Associated Test Scenario Id] | ListTestCases[Pre-Requisite Test Case] | ListTestCases[Regression Tests] | ListTestCases[Profile] | ListTestCases[Unique ID]
Switch Request Objection | E2E-D001 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-004-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-004-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity)) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-G001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  | X | X | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-004-03 | Gaining Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-G001 | E2E-010-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-007-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-010-04 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-004-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-L001 | E2E-010-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-L001 | E2E-007-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-004-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-L001 | E2E-010-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-L001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Traditional - Gas, Smart Meter - Electricity) | X |  | X | X | E2E-010-L001 | E2E-007-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-004-06 | Losing Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-L001 | E2E-010-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Successful | E2E-D002 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-013-01 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-016-01 | Gaining Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-G001 | E2E-013-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-013-02 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-016-02 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-G001 | E2E-013-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-013-03 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-016-03 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-G001 | E2E-013-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-013-04 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-016-04 | Gaining Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-G001 | E2E-013-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-013-05 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-016-05 | Losing Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-L001 | E2E-013-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-013-06 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-016-06 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-L001 | E2E-013-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-013-07 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-016-07 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-L001 | E2E-013-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-013-08 | Losing Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-016-08 | Losing Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-L001 | E2E-013-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Withdrawal | E2E-D003 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-019-01 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-G001 | E2E-10-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-019-02 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-019-03 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-019-04 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-G001 | E2E-010-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-019-05 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-010-06 | LosingSupplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-019-06 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-019-07 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-019-08 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-L001 | E2E-010-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Annulment | E2E-D004 | E2E-007-01 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-010-01 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-022-01 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-007-02 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-010-02 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-022-02 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-007-03 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-010-03 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meter with Primary MPAN) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-022-03 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-007-04 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-G001 | NA |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-010-04 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic,Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-022-04 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-G001 | E2E-010-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-007-05 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-010-05 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-022-05 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-007-06 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-010-06 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-022-06 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-007-07 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-010-07 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic smart Meter with Primary MPAN) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-022-07 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-007-08 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-010-08 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-022-08 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-L001 | E2E-010-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4

## Summary (hidden)
Test Scenario View |  |  |  |  | Summary
Priority | Fuel Type | E2E Scenario | Profile | Test Cases | Priority | Fuel Type | Profile | Distinct Count of Profile | Distinct Count of E2E Scenario | Test Cases
1 |  |  |  |  | 1
| All |  |  |  |  | All
|  | E2E-GED-001 |  |  |  |  | Domestic, Smart Meter | 1 | 1 | 6
|  |  | Domestic, Smart Meter | 6 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  |  | Domestic, Traditional Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 1 | 3
|  |  | Non Domestic, Smart Meter | 3 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 5
|  |  | Non Domestic, Traditional Meter | 5 |  | All Total |  | 4 | 1 | 18
|  | E2E-GED-001 Total |  | 18 |  | Dual
| All Total |  |  | 18 |  |  | Domestic, Smart Meter | 1 | 4 | 14
| Dual | [5 empty] | Domestic, Traditional Meter | 1 | 4 | 14
|  | E2E-D001 |  |  |  |  | Non Domestic, Smart Meter | 1 | 4 | 14
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 4 | 14
|  |  | Domestic, Traditional Meter | 2 |  | Dual Total |  | 4 | 4 | 56
|  |  | Non Domestic, Smart Meter | 2 |  | Electricity
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Smart Meter | 1 | 6 | 18
|  | E2E-D001 Total |  | 8 |  |  | Domestic, Traditional Meter | 1 | 6 | 16
|  | E2E-D002 |  |  |  |  | Non Domestic, Smart Meter | 1 | 6 | 20
|  |  | Domestic, Smart Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 6 | 16
|  |  | Domestic, Traditional Meter | 8 |  | Electricity Total |  | 4 | 6 | 70
|  |  | Non Domestic, Smart Meter | 8 |  | Gas
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Domestic, Smart Meter | 1 | 7 | 17
|  | E2E-D002 Total |  | 32 |  |  | Domestic, Traditional Meter | 1 | 7 | 17
|  | E2E-D003 |  |  |  |  | Non Domestic, Smart Meter | 1 | 7 | 21
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 7 | 17
|  |  | Domestic, Traditional Meter | 2 |  | Gas Total |  | 4 | 7 | 72
|  |  | Non Domestic, Smart Meter | 2 |  | SMS
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Service management | 1 | 1 | 7
|  | E2E-D003 Total |  | 8 |  | SMS Total |  | 1 | 1 | 7
|  | E2E-D004 |  |  | 1 Total |  |  | 5 | 19 | 223
|  |  | Domestic, Smart Meter | 2 | 2
|  |  | Domestic, Traditional Meter | 2 |  | Dual
|  |  | Non Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 2 | 6
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  | E2E-D004 Total |  | 8 |  |  | Non Domestic, Smart Meter | 1 | 1 | 4
| Dual Total |  |  | 56 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 4
| Electricity |  |  |  |  | Dual Total |  | 4 | 2 | 18
|  | E2E-E001 |  |  |  | Electricity
|  |  | Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 10 | 15
|  |  | Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 9 | 14
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 9 | 13
|  | E2E-E001 Total |  | 10 |  | Electricity Total |  | 4 | 11 | 54
|  | E2E-E002 |  |  |  | Gas
|  |  | Domestic, Smart Meter | 10 |  |  | Domestic, Smart Meter | 1 | 11 | 16
|  |  | Domestic, Traditional Meter | 8 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 10 |  |  | Non Domestic, Smart Meter | 1 | 8 | 13
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 8 | 11
|  | E2E-E002 Total |  | 36 |  | Gas Total |  | 4 | 11 | 54
|  | E2E-E003 |  |  | 2 Total |  |  | 4 | 24 | 126
|  |  | Domestic, Smart Meter | 2 | Grand Total |  |  | 5 | 43 | 349
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E003 Total |  | 8
E2E-E004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E004 Total |  | 8
E2E-E005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E005 Total |  | 4
E2E-E009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E009 Total |  | 4
| Electricity Total |  |  | 70
Gas
E2E-G001
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G001 Total |  | 10
E2E-G002
|  |  | Domestic, Smart Meter | 8
|  |  | Domestic, Traditional Meter | 8
|  |  | Non Domestic, Smart Meter | 10
|  |  | Non Domestic, Traditional Meter | 8
|  | E2E-G002 Total |  | 34
E2E-G003
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G003 Total |  | 8
E2E-G004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G004 Total |  | 8
E2E-G005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G005 Total |  | 4
E2E-G006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G006 Total |  | 4
E2E-G010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G010 Total |  | 4
| Gas Total |  |  | 72
SMS
E2E-SMS-001
|  |  | Service management | 7
|  | E2E-SMS-001 Total |  | 7
| SMS Total |  |  | 7
1 Total |  |  |  | 223
2
Dual
E2E-D005
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-D005 Total |  | 16
E2E-D006
|  |  | Domestic, Smart Meter | 2
|  | E2E-D006 Total |  | 2
| Dual Total |  |  | 18
Electricity
E2E-E006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E006 Total |  | 4
E2E-E007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E007 Total |  | 4
E2E-E008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E008 Total |  | 4
E2E-E010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E010 Total |  | 4
E2E-E011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E011 Total |  | 4
E2E-E012
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E012 Total |  | 6
E2E-E013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E013 Total |  | 4
E2E-E014
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-E014 Total |  | 16
E2E-E015
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E015 Total |  | 2
E2E-E016
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-E016 Total |  | 4
E2E-E017
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  | E2E-E017 Total |  | 2
| Electricity Total |  |  | 54
Gas
E2E-G007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G007 Total |  | 4
E2E-G008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G008 Total |  | 4
E2E-G009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G009 Total |  | 4
E2E-G011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G011 Total |  | 4
E2E-G012
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G012 Total |  | 4
E2E-G013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 3
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G013 Total |  | 6
E2E-G014
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G014 Total |  | 4
E2E-G015
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-G015 Total |  | 16
E2E-G016
|  |  | Domestic, Smart Meter | 2
|  | E2E-G016 Total |  | 2
E2E-G017
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-G017 Total |  | 4
E2E-G018
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  | E2E-G018 Total |  | 2
| Gas Total |  |  | 54
2 Total |  |  |  | 126
Grand Total |  |  |  | 349

## How To Use (hidden)
How To Use
Contents
1. How to Navigate this document
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Overview of the Test Case worksheets
1. How to Navigate this document
This section aims to provide an overview on how to navigate through this workbook.
The workbook consists of a number of worksheets arranged in a hieracrchy working from left to right.
The 'List of Test Scenarios' is broken down into a 'List of Test Cases', which consist of individual Test Cases.
Within the 'List of Test Scenarios' worksheet each of the Scenarios has a hyperlink ('Click to See Test Cases') which when selected takes the user to the Test Cases associated to the selected scenario on the 'List of Test Cases' worksheet.
. | From here, the user can then navigate to a more detailed view of the Test Scenario by clicking on the 'Click to view Test' link
To return to the 'List of Test Scenarios' worksheet the user would select 'Back to list of Test Scenarios', which will return the user to the top of the List of Test Scenarios worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
This section aims to provide an overview of the information contained in the List of Test Scenarios worksheet
The List of 'Test Scenarios' worksheet details each Test Scenario that will be part of the testing phase and provides links to the scenario and list of test cases that make up the basic scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Scenario Category | A short title of the Scenario being defined
| E2E Scenario | A Unique reference for each Scenario (e.g. E2E-G001 is the first Gas Scenario)
| E2E Scenario Title | A Unique Title for each Test Scenario consisting of the E2E Scenario & Test Scenario Category
| Link | A link to the List of Test Cases appropriate to the Test Scenario
| Test ID | A scenario will require one or more Test Cases to deliver the Test Scenario. The same Test might be used in multiple scenarios. Each Test Case that delivers a particular scenario will be listed in the order they would be executed.
| Link | A link to each Test and Steps that will be used within the scenario
| Test Title | The title of the Test ID. This is defined on the individual Test Case worksheets.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Priority | Test Priority for any Risk Based Testing
| Pre-Requisite Test Scenario | The ID of the Test that must be executed prior to this one to complete a Test Scenario
| Comments | Any additional information regarding the Test Scenario will be provided here
| CSS | Indicates the number of steps the Test Case has defined that interact with CSS
| UK Link | Indicates the number of steps the Test Case has defined that interact with UK Link
| DES | Indicates the number of steps the Test Case has defined that interact with DES
| MPAS | Indicates the number of steps the Test Case has defined that interact with MPAS
| ECOES | Indicates the number of steps the Test Case has defined that interact with ECOES
| Smart Metering | Indicates the number of steps the Test Case has defined that interact with Smart Metering
| Gaining Shipper | Indicates the number of steps the Test Case has defined that interact with a Single Shipper or Gaining Shipper where the Test Scenario involves a two parties
| Losing Shipper | Indicates the number of steps the Test Case has defined that interact with a Losing Shipper where the Test Scenario involves a two parties
| Gas Transporter | Indicates the number of steps the Test Case has defined that interact with a GT or iGT
| Data Collector | Indicates the number of steps the Test Case has defined that interact with a DC
| Data Aggregator | Indicates the number of steps the Test Case has defined that interact with a DA
| MEM | Indicates the number of steps the Test Case has defined that interact with a MEM
| MAP | Indicates the number of steps the Test Case has defined that interact with a MAP
| DNO | Indicator as to whether the Test Case defined has steps that interact with a DNO/iDNO
| Gaining Supplier | Indicates the number of steps the Test Case has defined that interact with a single Supplier or a Gaining Supplier where the Test Scenario involves a two parties
| Losing Supplier | Indicates the number of steps the Test Case has defined that interact with a Losing Supplier where the Test Scenario involves a two parties
Third-Party IT Provider
3. Overview of the 'List of Test Cases' worksheet
This section aims to provide an overview of the information contained in the 'List of Test Cases' worksheet
The List of Test Cases details each variation of the Test Scenarios as Test Cases that will form part of the testing phase, and provides links to the Tests & the steps that make up the each scenario. Which Test Cases an E2E participant needs to execute will depend on the Licensed Parties profile
(see '1. How to Navigate this document' for details on how to navigate to & from the List of Test Cases worksheet)
Where Switching functionality is being tested there will be a matching 'GAIN' and a 'LOSE' Test Case. When executing a Test Case with a paired Supplier, the gaining supplier will execute the GAIN test case, and the losing supplier will execute the matching LOSE test case.
A green line separates the GAIN and LOSE test cases for the same scenario.
A blue line separates each Test Scenario, and the Test Case ID will indicate the Tests that make up a single Test Case for a Scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Case Category | The short title of the Scenario that the Test Case variations cover
| E2E Scenario | The Test Scenario ID of the Scenario that the Test Case variations cover
| Test Case Id | The Test Case ID is a combination of the Test Scenario ID and a unique reference to link each of the Tests that make up the Test Case
| Associated Test Id | Details the actual Test ID
| Link | A hyperlink to each Test Case worksheet that forms part of the Test Case
| Test Case Title | Details the Title of the Test Case from the associated Test Case worksheet, plus the variants in place for this particular Test Case.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Day(s) | Details the number of Days each Switch Test will be assigned. This will be blank where the number of days is not relevant to the Test Case
| Domestic | This will be marked with an 'X' where the Test Case is intended for a Domestic Customer.
| Non Domestic | This will be marked with an 'X' where the Test Case is intended for a Non Domestic Customer.
| OFAF | This will be marked with an 'X' where the Test Case is intended for a Switch of more than one Fuel Type or more than one Meter of the same Fuel Type to ensure the 'One Fail, All Fail' switching rule. The Test Case may not test a Failure in all cases.
| Related MPAN | This will be marked with an 'X' where the Test Case is intended to include related MPANs (Electricity only).
| Pre-Requisite Test Case | Details the Test ID that must have been executed prior to this Test
| Profile | The profile describes the options selected for each Test Case (i.e. where X's have been placed in the previous fields)
| Requirements | The requirements listed are the unique Abacus references documented against the in the relevant Test Case Worksheet
4. Overview of the Test Case worksheets
This section aims to provide an overview of the information contained in each of the Test Case worksheets. For example worksheet E2E-002.
Each Test Case worksheet gives an overview of the Case and the agreed steps that need to be executed. These will be loaded to Jira to form each Test Case per LP and the LP will then be able to expand on the Test Steps within Jira to make them more pertinent to the specific LP's systems and processes.
(see '1. How to Navigate this document' for details on how to navigate to & from each Test Case worksheet)
| The following are the Test Case overview Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Scenario ID | The Test ID (as per the worksheet Name) that is used in the 'List of Test Scenarios' and 'List of Test Cases' worksheets to link Tests to Scenarios and Test Cases
| Title | The Short Title of the Test
| Description | An overview of the objectives of the Test
| Pre-Requisites | Any Pre-Requisites that need to be in place prior to this Test Case being executed
| Test Case Variable | A list of the Test Case variables that this particular Test should cater for.
| Mapped Requirements | A summary of the Abacus requirements that the Test Case covers
| Exception Codes | Exception Codes will not be applicable during E2E Testing, these will have been covered previously in SIT and/or UEPT
| The following are the Test Step Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Mapped Requirements | The Abacus requirement reference(s) that each step covers
| Step Title | A short title outlining the purpose of the step
| Evidence Required | A 'Y' or 'N' indicator to highlight whether the Test Participant would be expected to provide evidence for the step. An 'O' indicates evidence is optional based on whether the agents and registered and have agreed to provide support during testing.
| Step Description | A more detailed description of the purpose of the step
| Related System | The system where the step would be executed
| Pre-requisite | Any Pre-Requisites that this step is dependent upon
| Expected Result | A description of the outcome of this Step
| API (Inbound to CSS) | API details retained from the original SIT tests
| Route | Route details retained from the original SIT tests
| Webhook context (Outbound from CSS) | Webhook context details retained from the original SIT tests
| Event Type | Event Type details retained from the original SIT tests
| Acknowledgement Messages | Acknowledgement Message details retained from the original SIT tests
| Comments | Any additional information / comments regarding the step
At the bottom of each Test Case worksheet are the list of Test Cases where this Test Case is called.
| The following is a brief description of each field in this section: |  | Example:
| Field | Details
| No. | Incremental number for each linked Test Case
| Unique Test Id | The Unique Test ID from the 'List of Test Cases' worksheet for each Test Case where this Test Case is called
| Return to Test Case | A Hyperlink to return directly to the current Test within the Test Case in the 'List of Test Cases' worksheet
| Test Case Title | The Test Case Title from the 'List of Test Cases' worksheet of the Unique Test ID Test Case
| Test Case ID | The Test Case ID from the 'List of Test Cases' worksheet of the Test Case
| E2E Scenario | The E2E Scenario ID from the 'List of Test Cases' worksheet of the Test Case
| Test Case Category | The Test Case Category from the 'List of Test Cases' worksheet of the Test Case
List of Test Scenarios
List of Test Cases

## List MASTER (hidden)
High
Medium
Low
MPAN Ownership
Metering Changes
Meter to Bank
Trad
Smart
Advanced
Unmetered
In Progress
Blocked - Reqt Query
Drafted
Peer Reviewed
Rework
Design Reviewed
WG Reviewed (Working Group Drops)​
WG Approved
TMAG Approved

## Change Log
Date | Author | Release | Reason for change
2024-10-23 | SI Test Team | v0.1 | Initial draft
2024-11-15 | SI Test Team | V0.2 | Amendemenets made as per Industry consultaion
10th December 2024 | SI Test Team | V0.3 | TC02 - Changed Out of Hours to Inhours as we will not support out of hours testing
10th December 2024 | SI Test Team | V0.3 | Removed TC 4,5,6 13 & 14 as per Industry review comments - Incidents raised in Non MHHS supported systems dont require a ticket raising in SM.

## Scenario Overview
Scenario ID | MHHS-DEL3194 SITOPS SM01 - Incident Management Major Incident
Scenario Title | Incident Management - Major Incident
Theme | Theme 3 - Service Management
Description | Major Incident originating in MHHS supported system is raised by Service Users, Service Partners or tooling, Incident resolved by various Resolver groups either with or without a Change being required
Category | Major Incident Management
Creator | SI Test Team
Priority | High
Scenario size | Large
Design Document Ref | Service Definition Document v2.4 27/09/24 Low Level Service Design - Service Users v1.1 23/09/24 MHHS Service User - Operations Manual Draft - Section 4 NFR0314 - The DIP Service Provider shall ensure releases are controlled via a robust documented release management process NFR0301 - The DIP Service Provider shall put in incident and service requests procedures
Business Process
Boundaries | Raise, triage, assign, investigate, Resolve and Closure of Major Incident tickets Test steps aligned to the level of detail within SDD/LLSD No system changes will be implemented during this testing Note that any backlog of IF021 from a DIP outage will need to be considered for impact and resolution action.
Pre-Requisites | Service Users are registered on SM Portal
Test Case Variables | See table below
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Subject of Test | Raiser / support for the test
TC01/SC1 - no change | SIT_OPS_SM01_TC01 | SIT_OPS_SM01_TC01_DIP | Service Mngt - Major Incident Process - Closed manually before Day 5. | SDS, Service Users
TC02/SC2 - no change | SIT_OPS_SM01_TC02 | DIP Service Failure Out of Hours 90 mins) | Service Mngt - Major Incident Process - Closed automatically at DAY 5. | DIP, Service Users
TC03/SC3 - no change | SIT_OPS_SM01_TC03 | DIP Security Incident in working hours | Service Mngt - Major Incident Process Closed automatically at DAY 5. | DIP, Service Users
TC07/SC09 with Change | SIT_OPS_SM01_TC07 | VAS System Failure during Working Day as per settlement calendar | Service Mngt - Major Incident Process | SUPP, Service Users
TC08/SC10 - No change raise via telephone call | SIT_OPS_SM01_TC08 | MDS System Failure during Working Day as per settlement calendar | Service Mngt - Major Incident Process | LDSO (BUUK or SSEN), Service Users
TC09/SC11 - no change | SIT_OPS_SM01_TC09 | LSS System Failure during Working Day as per settlement calendar | Service Mngt - Major Incident Process | Adv Data Service, Service Users
TC10/SC12 No Change | SIT_OPS_SM01_TC10 | ISD incorrect Data going PPs In accordance with ISD timetable (monthly or fortnightly updates) | Service Mngt - Major Incident Process | LDSO, Service Users
TC11/SC13 No Change | SIT_OPS_SM01_TC11 | ISD System Failure In accordance with ISD timetable (monthly or fortnightly updates) | Service Mngt - Major Incident Process | SUPP, Service users
TC12/SC14 No Change | SIT_OPS_SM01_TC12 | DAH Failure | Service Mngt - Major Incident Process | Helix, Service users

## TC01 DIP No CR
No. |  | Test Case Id |  |  |  | Test Case Title
TC01 |  | SIT-OPS-SM01-TC01 |  |  |  | SIT-OPS SM01 TC01 DIP
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SIT_OPS_SM01_TC01_DIP | Raise case | 1 |  | SDD v2.4 - Section 6 LLSD v1.1 - Section 7 MHHS Service User - Operations Manual Draft - Section 4 | SDS |  | Note: This case needs to be raised for DIP Service failure in hours Service User SDS raises a case in the SM portal (CSM Service Catalog - Elexon Support) by selecting the 'Report a Service Issue' option and completing the following fields In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - SDS receiving http error message Description - SDS receiving http error message URL or related page section - insert if required Click submit Refer to Operations manual for Category drop down options DIP SP raise the case directly into Service Now Refer to Operations manual for Category drop down options | Case Reference displayed | Y
|  | 2 |  |  | Elexon Service Desk |  | Elexon Service Desk retrieve the case from the queue . The case undergoes review and 1st line triage to identify the correct SM function for the case to be assigned to Ticket status is set to New | Case is triaged within 15 mins Case is assessed as a Major Incident candidate and assigned to the Major Incident Manager | Y
| Prmote to MI | 3 |  |  | Major Incident Manager |  | Incident promotion request is reviewed by the Major Incident Manager performing validity checks as to whether a Major Incident by Major Incident Manager on a case by case basis Refer to operations manual for details on validity checks | Incident assessed as valid Major Incident | Y
|  | 4 |  |  | Major Incident Manager |  | Incident ticket promoted to Major Incident Severity = S1 Priority = P1 Status = In progress Refer to Operations manual for status options | Incident ticket updated correctly | Y
| Initial Comms | 5 |  |  | Major Incident Manager |  | Initial comms are sent via email to the MI Comms team list Note: The comms list recipients is tbc and will be a standard list os recipients The commination list for Major Incidents will be agreed at a later date and available in Service Now | Validate recipients receive the MI communication | Y
|  | 6 |  |  | Major Incident Manager |  | Major Incident Manager engages the MI team (Technical Resolver teams, product owner) and establishes MI bridge Comms for the engagement comms method - refer to Operations manual Note: Ticket assigned to Tech Resolver group (MIM remains accountable) | DIP Tech Resolver team/s, Product Mngr acknowledge and accept the issue | Y
|  | 7 |  |  | Service Desk |  | Incident update Communication issued to Service Users via ticket updates on the portal and email notification from Service now each time ticket is updated) Refer to Operations Manual for comms frequency and details | Incident updates received by Service Users | Y
| Circular required | 8 |  |  | Product Owner |  | Assess whether Industry Circular required Note: If Industry impacting then Circular sent - details to be provided in the Operations manual | Industry Circular is required | Y
|  | 9 |  |  | Major Incident Manager |  | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | BSC website is updated correctly | Y
| Investigate | 10 |  |  | Major Incident Manager / DIP Technical Resolvers |  | MI Investigation starts DIP Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident ticket status remains at In progress | Correct teams engaged - DIP SP | Y
|  | 11 |  |  | Major Incident Manager / DIP Technical Resolvers |  | Restorative actions identified, no Change required - Incident ticket status updated with fix details Mandatory Fields to be updated - tbc refer to operations manual Ticket status remains at In progress | Fix identified that does not require a Change to be raised for implementation, ticket is updated | Y
|  | 13 |  |  | DIP Tech Resolver Group / Major Incident Manager |  | Implement restorative actions | Actions to rectify the incident have been completed successfully | Y
| Resolve | 14 |  |  | DIP Tech Resolver Group / Major Incident Manager |  | Issue is deemed as being resolved, ticket is updated to reflect status of resolved and any other updates | Incident ticket reflects resolved | Y
|  | 15 |  |  | Product Owner |  | Assess whether Industry Circular required If Industry impacting then Circular sent - refer to Operations manual for further detail | Industry Circular is required and issued | Y
|  | 16 |  |  | Major Incident Manager |  | BSC website is update with Industry Circular details Refer to Ops Manual for details - where in BSC website will be located | BSC website is updated correctly | Y
| Comms | 17 |  |  | Service Desk |  | Communication sent to Service Users notifying them the incident is resolved (via ticket updates on portal, and email notification Service now) | Service user reviews actions taken, ticket status | Y
| Report | 18 |  |  | Service Desk / MIM / DIP Technical Resolvers |  | Post incident review takes place and Major Incident report produced and attached to ticket in Service Now within 3 WDs Refer to Operations Manual for further details | MI Report completed and attached to Incident ticket | Y
| Close | 19 |  |  | Service User (participant) |  | Service Users navigates to Case Ref# via Portal, and closes the ticket manually anytime before day 5. | Incident is manually closed by user | Y

## TC02 DIP No CR
No. |  | Test Case Id |  |  |  | Test Case Title | Meter Type | MPAN Type | Effective time
TC02 |  | SIT-OPS-SM01-TC02 |  |  |  | SIT-OPS SM01 TC02 DIP
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SIT_OPS_SM01_TC02_DIP | Raise case | 1 |  | SDD v2.4 section 6 LLSD v1.1 Section 7 MHHS Service User - Operations Manual Draft - Section 4 | DIP Monitoring triggers incident - case to raised directly into SN not auto generated during SIT ops |  | Note: This case needs to be raised by DIP monitoring triggers incident report for DIP Service failure in hours DIP SP raise the case directly into Service Now | Case Reference displayed | Y
|  | 2 |  |  | Elexon Service Desk |  | Elexon Service Desk retrieve the case from the queue . The case undergoes review and 1st line triage to identify the correct SM function for the case to be assigned to Ticket status is set to New | Case is triaged within 15 mins Case is assessed as a Major Incident candidate and assigned to the Major Incident Manager | Y
| Promote to MI | 3 |  |  | Major Incident Manager |  | Incident promotion request is reviewed by the Major Incident Manager performing validity checks as to whether a Major Incident by Major Incident Manager on a case by case basis Refer to operations manual for details on validity checks | Incident assessed as valid Major Incident | Y
|  | 4 |  |  | Major Incident Manager |  | Incident ticket promoted to Major Incident Severity = S1 Priority = P1 Status = In progress Refer to Operations manual for status options | Incident ticket updated correctly | Y
| Initial Comms | 5 |  |  | Major Incident Manager |  | Initial comms are sent via email to the MI Comms team list Note: The comms list recipients is tbc and will be a standard list os recipients The commination list for Major Incidents will be agreed at a later date and available in Service Now | Validate recipients receive the MI communication | Y
|  | 6 |  |  | Major Incident Manager |  | Major Incident Manager engages the MI team (Technical Resolver teams, product owner) and establishes MI bridge Comms for the engagement comms method - refer to Operations manual Note: Ticket assigned to Tech Resolver group (MIM remains accountable) | DIP Tech Resolver team/s, Product Mngr acknowledge and accept the issue | Y
|  | 7 |  |  | Service Desk |  | Incident update Communication issued to Service Users via ticket updates on the portal and email notification from Service now each time ticket is updated) Refer to Operations Manual for comms frequency and details | Incident updates received by Service Users | Y
| Circular required | 8 |  |  | Product Owner |  | Assess whether Industry Circular required Note: If Industry impacting then Circular sent - details to be provided in the Operations manual | Industry Circular is required | Y
|  | 9 |  |  | Major Incident Manager |  | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | BSC website is updated correctly | Y
| Investigate | 10 |  |  | Major Incident Manager / DIP Technical Resolvers |  | MI Investigation starts DIP Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident ticket status remains at In progress | Correct teams engaged - DIP SP | Y
|  | 11 |  |  | Major Incident Manager / DIP Technical Resolvers |  | Restorative actions identified, no Change required - Incident ticket status updated with fix details Mandatory Fields to be updated - tbc refer to operations manual Ticket status remains at In progress | Fix identified that does not require a Change to be raised for implementation, ticket is updated | Y
| Implement | 13 |  |  | DIP Tech Resolver Group / Major Incident Manager |  | Implement restorative actions | Actions to rectify the incident have been completed successfully | Y
| Resolved | 14 |  |  | DIP Tech Resolver Group / Major Incident Manager |  | Issue is deemed as being resolved, ticket is updated to reflect status of resolved and any other updates | Incident ticket reflects resolved | Y
|  | 15 |  |  | Product Owner |  | Assess whether Industry Circular required If Industry impacting then Circular sent - refer to Operations manual for further detail | Industry Circular is required and issued | Y
|  | 16 |  |  | Major Incident Manager |  | BSC website is update with Industry Circular details Refer to Ops Manual for details - where in BSC website will be located | BSC website is updated correctly | Y
| Comms | 17 |  |  | Service Desk |  | Communication sent to Service Users notifying them the incident is resolved (via ticket updates on portal, and email notification Service now) | Service user reviews actions taken, ticket status | Y
| Report | 18 |  |  | Service Desk / MIM / DIP Technical Resolvers |  | Post incident review takes place and Major Incident report produced and attached to ticket in Service Now within 3 WDs Refer to Operations Manual for further details | MI Report completed and attached to Incident ticket | Y
| Close | 19 |  |  | Service User (participant) |  | Service Users verify the issue is resolved and closes the incident ticket (ticket will be closed in 5 days automatically) | Incident is closed | Y

## TC03 DIP No CR
No. |  | Test Case Id |  |  |  | Test Case Title
TC03 |  | SIT-OPS-SM01-TC03 |  |  |  | SIT-OPS SM01 TC03 DIP
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SIT-OPS SM01 TC03 DIP | Raise case | 1 |  | SDD v2.4 section 6 LLSD v1.1 Section 7 MHHS Service User - Operations Manual Draft - Section 4 | DIP Monitoring triggers incident - case to raised directly into SN not auto generated during SIT ops |  | Note: This case needs to be raised by DIP monitoring triggers incident report for DIP Security incident within working hours DIP SP raise the case directly into Service Now | Case Reference displayed | Y
|  | 2 |  |  | Elexon Service Desk |  | Elexon Service Desk retrieve the case from the queue . The case undergoes review and 1st line triage to identify the correct SM function for the case to be assigned to Ticket status is set to New | Case is triaged within 15 mins Case is assessed as a Major Incident candidate and assigned to the Major Incident Manager | Y
| Promote to MI | 3 |  |  | Major Incident Manager |  | Incident promotion request is reviewed by the Major Incident Manager performing validity checks as to whether a Major Incident by Major Incident Manager on a case by case basis Refer to operations manual for details on validity checks | Incident assessed as valid Major Incident | Y
|  | 4 |  |  | Major Incident Manager |  | Incident ticket promoted to Major Incident Severity = S1 Priority = P1 Status = In progress Refer to Operations manual for status options | Incident ticket updated correctly | Y
| Initial Comms | 5 |  |  | Major Incident Manager |  | Initial comms are sent via email to the MI Comms team list Note: The comms list recipients is tbc and will be a standard list os recipients The commination list for Major Incidents will be agreed at a later date and available in Service Now | Validate recipients receive the MI communication | Y
|  | 6 |  |  | Major Incident Manager |  | Major Incident Manager engages the MI team (Technical Resolver teams, product owner) and establishes MI bridge Comms for the engagement comms method - refer to Operations manual Note: Ticket assigned to Tech Resolver group (MIM remains accountable) | DIP Tech Resolver team/s, Product Mngr acknowledge and accept the issue | Y
|  | 7 |  |  | Service Desk |  | Incident update Communication issued to Service Users via ticket updates on the portal and email notification from Service now each time ticket is updated) Refer to Operations Manual for comms frequency and details | Incident updates received by Service Users | Y
|  | 8 |  |  | Product Owner |  | Assess whether Industry Circular required Note: If Industry impacting then Circular sent - details to be provided in the Operations manual | Industry Circular is required | Y
|  | 9 |  |  | Major Incident Manager |  | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | BSC website is updated correctly | Y
| Investigate | 10 |  |  | Major Incident Manager / DIP Technical Resolvers |  | MI Investigation starts DIP Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident ticket status remains at In progress | Correct teams engaged - DIP SP | Y
|  | 11 |  |  | Major Incident Manager / DIP Technical Resolvers |  | Restorative actions identified, no Change required - Incident ticket status updated with fix details Mandatory Fields to be updated - tbc refer to operations manual Ticket status remains at In progress | Fix identified that does not require a Change to be raised for implementation, ticket is updated | Y
|  | 13 |  |  | DIP Tech Resolver Group / Major Incident Manager |  | Implement restorative actions | Actions to rectify the incident have been completed successfully | Y
| Resolve | 14 |  |  | DIP Tech Resolver Group / Major Incident Manager |  | Issue is deemed as being resolved, ticket is updated to reflect status of resolved and any other updates | Incident ticket reflects resolved | Y
|  | 15 |  |  | Product Owner |  | Assess whether Industry Circular required If Industry impacting then Circular sent - refer to Operations manual for further detail | Industry Circular is required and issued | Y
|  | 16 |  |  | Major Incident Manager |  | BSC website is update with Industry Circular details Refer to Ops Manual for details - where in BSC website will be located | BSC website is updated correctly | Y
| Comms | 17 |  |  | Service Desk |  | Communication sent to Service Users notifying them the incident is resolved (via ticket updates on portal, and email notification Service now) | Service user reviews actions taken, ticket status | Y
| Report | 18 |  |  | Service Desk / MIM / DIP Technical Resolvers |  | Post incident review takes place and Major Incident report produced and attached to ticket in Service Now within 3 WDs Refer to Operations Manual for further details | MI Report completed and attached to Incident ticket | Y
| Close | 19 |  |  | Service User (participant) |  | Service Users verify the issue is resolved and closes the incident ticket (ticket will be closed in 5 days automatically) | Incident is closed | Y

## TC07 VAS_With CR
No. |  | Test Case Id |  |  |  | Test Case Title
TC07 |  | SIT-OPS-SM01-TC07 |  |  |  | SIT-OPS SM01 TC07 VAS
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SIT-OPS SM01 TC07 VAS | Raise | 1 |  | SDD v2.4 section 6 LLSD v1.1 Section 7 MHHS Service User - Operations Manual Draft - Section 4 | Service User - Supplier role |  | Note: This case needs to be raised for a VAS System Failure Working Day as per settlement calendar Service User Supplier raises a case in the SM portal (CSM Service Catalog - Elexon Support) by selecting the 'Report a Service Issue' option and completing the following fields In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - no receipt of REP003 reports Description - no receipt of REP003 reports URL or related page section - insert if required Click submit Refer to Operations manual for for Category drop down options | Case Reference displayed | Y
| Triage | 2 |  |  | Elexon Service Desk |  | Elexon Service Desk retrieve the case from the queue . The case undergoes review and 1st line triage to identify the correct SM function for the case to be assigned to Ticket status is set to New | Case is triaged within 15 mins Case is assessed as a Major Incident candidate and assigned to the Major Incident Manager | Y
| Promote to MI | 3 |  |  | Major Incident Manager |  | Incident promotion request is reviewied by the Major Incident Manager performing validity checks as to whether a Major Incident by Major Incident Manager on a case by case basis Refer to operations manual for details on validity checks | Incident assessed as valid Major Incident | Y
|  | 4 |  |  | Major Incident Manager |  | Incident ticket promoted to Major Incident Severity = S1 Priority = P1 Status = In progress Refer to Operations manual for status options | Incident ticket updated correctly | Y
| Initial Comms | 5 |  |  | Major Incident Manager |  | Initial comms are sent via email to the MI Comms team list Note: The comms list recipients is tbc and will be a standard list os recipients The commication list for Major Incidents will be agreed at a later date and available in Service Now and Ops Manual | Validate recipients receive the MI communication | Y
|  | 6 |  |  | Major Incident Manager |  | Major Incident Manager engages the MI team (Technical Resolver teams, product owner) and establishes MI bridge Comms for the engagement comms method - refer to Operations manual Note: Ticket assigned to Tech Resolver group (MIM remains accountable) | VAS Tech Resolver team/s, Product Mngr acknowledge and accept the issue | Y
|  | 7 |  |  | Service Desk |  | Incident update Communication issued to Service Users via ticket updates on the portal and email notification from Service now each time ticket is updated) Refer to Operations Manual for comms frequency and details | Incident updates received by Service Users | Y
|  | 8 |  |  | Product Owner |  | Assess whether Industry Circular required Note: If Industry impacting then Circular sent - details to be provided in the Operations manual | Industry Circular is required | Y
| Circular | 9 |  |  | Major Incident Manager |  | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | BSC website is updated correctly | Y
| Investigate | 10 |  |  | Major Incident Manager /VAS SP Tech Resolver |  | MI Investigation starts VAS Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident ticket status remains at In progress | Correct teams engaged - VAS SP | Y
| Change required | 11 |  |  | Major Incident Manager /VAS SP Tech Resolver |  | Restorative actions identified, Change required - Incident ticket status updated with fix details Mandatory Fields to be updated - tbc refer to operations manual Ticket status changes to on hold | Fix identified that does require a Change to be raised for implementation, ticket is updated | Y
|  | 12 |  |  | Change Mngt, Major Incident Manager |  | Emergency Change raised for implementation of the restorative actions The related Incident ticket status is set to on hold - remains here until change completed and then set to resolved | Change raised , Incident ticket is linked to Change | Y
| ECAB | 13 |  |  | Change Mngt, Major Incident Manager |  | ECAB assembled Refer to Operations Manual for attendees, agenda, ECAB notification methods etc | All members of ECAB are notified via email from the SM tool | Y
|  | 14 |  |  | Change Mngt, VAS SP, MIM |  | ECAB meeting held to discuss and agree implementation for the change Consideration to time of day and any in-flight processing impacts , implementation sequence, fallback details etc Refer to Ops manual for further ECAB details | All ECAB attendees are present and Change approved | Y
| Comms | 15 |  |  | Change Mngt, MIM |  | Communication to Industry that a Change is required Refer to Ops manual for comms method | All Service Users receive Comms | Y
| Implement | 16 |  |  | Change Mngt, VAS SP, MIM |  | Change/s Implemented in correct sequence VAS Change | Change implemented by all SPs in correct sequence | Y
|  | 17 |  |  | Change Mngt, VAS SP, MIM |  | Validate Change outcome of the Change implementation | Outcome successful issue resolved | Y
|  | 18 |  |  | Change Mngt, MIM |  | Change Record updated - status is set to resolved Refer to Ops manual for details of fields to update | change record status is set to Resolved | Y
|  | 19 |  |  | Service Desk |  | Service user advised change implemented via email/ticket updates on SM portal Refer to Ops manual | Service User reviews actions taken and ticket status | Y
|  | 20 |  |  | Change Mngt MIM |  | Change Record Closed by change mngt Incident ticket may be closed here or later but within 5 days or auto closed Refer to Ops manual for details on ticket closure | Change Record and Incident closed | Y
|  | 21 |  |  | Service User |  | Service user receives notification of status change for the ticket and accesses the incident ticket to check the status | Case has been closed | Y
| PIR | 22 |  |  | Change Mngr, VAS SP |  | Assess if Post Implementation review required | PIR not required as change successful | Y
| Close | 23 |  |  | Change Mngr |  | Emergency Change/Incident Report produced | Report complete and attached the Change and Incident records | Y

## TC08 MDS No CR
No. |  | Test Case Id |  |  |  | Test Case Title
TC08 |  | SIT-OPS-SM01-TC08 |  |  |  | SIT-OPS SM01 TC08 MDS
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SIT-OPS SM01 TC08 MDS | Raise case | 1 |  | SDD v2.4 section 6 LLSD v1.1 Section 7 MHHS Service User - Operations Manual Draft - Section 4 | Service User - LDSO role |  | Note: This case needs to be raised for a MDS System Failure during Working Day as per settlement calendar Service User LDSO raises a case by contacting the Elexon Service desk by telephone - Note this is a simulated call and Elexon Service desk will create case directly in SM Refer to Operations manual for Category drop down options and raising by telephone details | Case Reference is given | Y
| Triage | 2 |  |  | Elexon Service Desk |  | Elexon Service Desk raise the case . The case undergoes review and 1st line triage to identify the correct SM function for the case to be assigned to Ticket status is set to New | Case is triaged as part of logging - Ops manual will detail questions to be answered when raising and SLA for triage Case is assessed as a Major Incident candidate and assigned to the Major Incident Manager | Y
| Promote to MI | 3 |  |  | Major Incident Manager |  | Incident promotion request is reviewed by the Major Incident Manager performing validity checks as to whether a Major Incident by Major Incident Manager on a case by case basis Refer to operations manual for details on validity checks | Incident assessed as valid Major Incident | Y
|  | 4 |  |  | Major Incident Manager |  | Incident ticket promoted to Major Incident Severity = S1 Priority = P1 Status = In progress Refer to Operations manual for status options | Incident ticket updated correctly | Y
| Initial Comms | 5 |  |  | Major Incident Manager |  | Initial comms are sent via email to the MI Comms team list Note: The comms list recipients is tbc and will be a standard list os recipients The commination list for Major Incidents will be agreed at a later date and available in Service Now | Validate recipients receive the MI communication | Y
|  | 6 |  |  | Major Incident Manager |  | Major Incident Manager engages the MI team (Technical Resolver teams, product owner) and establishes MI bridge Comms for the engagement comms method - refer to Operations manual Note: Ticket assigned to Tech Resolver group (MIM remains accountable) | MDS Tech Resolver team/s, Product Mngr acknowledge and accept the issue | Y
|  | 7 |  |  | Service Desk |  | Incident update Communication issued to Service Users via ticket updates on the portal and email notification from Service now each time ticket is updated) Refer to Operations Manual for comms frequency and details | Incident updates received by Service Users | Y
| Circular | 8 |  |  | Product Owner |  | Assess whether Industry Circular required Note: If Industry impacting then Circular sent - details to be provided in the Operations manual | Industry Circular is required | Y
|  | 9 |  |  | Major Incident Manager |  | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | BSC website is updated correctly | Y
| Investigate | 10 |  |  | Major Incident Manager / MDS Technical Resolvers |  | MI Investigation starts MDS Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident ticket status remains at In progress | Correct teams engaged - MDS SP | Y
|  | 11 |  |  | Major Incident Manager / MDS Technical Resolvers |  | Restorative actions identified, no Change required - Incident ticket status updated with fix details Mandatory Fields to be updated - tbc refer to operations manual Ticket status remains at In progress | Fix identified that does not require a Change to be raised for implementation, ticket is updated | Y
| Implement | 13 |  |  | MDS Tech Resolver Group / Major Incident Manager |  | Implement restorative actions | Actions to rectify the incident have been completed successfully | Y
|  | 14 |  |  | MDS Tech Resolver Group / Major Incident Manager |  | Issue is deemed as being resolved, ticket is updated to reflect status of resolved and any other updates | Incident ticket reflects resolved | Y
|  | 15 |  |  | Product Owner |  | Assess whether Industry Circular required If Industry impacting then Circular sent - refer to Operations manual for further detail | Industry Circular is required and issued | Y
|  | 16 |  |  | Major Incident Manager |  | BSC website is update with Industry Circular details Refer to Ops Manual for details - where in BSC website will be located | BSC website is updated correctly | Y
|  | 17 |  |  | Service Desk |  | Communication sent to Service Users notifying them the incident is resolved (via ticket updates on portal, and email notification Service now) | Service user reviews actions taken, ticket status | Y
| PIR | 18 |  |  | Service Desk / MIM / MDS Technical Resolvers |  | Post incident review takes place and Major Incident report produced and attached to ticket in Service Now within 3 WDs Refer to Operations Manual for further details | MI Report completed and attached to Incident ticket | Y
| Close | 19 |  |  | Service User |  | Service Users verify the issue is resolved and closes the incident ticket, (ticket will be closed in 5 days automatically) | Incident is set to closed | Y

## TC09 LSS No CR
No. |  | Test Case Id |  |  |  | Test Case Title
TC09 |  | SIT-OPS-SM01-TC09 |  |  |  | SIT-OPS SM01 TC09 LSS
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SIT-OPS SM01 TC09 LSS | Raise case | 1 |  | SDD v2.4 section 6 LLSD v1.1 Section 7 MHHS Service User - Operations Manual Draft - Section 4 | Service User - ADS role |  | Note: This case needs to be raised for a LSS Service Failure in hours within secure active window (duration 60 mins) Service User ADS raises a case in the SM portal (CSM Service Catalog - Elexon Support) by selecting the 'Report a Service Issue' option and completing the following fields In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - No receipt LSS Data Description - no receipt of LSS data URL or related page section - insert if required Click submit Refer to Operations manual for Category drop down options | Case Reference displayed | Y
|  | 2 |  |  | Elexon Service Desk |  | Elexon Service Desk retrieve the case from the queue . The case undergoes review and 1st line triage to identify the correct SM function for the case to be assigned to Ticket status is set to New | Case is triaged within 15 mins Case is assessed as a Major Incident candidate and assigned to the Major Incident Manager | Y
| Promote to MI | 3 |  |  | Major Incident Manager |  | Incident promotion request is reviewed by the Major Incident Manager performing validity checks as to whether a Major Incident by Major Incident Manager on a case by case basis Refer to operations manual for details on validity checks | Incident assessed as valid Major Incident | Y
|  | 4 |  |  | Major Incident Manager |  | Incident ticket promoted to Major Incident Severity = S1 Priority = P1 Status = In progress Refer to Operations manual for status options | Incident ticket updated correctly | Y
| Initial Comms | 5 |  |  | Major Incident Manager |  | Initial comms are sent via email to the MI Comms team list Note: The comms list recipients is tbc and will be a standard list os recipients The commination list for Major Incidents will be agreed at a later date and available in Service Now | Validate recipients receive the MI communication | Y
|  | 6 |  |  | Major Incident Manager |  | Major Incident Manager engages the MI team (Technical Resolver teams, product owner) and establishes MI bridge Comms for the engagement comms method - refer to Operations manual Note: Ticket assigned to Tech Resolver group (MIM remains accountable) | LSS Tech Resolver team/s, Product Mngr acknowledge and accept the issue | Y
|  | 7 |  |  | Service Desk |  | Incident update Communication issued to Service Users via ticket updates on the portal and email notification from Service now each time ticket is updated) Refer to Operations Manual for comms frequency and details | Incident updates received by Service Users | Y
| Circular | 8 |  |  | Product Owner |  | Assess whether Industry Circular required Note: If Industry impacting then Circular sent - details to be provided in the Operations manual | Industry Circular is required | Y
|  | 9 |  |  | Major Incident Manager |  | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | BSC website is updated correctly | Y
| Investigate | 10 |  |  | Major Incident Manager / LSS Technical Resolvers |  | MI Investigation starts LSS Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident ticket status remains at In progress | Correct teams engaged - LSS SP | Y
|  | 11 |  |  | Major Incident Manager / LSS Technical Resolvers |  | Restorative actions identified, no Change required - Incident ticket status updated with fix details Mandatory Fields to be updated - tbc refer to operations manual Ticket status remains at In progress | Fix identified that does not require a Change to be raised for implementation, ticket is updated | Y
| Implement | 13 |  |  | LSS Tech Resolver Group / Major Incident Manager |  | Implement restorative actions | Actions to rectify the incident have been completed successfully | Y
|  | 14 |  |  | LSS Tech Resolver Group / Major Incident Manager |  | Issue is deemed as being resolved, ticket is updated to reflect status of resolved and any other updates | Incident ticket reflects resolved | Y
|  | 15 |  |  | Product Owner |  | Assess whether Industry Circular required If Industry impacting then Circular sent - refer to Operations manual for further detail | Industry Circular is required and issued | Y
|  | 16 |  |  | Major Incident Manager |  | BSC website is update with Industry Circular details Refer to Ops Manual for details - where in BSC website will be located | BSC website is updated correctly | Y
|  | 17 |  |  | Service Desk |  | Communication sent to Service Users notifying them the incident is resolved (via ticket updates on portal, and email notification Service now) | Service user reviews actions taken, ticket status | Y
| PIR | 18 |  |  | Service Desk / MIM / LSS Technical Resolvers |  | Post incident review takes place and Major Incident report produced and attached to ticket in Service Now within 3 WDs Refer to Operations Manual for further details | MI Report completed and attached to Incident ticket | Y
| Close | 19 |  |  | Service User (participant) |  | Service Users verify the issue is resolved and closes the incident ticket, (ticket will be closed in 5 days automatically) | Incident is set to closed | Y

## TC10 ISD No CR
No. |  | Test Case Id |  |  |  | Test Case Title
TC10 |  | SIT-OPS-SM01-TC10 |  |  |  | SIT-OPS SM01 TC10 ISD
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SIT-OPS SM01 TC10 ISD | Raise case | 1 |  | SDD v2.4 section 6 LLSD v1.1 Section 7 MHHS Service User - Operations Manual Draft - Section 4 | Service User - LDSO role |  | Note: This case needs to be raised for Incorrect data sent impacting PPs - processing issue due to ISD mismatches Service User LDSO raises a case in the SM portal (CSM Service Catalog - Elexon Support) by selecting the 'Report a Service Issue' option and completing the following fields In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject -processing issue due to ISD mismatches Description - processing issue due to ISD mismatches URL or related page section - insert if required Click submit Refer to Operations manual for Category drop down options | Case Reference displayed | Y
| Triage | 2 |  |  | Elexon Service Desk |  | Elexon Service Desk retrieve the case from the queue . The case undergoes review and 1st line triage to identify the correct SM function for the case to be assigned to Ticket status is set to New | Case is triaged within 15 mins Case is assessed as a Major Incident candidate and assigned to the Major Incident Manager | Y
|  | 3 |  |  | Major Incident Manager |  | Incident promotion request is reviewed by the Major Incident Manager performing validity checks as to whether a Major Incident by Major Incident Manager on a case by case basis Refer to operations manual for details on validity checks | Incident assessed as valid Major Incident | Y
|  | 4 |  |  | Major Incident Manager |  | Incident ticket promoted to Major Incident Severity = S1 Priority = P1 Status = In progress Refer to Operations manual for status options | Incident ticket updated correctly | Y
| Initial Comms | 5 |  |  | Major Incident Manager |  | Initial comms are sent via email to the MI Comms team list Note: The comms list recipients is tbc and will be a standard list os recipients The commination list for Major Incidents will be agreed at a later date and available in Service Now | Validate recipients receive the MI communication | Y
|  | 6 |  |  | Major Incident Manager |  | Major Incident Manager engages the MI team (Technical Resolver teams, product owner) and establishes MI bridge Comms for the engagement comms method - refer to Operations manual Note: Ticket assigned to Tech Resolver group (MIM remains accountable) | ISD Tech Resolver team/s, Product Mngr acknowledge and accept the issue | Y
|  | 7 |  |  | Service Desk |  | Incident update Communication issued to Service Users via ticket updates on the portal and email notification from Service now each time ticket is updated) Refer to Operations Manual for comms frequency and details | Incident updates received by Service Users | Y
| Circular | 8 |  |  | Product Owner |  | Assess whether Industry Circular required Note: If Industry impacting then Circular sent - details to be provided in the Operations manual | Industry Circular is required | Y
|  | 9 |  |  | Major Incident Manager |  | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | BSC website is updated correctly | Y
| Investigate | 10 |  |  | Major Incident Manager / ISD Technical Resolvers |  | MI Investigation starts ISD Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident ticket status remains at In progress | Correct teams engaged - ISD SP | Y
|  | 11 |  |  | Major Incident Manager / ISD Technical Resolvers |  | Restorative actions identified, no Change required - Incident ticket status updated with fix details Mandatory Fields to be updated - tbc refer to operations manual Ticket status remains at In progress | Fix identified that does not require a Change to be raised for implementation, ticket is updated | Y
| Implement | 13 |  |  | ISD Tech Resolver Group / Major Incident Manager |  | Implement restorative actions | Actions to rectify the incident have been completed successfully | Y
|  | 14 |  |  | ISD Tech Resolver Group / Major Incident Manager |  | Issue is deemed as being resolved, ticket is updated to reflect status of resolved and any other updates | Incident ticket reflects resolved | Y
|  | 15 |  |  | Product Owner |  | Assess whether Industry Circular required If Industry impacting then Circular sent - refer to Operations manual for further detail | Industry Circular is required and issued | Y
|  | 16 |  |  | Major Incident Manager |  | BSC website is update with Industry Circular details Refer to Ops Manual for details - where in BSC website will be located | BSC website is updated correctly | Y
|  | 17 |  |  | Service Desk |  | Communication sent to Service Users notifying them the incident is resolved (via ticket updates on portal, and email notification Service now) | Service user reviews actions taken, ticket status | Y
| PIR | 18 |  |  | Service Desk / MIM / ISD Technical Resolvers |  | Post incident review takes place and Major Incident report produced and attached to ticket in Service Now within 3 WDs Refer to Operations Manual for further details | MI Report completed and attached to Incident ticket | Y
| Close | 19 |  |  | Service User (LDSO) |  | Service Users verify the issue is resolved and closes the incident ticket, (ticket will be closed in 5 days automatically) | Incident is set to closed | Y

## TC11 ISD No CR
No. |  | Test Case Id |  |  |  | Test Case Title | Meter Type | MPAN Type | Effective time
TC11 |  | SIT-OPS SM01 TC11 ISD |  |  |  | SIT-OPS SM01 TC11 ISD
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SIT-OPS SM01 TC11 ISD | Raise case | 1 |  | SDD v2.4 section 6 LLSD v1.1 Section 7 MHHS Service User - Operations Manual Draft - Section 4 | Service User - SUPP role |  | Note: This case needs to be raised for ISD system failure during ISD publication window Service User SUPP raises a case in the SM portal (CSM Service Catalog - Elexon Support) by selecting the 'Report a Service Issue' option and completing the following fields In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - Description - URL or related page section - insert if required Click submit Refer to Operations manual for Category drop down options | Case Reference displayed | Y
| Triage | 2 |  |  | Elexon Service Desk |  | Elexon Service Desk retrieve the case from the queue . The case undergoes review and 1st line triage to identify the correct SM function for the case to be assigned to Ticket status is set to New | Case is triaged within 15 mins Case is assessed as a Major Incident candidate and assigned to the Major Incident Manager | Y
|  | 3 |  |  | Major Incident Manager |  | Incident promotion request is reviewed by the Major Incident Manager performing validity checks as to whether a Major Incident by Major Incident Manager on a case by case basis Refer to operations manual for details on validity checks | Incident assessed as valid Major Incident | Y
|  | 4 |  |  | Major Incident Manager |  | Incident ticket promoted to Major Incident Severity = S1 Priority = P1 Status = In progress Refer to Operations manual for status options | Incident ticket updated correctly | Y
| Initial Comms | 5 |  |  | Major Incident Manager |  | Initial comms are sent via email to the MI Comms team list Note: The comms list recipients is tbc and will be a standard list os recipients The commination list for Major Incidents will be agreed at a later date and available in Service Now | Validate recipients receive the MI communication | Y
|  | 6 |  |  | Major Incident Manager |  | Major Incident Manager engages the MI team (Technical Resolver teams, product owner) and establishes MI bridge Comms for the engagement comms method - refer to Operations manual Note: Ticket assigned to Tech Resolver group (MIM remains accountable) | ISD Tech Resolver team/s, Product Mngr acknowledge and accept the issue | Y
|  | 7 |  |  | Service Desk |  | Incident update Communication issued to Service Users via ticket updates on the portal and email notification from Service now each time ticket is updated) Refer to Operations Manual for comms frequency and details | Incident updates received by Service Users | Y
| Circular | 8 |  |  | Product Owner |  | Assess whether Industry Circular required Note: If Industry impacting then Circular sent - details to be provided in the Operations manual | Industry Circular is required | Y
|  | 9 |  |  | Major Incident Manager |  | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | BSC website is updated correctly | Y
| Investigate | 10 |  |  | Major Incident Manager / ISD Technical Resolvers |  | MI Investigation starts ISD Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident ticket status remains at In progress | Correct teams engaged - ISD SP | Y
|  | 11 |  |  | Major Incident Manager / ISD Technical Resolvers |  | Restorative actions identified, no Change required - Incident ticket status updated with fix details Mandatory Fields to be updated - tbc refer to operations manual Ticket status remains at In progress | Fix identified that does not require a Change to be raised for implementation, ticket is updated | Y
| Implement | 13 |  |  | ISD Tech Resolver Group / Major Incident Manager |  | Implement restorative actions | Actions to rectify the incident have been completed successfully | Y
|  | 14 |  |  | ISD Tech Resolver Group / Major Incident Manager |  | Issue is deemed as being resolved, ticket is updated to reflect status of resolved and any other updates | Incident ticket reflects resolved | Y
|  | 15 |  |  | Product Owner |  | Assess whether Industry Circular required If Industry impacting then Circular sent - refer to Operations manual for further detail | Industry Circular is required and issued | Y
|  | 16 |  |  | Major Incident Manager |  | BSC website is update with Industry Circular details Refer to Ops Manual for details - where in BSC website will be located | BSC website is updated correctly | Y
|  | 17 |  |  | Service Desk |  | Communication sent to Service Users notifying them the incident is resolved (via ticket updates on portal, and email notification Service now) | Service user reviews actions taken, ticket status | Y
| PIR | 18 |  |  | Service Desk / MIM / ISD Technical Resolvers |  | Post incident review takes place and Major Incident report produced and attached to ticket in Service Now within 3 WDs Refer to Operations Manual for further details | MI Report completed and attached to Incident ticket | Y
| Close | 19 |  |  | Service User (participant) |  | Service Users verify the issue is resolved and closes the incident ticket, (ticket will be closed in 5 days automatically) | Incident is set to closed | Y

## TC12 DAH No CR
No. |  | Test Case Id |  |  |  | Test Case Title
TC12 |  | SIT-OPS-SM01-TC12 |  |  |  | SIT-OPS SM01 TC12 DAH
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SIT-OPS SM01 TC12 DAH | Raise case | 1 |  | SDD v2.4 section 6 LLSD v1.1 Section 7 MHHS Service User - Operations Manual Draft - Section 4 | Elexon raised |  | Note: This case needs to be raised for a DAH system failure weekday peak times This case is raised by Helix internal monitoring | Case Reference displayed | Y
| Triage | 2 |  |  | Elexon Service Desk |  | The case undergoes review and 1st line triage to identify the correct SM function for the case to be assigned to Ticket status is set to New | Case is triaged within 15 mins Case is assessed as a Major Incident candidate and assigned to the Major Incident Manager | Y
| Promote to MI | 3 |  |  | Major Incident Manager |  | Incident promotion request is reviewed by the Major Incident Manager performing validity checks as to whether a Major Incident by Major Incident Manager on a case by case basis Refer to operations manual for details on validity checks | Incident assessed as valid Major Incident | Y
|  | 4 |  |  | Major Incident Manager |  | Incident ticket promoted to Major Incident Severity = S1 Priority = P1 Status = In progress Refer to Operations manual for status options | Incident ticket updated correctly | Y
| Initial comms | 5 |  |  | Major Incident Manager |  | Initial comms are sent via email to the MI Comms team list Note: The comms list recipients is tbc and will be a standard list os recipients The commination list for Major Incidents will be agreed at a later date and available in Service Now | Validate recipients receive the MI communication | Y
|  | 6 |  |  | Major Incident Manager |  | Major Incident Manager engages the MI team (Technical Resolver teams, product owner) and establishes MI bridge Comms for the engagement comms method - refer to Operations manual Note: Ticket assigned to Tech Resolver group (MIM remains accountable) | DAH Tech Resolver team/s, Product Mngr acknowledge and accept the issue | Y
|  | 7 |  |  | Service Desk |  | Incident update Communication issued to Service Users via ticket updates on the portal and email notification from Service now each time ticket is updated) Refer to Operations Manual for comms frequency and details | Incident updates received by Service Users | Y
| Circular | 8 |  |  | Product Owner |  | Assess whether Industry Circular required Note: If Industry impacting then Circular sent - details to be provided in the Operations manual | Industry Circular is required | Y
|  | 9 |  |  | Major Incident Manager |  | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | BSC website is updated correctly | Y
| Investigate | 10 |  |  | Major Incident Manager / DAH Technical Resolvers |  | MI Investigation starts DAH Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident ticket status remains at In progress | Correct teams engaged - DAH SP | Y
|  | 11 |  |  | Major Incident Manager / DAH Technical Resolvers |  | Restorative actions identified, no Change required - Incident ticket status updated with fix details Mandatory Fields to be updated - tbc refer to operations manual Ticket status remains at In progress | Fix identified that does not require a Change to be raised for implementation, ticket is updated | Y
| Implement | 13 |  |  | DAH Tech Resolver Group / Major Incident Manager |  | Implement restorative actions | Actions to rectify the incident have been completed successfully | Y
|  | 14 |  |  | DAH Tech Resolver Group / Major Incident Manager |  | Issue is deemed as being resolved, ticket is updated to reflect status of resolved and any other updates | Incident ticket reflects resolved | Y
|  | 15 |  |  | Product Owner |  | Assess whether Industry Circular required If Industry impacting then Circular sent - refer to Operations manual for further detail | Industry Circular is required and issued | Y
|  | 16 |  |  | Major Incident Manager |  | BSC website is update with Industry Circular details Refer to Ops Manual for details - where in BSC website will be located | BSC website is updated correctly | Y
|  | 17 |  |  | Service Desk |  | Communication sent to Service Users notifying them the incident is resolved (via ticket updates on portal, and email notification Service now) | Service user reviews actions taken, ticket status | Y
| PIR | 18 |  |  | Service Desk / MIM / DAH Technical Resolvers |  | Post incident review takes place and Major Incident report produced and attached to ticket in Service Now within 3 WDs Refer to Operations Manual for further details | MI Report completed and attached to Incident ticket | Y
| Close | 19 |  |  | Service User (participant) |  | Service Users verify the issue is resolved and closes the incident ticket, (ticket will be closed in 5 days automatically) | Incident is set to closed | Y

## DPCache_List of Test Scenarios (hidden)
Test Category | Test Scenario | Scenario Title | Test Cases Link | Test ID | Test Scenario Link | Status Date | Status | Test Title | Priority | Pre-Requisite Test Scenario
Advisory Notification | E2E-001 | SITFTS-001 - Advisory Notification | Click to See Test Cases | E2E-001 | Click to view Test | 2023-02-09 | WG Reviewed (Working Group Drops)​ | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Advisory Notification | E2E-E004 | E2E-E004 - Advisory Notification | Click to See Test Cases | E2E-004 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-G006 |  | Click to See Test Cases | E2E-006 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-E007 | E2E-E007 - Switch Request Objection | Click to See Test Cases | E2E-007 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Objection | E2E-D008 |  | Click to See Test Cases | E2E-008 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Successful | E2E-G012 | E2E-G012 - Switch Request Successful | Click to See Test Cases | E2E-012 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA
Switch Request Successful | E2E-E011 |  | Click to See Test Cases | E2E-011 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA