## Sheet1
March
Time | 2025-03-03 | 2025-03-04 |  | 2025-03-05 |  | 2025-03-06 |  | 2025-03-07 |  | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21
6:00 | [7 empty] | Avanade DIP and Message Catcher Scale Up | LDP Support activities
7:00
8:00
9:00 | Helix Event Hub scale up | Avanade DIP and Message Catcher Scale Up | LDP support activities | Avanade DIP and Message Catcher Scale Up | LDP support activities | Avanade DIP and Message Catcher Scale Up | LDP support activities | 8 hour soak test execution (Maybe ramp up and ramp down required?) |  | 2025-03-10: Theme 1 NFT Completion report generation; 2025-03-13: Results presentation/walkthrough and proposal for sign off; 2025-03-14: Sign off achieved for Theme 1 NFT; 2025-03-17: Contingency
10:00 | Smoke testing and environment shakedown activities
11:00
12:00 |  | 2 hr peak load test with ramp up and ramp down (Run 1) |  | 2 hr peak load test with ramp up and ramp down (Run 2) |  | 2 hr peak load test with ramp up and ramp down (Run 3)
13:00
14:00
15:00 |  | Avanade DIP and Message Catcher Scale down | LDP test results collation/Interim test results report generation | Avanade DIP and Message Catcher Scale down | LDP test results collation/Interim test results report generation | Avanade DIP and Message Catcher Scale down | LDP test results collation/Interim test results report generation
16:00
17:00 | [7 empty] | Avanade DIP and Message Catcher Scale down | Helix Event Hub scale down
18:00
| Assumptions |  |  |  |  | Execution
| Avanade suggestion of dynamic scaling around test windows is possible |  |  |  |  | LDP Activity
Helix Event Hub scale up occurs in advance of Theme 1 start and scale down at conclusion
Restrictions
Processing windows limited to between 5am and 6pm