## Sheet1
Time | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02
6:00
7:00
8:00
9:00 | Smoke testing and environment shakedown activities | Cohort A, B, C, E, F, G, H, J Day 1 processing. Initial notifications for COS and COA. Joint cohorts for COS. Includes consumption traffic. Includes EOD processing of gate closure events for MPRS between 3-4 | Cohort A, B, C, E, F, G, H, J Day 2 processing. Initial notifications for COS and COA. Physical processing of Day 1 notifications. Joint cohorts for COS. Includes consumption traffic. Includes EOD processing of gate closure events for MPRS between 3-4 | Cohort A, B, C, E, F, G, H, J Day 2 processing. Initial notifications for COS and COA. Physical processing of Day 2 notifications. Joint cohorts for COS. Includes consumption traffic. Includes EOD processing of gate closure events for MPRS between 3-4 | Cohort A, B, C, E, F, G, H, J Day 2 processing. Initial notifications for COS and COA. Physical processing of Day 3 notifications. Joint cohorts for COS. Includes consumption traffic. Includes EOD processing of gate closure events for MPRS between 3-4 | Contingency
10:00
11:00
12:00
13:00
14:00
15:00
16:00 | 2025-04-22: Cohort A, B, C, E, F, G, H, J Settlements Day 1 results and evidence collation and upload to ADO/Interim Test Results Report generation; 2025-04-23: Cohort A, B, C, E, F, G, H, J Settlements Day 2 results and evidence collation and upload to ADO/Interim Test Results Report generation; 2025-04-24: Cohort A, B, C, E, F, G, H, J Settlements Day 3 results and evidence collation and upload to ADO/Interim Test Results Report generation; 2025-04-25: Cohort A, B, C, E, F, G, H, J Settlements Day 4 results and evidence collation and upload to ADO/Interim Test Results Report generation
17:00
18:00
| Assumptions | [6 empty] | PP Execution
| Message processing blocks include all necessary choreography meetings between NFT team and PPs to facilitate data readiness and validate state in advance of next steps | [6 empty] | LDP Activity
Results and evidence collation blocks include all necessary choreography meetings between NFT team and PPs to facilitate data readiness and validate state in advance of next steps
Restrictions
Processing windows limited to between 5am and 6pm