## Sheet1
Time | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18
6:00
7:00
8:00
9:00 | Smoke testing and environment shakedown activities ( As this is currently running straight on from Theme 2 smoke testing may not be required) | Cohort A Supplier, SDS, ADS, MSS, MSA, UMSDS message injection readiness | Cohort B Supplier, SDS, ADS, MSS, MSA message injection readiness | Cohort C Supplier, SDS, ADS, MSS, MSA message injection readiness | Cohort E Supplier, SDS, ADS, MSS, MSA message injection readiness | Cohort F Supplier, SDS, ADS, MSS, MSA message injection readiness | Cohort G Supplier, SDS, ADS, MSS, MSA, UMSDS message injection readiness | Cohort H Supplier, SDS, ADS, MSS, MSA message injection readiness | Cohort J Supplier, SDS, ADS, MSS, MSA, UMSDS message injection readiness | Contingency
10:00
11:00
12:00 | 2025-04-01: DIP Takedown Message Submission DIP Restoration; 2025-04-02: DIP Takedown Message Submission DIP Restoration; 2025-04-03: DIP Takedown Message Submission DIP Restoration; 2025-04-04: DIP Takedown Message Submission DIP Restoration; 2025-04-07: DIP Takedown Message Submission DIP Restoration; 2025-04-08: DIP Takedown Message Submission DIP Restoration; 2025-04-09: DIP Takedown Message Submission DIP Restoration; 2025-04-10: DIP Takedown Message Submission DIP Restoration
13:00 | 2025-04-01: Cohort A Supplier, SDS, ADS, MSS, MSA, UMSDS resilience results and evidence collation and upload to ADO; 2025-04-02: Cohort B Supplier, SDS, ADS, MSS, MSA resilience results and evidence collation and upload to ADO; 2025-04-03: Cohort C Supplier, SDS, ADS, MSS, MSA resilience results and evidence collation and upload to ADO; 2025-04-04: Cohort E Supplier, SDS, ADS, MSS, MSA resilience results and evidence collation and upload to ADO; 2025-04-07: Cohort F Supplier, SDS, ADS, MSS, MSA resilience results and evidence collation and upload to ADO; 2025-04-08: Cohort G Supplier, SDS, ADS, MSS, MSA, UMSDS resilience results and evidence collation and upload to ADO; 2025-04-09: Cohort H Supplier, SDS, ADS, MSS, MSA resilience results and evidence collation and upload to ADO; 2025-04-10: Cohort J Supplier, SDS, ADS, MSS, MSA, UMSDS resilience results and evidence collation and upload to ADO
14:00
15:00
16:00
17:00
18:00
| Assumptions | [6 empty] | PP Execution
| Message processing blocks include all necessary choreography meetings between NFT team and PPs to facilitate data readiness and validate state in advance of next steps | [6 empty] | LDP Activity
Results and evidence collation blocks include all necessary choreography meetings between NFT team and PPs to facilitate data readiness and validate state in advance of next steps
Restrictions
Processing windows limited to between 5am and 6pm