## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Change Log
Date | Author | Release | Reason for change
2025-03-20 | SI NFT Team | 0.1 | Initial version, smaller version of T2 test case, will use same day to avoid MPAN loss

## SITNFT-T3 220 Overview
Scenario ID | SITNFT-T3 220
Theme | Change Of Agent
Scenario Title | Change of Agent Notifications
Description | TC01 - Smart - Single MPAN, change of data and metering service
Functional Category | Migration
Functional Area 1 | Migration
Functional Area 2
Creator | Iain Smith
Priority | High
Scenario size | Large
Design Document Ref
Business Process | Migration
Pre-Requisites
Boundaries
Test Case Variables | (1) SITNFT-T3 220 010 Smart
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Case Version | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITNFT-T3 220 010 | SITNFT-T3 220 010 Smart | 0.1 | Smart - Single MPAN, change of data and metering service 'Appointment date today today | Smart Meter | Single MPAN | Calendar
Back to List of
Test Scenarios

## SITNFT-T3 220 010
No. | Test Case Id |  |  | Test Case Version |  |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITNFT-T3 220 010 |  |  | 0.1 |  |  | SITNFT-T3 220 010 Smart | Smart - Single MPAN, change of data and metering service 'Appointment date today today | Smart Meter | Single MPAN | Calendar
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITNFT-T3 220 010 Smart | Determine Service Required | 1 | BP002 BP003 | 5 10 |  | N/A | N/A | N/A | N/A | Supplier must identify the correct Market Segment | N/A | N
|  | 2 | N/A | N/A | N/A | DIP | N/A | N/A | All | IF-031 Interface between Registration Participant and DIP is disable/configured to return error | Inbound/Outbound traffic to DIP suspended | Y
| Setting up Appointments | 3 | 6 | 20 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | SUPC | IF-031 | [MSApp] | DIP | Supplier will send the correct appointment details for the appropriate Service provider | http 202 response from DIP | Y
|  | 4 | N/A | N/A | N/A | DIP | N/A | N/A | All | IF-031 Interface between Registration Participant and DIP is enabled/configured to return process as normal | Inbound/Outbound traffic to DIP resumed, queued messages show hhtp 202 response from DIP | Y
|  | 5 | BP002 | 30 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_130 | DIP | PUB-031 | [MSApp] | REGS | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems. | Y
|  | 6 | N/A | N/A | N/A | DIP | N/A | N/A | All | IF-031 Interface between Registration Participant and DIP is disable/configured to return error | Inbound/Outbound traffic to DIP suspended | Y
|  | 7 | BP003 | 20 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | SUPC | IF-031 | [DSApp] | DIP | Supplier will send the correct appointment details for the appropriate Service provider | http 202 response from DIP | Y
|  | 8 | N/A | N/A | N/A | DIP | N/A | N/A | All | IF-031 Interface between Registration Participant and DIP is enabled/configured to return process as normal | Inbound/Outbound traffic to DIP resumed, queued messages show hhtp 202 response from DIP | Y
|  | 9 | BP003 | 30 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_130 | DIP | PUB-031 | [DSApp] | REGS | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems. | Y
| All Appointment Requests | 10 | BP002 | 45 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | REGS | IF-032 | [MSAppInitialResp] | DIP | The REGS will accept the 'Supplier Service Appointment Request' | http 202 response from DIP | Y
|  | 11 | BP002 | 50 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_140 | DIP | PUB-032 | [MSAppInitialResp] | SUPC | The DIP will publish the REGS response to the 'Supplier Service Appointment Request' | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems. | Y
|  | 12 | BP002 | 55 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_140 | DIP | PUB-032 | [MSAppInitialResp] | SUPC | Supplier will receive response to the appointment request from the REGS | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems. | Y
|  | 13 | BP003 | 45 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | REGS | IF-032 | [DSAppInitialResp] | DIP | The REGS will accept the 'Supplier Service Appointment Request' | http 202 response from DIP | Y
|  | 14 | BP003 | 50 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_140 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | The DIP will publish the REGS response to the 'Supplier Service Appointment Request' | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems. | Y
|  | 15 | BP003 | 55 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_140 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | Supplier will receive response to the appointment request from the REGS | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems. | Y
| Valid Requests Only | 16 | BP002 | 60 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | REGS | IF-033 | [MSAppSPRequest] | DIP | The REGS will send 'REGS Request for Service Appointment' to the correct service provider via the DIP | http 202 response from DIP | Y
|  | 17 | BP002 | 65 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_150 | DIP | PUB-033 | [MSAppSPRequest] | SMSI | The DIP will publish the 'REGS Request for Service Appointment' to the Metering Service | Evidence that Metering Service processes the PUB-033 generated by DIP; log screenshots in downstream systems. | Y
|  | 18 | BP002 | 70 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_150 | DIP | PUB-033 | [MSAppSPRequest] | SMSI | Metering Service will receive an appointment from the Supplier via the REGS. Metering Service must process and validate the appointment request as per the validation rules. Metering Service should be aware that an acceptance will result in the transfer of MPAN(s) | Evidence that Metering Service processes the PUB-033 generated by DIP; log screenshots in downstream systems. | Y
|  | 19 | BP002 | 75 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | SMSI | IF-034 | [MSAppSPResponse] | DIP | The Metering Service will accept the appointment request | http 202 response from DIP | Y
|  | 20 | BP002 | 80 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_160 | DIP | PUB-034 | [MSAppSPResponse] | REGS | The DIP will publish the responses from service providers | Evidence that REGS processes the PUB-034 generated by DIP; log screenshots in downstream systems. | Y
|  | 21 | BP002 | 85 |  | N/A | N/A | N/A | N/A | The REGS will manage the appointment responses from the Metering Service and retain accepted responses in the background until the Effective from date when it will reflect as a live appointment
|  | 22 | BP003 | 60 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | REGS | IF-033 | [DSAppSPRequest] | DIP | The REGS will send 'REGS Request for Service Appointment' to the correct Service provider via the DIP | http 202 response from DIP | Y
|  | 23 | BP003 | 65 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_150 | DIP | PUB-033 | [DSAppSPRequest] | SDSI | The DIP will publish the 'REGS Request for Service Appointment' to the Data Service | Evidence that Data Service processes the PUB-033 generated by DIP; log screenshots in downstream systems. | Y
|  | 24 | BP003 | 220 |  | N/A | N/A | N/A | N/A | Data Services will receive an appointment from the supplier via the REGS. Data services must process and validate the appointment request as per the validation rules
|  | 25 | BP003 | 221 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | SDSI | IF-034 | [DSAppSPResponse] | DIP | The Data Service will accept the appointment request. | http 202 response from DIP | Y
| Additional step for DS in case of Acceptances | 26 | BP003 | 230 |  | N/A | N/A | N/A | N/A | Once the Data Service has accepted the appointment they must appoint the nominated 3rd parties as per the agreed contract and the agreed method.
| All Outcomes | 27 | BP003 | 80 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_160 | DIP | PUB-034 | [DSAppSPResponse] | REGS | The DIP will publish the responses from Data services | Evidence that REGS processes the PUB-034 generated by DIP; log screenshots in downstream systems. | Y
|  | 28 | BP003 | 85 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | REGS | IF-035 | [DSAppAccepted] | DIP | The REGS will manage the appointment responses from the Data services and retain accepted responses in the background until the Effective from date when it will reflect as a live appointment. The REGS must Publish all responses via the DIP and notify the metering service | http 202 response from DIP. Capture evidence that Metering Service has processed the IF-035 message from REGS. | Y
| For All Appointment Responses | 29 | BP002 | 87 | E2E0014 E2E0101 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | REGS | IF-035 | [MSAppAccepted] | DIP | The REGS will send out all responses it has received from the Metering Services back to Supplier via the DIP. | http 202 response from DIP | Y
|  | 30 | BP002 | 91 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_170 MHHS-BR-SU-124 MHHS-BR-LD-060 MHHS-BR-DS-142 | DIP | PUB-035 | [MSAppAccepted] | SUPC SMSI | The DIP will publish the Metering Service response for the appointment to Supplier. | Evidence that Supplier & Metering Services processes the PUB-035 generated by DIP; log screenshots in downstream systems. | Y
|  | 31 | BP002 | 92 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_170 MHHS-BR-SU-124 MHHS-BR-LD-060 MHHS-BR-DS-142 | DIP | PUB-035 | [MSAppAccepted] | SMSI | Metering Services will receive PUB-035 confirming the REGS has received the Metering Services response to the appointment | Evidence that Metering Service processes the PUB-035 generated by DIP; log screenshots in downstream systems. | Y
|  | 32 | BP003 | 90 | E2E0014 E2E0201 E2E0202 E2E0207 E2E0211 E2E1003 E2E1009 OPC_170 MHHS-BR-SU-124 MHHS-BR-LD-060 MHHS-BR-DS-142 | DIP | PUB-035 | [DSAppAccepted] | SDSI SUPC | The DIP will send out all responses it has received from the Data Services back to Supplier. | Evidence that Data Service & Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems. | Y
|  | 33 | BP003 | 86 |  | REGS | IF-035 | [DSAppAccepted] | SMSC | The Meter Service will receive accepted appointment responses from the REGSs | Evidence that Metering Service processes the IF-035 generated by REGS; log screenshots in downstream systems. | Y
|  | 34 | BP003 | 91 |  | DIP | PUB-035 | [DSAppAccepted] | SDSI | Data Services will receive PUB-035 confirming Registrations received the Data Services response to the appointment | Evidence that New Data Service processes the PUB-035 generated by DIP; log screenshots in downstream systems. | Y
| Manage Prospective Appointment | 35 | BP002 | 95 |  | DIP | PUB-035 | [MSAppAccepted] | SUPC | Supplier will receive the publication of the Metering Service response to the appointment. Successful appointments will remain in a pending status until the effective from date. | Evidence that Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems. | Y
|  | 36 | BP003 | 95 |  | DIP | PUB-035 | [DSAppAccepted] | SUPC | Supplier will receive the publication for the Data Service response to the appointment. Successful appointments will remain in a pending status until the effective from date. | Evidence that Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems. | Y