## Overview Sheet
ID | Description | Objectives | Process Categories | Roles
TC_MI01 | To validate end-to-end coordination, escalation, failover handling, and post-incident review across Market Participant and Elexon Service Desks during a simulated major incident. - Scenario DIP becomes unavailable or inaccessible for a large proportion of participants (e.g. >10% of the industry or multiple market roles affected | Incident Handling Between Parties | Major Incident Cross Party | Service User Elexon Service Desk Major Incident Management Technical Resolver Avanade
TC_MI02 | LDSO identifies an issue processing settlement reports due to DUoS Billing system logic failures. | Incident Handling Between Parties | Major Incident Cross Party | Service User (LDSO) Elexon Service Desk Major Incident Management Elexon Technical Resolvers
TC_MI03 | Data corruption identified by any party affecting critical data exchanges | Incident Handling Between Parties | Major Incident Cross Party | Service User Elexon Service Desk Major Incident Management Elexon Technical Resolvers
TC_MI04 | Validate Elexon’s ability to coordinate resolution of a complex incident requiring engagement with Avanade (DIP), LDSOs (MPAN issues), DCC (Smart Metering), and Suppliers (billing discrepancies) | Incident Handling Between Parties | Major Incident Cross Party / Problem Management | Service User Elexon Service Desk Major Incident Management Elexon Technical Resolvers
TC_NI01 | Simulate or detect that a DIP message sent from REGS is not received by the Supplier within the expected timescale. | Incident Handling Between Parties | Normal Incident Cross Party | Service User LDSO Elexon Service Desk Major Incident Management Elexon Technical Resolvers
TC_NI02 | An incident involves ISD updates not notified. Changes to ISD have been made but messages not received by multiple parties | Incident Handling Between Parties | Normal Incident Cross Party | Service User Elexon Service Desk Elexon Technical Resolvers
TC_NI03 | Data Service identifies issue with Load Shaping data. Data Service identifies issues with the Load Shaping data during their estimation process | Incident Handling Between Parties | Normal Incident Cross Party | Service User Elexon Service Desk Elexon Technical Resolvers
TC_NI04 | LDSO unable to access the DIP but the internal DIP adaptor is working | Incident Handling Between Parties | Normal Incident Cross Party | Service User (LDSO) Elexon Service Desk Elexon Technical Resolvers
TC_NI05 | Incident Logging via ServiceNow Portal - DIP Registration Issue | Incident Logging via ServiceNow Portal | Normal Incident Cross Party | Service User Elexon Service Desk Elexon Technical Resolvers
TC_PROB_01 | Validate that a Problem Record can be raised reactively from repeat incidents logged by a single participant. | Verify that a Problem Record can be created reactively when multiple incidents are logged by the same user (participant), | Problem Management | SerivceUser Elexon Service Desk Problem Manager
TC_PORT_01 | Validate portal behaviour when registering an account without selecting an organisation. | Testing of ServiceNow Support Portal Access | Parent | Service User
TC_PORT_02 | Successful RBAC access: Parent can access child account cases | Testing of ServiceNow Support Portal Access | Parent / Child Accounts | Service User (Parent)
TC_PORT_03 | Parent logs case on behalf of child | Testing of ServiceNow Support Portal Parent/Child | Parent / Child Accounts | Service User (Parent)
TC_PORT_04 | Validate that a Parent user can view both their own cases and cases logged by linked Child organisations in the Elexon Support Portal. | Testing of ServiceNow Support Portal Access | Parent / Child Accounts | Service User (Parent)
TC_PORT_05 | Validate that a Child user cannot view or access cases logged by their Parent organisation, ensuring Parent-Child boundaries are enforced. | Testing of ServiceNow Support Portal Access | Parent / Child Accounts | Service User (Child)
TC_SR01 | Service Request Logging via ServiceNow | To verify that service requests can be successfully logged and tracked via the ServiceNow platform, with all requests routed through the Elexon Support Portal and assigned a default priority of P4. | Service Request | Service User Elexon Service Desk

## TC_MI01
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles | Role
To validate end-to-end coordination, escalation, failover handling, and post-incident review across Market Participant and Elexon Service Desks during a simulated major incident. - Scenario DIP becomes unavailable or inaccessible for a large proportion of participants (e.g. >10% of the industry or multiple market roles affected | Incident Handling Between Parties | ServiceNow Available DIP Portal Available Participants Systems Available | 1 | Service User identifies: DIP becomes unavailable or inaccessible for a large proportion of participants (e.g. >10% of the industry or multiple market roles affected | Impact is validated by the user; >10% threshold or multi-role disruption noted | Service User Elexon Service Desk Major Incident Management Technical Resolver Avanade | Service User (LDSO)
|  |  | 2 | Service User checks DIP Portal for Self Triage | User determines issue cannot be resolved independently; escalation justified |  | Service User (LDSO)
|  |  | 3 | Log in to the Elexon Support Portal. (https://support.elexon.co.uk/csm), Select Report a Service Issue | Access to form confirmed |  | Service User (LDSO)
|  |  | 4 | In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - Please complete the details (Prefix subject with ORT-) Description - Please complete the details URL or related page section - Complete if required Click submit | Case successfully created; system issues confirmation |  | Service User (LDSO)
|  |  | 5 | Confirm receipt via ServiceNow notification. | User receives automated confirmation of case creation |  | ServiceNow Portal
|  |  | 6 | Case Triaged - priority increased to P3 | Elexon Service Desk validates the nature of the issue and gathers impact evidence |  | Elexon Service Desk
|  |  | 7 | Create Incident from the case | Incident record linked to original case is opened in ServiceNow |  | Elexon Service Desk
|  |  | 8 | Propose Incident as a "Major Incident Candidate." and assign to MI Manager | MI Candidate is escalated and ownership transferred |  | MI Manager
|  |  | 9 | Major Incident Manager confirms Major Incident Validity, and promote to Major Incident | Formal validation complete; incident confirmed as Major |  | MI Manager
|  |  | 10 | Incident promoted to Major Incident Severity = S1 Priority = P1 Status = In progress | Incident status updated to S1/P1; visible to stakeholders |  | MI Manager
|  |  | 11 | Case Priority is raised to reflect Major Incident Severity =S1 Priority=P1 | ServiceNow reflects S1/P1 priority and high visibility |  | MI Manager
|  |  | 12 | Notify stakeholders via initial MI communications List | Initial comms issued; stakeholders aware of the MI |  | MI Manager
|  |  | 13 | Initiate a bridge call / Teams Chat and circulate contact details to technical stakeholders. | Real-time coordination begins; technical contacts engaged |  | Technical Stakeholders
|  |  | 14 | Incident update Communication issued to Service Users via case updates on the portal and email notification from Service now each time the case is updated | Transparent updates provided to all impacted parties |  | Service User (LDSO)
|  |  | 15 | Assess whether Industry Circular required. Draft Industry Circular and distribute to mailing list | Circular drafted and sent if incident has market-wide impact |  | MI Manager
|  |  | 16 | BSC website is updated with Industry Circular details | Information made available to all via agreed BSC location |  | MI Manager
|  |  | 17 | MI Investigation starts. Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident status remains at In progress | Root cause investigation begins based on inputs received |  | Technical Resolver Avanade and DIP Manager
|  |  | 18 | Restorative actions identified - Incident status updated with fix details | Resolution actions defined and documented in ServiceNow |  | Service Desk CGI
|  |  | 19 | Implement restorative actions - Incident status updated with details | Fixes deployed and status updated with detailed notes |  | Service Desk CGI
|  |  | 20 | Issue is deemed as being resolved, Case is updated to reflect status of resolved and any other updates | System reflects resolution; user-visible status = Resolved |  | Service Desk CGI
|  |  | 21 | Industry Circular sent to confirm resolution has been implemented | Market formally notified that the MI is closed |  | Elexon Service Desk
|  |  | 22 | BSC website is updated with Industry Circular details | Updated industry record for audit and reference |  | Service Desk CGI
|  |  | 23 | Communication sent to Major Incident comms list notifying them the incident is resolved | Confirmation sent to stakeholders |  | Major Incident Comms List
|  |  | 24 | Case is set to resolved | ServiceNow case resolved by Elexon |  | Service Desk CGI
|  |  | 25 | Post incident review takes place and Major Incident report produced and sent to Major Incident comms list | Lessons learned and RCA report shared |  | MI Manager
|  |  | 26 | Service Users navigates to Case Ref# via Portal, and closes the case manually. If case is not closed within 5 days, it will automatically close | Case lifecycle ends, audit trail maintained |  | Service Users - LDSO

## TC_MI02
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles | Role
LDSO identifies an issue processing settlement reports due to DUoS Billing system logic failures. | Incident Handling Between Parties | ServiceNow Available DIP Portal Available Participants Systems Available | 1 | LDSO identifies that DUoS settlement messages are failing due to billing system logic (e.g., invalid tariff format). | Issue diagnosed locally; impact and root cause confirmed by LDSO | Service User (LDSO) Elexon Service Desk Major Incident Management Elexon Technical Resolvers | Service User (LDSO)
|  |  | 2 | LDSO triages and confirms the root cause internally. | Problem is not due to third-party system; internal root cause confirmed for escalation |  | Service User (LDSO)
|  |  | 3 | Log in to the Elexon Support Portal. (https://support.elexon.co.uk/csm), Select Report a Service Issue | Portal access is successful |  | Service User (LDSO)
|  |  | 4 | In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - Please complete the details (Prefix subject with ORT-) Description - Please complete the details URL or related page section - Complete if required Click submit | Case submission form is fully and accurately completed |  | Service User (LDSO)
|  |  | 5 | Confirm receipt via ServiceNow notification. | Case is successfully created in ServiceNow. Automated confirmation sent to LDSO with case reference |  | ServiceNow Portal
|  |  | 6 | Case Triaged - priority upgraded to P3 | Elexon reviews case content and verifies validity for escalation |  | Elexon Service Desk
|  |  | 7 | Create Incident from the case | Linked Incident record is created from initial case |  | Elexon Service Desk
|  |  | 8 | Propose Incident as a "Major Incident Candidate." and assign to MI Manager | Candidate flag applied; escalated to appropriate owner |  | MI Manager
|  |  | 9 | Major Incident Manager confirms Major Incident Validity, and promote to Major incident | Governance check complete; promoted with justification |  | MI Manager
|  |  | 10 | Incident promoted to Major Incident Severity = S1 Priority = P1 Status = In progress | Incident severity and priority updated visibly in ServiceNow |  | MI Manager
|  |  | 11 | Case Priority is raised to reflect Major Incident Severity =S1 Priority=P1 | System reflects critical status and urgency to all parties |  | MI Manager
|  |  | 12 | Notify stakeholders via initial MI communications List | All pre-defined stakeholders informed of Major Incident |  | MI Manager
|  |  | 13 | Initiate a bridge call / Teams Chat and circulate contact details to technical stakeholders. | Real-time resolution coordination initiated |  | Technical Stakeholders
|  |  | 14 | Incident update Communication issued to Service Users via case updates on the portal and email notification from Service now each time the case is updated | All updates are issued in sync via ServiceNow and email |  | Service Users
|  |  | 15 | Assess whether Industry Circular required. Draft Industry Circular and distribute to mailing list | If market-wide impact confirmed, comms issued proactively |  | MI Manager
|  |  | 16 | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | Industry public record maintained for audit and visibility |  | MI Manager
|  |  | 17 | MI Investigation starts. Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident status remains at In progress | Technical team engaged, confirms info is sufficient to proceed |  | Technical Resolver - ElectraLink, Avanade / DIP Manager / LDSO
|  |  | 18 | Restorative actions identified - Incident status updated with fix details | Resolution plan logged with audit trail |  | Service Desk CGI
|  |  | 19 | Implement restorative actions - Incident status updated with details | Fixes applied to affected systems or processes |  | Technical Resolver - ElectraLink, Avanade / DIP Manager / LDSO
|  |  | 20 | Issue is deemed as being resolved, case is updated to reflect status of resolved and any other updates | ServiceNow reflects resolved status and detail of actions taken |  | Technical Resolver - ElectraLink, Avanade / DIP Manager / LDSO
|  |  | 21 | Industry Circular sent to confirm resolution has been implemented | Stakeholders officially notified of outcome |  | Elexon Service Desk
|  |  | 22 | BSC website is update with Industry Circular details | Permanent resolution record available to all |  | Service Desk CGI
|  |  | 23 | Communication sent to Major Incident comms list notifying them the incident is resolved | Formal closure message delivered |  | Major Incident Comms List
|  |  | 24 | Case is set to resolved | ServiceNow case resolved by Elexon |  | Service Desk CGI
|  |  | 25 | Post incident review takes place and Major Incident report produced and sent to Major Incident comms list | PIR report shared with Major Incident comms list |  | MI Manager
|  |  | 26 | Service Users navigates to Case Ref# via Portal, and closes the case manually. If case is not closed within 5 days, it will automatically close | End-user confirms closure or timeout auto-closes for audit trail |  | Service Users - LDSO
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Who is the resolution group for this

## TC_MI03
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles | Role
Data corruption identified by any party affecting critical data exchanges | Incident Handling Between Parties | ServiceNow Available Participants Systems Available | 1 | Service User identifies Data Corruption affecting critical data exchanges | Issue is observed and confirmed by the Service User as affecting core industry processes. | Service User Elexon Service Desk Major Incident Management Elexon Technical Resolvers | Service User
|  |  | 2 | Log in to the Elexon Support Portal. (https://support.elexon.co.uk/csm), Select Report a Service Issue | Portal accessed successfully. |  | Service User
|  |  | 3 | In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - Please complete the details (Prefix subject with ORT-) Description - Please complete the details URL or related page section - Complete if required Click submit | Form is completed with valid inputs and appropriate categorisation. |  | Service User
|  |  | 4 | Confirm receipt via ServiceNow notification. | Case is created in ServiceNow and acknowledgement triggered. |  | Service User
|  |  | 5 | Case Triaged and priority raised to P3 | User receives confirmation of case creation. |  | Service User
|  |  | 6 | Create Incident from the case | Elexon assesses severity and prepares to escalate. |  | Elexon Service Desk
|  |  | 7 | Propose Incident as a "Major Incident Candidate." and assign to MI Manager | Incident record linked to original case is opened. |  | Elexon Service Desk
|  |  | 8 | Major Incident Manager confirms Major Incident Validity, and promote to Major incident | Candidate marked and ownership assigned to MI Manager. |  | MI Manager
|  |  | 9 | Incident promoted to Major Incident Severity = S1 Priority = P1 Status = In progress | Formal validation complete; status and ownership escalated. |  | MI Manager
|  |  | 10 | Case Priority is raised to reflect Major Incident Severity =S1 Priority=P1 | Priority/severity updated to critical and status set to active. |  | MI Manager
|  |  | 11 | Notify stakeholders via initial MI communications List | ServiceNow reflects escalated priority. |  | MI Manager
|  |  | 12 | Initiate a bridge call / Teams Chat and circulate contact details to technical stakeholders. | Stakeholders receive alert that MI has been declared. |  | Elexon Service Desk
|  |  | 13 | Incident update Communication issued to Service Users via case updates on the portal and email notification from Service now each time case is updated | Real-time coordination initiated across relevant teams. |  | Elexon Service Desk
|  |  | 14 | Assess whether Industry Circular required. Draft Industry Circular and distribute to mailing list | Comms drafted and issued if market impact is confirmed. |  | Elexon Service Desk -
|  |  | 15 | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | Comms drafted and issued if market impact is confirmed. |  | Elexon Service Desk
|  |  | 16 | MI Investigation starts. Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident status remains at In progress | Circular information is published in agreed public space. |  | Technical Resolver Team -DIP Manager / Avanade
|  |  | 17 | Restorative actions identified - Incident status updated with fix details | Root cause analysis begins with adequate data. |  | Elexon Service Desk - CGI
|  |  | 18 | Implement restorative actions - Incident status updated with details | Resolution plan confirmed and logged. |  | Technical Resolver Team
|  |  | 19 | Issue is deemed as being resolved, case is updated to reflect status of resolved and any other updates | Technical fixes applied and validated. |  | Elexon Service Desk
|  |  | 20 | Industry Circular sent to confirm resolution has been implemented | Status changed to Resolved; summary added. |  | Elexon Service Desk
|  |  | 21 | BSC website is update with Industry Circular details | Market officially notified of successful resolution. |  | Technical Resolver Team -DIP Manager / Avanade
|  |  | 22 | Communication sent to Major Incident comms list notifying them the incident is resolved | Public resolution info updated. |  | MI Comms list
|  |  | 23 | Case is set to resolved | User notified incident is resolved. |  | Elexon Service Desk
|  |  | 24 | Post incident review takes place and Major Incident report produced and sent to Major Incident comms list | PIR available in the incident |  | MI Manager
|  |  | 25 | Service Users navigates to Case Ref# via Portal, and closes the case manually. If case is not closed within 5 days, it will automatically close | RCA report created and shared. |  | Service User
|  |  | 26 | Elexon Service Desk user identifies MI closure without RCA. |  |  | MI Manager
|  |  | 27 | Manually creates Problem Record in ServiceNow: |  |  | MI Manager
|  |  | 28 | Links MI reference |  |  | MI Manager
|  |  | 29 | Describes issue, scope, potential impact. |  |  | MI Manager
|  |  | 30 | Assigns to Problem Manager. |  |  | MI Manager
|  |  | 31 | Problem Manager accepts ownership |  |  | Problem Manager
|  |  | 32 | Updates Problem Record to reflect assigned owner. - Changes status to “Under Investigation”. - Notifies key stakeholders (e.g., via email or ServiceNow comments). |  |  | Problem Manager
|  |  | 33 | Review related Incidents/MIs linked to the Problem. |  |  | Problem Manager
|  |  | 34 | Check error logs, evidence, user reports, and impact statements. |  |  | Problem Manager
|  |  | 35 | Manually contact technical teams |  |  | Problem Manager
|  |  | 36 | Schedule investigation sessions (e.g., calls, Teams) |  |  | Problem Manager
|  |  | 37 | Document findings, system checks, and technical observations. |  |  | Problem Manager
|  |  | 38 | Record detailed RCA findings in Problem Record |  |  | Problem Manager
|  |  | 39 | Identify root cause or contributing factors |  |  | Problem Manager
|  |  | 40 | Provide status updates via ServiceNow comments and/or direct communication. |  |  | Problem Manager
|  |  | 41 | Confirm technical teams have implemented fixes. |  |  | Problem Manager
|  |  | 42 | Update Problem Record status to “Resolved” or “Workaround Implemented” |  |  | Problem Manager

## TC_MI04
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles | Role
Validate Elexon’s ability to coordinate resolution of a complex incident requiring engagement with Avanade (DIP), LDSOs (MPAN issues), DCC (Smart Metering), and Suppliers (billing discrepancies) | Incident Handling Between Parties | 1. DIP message failure has occurred (simulated). 2. >Impact is DIP failure, MPAN, and Smart Meter data impact. 3. User attempted DIP Portal self-triage, escalation justified. 4. External Desks ready for case exchange. 5. Elexon ServiceNow operational. | 1 | User identifies incident: DIP failure, MPAN, and Smart Meter data impact. |  | Service User Elexon Service Desk Major Incident Management Elexon Technical Resolvers | Service User -
|  |  | 2 | User checks DIP Portal for self-triage; determines issue cannot be resolved; escalates to Elexon. | User determines issue cannot be resolved independently; escalation justified |  | Service User -
|  |  | 3 | Log in to the Elexon Support Portal. (https://support.elexon.co.uk/csm), Select Report a Service Issue | Access to form confirmed |  | Service User -
|  |  | 4 | In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - Please complete the details (Prefix subject with ORT-) Description - Please complete the details URL or related page section - Complete if required Click submit | Case successfully created; system issues confirmation |  | Service User -
|  |  | 5 | Confirm receipt via ServiceNow notification. | User receives automated confirmation of case creation |  | Service User -
|  |  | 6 | Case Triaged - priority increased to P3 | Elexon Service Desk validates the nature of the issue and gathers impact evidence |  | Elexon Service DESK - CGI
|  |  | 7 | Create Incident from the case | Incident record linked to original case is opened in ServiceNow |  | Elexon Service DESK - CGI
|  |  | 8 | Propose Incident as a "Major Incident Candidate." and assign to MI Manager | MI Candidate is escalated and ownership transferred |  | MI Manager
|  |  | 9 | Major Incident Manager confirms Major Incident Validity, and promote to Major Incident | Formal validation complete; incident confirmed as Major |  | MI Manager
|  |  | 10 | Incident promoted to Major Incident Severity = S1 Priority = P1 Status = In progress | Incident status updated to S1/P1; visible to stakeholders |  | MI Manager
|  |  | 11 | Case Priority is raised to reflect Major Incident Severity =S1 Priority=P1 | ServiceNow reflects S1/P1 priority and high visibility |  | MI Manager
|  |  | 12 | Notify stakeholders via initial MI communications List | Initial comms issued; stakeholders aware of the MI |  | MI Manager
|  |  | 13 | Initiate a bridge call / Teams Chat and circulate contact details to technical stakeholders. | Real-time coordination begins; technical contacts engaged |  | MI Manager
|  |  | 14 | Elexon initiates bridge call/Teams chat; circulates contacts to all technical stakeholders: - Avanade (DIP) - LDSO Help Desks - DCC Service Desk - Smart Metering Service Desk (SECCo) - Supplier Service Desks - REC Service Desk - EES Service Desk - Switching Service Desk - ERDS Service Desk. |  |  | Elexon Service DESK - CGI
|  |  | 15 | Information is shared with all technical stakeholders: - Impacted systems/parties (e.g., DIP, MPANs, Smart Metering, CSS) - References (MPANs, timestamps, error codes) - Supporting evidence. |  |  | Elexon Service DESK - CGI
|  |  | 16 | External Desks acknowledge receipt; provide updates. |  |  | Elexon Service DESK - CGI
|  |  | 17 | Incident update Communication issued to Service Users via case updates on the portal and email notification from Service now each time the case is updated | Transparent updates provided to all impacted parties |  | Elexon Service DESK - CGI
|  |  | 18 | Assess whether Industry Circular required. Draft Industry Circular and distribute to mailing list | Circular drafted and sent if incident has market-wide impact |  | Elexon Service DESK - CGI
|  |  | 19 | BSC website is updated with Industry Circular details | Information made available to all via agreed BSC location |  | Elexon Service DESK - CGI
|  |  | 20 | MI Investigation starts. Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident status remains at In progress | Root cause investigation begins based on inputs received |  | Technical Resolver Group - Avanade / DIP manager
|  |  | 21 | Restorative actions identified - Incident status updated with fix details | Resolution actions defined and documented in ServiceNow |  | Technical Resolver Group - Avanade / DIP manager
|  |  | 22 | Implement restorative actions - Incident status updated with details | Fixes deployed and status updated with detailed notes |  | Technical Resolver Group - Avanade / DIP manager
|  |  | 23 | Issue is deemed as being resolved, Case is updated to reflect status of resolved and any other updates | System reflects resolution; user-visible status = Resolved |  | MI Manager
|  |  | 24 | Industry Circular sent to confirm resolution has been implemented | Market formally notified that the MI is closed |  | MI Manager
|  |  | 25 | BSC website is updated with Industry Circular details | Updated industry record for audit and reference |  | MI Manager
|  |  | 26 | Communication sent to Major Incident comms list notifying them the incident is resolved | Confirmation sent to stakeholders |  | MI Manager
|  |  | 27 | Case is set to resolved | ServiceNow case resolved by Elexon |  | Elexon Service Desk - CGI
|  |  | 28 | Post incident review takes place and Major Incident report produced and sent to Major Incident comms list | Lessons learned and RCA report shared |  | MI Manager
|  |  | 29 | Service Users navigates to Case Ref# via Portal, and closes the case manually. If case is not closed within 5 days, it will automatically close | Case lifecycle ends, audit trail maintained |  | Service User

## TC_NI01
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles | Role
Simulate or detect that a DIP message sent from REGS is not received by the Supplier within the expected timescale. | Incident Handling Between Parties | ServiceNow Available DIP Portal Available Participants Systems Available | 1 | Simulate that a DIP message from REGS is not received by the Supplier within the expected timeframe. | Issue simulated to trigger response process for missing DIP message. | Service User LDSO Elexon Service Desk Major Incident Management Elexon Technical Resolvers
|  |  | 2 | Supplier checks DIP Portal message status | No message activity found; issue confirmed via DIP Portal. |  | Technical Resolver - Avanade?
|  |  | 3 | Supplier confirms no send activity recorded in DIP | Lack of message send event verified. |  | Technical Resolver - Avanade?
|  |  | 4 | Supplier attempts internal resolution if message is queued | Supplier confirms no internal error; proceeds with external escalation. |  | Technical Resolver - Avanade?
|  |  | 5 | Supplier logged with LDSO with MPID, message ID, timestamp, and context | LDSO receives detailed issue report from Supplier. |  | Service User
|  |  | 6 | LDSO confirms issue lies with REGS message generation and engages internal desk | Internal LDSO team accepts investigation responsibility. |  | Service User (LDSO)
|  |  | 7 | Log in to the Elexon Support Portal. (https://support.elexon.co.uk/csm), Select Report a Service Issue | Portal accessed successfully. |  | Service User (LDSO)
|  |  | 8 | In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - Please complete the details (Prefix subject with ORT-) Description - Please complete the details URL or related page section - Complete if required Click submit | Case data submitted with valid structure. |  | Service User (LDSO)
|  |  | 9 | Confirm receipt via ServiceNow notification. | Acknowledgment received by Supplier. |  | Service User
|  |  | 10 | Case Triaged and priority raised to P3 | Elexon assesses and categorises the issue. |  | Elexon Service Desk
|  |  | 11 | Create Incident from the case | Incident record opened. |  | Elexon Service Desk
|  |  | 12 | Engage Technical Resolver and Product owner | Technical and business resources assigned. |  | Elexon Service Desk
|  |  | 13 | ServiceNow update sends link to the portal for an update to raiser | LDSO informed of progress. |  | Elexon Service Desk
|  |  |  | Incident update Communication issued to LDSOs via ticket updates on the portal and email notification from Service now each time case is updated | Notifications shared for traceability. |  | Elexon Service Desk
|  |  | 14 | Review the ticket and attempt resolution, Technical resolver engages LDSO to understand steps taken in order to re-produce the issue | Collaboration initiated to aid technical diagnosis. |  | Technical Resolver - Avanade/ DIP Manager
|  |  | 15 | Technical resolver identify resolution | Root cause confirmed and fix prepared. |  | Technical Resolver - Avanade/ DIP Manager
|  |  | 16 | Send resolution comms with update to LDSO, case is updated to reflect current status | LDSO receives confirmation of fix. |  | Service User (LDSO)
|  |  | 17 | LDSO sends resolution comms with update to Supplier | Supplier notified of issue closure. |  | Service User (LDSO)
|  |  | 18 | LDSO adds response to the ticket and sets to closed | Case closed in ServiceNow with audit trail. |  | Service User (LDSO)

## TC_NI02
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles | Role
An incident involves ISD updates not notified. Changes to ISD have been made but messages not received by multiple parties | Incident Handling Between Parties | ServiceNow Available DIP Portal Available Participants Systems Available | 1 | Supplier identifies missing ISD messages across multiple participants. Verifies using DIP Portal. Expected: Supplier confirms anomaly with broadcast message receipt. | Supplier confirms anomaly based on DIP broadcast message logs. | Service User Elexon Service Desk Elexon Technical Resolvers | Service User (LDSO)
|  |  | 2 | Log in to the Elexon Support Portal. (https://support.elexon.co.uk/csm), Select Report a Service Issue | Portal accessed successfully. |  | Service User (LDSO)
|  |  | 3 | In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - Please complete the details (Prefix subject with ORT-) Description - Please complete the details URL or related page section - Complete if required Click submit | Form submitted with correct and complete data. |  | Service User (LDSO)
|  |  | 4 | Confirm receipt via ServiceNow notification. | Case created in ServiceNow. |  | Service User (LDSO)
|  |  | 5 | Case Triaged and priority upgraded to P3 | Supplier receives automated case confirmation. |  | Elexon Service Desk
|  |  | 6 | Create Incident from the case | Elexon validates data and flags for further investigation. |  | Elexon Service Desk
|  |  | 7 | Engage Technical Resolver and Product owner | Incident linked to original case is opened. |  | Elexon Service Desk
|  |  | 8 | Send comms with update to Supplier, case is updated to reflect current status | Issue assigned to appropriate support team. |  | Elexon Service Desk
|  |  | 9 | Incident update Communication issued to Supplier via ticket updates on the portal and email notification from Service now each time ticket is updated | Supplier informed of progress and investigation status. |  | Elexon Service Desk
|  |  | 10 | Review the ticket and attempt resolution, Technical resolver engages LDSO to understand steps taken in order to re-produce the issue | Supplier receives consistent updates through both channels. |  | Technical Resolver - Avanade / CGI
|  |  | 11 | Technical resolver identify resolution | Resolution process initiated with supporting party involvement. |  | Technical Resolver - Avanade / CGI / DIP Manager
|  |  | 12 | Send resolution comms with update to Supplier, case is updated to reflect current status | Root cause is confirmed and fix is ready. Supplier receives confirmation of issue fix and ticket status update. |  | Elexon Service Desk
|  |  | 13 | Supplier adds response to the case and sets to closed | Supplier acknowledges resolution; case is formally closed. |  | Service User (LDSO)

## TC_NI03
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles | Role
Data Service identifies issue with Load Shaping data. Data Service identifies issues with the Load Shaping data during their estimation process | Incident Handling Between Parties | ServiceNow Available DIP Portal Available Participants Systems Available | 1 | LDSO identifies inconsistencies in Load Shaping data during estimation. Performs initial review using DIP Portal and historical Load Shaping trends. Expected: Anomaly in data confirmed by Data Service. | Initial issue flagged by data monitoring processes. Anomaly confirmed through pattern comparison and DIP validation. | Service User Elexon Service Desk Elexon Technical Resolvers | Service User (LDSO)
|  |  | 2 | Log in to the Elexon Support Portal. (https://support.elexon.co.uk/csm), Select Report a Service Issue | Portal access is successful. |  | Service User (LDSO)
|  |  | 3 | In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - Please complete the details (Prefix subject with ORT-) Description - Please complete the details URL or related page section - Complete if required Click submit | Case is logged correctly with required detail. |  | Service User (LDSO)
|  |  | 4 | All Cases to be raised | Case is created in ServiceNow. |  | Service User (LDSO)
|  |  | 5 | Confirm receipt via ServiceNow notification. | Priority level set to P4 by default. |  | Service User (LDSO)
|  |  | 6 | Case Triaged and priority raised to P3 | Acknowledgment received by Data Service. |  | Elexon Service Desk - CGI
|  |  | 7 | Create Incident from the case | Issue severity and relevance assessed by Elexon. |  | Elexon Service Desk - CGI
|  |  | 8 | Engage Technical Resolver and Product owner | Incident record opened and linked to original case. |  | Elexon Service Desk - CGI
|  |  | 9 | Send comms with update to Supplier, case is updated to reflect current status | Technical resources and business SMEs assigned. |  | Elexon Service Desk - CGI
|  |  | 10 | Incident update Communication issued to Supplier via case updates on the portal and email notification from Service now each time case is updated | Supplier is informed of investigation progress. |  | Elexon Service Desk - CGI
|  |  | 11 | Review the incident and attempt resolution, Technical resolver engages Data Supplier to understand steps taken in order to re-produce the issue | Supplier receives system-triggered updates. |  | Technical Resolver -CGI / Avanade / DIP Manager
|  |  | 12 | Technical resolver identify resolution | Steps to reproduce issue are discussed for deeper analysis. |  | Technical Resolver -CGI / Avanade / DIP Manager
|  |  | 13 | Send resolution comms with update to Data Service case is updated to reflect current status | Supplier receives fix notification and confirmation. |  | Elexon Service Desk - CGI
|  |  | 14 | LDSO adds response to the case and sets to closed | Final input provided and case is marked as resolved. |  | Service User (LDSO)

## TC_NI04
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles | Role
LDSO unable to access the DIP but the internal DIP adaptor is working | Incident Handling Between Parties | ServiceNow Available Participants Systems Available | 1 | LDSO observes that their internal DIP adaptor is operational, but they cannot access the external DIP Portal. They begin triage using internal tools and DIP Portal diagnostics. Expected: LDSO confirms issue is not local. | Initial triage confirms local system is functional; DIP access issue appears external. LDSO confirms issue is not internal. | Service User (LDSO) Elexon Service Desk Elexon Technical Resolvers | Service user (LDSO)
|  |  | 2 | Log in to the Elexon Support Portal. (https://support.elexon.co.uk/csm), Select Report a Service Issue | Portal accessed successfully. |  | Service user (LDSO)
|  |  | 3 | In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - Please complete the details (Prefix subject with ORT-) Description - Please complete the details URL or related page section - Complete if required Click submit | Form submitted with accurate details. |  | Service user (LDSO)
|  |  | 4 | Case created | Case created in ServiceNow. System registers issue as a P4 priority. |  | Service user (LDSO)
|  |  | 5 | Confirm receipt via ServiceNow notification. | LDSO receives case confirmation. |  | Service user (LDSO)
|  |  | 6 | Case Triaged and priority raised to P3 | Elexon validates scope and triggers incident workflow. |  | Elexon Service Desk
|  |  | 7 | Create Incident from the case | Incident record opened in ServiceNow. |  | Elexon Service Desk
|  |  | 8 | Engage Technical Resolver - DIP Managers | Technical experts assigned to investigate. |  | Elexon Service Desk
|  |  | 9 | Incident update Communication issued to LDSOs via case updates on the portal and email notification from Service now each time case is updated | Progress communicated to LDSO via ServiceNow. |  | Elexon Service Desk
|  |  | 10 | Incident update Communication issued to LDSOs via case updates on the portal and email notification from Service now each time case is updated | LDSO notified on each update. |  | Elexon Service Desk
|  |  | 11 | Review the incident and attempt resolution, Technical resolver engages LDSO to understand steps taken in order to re-produce the issue | Context shared and steps discussed to confirm issue reproduction. |  | Technical Resolver - Avanade - DIP Manager
|  |  | 12 | Technical resolver identify resolution | Root cause confirmed and corrective action identified. |  | Technical Resolver - Avanade - DIP Manager
|  |  | 13 | Incident update Communication issued to LDSOs via case updates on the portal and email notification from Service now each time case is updated | LDSO notified of successful resolution. |  | Elexon Service Desk
|  |  | 14 | LDSO adds response to the case and sets to closed | LDSO confirms issue resolved and closes case. |  | Service user (LDSO)

## TC_NI05
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles | Role
Incident Logging via ServiceNow Portal - DIP Registration Issue | Incident Logging via ServiceNow Portal | ServiceNow Available DIP Portal Available Participants Systems Available | 1 | A Service User with appropriate Data Role raises an incident in the ServiceNow portal for a DIP Registration or User Privileges issue. Expected: Issue is correctly described and logged under the appropriate category. | Issue is correctly identified by an authorised user. | Service User Elexon Service Desk Elexon Technical Resolvers | Service User
|  |  | 2 | Service User raises case with Elexon via Support Portal. | Portal accessed successfully. |  | Service User
|  |  | 3 | In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - Please complete the details (Prefix subject with ORT-) Description - Please complete the details URL or related page section - Complete if required Click submit | Form completed with accurate detail and categorisation. |  | Service User
|  |  | 4 | Case raised | Case created in ServiceNow. Priority automatically set to P4. |  | Service User
|  |  | 5 | Confirm receipt via ServiceNow notification. | User receives confirmation message with case reference. |  | Service User
|  |  | 6 | Case Triaged and priority raised to P3 | Elexon categorises and validates the issue. |  | Elexon Service Desk- CGI
|  |  | 7 | Create Incident from the case | Incident record is opened and linked to original case. |  | Elexon Service Desk- CGI
|  |  | 8 | Engage Technical Resolver and Product owner | Relevant support and process owners assigned. |  | Elexon Service Desk- CGI
|  |  | 9 | Send comms with update to Service User, case is updated to reflect current status | Progress update sent via ServiceNow. |  | Elexon Service Desk- CGI
|  |  | 10 | Incident update Communication issued to Service User via case updates on the portal and email notification from Service now each time case is updated | User receives status updates for traceability. |  | Elexon Service Desk- CGI
|  |  | 11 | Review the incident and attempt resolution, Technical resolver engages Service User to understand steps taken in order to re-produce the issue | Steps clarified to facilitate investigation. |  | Elexon Service Desk- CGI
|  |  | 12 | Technical resolver (DIP Manager)identify resolution | Cause identified and fix developed. |  | Technical Resolver - DIP Manager
|  |  | 13 | Send resolution comms with update to Service User, case is updated to reflect current status | User receives confirmation of issue resolution. |  | Elexon Service Desk- CGI
|  |  | 14 | Service User adds response to the case and sets to closed | Case is acknowledged and formally closed by user. |  | Service User

## TC_PROB_01
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles | Role
Validate that a Problem Record can be raised reactively from repeat incidents logged by a single participant. | Verify that a Problem Record can be created reactively when multiple incidents are logged by the same user (participant), | ServiceNow Available | 1 | Service User logs the first case to request Problem Management regarding DIP registration issue | Incident is successfully created and visible in ServiceNow. | SerivceUser Elexon Service Desk Problem Manager | Service User
|  |  | 2 | Service Desk triages to confirm Problem Creation | Confirms no ongoing incident, review previous incidents relating to problem |  | Elexon Service Desk
|  |  | 3 | Elexon manually initiates creation of a Problem Record from one of the related incidents | New Problem Record is created with a unique ID and linked to the originating incident. |  | Problem Manager
|  |  | 4 | Link all relevant historical incidents to the Problem Record | All past related incidents appear in the Problem Record’s ‘Affected Incidents’ field. |  | Problem Manager
|  |  | 5 | Add Problem description, impact notes, and assign to Resolver Group | Problem Record is populated with context and assigned to the appropriate resolver team. |  | Problem Manager
|  |  | 6 | Confirm the incidents now show a reference to the new Problem Record | Each incident displays a reference field to the associated Problem Record. |  | Problem Manager
|  |  | 7 | Notify the participant that a Problem Record has been initiated | Participant receives notification via ServiceNow or email regarding the Problem Record. |  | Elexon Service Desk

## TC_PORT_01
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles | Role
Validate portal behaviour when registering an account without selecting an organisation. | Testing of ServiceNow Support Portal Access | Elexon ServiceNow Portal is available Email address is not already registered in the Portal User has a mobile phone to allow Authenticator installed | 1 | Navigate to https://support.elexon.co.uk/csm | Portal homepage is displayed. | Service User | Service user
|  |  | 2 | Select Register and account then select register | Registration page is displayed. |  | Service user
|  |  | 3 | Follow the instructions in the Service Operations Manual on how to register an account | Account is registered |  | Service user
|  |  | 4 | Access to the Portal is granted | Access to Elexon Support Portal is granted with login session active. |  | Service user

## TC_PORT_02
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles | Role
Successful RBAC access: Parent can access child account cases | Testing of ServiceNow Support Portal Access | Elexon ServiceNow Portal is available ServiceNow Parent / Child Configured | 1 | Log into Elexon Support Portal at https://support.elexon.co.uk/csm | Portal homepage is displayed. | Service User (Parent) | Service User (Parent)
|  |  | 2 | Navigate to the “Cases” section. | Cases Section is available |  | Service User (Parent)
|  |  | 3 | Open case details and confirm visibility of case content (subject, description, category, status, updates). | Child Case can be viewed |  | Service User (Parent)
|  |  | 4 | Attempt to update case status or add a comment (if permitted by role). | Child Case can be updated |  | Service User (Parent)

## TC_PORT_03
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles | Role
Parent logs case on behalf of child | Testing of ServiceNow Support Portal Parent/Child | Portal is accessible to new users via public registration. | 1 | Navigate to the Elexon Support Portal as a parent organisation user | Portal loads with parent organisation privileges enabled | Service User (Parent) | Service User (Parent)
|  |  | 2 | Initiate a new case request | Case creation screen is displayed |  | Service User (Parent)
|  |  | 3 | Complete the Case form with valid details including Child organisation details | Form is validated and ready for submission |  | Service User (Parent)
|  |  | 4 | Submit the case on behalf of the child organisation | Case is logged successfully against the child organisation, visible to both parent and child; unique case ID generated |  | Service User (Parent)

## TC_PORT_04
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles | Role
Validate that a Parent user can view both their own cases and cases logged by linked Child organisations in the Elexon Support Portal. | Testing of ServiceNow Support Portal Access | Parent account configured in ServiceNow. At least one Child account (e.g., “Green Energy Co.”) correctly linked to Parent. At least one open case logged under Parent. At least one open case logged under Child. ServiceNow Parent-Child configuration validated.C12 | 1 | Parent User logs into Elexon Support Portal at https://support.elexon.co.uk/csm | Portal homepage is displayed. | Service User (Parent) | Service User (Parent)
|  |  | 2 | Navigate to the “Cases” section. | Cases Section is available |  | Service User (Parent)
|  |  | 3 | Views list of cases. | Filter work correctly |  | Service User (Parent)
|  |  | 4 | Confirms visibility of: -Cases logged by Parent Organisation -Cases logged by Child Organisation | Child Case can be viewed |  | Service User (Parent)
|  |  | 5 | Views case details for Child cases. | Case can be viewed |  | Service User (Parent)
|  |  | 6 | Optionally, adds comments or updates on Child case (if permissions allow). | Comments can be added |  | Service User (Parent)

## TC_PORT_05
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles | Role
Validate that a Child user cannot view or access cases logged by their Parent organisation, ensuring Parent-Child boundaries are enforced. | Testing of ServiceNow Support Portal Access | Parent account configured in ServiceNow. At least one Child account correctly linked to Parent. At least one open case logged under Parent. At least one open case logged under Child. ServiceNow Parent-Child configuration validated.C12 | 1 | Child user logs into https://support.elexon.co.uk/csm. | Portal homepage is displayed. | Service User (Child) | Service User (Child)
|  |  | 2 | Navigates to Cases dashboard. | Cases Section is available |  | Service User (Child)
|  |  | 3 | Attempt to search or filter on another case not related to you | No Filter should be able |  | Service User (Child)
|  |  | 4 | Attempts to open Parent case details directly (e.g., by URL or case ID). | Cannot access Parent Cases details |  | Service User (Child)
|  |  | 5 | Attempts to search by Parent’s Party ID | No results returned |  | Service User (Child)

## TC_SR01
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles | Role
Service Request Logging via ServiceNow | To verify that service requests can be successfully logged and tracked via the ServiceNow platform, with all requests routed through the Elexon Support Portal and assigned a default priority of P4. | ServiceNow Available Service User has a portal account | 1 | Navigate to the Elexon Support Portal and open a new service issue. Expected: Access to the portal is successful and the case creation form is available. | Access to the portal is successful and the case creation form is available. | Service User Elexon Service Desk | Service User
|  |  | 2 | Service User raises a case in the SM portal (CSM Service Catalogue - Elexon Support) by selecting the 'Report a Service Issue' option and completing the following fields In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - MHHS Subject - Service Request: Add Child Account Description - Add Child Account URL or related page section - insert if required | Predefined options are available and selectable based on request type. Form validates inputs and accepts the submission. |  | Service User
|  |  | 3 | Request is then assigned to the Service Request Manager for approval. | Service Request Manager receives notification of request |  | Service User
|  |  | 4 | Request is approved by Service Request Manager | Request appears in the portal dashboard. |  | Service User
|  |  | 5 | Assigned for fulfilment. | Request is assigned |  | Service User
|  |  | 6 | Request is fulfilled | ServiceNow shows request if fulfilled |  | Elexon Service Desk
|  |  | 7 | Request is completed update communicated with Service User. | User can view status updates. |  | Service User
|  |  | 8 | Service confirms request fulfilled and closes the ticket | All interactions are recorded in the request history. |  | Service User